## NBN_MWI & Pipe Data
Contract | Location | PE | Inv No. | Date Invoice Created | Date Project Completions handed over | PC Request Date Submitted | Variation Request submitted | Variation Approval | PC Due | Payment Date | PC, Variation & Payment Comments | Month Claimed | Actual Payment Date | FSAM/MPS | Suburb | CSPO Amount | Variation | Total Revenue | GST Inc | DJC Cost | Internal DJC Cost | Total Cost | Margin | % | Status | Date Expected Payment | Comments | NBN PO/PM | Project Quote Submitted | Project Award Date | Days to Award | Customer required date | Difference CRD to Award
A401/Greenfield | Sydney | Mickey Tran | Inv 13693 | 2018-06-06 | 2018-05-02 | 2018-05-03 | 2018-05-08 | 2018-05-09 | 2018-05-17 | 2018-06-05 |  | May-18 | Jun-18 | MW20507 - AYCA-2Y5DX4 - Bridgeland Investment | Epping | 6265.77 | 7637.882 | 13903.652 | 15294.0172 | 3486.54 |  | 3486.54 | 10417.112 | 74.92% |  |  |  | Andrew Partalis | 2017-03-23 | 2017-04-08 | 16 | 2017-04-07 | -1
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW20698 - AYCA-1SQ3K5 - 189 Macquarie Street | Parramatta | 1056.78 |  | 1056.78 | 1162.458 | 235 |  | 235 | 821.78 | 77.76% |  | 2019-04-13 |  | Lindy Chan | Direct Award | 2017-05-08
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14141 | 2018-09-11 | 2018-08-03 | 2018-08-03 | 2018-07-03 | 2018-08-29 | 2018-08-17 | 2018-08-31 |  | Aug-18 | Aug-18 | MW20888 - AYCA-39AB50 -2HOR-62 -JAAN – 1 | Asquith | 1035.19 | 4631.1112 | 5666.3012 | 6232.9314 | 2974.72 |  | 2974.72 | 2691.5812 | 47.5% |  | 2018-08-17 |  | Andrew Partalis | Direct Award | 2017-07-04
A401/Greenfield | Sydney | Damien Marov | Inv 14582 | 2019-01-07 | 2018-11-12 | 2018-11-12 | 2018-11-27 | 2018-12-13 | 2018-11-26 | 2019-01-08 |  | Nov-18 | Jan-19 | MW21097 - 2LIV-04 - AYCA-476RM9 - NSB - 87-91 Campbell St Build | Liverpool | 8773.94 | 11072.91 | 19846.85 | 21831.535 | 10967.35 |  | 10967.35 | 8879.5 | 44.74% |  | 2018-11-26 |  | Andrew Mahassy | 2017-08-22 |  |  | 2017-09-30
A401/Greenfield | Sydney Sth | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW21325 - 2NRL-20 - AYCA-2QFUTJ - Camden Day Hospital - 1 | Elderslie | 2322.6893 |  | 2322.6893 | 2554.9582 |  |  | 0 | 2322.6893 | 100% |  | 2019-04-13 | Completed and handover forwarded | Nabeel Jaimon | 2017-09-29 | 2017-10-18 | 19 | 2017-10-26 | 8
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13697 | 2018-06-06 | 2018-05-17 | 2018-05-17 | 2018-05-18 | 2018-05-30 | 2018-05-30 | 2018-06-07 |  | May-18 | Jun-18 | MW20917 - AYCA-3A485K -2LID-03 - Lidbury Street Berala - 1 - EXTERNAL | Berala | 82.91 | 6597 | 6679.91 | 7347.901 | 4651.88 |  | 4651.88 | 2028.03 | 30.36% |  | 2018-05-31 |  | Lindy Chan | Direct Award | 2017-10-19 |  | 2017-11-22 | 34
A401/Greenfield | Central West | Marshell Antonio | Inv 14543 | 2018-12-14 | 2018-11-16 | 2018-11-16 | 2018-11-16 | 2018-11-28 | 2018-11-30 | 2018-12-14 |  | Nov-18 | Dec-18 | MW21395 - 2BTH-01 - AYCA-4LYVIU - Arndilly - 2 | Bathurst | 4802.37 | 3300.753 | 8103.123 | 8913.4353 |  |  | 0 | 8103.123 | 100% |  | 2018-11-30 |  | Mark Leal | 2017-09-27 | 2017-10-23 | 26 | 2017-11-01 | 9
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13910 | 2018-07-24 | 2018-06-06 | 2018-06-07 | 2018-06-06 | 2018-06-19 | 2018-06-21 | 2018-07-24 |  | Jun-18 | Jul-18 | MW21524 - AYCA-47C97W-2BLK-01 -51 Kildare Rd Blacktown | Blacktown | 1711.6 | 1825.26 | 3536.86 | 3890.546 | 1221.19 |  | 1221.19 | 2315.67 | 65.47% |  | 2018-06-21 |  | Ertan Cicek | Direct Award | 2017-12-07 |  | 2017-12-15 | 8
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14211 | 2018-10-09 | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-25 | 2018-09-19 | 2018-10-09 |  | Sep-18 | Oct-18 | MW21570-AYCA-1L7010 - 2LID-08 - Mixed Use Development - Tower A and B | Auburn | 2066.42 | 8430.59 | 10497.01 | 11546.711 | 4673.01 |  | 4673.01 | 5824 | 55.48% |  | 2018-09-19 |  | Ertan Cicek | Direct Award | 2017-12-12 |  | 2018-01-04 | 23
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-02-20 | 2019-02-20 | 2019-02-27 |  | 2019-03-06 | 2019-03-20 |  | Feb-19 | Mar-19 | MW21705-AYCA-468RZY-2LID-04-23 RAILWAY PARADE - Ext | Lidcombe | 671.72 | 2114.6 | 2786.32 | 3064.952 |  |  | 0 | 2786.32 | 100% |  | 2019-03-06 |  | Nabeel Jaimon | Direct Award | 2018-01-04 |  | 2018-02-15 | 42
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW21699-AYCA-3E5O97-2ROU-03-Hancy - 1 | Kellyville | 3447.12 |  | 3447.12 | 3791.832 |  |  | 0 | 3447.12 | 100% |  | 2019-04-13 |  | Ertan Cicek | Direct Award | 2018-01-04 |  | 2018-02-15 | 42
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW21728-AYCA-4HTS7R-2RIV-03-875 RICHMOND RD, MARSDEN PARK | Marsden Park | 731.99 |  | 731.99 | 805.189 |  |  | 0 | 731.99 | 100% |  | 2019-04-13 |  | Ertan Cicek | Direct Award | 2018-01-09 |  | 2018-02-27 | 49
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-02-27 | 2019-03-01 | 2019-03-01 |  | 2019-03-15 | 2019-03-29 |  | Mar-19 | Mar-19 | MW21638- AYCA-3NFID7-2PTH-04 - Tench Ave Jamisontown 1 | Jamisontown | 2209.46 | 3782.49 | 5991.95 | 6591.145 | 3411.2 |  | 3411.2 | 2580.75 | 43.07% |  | 2019-03-15 |  | Ertan Cicek | Direct Award | 2017-12-19 |  | 2018-01-30 | 42
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-02-20 | 2019-02-21 | 2019-02-21 |  | 2019-03-07 | 2019-03-21 |  | Feb-19 | Mar-19 | MW21791-AYCA-468RZY-2LID-04-23 Railway Parade - Internals | Lidcombe | 1400 | 2114.6 | 3514.6 | 3866.06 |  |  | 0 | 3514.6 | 100% |  | 2019-03-07 |  | Nabeel Jaimon | Direct Award | 2018-02-01 |  | 2018-03-01 | 28
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13985 | 2018-08-03 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-07-26 | 2018-07-11 | 2018-08-02 |  | Jun-18 | Aug-18 | MW21819-AYCA-4KXY8F-2BTH-02-1 Wark Parade, Windradyne | Camden | 1240.76 | 10448.27 | 11689.03 | 12857.933 |  |  | 0 | 11689.03 | 100% |  | 2018-07-11 |  | Ertan Cicek | Direct Award | 2018-02-20 |  | 2018-03-22 | 30
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2018-01-30 | [5 empty] | Jan-18 | Jan-00 | MW21884-AYCA-47OO3O- 2LIV-03- 188-190 Moore st, Liverpool | Liverpool | 857.61 |  | 857.61 | 943.371 |  |  | 0 | 857.61 | 100% |  | 2018-02-13 |  | Ertan Cicek | Direct Award | 2018-02-20 |  | 2018-03-22 | 30
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW21876-AYCA-21PVTM - 2BLK-03 - 5 Second Avenue, Blacktown | Blacktown | 592.62 |  | 592.62 | 651.882 |  |  | 0 | 592.62 | 100% |  | 2019-05-14 |  | Ertan Cicek | Direct Award | 2018-02-20 |  | 2018-03-22 | 30
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13922 | 2018-07-26 | 2018-06-22 | 2018-06-22 | 2018-06-26 | 2018-07-18 | 2018-07-06 | 2018-07-26 |  | Jun-18 | Jul-18 | MW21820-AYCA-4W4BKH-2HOM-02-38 Weeroona Rd, Strathfield Ext | Strathfield | 5741.5 | 5141.04 | 10882.54 | 11970.794 | 3623.46 |  | 3623.46 | 7259.08 | 66.7% |  | 2018-07-06 |  | Nabeel Jaimon | Direct Award | 2018-02-20 |  | 2018-03-22 | 30
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13937 | 2018-07-27 | 2018-06-22 | 2018-06-22 | 2018-06-22 | 2018-07-18 | 2018-07-06 | 2018-07-31 |  | Jun-18 | Jul-18 | MW21857-AYCA-442ZEA- 2PAR-63-2 Good st, Westmead | Westmead | 1825.19 | 11374.1765 | 13199.3665 | 14519.3031 | 7231.46 | 903.1955 | 8134.6555 | 5064.711 | 38.37% |  | 2018-07-06 |  | Ertan Cicek | Direct Award | 2018-02-22 |  | 2018-03-22 | 28
A401/Minor works | Sth Coast | Mickey Tran | Inv 13829 | 2018-07-06 | 2018-06-14 | 2018-06-15 | 2018-06-15 | 2018-06-27 | 2018-07-02 | 2018-07-05 |  | Jun-18 | Jul-18 | MW21390 - AYCA-4QG9AV - NSB - 33 Shoalhaven St Kiama Surevy & Build | Kiama | 1919 | 5178.72 | 7097.72 | 7807.492 | 1120 | 2043.8035 | 3163.8035 | 3933.9165 | 55.43% |  | 2018-06-29 |  | Andrew Mahassy | 2017-12-10 | 2018-02-23 | 75 | 2018-02-16 | -7
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW21875 - AYCA-42N8QF- 2PEN-67- Macklin 38 | Pendle Hill | 515.58 |  | 515.58 | 567.138 |  |  | 0 | 515.58 | 100% |  | 2019-04-13 |  | Ertan Cicek | Direct Award | 2018-02-23 |  | 2018-03-22 | 27
A417 Greenfield MDU | Sth Coast | Mickey Tran | Inv 14215 | 2018-10-05 | 2018-09-03 | 2018-09-03 | 2018-09-04 | 2018-09-25 | 2018-09-17 | 2018-10-09 |  | Sep-18 | Oct-18 | MW21827-AYCA-4O03IQ-2COR-09-17 Ryan Street, Balgownie Ext | Balgownie | 1924.61 | 14905.61 | 16830.22 | 18513.242 | 5425.54 | 2800 | 8225.54 | 8604.68 | 51.13% |  | 2018-09-17 |  | Nabeel Jaimon | Direct Award | 2018-02-26 |  | 2018-03-20 | 22
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13752 | 2018-06-20 | 2018-05-28 | 2018-05-29 | 2018-05-31 | 2018-06-05 | 2018-06-08 | 2018-06-19 |  | May-18 | Jun-18 | MW21970-AYCA-4YZGFK-2PEN-66-51 Boronia St, South Wentworthville | Wentworthville | 1021.38 | 3224.76 | 4246.14 | 4670.754 | 2111.52 |  | 2111.52 | 2134.62 | 50.27% |  | 2018-06-12 |  | Ertan Cicek | Direct Award | 2018-03-02 |  | 2018-04-06 | 35
A401/Minor works | Sydney West | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW21456 - 2BLK-07-16 - 51 Huntingwood Drive | Huntingwood | 30428.35 |  | 30428.35 | 33471.185 | 9404.68 |  | 9404.68 | 21023.67 | 69.09% |  | 2019-03-14 |  | Greg Moeller | 2017-11-27 | 2018-03-28 |  | 2018-04-30 | 33
NBN Assurance Wagga | NSW | Andrew McPherson | Inv 13358 | 2018-03-08 | 2018-03-08 | 2018-03-08 |  |  |  | 2018-05-17 |  | Mar-18 | May-18 | MW22235 - INC000007210193 - 36 Blakemore Av, Ashmont, NSW | Ashmont | 1153.26 |  | 1153.26 | 1268.586 |  | 450 | 450 | 703.26 | 60.98% |  | #REF! |  | Tony Gabriel
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13672 | 2018-05-28 | 2018-05-09 | 2018-05-09 | 2018-05-15 | 2018-05-02 | 2018-05-23 | 2018-06-12 |  | May-18 | Jun-18 | MW21835-AYCA-4MJ7W3-2WRO-63-8-10 Park Ave, Waitara | Waitara | 704.71 | 4996.36 | 5701.07 | 6271.177 | 1885.45 |  | 1885.45 | 3815.62 | 66.93% |  | 2018-05-23 |  | Ertan Cicek | Direct Award | 2018-03-07 |  | 2018-03-20 | 13
A401/Greenfield | Central West | Mickey Tran | Inv 13718 | 2018-06-14 | 2018-06-04 | 2018-06-04 |  |  | 2018-06-15 | 2018-06-22 |  | Jun-18 | Jun-18 | MW22035-AYCA-4C4E63-2CWR-01-11 Liverpool Street Cowra | Cowra | 8506.73 |  | 8506.73 | 9357.403 |  |  | 0 | 8506.73 | 100% |  | 2018-06-18 |  | Dave Yoemans | 2018-03-05 | 2018-03-16 |  | 2018-04-01 | 16
A401/Greenfield | Sth NSW | Mickey Tran | Inv 13776 | 2018-06-29 | 2018-06-05 | 2018-06-05 |  |  | 2018-06-20 | 2018-06-26 |  | Jun-18 | Jun-18 | MW22033 -AYCA-4PX9WA- 2YAS-01 - 23 Browne Street Yass | Yass | 2191.88 |  | 2191.88 | 2411.068 |  |  | 0 | 2191.88 | 100% |  | 2018-06-19 |  | Dave Yoemans | 2018-03-05 | 2018-03-16 |  | 2018-04-01 | 16
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-02-21 | 2019-02-21 | 2019-02-21 |  | 2019-03-07 | 2019-03-21 |  | Feb-19 | Mar-19 | MW21971-AYCA-4X6TWU-2LID-08-43 - 47 Harrow Rd, Auburn, EXT | Auburn | 279.01 | 4023.2 | 4302.21 | 4732.431 | 2486.77 |  | 2486.77 | 1815.44 | 42.2% |  | 2019-03-07 |  | Nabeel Jaimon | Direct Award | 2018-02-28 |  | 2018-04-06 | 37
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13921 | 2018-07-26 | 2018-06-25 | 2018-06-25 |  |  | 2018-07-09 | 2018-07-12 |  | Jun-18 | Jul-18 | MW21994-AYCA-4W4BKH-2HOM-02-38 Weeroona Rd Strathfield INT | Strathfield | 840 |  | 840 | 924 |  |  | 0 | 840 | 100% |  | 2018-07-09 |  | Nabeel Jaimon | Direct Award | 2018-03-06 |  | 2018-03-28 | 22
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-02-21 | 2019-02-21 |  |  | 2019-03-07 | 2019-03-21 |  | Feb-19 | Mar-19 | MW22002-AYCA-4X6TWU-2LID-08-43-47 Harrow Rd Auburn, INT | Auburn | 560 |  | 560 | 616 |  |  | 0 | 560 | 100% |  | 2019-03-07 |  | Nabeel Jaimon | Direct Award | 2018-03-06 |  | 2018-04-03 | 28
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14630 | 2019-01-22 | 2018-12-11 | 2018-12-11 | 2018-12-11 | 2018-12-21 | 2018-12-25 | 2019-01-22 |  | Dec-18 | Jan-19 | MW22007-AYCA-4VJFPP-2NEW-22-19-21 Eve St, Erskineville | Erskinville | 1201.18 | 5549.32 | 6750.5 | 7425.55 | 3800.64 |  | 3800.64 | 2949.86 | 43.7% |  | 2018-12-25 |  | Ertan Cicek | Direct Award | 2018-03-07 |  | 2018-04-05 | 29
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13637 | 2018-05-22 | 2018-05-03 | 2018-05-03 | 2018-05-08 | 2018-05-10 | 2018-05-16 | 2018-05-22 |  | May-18 | May-18 | MW22022--AYCA-3TBATE-2PAR-6111 Hassall St, Paramatta | Parramatta | 1400.62 | 7702.47 | 9103.09 | 10013.399 | 4761.73 |  | 4761.73 | 4341.36 | 47.69% |  | 2018-05-17 |  | Ertan Cicek | Direct Award | 2018-03-08 |  | 2018-04-10 | 33
A401/Greenfield | Sydney West | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW22024-AYCA-35DF0W-2KEL-07-1, 1A & 1B President Rd, Kellyville | Kellyville | 2197.21 |  | 2197.21 | 2416.931 | 2161.86 |  | 2161.86 | 35.35 | 1.609% |  | 2019-07-14 |  | Ertan Cicek | Direct Award | 2018-03-08 |  | 2018-04-10 | 33
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14084 | 2018-08-29 | 2018-07-12 | 2018-07-12 | 2018-07-16 | 2018-07-31 | 2018-08-16 | 2018-08-28 |  | Jul-18 | Aug-18 | MW22023-AYCA-48280D - 2RED-03 - 906 Bourke St, Zetland | Zetland | 3858.83 | 14876.74 | 18735.57 | 20609.127 | 11554.27 |  | 11554.27 | 7181.3 | 38.33% |  | 2018-07-26 |  | Ertan Cicek | Direct Award | 2018-03-13 |  | 2018-04-09 | 27
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  | 2019-02-19 | 2019-02-19 |  |  | 2019-03-05 | 2019-03-19 |  | Feb-19 | Mar-19 | MW21914 - AYCA-4SRFAN-2BAL-62 - 22/26 Roseberry St Balgowlah NSW INT | Balgowlah | 560 |  | 560 | 616 |  |  | 0 | 560 | 100% |  | 2019-03-05 |  | Lindy Chan | Direct Award | 2018-03-14 |  | 2018-05-15 | 62
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14143 | 2018-09-11 | 2018-07-24 | 2018-07-24 | 2018-07-25 | 2018-08-30 | 2018-08-07 | 2018-09-11 |  | Jul-18 | Sep-18 | MW22048-AYCA-52ZO0L-2LID-04-32 Norval St, Auburn EXT | Aurburn | 1156.52 | 4793.13 | 5949.65 | 6544.615 | 1105.71 |  | 1105.71 | 4843.94 | 81.42% |  | 2018-08-07 |  | Richard Huffadine | Direct Award | 2018-03-15 |  | 2018-04-30 | 46
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14191 | 2018-09-24 | 2018-08-31 | 2018-08-31 |  |  | 2018-09-14 | 2018-09-28 |  | Aug-18 | Sep-18 | MW22053-AYCA-4O03IQ-2COR-09-17 Ryan Street Balgownie Int | Balgowie | 2731.54 |  | 2731.54 | 3004.694 |  | 1200 | 1200 | 1531.54 | 56.07% |  | 2018-09-14 |  | Nabeel Jaimon | Direct Award | 2018-03-15 |  | 2018-05-11 | 57
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14153 | 2018-09-18 | 2018-08-21 | 2018-08-21 | 2018-08-22 | 2018-08-30 | 2018-09-04 | 2018-09-18 |  | Aug-18 | Sep-18 | MW22042-AYCA-4SV0JO2ING-65-41-47 Stennett Rd Ingleburn, Int HMDU | Ingelburn | 560 | 512.56 | 1072.56 | 1179.816 |  |  | 0 | 1072.56 | 100% |  | 2018-09-04 |  | Richard Huffadine | Direct Award | 2018-03-15 |  | 2018-05-31 | 77
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW21898-AYCA-26KP9Q-2ROU-02-Caddies Boulevard & White Hart Drive, Rouse Hill | Rouse Hill | 2930.88 |  | 2930.88 | 3223.968 |  |  | 0 | 2930.88 | 100% |  | 2019-07-14 |  | Ertan Cicek | Direct Award | 2018-03-15 |  | 2018-03-26 | 11
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13695 | 2018-06-06 | 2018-05-14 | 2018-05-15 | 2018-05-18 | 2018-05-30 | 2018-05-29 | 2018-06-05 |  | May-18 | Jun-18 | MW22047-AYCA-53E534-2LIV-12-25 Glenfield Rd, Glenfield Ext | Glenfield | 5800.45 | -1002.48 | 4797.97 | 5277.767 |  |  | 0 | 4797.97 | 100% |  | 2018-05-29 |  | Richard Huffadine | Direct Award | 2018-03-15 |  | 2018-04-16 | 32
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14196 | 2018-09-26 | 2018-07-24 | 2018-07-24 |  |  | 2018-09-13 | 2018-09-27 |  | Jul-18 | Sep-18 | MW22055-AYCA-52ZO0L-2LID-04-32 Norval St Auburn INT | Auburn | 2800 |  | 2800 | 3080 | 1434.4 |  | 1434.4 | 1365.6 | 48.77% |  | 2018-08-07 |  | Richard Huffadine | Direct Award | 2018-03-15 |  | 2018-04-30 | 46
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13683 | 2018-05-30 | 2018-05-03 | 2018-05-03 | 2018-05-10 | 2018-05-23 | 2018-05-16 | 2018-05-31 |  | May-18 | May-18 | MW22057 - AYCA-4EOA07-2MIR-24 - 298-300 Taren Point Rd, Caringbah | Caringbah | 1692.36 | 8088.39 | 9780.75 | 10758.825 | 7048.27 |  | 7048.27 | 2732.48 | 27.94% |  | 2018-05-17 |  | Ertan Cicek | Direct Award | 2018-03-19 |  | 2018-04-18 | 30
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13667 | 2018-06-12 | 2018-06-07 | 2018-06-07 | 2018-06-07 | 2018-06-21 | 2018-06-21 | 2018-06-28 |  | Jun-18 | Jun-18 | MW22050-AYCA-53E534-2LIV-12-25 Glenfield Rd Glenfield Int | Glenfield | 2640 | 512.56 | 3152.56 | 3467.816 |  |  | 0 | 3152.56 | 100% |  | 2018-06-21 |  | Richard Huffadine | Direct Award | 2018-03-21 |  | 2018-04-10 | 20
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-03-05 | 2019-03-05 | 2019-03-05 |  | 2019-03-19 | 2019-04-02 |  | Mar-19 | Apr-19 | MW22071- AYCA-4M02LB -2UND-62-401-405 Illawarra Road, Marrickville | Marrickville | 857.61 | 745.96 | 1603.57 | 1763.927 |  |  | 0 | 1603.57 | 100% |  | 2019-03-19 |  | Ertan Cicek | Direct Award | 2018-03-21 |  | 2018-04-23 | 33
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13631 | 2018-05-22 | 2018-05-03 | 2018-05-03 | 2018-05-08 | 2018-05-14 | 2018-05-16 | 2018-05-22 |  | May-18 | May-18 | MW22080-2QUA-02-AYCA-3I5VJ6-67 Dongola Circuit Schofields | Schofields | 355.84 | 668.36 | 1024.2 | 1126.62 |  |  | 0 | 1024.2 | 100% |  | 2018-05-17 |  | Ertan Cicek | Direct Award | 2018-03-23 |  | 2018-05-01 | 39
NBN Assurance Wagga | NSW | Mickey Tran | Inv 13429 | 2018-03-27 | 2018-03-21 | 2018-03-21 |  |  |  | 2018-06-07 |  | Mar-18 | Jun-18 | MW22116 - INC000007403862 – 49 RACECOURSE RD, ORANGE | Orange | 5297.075 |  | 5297.075 | 5826.7825 | 1496 | 580.83 | 2076.83 | 3220.245 | 60.79% |  | 2018-04-04 |  | Tony Gabriel
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14618 | 2019-01-16 | 2018-11-01 | 2018-11-05 | 2018-11-13 | 2018-12-18 | 2018-11-19 | 2019-01-10 |  | Nov-18 | Jan-19 | MW417R000129-AYCA-4CG9U4-2KNS-04-29-31 Dunning Avenue Rosebery | Roseberry | 1263 | 5374.42 | 6637.42 | 7301.162 |  |  | 0 | 6637.42 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-11 |  | 2018-08-30 | 80
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-12-30 | [5 empty] | Dec-19 | Jan-00 | MW22096-AYCA-3W384B-2HOR-62-433-437 Pacific Highway, Asquith | Asquith | 1358.92 |  | 1358.92 | 1494.812 |  |  | 0 | 1358.92 | 100% |  | 2020-01-13 |  | Ertan Cicek | Direct Award | 2018-03-28 |  | 2018-04-24 | 27
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW22095-AYCA-4H8EZO- 2HUH-22-117-123 Victoria Rd, Gladesville | Gladesville | 1828.86 |  | 1828.86 | 2011.746 |  |  | 0 | 1828.86 | 100% |  | 2019-07-14 |  | Ertan Cicek | Direct Award | 2018-03-29 |  | 2018-04-24 | 26
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14002 | 2018-08-09 | 2018-07-13 | 2018-07-13 | 2018-07-16 | 2018-07-31 | 2018-07-27 | 2018-08-09 |  | Jul-18 | Aug-18 | MW22093-AYCA-4RGB2W-2EAS-62-111-139 Darlinghurst Rd, Potts Point | Potts Point | 1428.48 | 11165.86 | 12594.34 | 13853.774 | 6326.5 | 451.5977 | 6778.0977 | 5816.2423 | 46.18% |  | 2018-07-27 |  | Ertan Cicek | Direct Award | 2018-03-29 |  | 2018-04-24 | 26
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13696 | 2018-06-06 | 2018-05-14 | 2018-05-15 | 2018-05-18 | 2018-05-25 | 2018-05-29 | 2018-06-05 |  | May-18 | Jun-18 | MW22104-AYCA-4DRN0U-2BRG-03-182 Raby Road Gledswood Hills | Gledswood Hills | 69.16 | 524.42 | 593.58 | 652.938 |  |  | 0 | 593.58 | 100% |  | 2018-05-29 |  | Ertan Cicek | Direct Award | 2018-04-04 |  | 2018-05-16 | 42
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13592 | 2018-06-21 | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-05 | 2018-06-14 | 2018-06-22 |  | Jun-18 | Jun-18 | MW22200-AYCA-213H8O-2DAP-01-1 Wongawilli Road Wongawilli The Grove- Stage 4 | Wongawilli | 110.88 | 544.42 | 655.3 | 720.83 |  |  | 0 | 655.3 | 100% |  | 2018-06-15 |  | Ertan Cicek | Direct Award | 2018-04-10 |  | 2018-05-18 | 38
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14054 | 2018-08-22 | 2018-07-31 | 2018-07-31 |  |  | 2018-08-14 | 2018-08-22 |  | Jul-18 | Aug-18 | MW22532-AYCA-55KUFO-2MIR-22-31 Bay Road Taren Point | Taren Point | 2382.07 |  | 2382.07 | 2620.277 | 2463.42 |  | 2463.42 | -81.35 | -3.415% |  |  |  | Ertan Cicek | Direct Award | 2018-05-30 |  | 2018-08-29 | 91
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13848 | 2018-07-06 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-25 | 2018-07-03 | 2018-07-10 |  | Jun-18 | Jul-18 | MW22177-AYCA-54QSHT-2MIL-20-42A Kurrajong Rd Prestons | Prestons | 285.6 | 512.56 | 798.16 | 877.976 |  |  | 0 | 798.16 | 100% |  | 2018-07-03 |  | Nabeel Jaimon | Direct Award | 2018-04-11 |  | 2018-05-20 | 39
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13638 | 2018-05-22 | 2018-05-07 | 2018-05-07 |  |  | 2018-05-17 | 2018-05-22 |  | May-18 | May-18 | MW22203-AYCA-2LIFV6-2ROU-02-4 Stringer Rd Kellyville | Kellyville | 1784.38 |  | 1784.38 | 1962.818 |  |  | 0 | 1784.38 | 100% |  | 2018-05-21 |  | Ertan Cicek | Direct Award | 2018-04-12 |  | 2018-05-30 | 48
A401/Greenfield | Sydney | Mickey Tran | Inv 13634 | 2018-05-22 | 2018-05-03 | 2018-05-03 |  |  | 2018-05-17 | 2018-05-22 |  | May-18 | May-18 | MW22183-AYCA-55F4KR-2REV-20-15 Fitzpatrick St, Revesby | Revesby | 3090.06 |  | 3090.06 | 3399.066 |  | 380.1827 | 380.1827 | 2709.8773 | 87.7% |  | 2018-05-17 |  | Ertan Cicek | 2018-04-10 | 2018-04-13 | 3 | 2018-06-08 | 56
A401/Greenfield | Sth Coast | Mickey Tran | Inv 13664 | 2018-05-24 | 2018-05-07 | 2018-05-07 | 2018-05-08 | 2018-05-14 | 2018-05-17 | 2018-05-24 |  | May-18 | May-18 | MW22171-AYCA-54VFA3-2COR-02- 50 Squires Cres Coledale | Coledale | 6788.96 | 3392.1154 | 10181.0754 | 11199.183 | 2366.54 |  | 2366.54 | 7814.5354 | 76.76% |  | 2018-05-21 |  | Sogand Mohtat | 2018-04-10 | 2018-04-13 | 3 | 2018-05-11 | 28
A401/Greenfield | Sydney | Mickey Tran | Inv 13714 | 2018-06-14 | 2018-05-21 | 2018-05-21 | 2018-05-22 | 2018-05-30 | 2018-05-31 | 2018-06-07 |  | May-18 | Jun-18 | MW22186 - AYCA-3L48XJ - 2CAS-23 - 2 Anella Avenue Castle Hill | Castle Hill | 4057.47 | 3402.18 | 7459.65 | 8205.615 |  | 1200.0607 | 1200.0607 | 6259.5892 | 83.91% |  | 2018-06-04 |  | Ertan Cicek | 2018-04-10 | 2018-04-13 | 3 | 2018-05-11 | 28
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13849 | 2018-07-06 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-07-02 | 2018-07-02 | 2018-07-10 |  | Jun-18 | Jul-18 | MW22195 - AYCA-4SOX62-2LIV-03- 186 Moore St Liverpool | Liverpool | 1382.92 | 5222.21 | 6605.13 | 7265.643 | 3074 |  | 3074 | 3531.13 | 53.46% |  | 2018-07-02 |  | Ertan Cicek | Direct Award | 2018-04-16 |  | 2018-06-16 | 61
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14199 | 2018-09-26 | 2018-08-21 | 2018-08-21 | 2018-08-22 | 2018-09-19 | 2018-09-04 | 2018-09-27 |  | Aug-18 | Sep-18 | MW21878-AYCA-2Q0B3G-2PAR-63-148-150 Great Western Hwy, Westmead | Westmead | 1061.65 | 5193.89 | 6255.54 | 6881.094 | 477.28 |  | 477.28 | 5778.26 | 92.37% |  | 2018-09-04 |  | Ertan Cicek | Direct Award | 2018-04-16 |  | 2018-05-30 | 44
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13715 | 2018-06-14 | 2018-05-04 | 2018-05-07 | 2018-05-08 | 2018-05-09 | 2018-05-17 | 2018-06-07 |  | May-18 | Jun-18 | MW22223-AYCA-4S0RD5-2RIV-03-14 Argowan Rd Schofields | Schofields | 13978.73 | -6944.382 | 7034.348 | 7737.7828 | 3157.04 |  | 3157.04 | 3877.308 | 55.12% |  | 2018-05-21 |  | Ertan Cicek | Direct Award | 2018-04-16 |  | 2018-05-17 | 31
A401/Greenfield | Sydney | Mickey Tran | Inv 13738 | 2018-06-20 | 2018-05-18 | 2018-05-21 | 2018-05-22 | 2018-06-14 | 2018-05-31 | 2018-06-19 |  | May-18 | Jun-18 | MW22100 - AYCA-4QBUIV - 2KTB-02 - NSB - Letitia St Katoomb | Katoomba | 2772.4 | 16972.475 | 19744.875 | 21719.3625 | 13346.45 |  | 13346.45 | 6398.425 | 32.41% |  | 2018-06-04 |  | Ertan Cicek | Direct Award | 2018-04-16 |  | 2018-05-09 | 23
A401/Greenfield | Sydney | Mickey Tran | Inv 13636 | 2018-05-22 | 2018-05-07 | 2018-05-07 |  |  | 2018-05-17 | 2018-05-22 |  | May-18 | May-18 | MW22188-AYCA-4YPJJH-2BAN-60-62 Hume Hwy Chullora | Chullora | 789.43 |  | 789.43 | 868.373 |  | 380.1827 | 380.1827 | 409.2473 | 51.84% |  | 2018-05-21 |  | Ertan Cicek | 2018-04-11 | 2018-04-18 | 7 | 2018-05-11 | 23
A401/Greenfield | Sydney | Mickey Tran | Inv 13632 | 2018-05-22 | 2018-05-03 | 2018-05-03 |  |  | 2018-05-16 | 2018-05-22 |  | May-18 | May-18 | MW22208-AYCA-4PWSOZ- 2KEL-07-1B Fairway Dr Kellyville | Kellyville | 7979.71 |  | 7979.71 | 8777.681 | 1203.8 |  | 1203.8 | 6775.91 | 84.91% |  | 2018-05-17 |  | Ertan Cicek | 2018-04-11 | 2018-04-18 | 7 | 2018-05-15 | 27
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13846 | 2018-07-06 | 2018-06-20 | 2018-06-20 | 2018-06-22 | 2018-06-16 | 2018-07-04 | 2018-07-10 |  | Jun-18 | Jul-18 | MW22258-AYCA-4BT0OX-2RIV-02-66 Schofields Road Schofields | Schofields | 1747.53 | 1318.32 | 3065.85 | 3372.435 | 490.78 |  | 490.78 | 2575.07 | 83.99% |  | 2018-07-04 |  | Ertan Cicek | Direct Award | 2018-04-18 |  | 2018-06-08 | 51
A401/Greenfield | Sydney | Mickey Tran | Inv 14492 | 2018-12-05 | 2018-10-18 | 2018-10-18 | 2018-10-24 | 2018-11-27 | 2018-11-01 | 2018-12-04 |  | Oct-18 | Dec-18 | MW22191-AYCA-4Z4FSB - 2MIL-20 - Mainfreight Logistics - 1 | Prestons | 41413.6596 | -158.48 | 41255.1796 | 45380.6976 | 23620.58 | 413.19 | 24033.77 | 17221.4096 | 41.74% |  | 2018-11-01 |  | Ertan Cicek | 2018-04-10 | 2018-04-19 | 9 | 2018-05-11 | 22
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14207 | 2018-09-26 | 2018-08-03 | 2018-08-03 | 2018-08-10 | 2018-09-18 | 2018-08-17 | 2018-09-27 |  | Aug-18 | Sep-18 | MW22218 - AYCA-4JMOL9 - 2DRU-60 - 50-52 East St, Five Dock | Five Dock | 585.25 | 5396.85 | 5982.1 | 6580.31 | 3140.46 |  | 3140.46 | 2841.64 | 47.5% |  | 2018-08-17 |  | Ertan Cicek | Direct Award | 2018-04-19 |  | 2018-06-30 | 72
A417 Greenfield MDU | Sydney | Mickey Tran | inv 13629 | 2018-05-22 | 2018-05-04 | 2018-05-04 | 2018-05-10 | 2018-05-14 | 2018-05-18 | 2018-05-22 |  | May-18 | May-18 | MW22243 - AYCA-4EUBZX - 2PTH-06 - 82 Cox Avenue, Penrith | Penrith | 410.89 | 4035.277 | 4446.167 | 4890.7837 |  |  | 0 | 4446.167 | 100% |  | 2018-05-18 |  | Ertan Cicek | Direct Award | 2018-04-19 |  | 2018-06-07 | 49
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13694 | 2018-06-06 | 2018-05-14 | 2018-05-14 | 2018-05-18 | 2018-05-30 | 2018-05-25 | 2018-06-05 |  | May-18 | Jun-18 | MW22260-AYCA-56YKSC-2CAM-02-38 Wonga St, Canterbury | Canterbury | 1202.46 | 3353.983 | 4556.443 | 5012.0873 | 1225.45 |  | 1225.45 | 3330.993 | 73.11% |  | 2018-05-28 |  | Ertan Cicek | Direct Award | 2018-04-20 |  | 2018-06-29 | 70
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14156 | 2018-09-17 | 2018-08-24 | 2018-08-24 | 2018-08-26 | 2018-09-05 | 2018-09-07 | 2018-09-21 |  | Aug-18 | Sep-18 | MW22279-AYCA-45Q6J5-2EPP-62-35 Oxford St Epping | Epping | 973.82 | 10347.61 | 11321.43 | 12453.573 | 7081.22 |  | 7081.22 | 4240.21 | 37.45% |  | 2018-09-07 |  | Ertan Cicek | Direct Award | 2018-04-20 |  | 2018-07-13 | 84
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14505 | 2018-12-05 | 2018-09-20 | 2018-09-20 | 2018-10-23 | 2018-11-27 | 2018-10-05 | 2018-12-04 |  | Sep-18 | Dec-18 | MW22284-AYCA-4KZ476-2PTH-02-38-40 Doonmore St Penrith | Penrith | 5790.01 | 4568.29 | 10358.3 | 11394.13 | 6099.75 |  | 6099.75 | 4258.55 | 41.11% |  | 2018-10-04 |  | Ertan Cicek | Direct Award | 2018-04-23 |  | 2018-07-13 | 81
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW22293 - AYCA-4NNOGX - 2PTH-02 - 240-250 Great Western Hwy Kingswood | Kingswood | 1801.74 |  | 1801.74 | 1981.914 | 3259.51 |  | 3259.51 | -1457.77 | -80.91% |  | 2019-03-14 |  | Ertan Cicek | Direct Award | 2018-04-23 |  | 2018-07-23 | 91
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13832 | 2018-07-06 | 2018-06-14 | 2018-06-14 | 2018-06-15 | 2018-06-27 | 2018-06-28 | 2018-07-05 |  | Jun-18 | Jul-18 | MW22209-AYCA-48LNJ7-2ORG-02-Cedar St Orange | Orange | 7615.85 | 1488.41 | 9104.26 | 10014.686 |  |  | 0 | 9104.26 | 100% |  | 2018-06-28 |  | Mark Leal | 2018-04-16 | 2018-04-23 | 7 | 2018-05-15 | 22
NBN Assurance Sydney | NSW | Andrew McPherson | Inv 13526 | 2018-04-24 | 2018-04-23 | 2018-04-23 |  |  |  | 2018-07-24 |  | Apr-18 | Jul-18 | MW417R000214 - INC000007724800 - Lot 1, 1 Asquith Av, Wentworth Falls | Wentworth Falls | 1153.26 |  | 1153.26 | 1268.586 |  | 329.12 | 329.12 | 824.14 | 71.46% |  | 2018-05-07 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Andrew McPherson | Inv 13529 | 2018-04-24 | 2018-04-05 | 2018-04-05 |  |  |  | 2018-06-07 |  | Apr-18 | Jun-18 | MW22342 - INC000007317444 - Lot 1, 40 Grenfell St, West Wyalong | West Wyalong | 4275.79 |  | 4275.79 | 4703.369 | 1736 | 875 | 2611 | 1664.79 | 38.94% |  | 2018-04-19 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Andrew McPherson | Inv 13531 | 2018-04-24 | 2018-03-26 | 2018-03-26 |  |  |  | 2018-07-24 |  | Mar-18 | Jul-18 | MW417R000205 - INC000007476665 - Lot 5, 23 Kookora Street, Griffith | Griffth | 896.98 |  | 896.98 | 986.678 |  | 300 | 300 | 596.98 | 66.55% |  | 2018-04-09 |  | Tony Gabriel
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13741 | 2018-06-27 | 2018-06-07 | 2018-06-07 | 2018-06-14 | 2018-06-21 | 2018-06-21 | 2018-06-28 |  | Jun-18 | Jun-18 | MW22297-AYCA-58QIXQ-2LIV-02-29 SCOTT ST, LIVERPOOL | Liverpool | 874.86 | 4861.045 | 5735.905 | 6309.4955 | 3000.14 | 1211.9632 | 4212.1033 | 1523.8017 | 26.57% |  | 2018-06-21 |  | Ertan Cicek | Direct Award | 2018-04-24 |  | 2018-06-29 | 66
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14442 | 2018-11-22 | 2018-09-20 | 2018-09-20 | 2018-09-24 | 2018-10-31 | 2018-10-04 | 2018-11-21 |  | Sep-18 | Nov-18 | MW417R000051-AYCA-55JW1J-2BOT-01-180 – 188 Maroubra Rd, Maroubra | Maroubra | 1343.18 | 4722.6 | 6065.78 | 6672.358 | 3524.25 |  | 3524.25 | 2541.53 | 41.9% |  |  |  | Ertan Cicek | Direct Award | 2018-05-22 |  | 2018-08-01 | 71
VPL New Devs | Sydney | Mickey Tran | Inv 13589 | 2018-05-10 | 2018-04-27 | 2018-04-27 | 2018-05-03 | 2018-05-07 | 2018-05-11 | 2018-06-08 |  | Apr-18 | Jun-18 | 2BUR-03-AYCA-2EBL4P | Burwood | 34899.44 |  | 34899.44 | 38389.384 | 25151.94 |  | 25151.94 | 9747.5 | 27.93% |  | 2018-05-11 |  | Adnan Khabbaz | Direct Award | 2018-04-05 |  | 2018-04-27 | 22
VPL New Devs | Sydney | Mickey Tran | Inv 13590 | 2018-05-10 | 2018-04-27 | 2018-04-27 | 2018-05-03 | 2018-05-08 | 2018-05-11 | 2018-06-08 |  | Apr-18 | Jun-18 | 2CAM-60-AYCA-4VCIKM | Campsie | 30368.89 |  | 30368.89 | 33405.779 | 15394.18 |  | 15394.18 | 14974.71 | 49.31% |  | 2018-05-11 |  | Adnan Khabbaz | Direct Award | 2018-04-05 |  | 2018-04-20 | 15
VPL New Devs | Sydney | Mickey Tran | Inv 13724 | 2018-06-18 | 2018-06-01 | 2018-06-01 | 2018-06-06 | 2018-06-13 | 2018-06-15 | 2018-07-20 |  | Jun-18 | Jul-18 | 2KRG-03-AYCA-2Z4T2N | Kooringal | 39419.23 |  | 39419.23 | 43361.153 |  | 21000 | 21000 | 18419.23 | 46.73% |  | 2018-06-15 |  | Adnan Khabbaz | Direct Award | 2018-04-18 |  | 2018-05-22 | 34
VPL New Devs | Sydney | Mickey Tran | Inv 13656 | 2018-05-23 | 2018-05-14 | 2018-05-14 | 2018-05-18 | 2018-05-21 | 2018-05-21 | 2018-06-08 |  | May-18 | Jun-18 | 2NRN-05-AYCA-4B5K39 | Narrellen | 1897.3507 |  | 1897.3507 | 2087.0857 | 443.04 | 208 | 651.04 | 1246.3107 | 65.69% |  | 2018-05-28 |  | Adnan Khabbaz | Direct Award | 2018-04-20 |  | 2018-06-04 | 45
VPL New Devs | Sydney | Mickey Tran | Inv 13834 | 2018-07-06 | 2018-05-22 | 2018-05-22 |  |  | 2018-06-05 | 2018-07-20 |  | May-18 | Jul-18 | 2PET-67-AYCA-4W7GEZ, | Petersham | 46564.38 |  | 46564.38 | 51220.818 | 27635.11 |  | 27635.11 | 18929.27 | 40.65% |  | 2018-06-05 |  | Adnan Khabbaz | Direct Award | 2018-04-05 |  | 2018-04-12 | 7
VPL New Devs | Sydney | Mickey Tran | Inv 13835 | 2018-07-06 | 2018-06-25 | 2018-06-25 |  |  | 2018-07-09 | 2018-07-20 |  | Jun-18 | Jul-18 | 2PET-69-AYCA-3G34XT | Petersham | 30911.4093 |  | 30911.4093 | 34002.5502 | 22810.11 |  | 22810.11 | 8101.2993 | 26.21% |  | 2018-07-09 |  | Adnan Khabbaz | Direct Award | 2018-04-05 |  | 2018-04-30 | 25
VPL New Devs | Sydney | Mickey Tran | Inv 13591 | 2018-05-10 | 2018-04-26 | 2018-04-26 | 2018-05-08 | 2018-05-10 | 2018-05-10 | 2018-06-08 |  | Apr-18 | Jun-18 | 2ROU-04-AYCA-39XZGZ | Rouse Hill | 5918.97 |  | 5918.97 | 6510.867 |  | 1000 | 1000 | 4918.97 | 83.11% |  | 2018-05-10 |  | Adnan Khabbaz | Direct Award | 2018-04-11 |  | 2018-05-08
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13751 | 2018-06-20 | 2018-05-29 | 2018-05-29 | 2018-05-31 | 2018-06-05 | 2018-06-08 | 2018-06-19 |  | May-18 | Jun-18 | MW22091-AYCA-4MNF1P-2NRN-10-11 & 15 Holborn Circuit, Gregory Hills | Gregory Hills | 4140.32 | 7286.54 | 11426.86 | 12569.546 | 6489.44 |  | 6489.44 | 4937.42 | 43.21% |  | 2018-06-12 |  | Nabeel Jaimon | Direct Award | 2018-04-24 |  | 2018-05-31 | 37
A401/Greenfield | Sydney | Mickey Tran | Inv 13691 | 2018-06-06 | 2018-05-16 | 2018-05-16 | 2018-05-18 | 2018-05-23 | 2018-06-05 | 2018-06-05 |  | May-18 | Jun-18 | MW22288-AYCA-4R7UP6-2MIL-04-40 Government Rd, Hinchinbrook | Hinchinbrook | 8639.27 | -2352.55 | 6286.72 | 6915.392 | 1143.61 | 704 | 1847.61 | 4439.11 | 70.61% |  | 2018-05-30 |  | Andrwe Mahassy | 2018-04-19 | 2018-04-24 | 5 | 2018-05-23 | 29
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13984 | 2018-08-03 | 2018-06-27 | 2018-06-27 | 2018-07-02 | 2018-07-26 | 2018-07-11 | 2018-08-09 |  | Jun-18 | Aug-18 | MW22309-AYCA-3V5BM6-2DRU-61-197-199 Lyons Rd Drummoyne | Drummoyne | 1734.4 | 13956.892 | 15691.292 | 17260.4212 | 9740.19 |  | 9740.19 | 5951.102 | 37.93% |  | 2018-07-11 |  | Ertan Cicek | Direct Award | 2018-04-24 |  | 2018-05-23 | 29
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14619 | 2019-01-16 | 2018-10-26 | 2018-10-26 | 2018-11-13 | 2018-12-18 | 2018-11-09 | 2019-01-10 |  | Oct-18 | Jan-19 | MW22296-AYCA-4RB8MD-2LID-03-2 Clarke St, Berala | Berala | 742.8 | 15057.09 | 15799.89 | 17379.879 | 6285.84 |  | 6285.84 | 9514.05 | 60.22% |  | 2018-11-09 |  | Ertan Cicek | Direct Award | 2018-04-24 |  | 2018-06-29 | 66
A417 Greenfield MDU | Sydney | Mickey Tran | inv 13773 | 2018-06-29 | 2018-06-06 | 2018-06-07 | 2018-06-07 | 2018-06-08 | 2018-06-21 | 2018-06-22 |  | Jun-18 | Jun-18 | MW22287-AYCA-4LQOVR-2KEL-08-25 Water Creek Boulevard Kellyville | Kellyville | 363.7 | 599.79 | 963.49 | 1059.839 |  |  | 0 | 963.49 | 100% |  | 2018-06-21 |  | Ertan Cicek | Direct Award | 2018-04-27 |  | 2018-06-15 | 49
A417 Greenfield MDU | Nth Coast | Mickey Tran | Inv 13911 | 2018-07-24 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2018-07-12 | 2018-07-13 | 2018-07-24 |  | Jun-18 | Jul-18 | MW22301-AYCA-541Y7O-2WAU-20-728-730 Beechwood | Wauchope | 1370.1 | 5576.54 | 6946.64 | 7641.304 | 4422.17 |  | 4422.17 | 2524.47 | 36.34% |  | 2018-07-13 |  | Ertan Cicek | Direct Award | 2018-04-27 |  | 2018-07-16 | 80
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2018-01-30 | [5 empty] | Jan-18 | Jan-00 | MW22319-AYCA-33L9HP-2BAN-64-Restwell & Leonard St Bankstown | Bankstown | 2255.04 |  | 2255.04 | 2480.544 | 3673.03 |  | 3673.03 | -1417.99 | -62.88% |  | 2018-02-13 |  | Ertan Cicek | Direct Award | 2018-04-27 |  | 2018-06-29 | 63
A417 Greenfield MDU | Sth NSW | Mickey Tran | Inv 14082 | 2018-08-29 | 2018-08-08 | 2018-08-08 |  |  | 2018-08-22 | 2018-08-28 |  | Aug-18 | Aug-18 | MW22334-AYCA-3V2064-2WAG-01-29 Gibson St, Boorooma | Boorooma | 4344.17 |  | 4344.17 | 4778.587 |  |  | 0 | 4344.17 | 100% |  | 2018-08-22 |  | Ertan Cicek | Direct Award | 2018-04-27 |  | 2018-07-10 | 74
NBN Assurance Sydney | NSW | Mickey Tran | Inv 13544 | 2018-04-30 | 2018-03-26 | 2018-03-26 |  |  |  | 2018-07-05 |  | Mar-18 | Jul-18 | MW417R000206 - INC000007540081 - Lot 4, 126 Aberford Street, Coonamble | Coonamble | 1550.47 |  | 1550.47 | 1705.517 |  | 419.33 | 419.33 | 1131.14 | 72.95% |  | 2018-04-09 |  | Tony Gabriel
NBN Assurance Sydney | NSW | Mickey Tran | Inv 13547 | 2018-04-30 | 2018-03-26 | 2018-03-26 |  |  |  | 2018-07-05 |  | Mar-18 | Jul-18 | MW417R000208 - INC000007494309 - LOT 4, 9 DUBBO ST, COONAMBLE | Coonamble | 640.7 |  | 640.7 | 704.77 |  | 176.56 | 176.56 | 464.14 | 72.44% |  | 2018-04-09 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Mickey Tran | Inv 13549 | 2018-04-30 | 2018-03-28 | 2018-03-28 |  |  |  | 2018-06-19 |  | Mar-18 | Jun-18 | MW417R000207 - INC000007482861 - 52-58 WARATAH ST COWRA | Cowra | 640.7 |  | 640.7 | 704.77 |  | 175 | 175 | 465.7 | 72.69% |  | 2018-04-11 |  | Tony Gabriel
NBN Assurance Sydney | NSW | Mickey Tran | Inv 13550 | 2018-04-30 | 2018-03-27 | 2018-03-27 |  |  |  | 2018-07-05 |  | Mar-18 | Jul-18 | MW417R000213-2ORG-03-183 Summer St, Orange | Orange | 256.28 |  | 256.28 | 281.908 |  | 112 | 112 | 144.28 | 56.3% |  | 2018-04-10 |  | Tony Gabriel
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13752 | 2018-06-20 | 2018-05-30 | 2018-05-30 | 2018-06-14 | 2018-06-21 | 2018-06-13 | 2018-06-28 |  | May-18 | Jun-18 | MW22314-AYCA-4A5XPU-2BLK-11-29 Norfolk Street, Blacktown | Blacktown | 685.25 | 2551.76 | 3237.01 | 3560.711 | 306.4 |  | 306.4 | 2930.61 | 90.53% |  | 2018-06-13 |  | Ertan Cicek | Direct Award | 2018-04-27 |  | 2018-07-11 | 75
A401/Greenfield | Sth Coast | Mickey Tran | Inv 14083 | 2018-08-29 | 2018-08-08 | 2018-08-08 | 2018-08-14 | 2018-08-16 | 2018-08-22 | 2018-09-05 |  | Aug-18 | Sep-18 | MW21532-AYCA-4TBHNX - 2SHH-05 - NSB - 125 LAKE ENTRANCE - SURVEY | Barrack Heights | 1698 | 9194.36 | 10892.36 | 11981.596 | 2387.68 | 8787.32 | 11175 | -282.64 | -2.595% |  | 2018-08-22 |  | Andrew Mahssy | 2017-10-23 | 2018-02-15 | 115 | 2018-03-23 | 36
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14204 | 2018-09-26 | 2018-08-20 | 2018-08-20 | 2018-08-21 | 2018-09-19 | 2018-09-03 | 2018-09-27 |  | Aug-18 | Sep-18 | MW22263-AYCA-31DCKF-2EAS-62-18-20 Neild Ave Darlinghurst | Darlinghurst | 2099.66 | 6645.09 | 8744.75 | 9619.225 | 3019.28 |  | 3019.28 | 5725.47 | 65.47% |  | 2018-09-03 |  | Lindy Chan | Direct Award | 2018-04-30 |  | 2018-07-16 | 77
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13772 | 2018-06-29 | 2018-06-01 | 2018-06-04 | 2018-06-06 | 2018-06-18 | 2018-06-18 | 2018-06-26 |  | Jun-18 | Jun-18 | MW22265-AYCA-4R1HNT-2MIL-62-6-8 Facey Cres Lurnea | Lumea | 1554.24 | 13339.46 | 14893.7 | 16383.07 | 6425.2 |  | 6425.2 | 8468.5 | 56.86% |  | 2018-06-18 |  | Ertan Cicek | Direct Award | 2018-05-01 |  | 2018-06-29 | 59
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13774 | 2018-06-29 | 2018-05-25 | 2018-05-29 | 2018-05-31 | 2018-06-19 | 2018-06-08 | 2018-06-22 |  | May-18 | Jun-18 | MW22347-AYCA-4XTH50-2HOM-03-31-35 Smallwood Ave Homebush | Homebush | 2743.96 | 6734.32 | 9478.28 | 10426.108 | 6152.49 |  | 6152.49 | 3325.79 | 35.09% |  | 2018-06-12 |  | Ertan Cicek | Direct Award | 2018-05-01 |  | 2018-06-08 | 38
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14387 | 2018-11-14 | 2018-10-03 | 2018-10-03 | 2018-10-11 | 2018-10-26 | 2018-10-17 | 2018-11-13 |  | Oct-18 | Nov-18 | MW22346-AYCA-50FP2M-2ROU-03-Oxlade Street Kellyville | Kellyville | 9295.62 | 72631.09 | 81926.71 | 90119.381 | 55633.47 |  | 55633.47 | 26293.24 | 32.09% |  | 2018-10-17 |  | Ertan Cicek | Direct Award | 2018-05-01 |  | 2018-06-27 | 57
A401/Greenfield | Sth Coast | Mickey Tran |  |  | 2018-07-05 | 2018-07-05 | 2018-07-09 | 2018-07-16 | 2018-07-19 | 2018-07-31 |  | Jul-18 | Jul-18 | MW22333 - AYCA-54SUCD - 2PKE-06 - Warehouse Pl Berkeley | Berkeley | 3573.39 | 1133.6 | 4706.99 | 5177.689 | 1960 |  | 1960 | 2746.99 | 58.36% |  | 2018-07-19 |  | Mark Leal | Direct Award | 2018-05-01 |  | 2018-06-22 | 52
A401/Greenfield | Nth Coast | Mickey Tran | Inv 13912 | 2018-07-24 | 2018-06-21 | 2018-06-21 | 2018-06-29 | 2018-07-12 | 2018-07-05 | 2018-07-24 |  | Jun-18 | Jul-18 | MW22336-AYCA-4MJKV1-2KMS-21-Lot 37 Springfields Drive, Greenhill | Greenhill | 7769.35 | -120 | 7649.35 | 8414.285 | 3003.86 |  | 3003.86 | 4645.49 | 60.73% |  | 2018-07-05 |  | Mark Leal | 2018-04-27 | 2018-05-01 | 4 | 2018-05-30 | 29
A401/Greenfield | Central Coast | Mickey Tran | Inv 13831 | 2018-07-06 | 2018-06-15 | 2018-06-15 | 2018-06-15 | 2018-06-27 | 2018-06-29 | 2018-07-05 |  | Jun-18 | Jul-18 | MW22335 - AYCA-55S741 - 2WOY-03 -Broken Bay – 1 | Ettalong Beach | 5278.06 | 535.66 | 5813.72 | 6395.092 |  |  | 0 | 5813.72 | 100% |  |  |  | Mark Leal | 2018-04-27 | 2018-05-02 | 5 | 2018-05-30 | 28
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14206 | 2018-09-27 | 2018-08-23 | 2018-08-23 | 2018-04-24 | 2018-09-18 | 2018-09-06 | 2018-09-27 |  | Aug-18 | Sep-18 | MW22331-AYCA-3CFI3W-2EPP-05-120 Herring Road Marsfield | Marsfield | 1102.48 | 7741.48 | 8843.96 | 9728.356 |  |  | 0 | 8843.96 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-05-02 |  | 2018-06-06 | 35
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-12-30 | [5 empty] | Dec-19 | Jan-00 | MW22313 - AYCA-48S696 - 2BLK-03 - 3-7 Wallace St Blacktown | Blacktown | 1763.74 |  | 1763.74 | 1940.114 |  |  | 0 | 1763.74 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-05-02 |  | 2018-06-29 | 58
A401/Greenfield | Central Coast | Mickey Tran | Inv 13743 | 2018-06-18 | 2018-05-03 | 2018-05-30 |  |  | 2018-06-14 | 2018-06-19 |  | May-18 | Jun-18 | MW22477 - AYCA-4XVGZ8 - 2WYO-03 -140 Pacific Highway Tuggerah | Tuggerah | 3243.26 |  | 3243.26 | 3567.586 | 2358.27 |  | 2358.27 | 884.99 | 27.29% |  |  |  | Dave Yeomans | 2018-05-03 | 2018-05-30 | 27 | 2018-07-02 | 33
A401/Greenfield | Nth Coast | Mickey Tran | Inv 13844 | 2018-07-06 | 2018-06-06 | 2018-06-15 | 2018-06-18 | 2018-06-20 | 2018-06-29 | 2018-07-10 |  | Jun-18 | Jul-18 | MW22472 - 2PTM-23 - AYCA-4Q0G0C-20 Scarborough Close Port Macquarie | Port Macquarie | 8260.8 | 8719.58 | 16980.38 | 18678.418 |  |  | 0 | 16980.38 | 100% |  |  |  | Dave Yeomans | 2018-05-29 | 2018-06-14 | 16 | 2018-07-02 | 18
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13692 | 2018-06-06 | 2018-05-18 | 2018-05-18 |  |  | 2018-05-31 | 2018-06-05 |  | May-18 | Jun-18 | MW22351-AYCA-49Z80V-2PIT-01-44 Wells Street Pitt Town | Pitt Town | 2366 |  | 2366 | 2602.6 | 1129.72 |  | 1129.72 | 1236.28 | 52.25% |  |  |  | Ertan Cicek | Direct Award | 2018-05-03 |  | 2018-06-27 | 55
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13775 | 2018-06-29 | 2018-05-14 | 2018-05-15 | 2018-05-30 | 2018-06-08 | 2018-05-29 | 2018-06-22 |  | May-18 | Jun-18 | MW22358-AYCA-4OHMS3-2BLK-07-35 Holbeche Road Arndell Park-INT HMDU | Arndell park | 285.6 | 294.54 | 580.14 | 638.154 |  |  | 0 | 580.14 | 100% |  |  |  | Nabeel Jaimon | Direct Award | 2018-05-03 |  | 2018-05-30 | 27
A401/Greenfield | ACT | Mickey Tran | Inv 14007 | 2018-08-09 | 2018-07-16 | 2018-07-16 | 2018-07-16 | 2018-07-26 | 2018-07-30 | 2018-08-09 |  | Jul-18 | Aug-18 | MW22350-AYCA-4VAQ8P-9SCU-07-11 Prevost Pl MacGregor, ACT | MacGregor | 10564.934 | 3577.89 | 14142.824 | 15557.1064 | 7339.16 |  | 7339.16 | 6803.664 | 48.11% |  |  |  | Andrew Mahassy | 2018-05-01 | 2018-05-07 | 6 | 2018-06-11 | 35
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14671 | 2019-01-18 | 2019-04-30 | 2018-12-14 |  |  | 2018-12-28 | 2019-01-24 |  | Dec-18 | Jan-19 | MW22378-AYCA-4YJULB-2REV-22-479 Henry Lawson Drive Milperra | Milperra | 2570.4 |  | 2570.4 | 2827.44 |  |  | 0 | 2570.4 | 100% |  |  |  | Nabeel Jaimon | Direct Award | 2018-05-07 |  | 2018-06-26 | 50
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13936 | 2018-07-27 | 2018-07-04 | 2018-07-04 | 2018-07-09 | 2018-07-19 | 2018-07-18 | 2018-07-31 |  | Jul-18 | Jul-18 | MW22405-AYCA-3BBGCI-2RIV-04-737 Windsor Rd Box Hill | Box Hill | 611.63 | 530.88 | 1142.51 | 1256.761 |  |  | 0 | 1142.51 | 100% |  |  |  | Mark Leal | Direct Award | 2018-05-07 |  | 2018-08-02 | 87
NBN FttC Drops | Sydney | Mickey Tran | Inv 13746 | 2018-06-14 | 2018-06-14 | 2018-06-08 |  |  |  | 2018-06-14 |  | Jun-18 | Jun-18 | MW417R000166-2MIR-31-STELLAR NPDL_MWR (A417)-Miranda | Miranda | 6924.696 |  | 6924.696 | 7617.1656 |  |  | 0 | 6924.696 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Mickey Tran | Inv 14338 | 2018-10-29 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-11 | 2018-10-19 | 2018-10-29 |  | Oct-18 | Oct-18 | MW417R000166-2MIR-31-STELLAR NPDL_MWR (A417)-Miranda | Miranda | 15716.664 | 33253.06 | 48969.724 | 53866.6964 | 25274 |  | 25274 | 23695.724 | 48.39% |  |  |  | Kirsty Doyle | Direct Award
A417 Greenfield MDU | Sydney East | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R000049-AYCA-24QAXK-2ROC-03-10 Martin Avenue Arncliffe | Arncliffe | 2655.28 |  | 2655.28 | 2920.808 | 5927.53 |  | 5927.53 | -3272.25 | -123.2% |  |  |  | Ertan Cicek | Direct Award | 2018-05-22 |  | 2018-08-06 | 76
NBN FttC Drops | Sydney | Mickey Tran | Inv 14270 | 2018-10-16 | 2018-08-24 | 2018-08-24 | 2018-09-06 | 2018-09-14 | 2018-09-07 | 2018-10-18 |  | Aug-18 | Oct-18 | MW417R000169-2MIR-29-STELLAR NPDL_MWR (A417)-Miranda | Miranda | 19955.096 | 120118.47 | 140073.566 | 154080.9226 | 37920 | 3861.34 | 41781.34 | 98292.226 | 70.17% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13747 | 2018-06-14 | 2018-06-14 | 2018-06-08 |  |  |  | 2018-06-14 |  | Jun-18 | Jun-18 | MW417R000169-2MIR-29-STELLAR NPDL_MWR (A417)-Miranda | Miranda | 8552.184 |  | 8552.184 | 9407.4024 |  |  | 0 | 8552.184 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14158 | 2018-09-17 | 2018-08-09 | 2018-08-09 | 2018-08-20 | 2018-08-22 | 2018-08-30 | 2018-09-18 |  | Aug-18 | Sep-18 | MW417R000170-2MIR-22-STELLAR NPDL_MWR (A417)-Miranda | Miranda | 14019.04 | 43239.62 | 57258.66 | 62984.526 | 34165 |  | 34165 | 23093.66 | 40.33% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13745 | 2018-06-14 | 2018-06-14 | 2018-06-08 |  |  |  | 2018-06-14 |  | Jun-18 | Jun-18 | MW417R000170-2MIR-22-STELLAR NPDL_MWR (A417)-Miranda | Miranda | 6008.16 |  | 6008.16 | 6608.976 |  |  | 0 | 6008.16 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13750 | 2018-06-14 | 2018-06-14 | 2018-07-30 |  |  |  | 2018-06-14 |  | Jul-18 | Jun-18 | MW417R000172-2MON-25-STELLAR NPDL_MWR (A417)-Mona Vale | Mona Vale | 5434.32 |  | 5434.32 | 5977.752 |  |  | 0 | 5434.32 | 100% |  |  |  | Kirsty Doyle | Direct Award
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2019-02-28 | 2019-03-14 |  | Feb-19 | Mar-19 | MW417R000502-AYCA-4UMUPA-2KEL-07-21 Fairway Dr, Kellyville | Kellyville | 1976.12 | 7783.01 | 9759.13 | 10735.043 | 6589.49 |  | 6589.49 | 3169.64 | 32.48% |  | 2019-02-28 |  | Ertan Cicek | Direct Award | 2018-07-05 |  | 2018-09-28 | 85
NBN FttC Drops | Sydney | Rob Panovski | Inv 14726 | 2019-02-15 | 2019-01-15 | 2019-01-15 | 2019-01-15 | 2019-01-17 | 2019-01-29 | 2019-02-15 |  | Jan-19 | Feb-19 | MW417R000172-2MON-25-STELLAR NPDL_MWR (A417)-Mona Vale | Mona Vale | 12680.08 | 34984.539 | 47664.619 | 52431.0809 | 25885 |  | 25885 | 21779.619 | 45.69% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14213 | 2018-10-04 | 2018-08-24 | 2018-08-24 | 2018-09-07 | 2018-09-14 | 2018-09-07 | 2018-10-04 |  | Aug-18 | Oct-18 | MW417R000174-2MIR-26-STELLAR NPDL_MWR (A417)-Miranda | Miranda | 18303.712 | 92993.03 | 111296.742 | 122426.4162 | 71034.05 |  | 71034.05 | 40262.692 | 36.18% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13748 | 2018-06-14 | 2018-06-14 | 2018-06-08 |  |  |  | 2018-06-14 |  | Jun-18 | Jun-18 | MW417R000174-2MIR-26-STELLAR NPDL_MWR (A417)-Miranda | Miranda | 7844.448 |  | 7844.448 | 8628.8928 |  |  | 0 | 7844.448 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14212 | 2018-10-04 | 2018-08-24 | 2018-08-24 | 2018-09-05 | 2018-09-14 | 2018-09-07 | 2018-10-04 |  | Aug-18 | Oct-18 | MW417R000180-2MIR-25-STELLAR NPDL_MWR (A417)-Miranda | Miranda | 37629.37 | 248469.0625 | 286098.4325 | 314708.2758 | 195778 |  | 195778 | 90320.4325 | 31.57% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13749 | 2018-06-14 | 2018-06-14 | 2018-06-08 |  |  |  | 2018-06-14 |  | Jun-18 | Jun-18 | MW417R000180-2MIR-25-STELLAR NPDL_MWR (A417)-Miranda | Miranda | 16126.87 |  | 16126.87 | 17739.557 |  |  | 0 | 16126.87 | 100% |  |  |  | Kirsty Doyle | Direct Award
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14614 | 2019-01-16 | 2018-11-13 | 2018-11-13 | 2018-11-13 | 2018-12-18 | 2018-11-28 | 2019-01-10 |  | Nov-18 | Jan-19 | MW417R002068 - AYCA-5PIVSY -2BTH-02 - 11 Lombard Drive, Robin Hill Ext | Robin Hill | 6507.52 | 4822.632 | 11330.152 | 12463.1672 | 3171.2 |  | 3171.2 | 8158.952 | 72.01% |  |  |  | Ertan Cicek | Direct Award | 2018-10-31 |  | 2018-12-20 | 50
NBN FttC Drops | Sydney | Rob Panovski | Inv 14267 | 2018-10-16 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-13 | 2018-09-24 | 2018-10-18 |  | Sep-18 | Oct-18 | MW417R000536-2BGI-20-STELLAR NPDL_MWR (A417)-Boggabri | Boggabri | 27298.42 | -3015.41 | 24283.01 | 26711.311 | 10557.5 |  | 10557.5 | 13725.51 | 56.52% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski |  |  | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-13 | 2018-09-24 | 2018-10-08 |  | Sep-18 | Oct-18 | MW417R000540-2CTH-20-STELLAR NPDL_MWR (A417)-Crescent Head | Cresent Heads | 9725.67 | 100876.49 | 110602.16 | 121662.376 | 69400.25 |  | 69400.25 | 41201.91 | 37.25% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13870 | 2018-07-18 | 2018-07-18 | 2018-07-14 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000540-2CTH-20-STELLAR NPDL_MWR (A417)-Crescent Head | Cresent Heads | 4168.15 |  | 4168.15 | 4584.965 |  |  | 0 | 4168.15 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14337 | 2018-10-29 | 2018-10-08 | 2018-10-08 | 2018-10-08 | 2018-10-18 | 2018-10-22 | 2018-10-29 |  | Oct-18 | Oct-18 | MW417R000541-2DRG-20-STELLAR NPDL_MWR (A417)-Dorrigo | Dorrigo | 11915.09 | 65538.04 | 77453.13 | 85198.443 | 43326.5 |  | 43326.5 | 34126.63 | 44.06% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13875 | 2018-07-17 | 2018-07-17 | 2018-08-30 |  |  |  | 2018-07-17 | Jul-18 | Aug-18 | Jul-18 | MW417R000541-2DRG-20-STELLAR NPDL_MWR (A417)-Dorrigo | Dorrigo | 5106.47 |  | 5106.47 | 5617.117 |  |  | 0 | 5106.47 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14339 | 2018-10-29 | 2018-09-20 | 2018-09-20 | 2018-10-05 | 2018-10-11 | 2018-10-04 | 2018-10-29 |  | Sep-18 | Oct-18 | MW417R000545-2ERP-20-STELLAR NPDL_MWR (A417)-Eastern Creek | Eastern Creek | 12367.66 | 104672.1228 | 117039.7828 | 128743.761 | 77282 |  | 77282 | 39757.7828 | 33.97% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13871 | 2018-07-18 | 2018-07-18 | 2018-07-14 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000545-2ERP-20-STELLAR NPDL_MWR (A417)-Eastern Creek | Eastern Creek | 5300.42 |  | 5300.42 | 5830.462 |  |  | 0 | 5300.42 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14590 | 2018-12-19 | 2018-11-23 | 2018-11-23 | 2018-11-29 | 2018-12-07 | 2018-11-28 | 2018-12-20 |  | Nov-18 | Dec-18 | MW417R000546-2ERP-21 STELLAR NPDL_MWR (A417)- Erskine Park | Eskine park | 2117.05 | 17704.82 | 19821.87 | 21804.057 | 9950 |  | 9950 | 9871.87 | 49.8% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14274 | 2018-10-17 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-17 | 2018-09-26 | 2018-10-18 |  | Sep-18 | Oct-18 | MW417R000548-2LCT-01 - STELLAR NPDL_MWR (A417)-Lake Cathie | Lake Cathie | 1744.7 | 15411.875 | 17156.575 | 18872.2325 | 5961 |  | 5961 | 11195.575 | 65.26% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14268 | 2018-10-16 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-13 | 2018-09-24 | 2018-10-18 |  | Sep-18 | Oct-18 | MW417R000549 - 2MAN-20 - STELLAR NPDL_MWR (A417)-Manilla | Manilla | 6597.93 | 31965.91 | 38563.84 | 42420.224 | 19796.5 |  | 19796.5 | 18767.34 | 48.67% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | inv 13865 | 2018-07-17 | 2018-07-17 | 2018-07-14 |  |  |  | 2018-07-17 | Aug-18 | Jul-18 | Jul-18 | MW417R000549 - 2MAN-20 - STELLAR NPDL_MWR (A417)-Manilla | Manilla | 2827.69 |  | 2827.69 | 3110.459 |  |  | 0 | 2827.69 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14394 | 2018-11-14 | 2018-10-05 | 2018-10-05 | 2018-10-12 | 2018-10-24 | 2018-10-19 | 2018-11-15 |  | Oct-18 | Nov-18 | MW417R000550 - 2MIR-24 - STELLAR NPDL_MWR (A417)-Miranda | Miranda | 27032.5 | 215504.5903 | 242537.0903 | 266790.7993 | 166289 |  | 166289 | 76248.0903 | 31.44% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13876 | 2018-07-18 | 2018-07-18 | 2018-07-18 |  |  |  | 2018-07-19 |  | Jul-18 | Jul-18 | MW417R000550 - 2MIR-24 - STELLAR NPDL_MWR (A417)-Miranda | Miranda | 11585.36 |  | 11585.36 | 12743.896 |  |  | 0 | 11585.36 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14587 | 2018-12-19 | 2018-11-23 | 2018-11-23 | 2018-11-29 | 2018-12-10 | 2018-12-07 | 2018-12-20 |  | Nov-18 | Dec-18 | MW417R000552-2MON-28-STELLAR NPDL_MWR (A417) - Mona Vale | Mona Vale | 18014.18 | 149994.038 | 168008.218 | 184809.0398 | 113668 |  | 113668 | 54340.218 | 32.34% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13872 | 2018-07-18 | 2018-07-18 | 2018-07-14 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000552-2MON-28-STELLAR NPDL_MWR (A417) - Mona Vale | Mona Vale | 7720.37 |  | 7720.37 | 8492.407 |  |  | 0 | 7720.37 | 100% |  |  |  | Kirsty Doyle | Direct Award
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 13845 | 2018-07-06 | 2018-06-07 | 2018-06-07 | 2018-06-08 | 2018-07-02 | 2018-06-21 | 2018-07-10 |  | Jun-18 | Jul-18 | MW22372-AYCA-4WVTLQ-2DBB-01-48 Southlakes Parade Dubbo | Dubbo | 93.73 | 2506.95 | 2600.68 | 2860.748 |  |  | 0 | 2600.68 | 100% |  |  |  | Mark Leal | Direct Award | 2018-05-08 |  | 2018-08-01 | 85
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13635 | 2018-05-22 | 2018-05-23 | 2018-05-23 | 2018-05-31 | 2018-06-05 | 2018-06-05 | 2018-06-12 |  | May-18 | Jun-18 | MW22345-AYCA-4R1HAL-2RIV-07-Crown, Edmund, William St-7 Riverstone | Riverstone | 651.87 | 755.6 | 1407.47 | 1548.217 | 384.8427 |  | 384.8427 | 1022.6273 | 72.66% |  |  |  | Ertan Cicek | Direct Award | 2018-05-09 |  | 2018-07-13 | 65
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  | 2019-02-22 | 2019-02-22 | 2019-02-22 |  | 2019-03-08 | 2019-03-22 |  | Feb-19 | Mar-19 | MW22436 - AYCA-4SRFAN-2226 Roseberry St Balgowlah NSW EXT | Balgowlah | 1928.04 | 9152.64 | 11080.68 | 12188.748 | 5809.61 |  | 5809.61 | 5271.07 | 47.57% |  |  |  | Lindy Chan | Direct Award | 2018-05-11 |  | 2018-07-25 | 75
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14001 | 2018-08-09 | 2018-07-16 | 2018-07-16 | 2018-07-17 | 2018-07-31 | 2018-07-30 | 2018-08-09 |  | Jul-18 | Aug-18 | MW22437-AYCA-4PIIN5-2RYD-66-101 Church St Ryde | Ryde | 646.2 | 3120.542 | 3766.742 | 4143.4162 |  |  | 0 | 3766.742 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-05-11 |  | 2018-06-26 | 46
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13717 | 2018-06-14 | 2018-05-24 | 2018-05-25 | 2018-05-24 | 2018-05-30 | 2018-06-05 | 2018-06-12 |  | May-18 | Jun-18 | MW22366-AYCA-117I3H-2RIV-01-34 Station Street Schofields | Schofields | 1073.74 | 14716.48 | 15790.22 | 17369.242 | 11326.55 |  | 11326.55 | 4463.67 | 28.27% |  |  |  | Ertan Cicek | Direct Award | 2018-05-14 |  | 2018-08-01 | 79
A401/Greenfield | Central West | Marshell Antonio | Inv 14217 | 2018-10-09 | 2018-09-14 | 2018-09-14 | 2018-09-18 | 2018-09-27 | 2018-09-28 | 2018-10-09 |  | Sep-18 | Oct-18 | MW22392-AYCA-53Y8BE-2WEL-01-2WEL-01-17 Nicholii St, Montefiores | Montefiores | 7630.73 | -2923.09 | 4707.64 | 5178.404 |  |  | 0 | 4707.64 | 100% |  |  |  | Mark Leal | Direct Award | 2018-05-14 |  | 2018-06-15 | 32
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14385 | 2018-11-14 | 2018-08-31 | 2018-08-31 | 2018-09-17 | 2018-10-26 | 2018-09-14 | 2018-11-13 |  | Aug-18 | Nov-18 | MW417R000397-AYCA-5BX3DW-2NEW-23-7-9 Hutchinson St, St Peters - 1 | St Peters | 1998.95 | 5280.69 | 7279.64 | 8007.604 | 3562.29 |  | 3562.29 | 3717.35 | 51.07% |  |  |  | Ertan Cicek | Direct Award | 2018-06-29 |  | 2018-09-28 | 91
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13716 | 2018-06-20 | 2018-05-31 | 2018-05-31 | 2018-05-31 | 2018-06-05 | 2018-06-14 | 2018-06-22 |  | May-18 | Jun-18 | MW22454-AYCA-2CVKCU-2ROT-60-60 Wallgrove Rd Easter Creek | Eastern Creek | 1556.8 | 1927.12 | 3483.92 | 3832.312 | 2361.42 |  | 2361.42 | 1122.5 | 32.22% |  |  |  | Ertan Cicek | Direct Award | 2018-05-17 |  | 2018-07-31 | 75
A401/Greenfield | Sth NSW | Mickey Tran | Inv 14280 | 2018-10-17 | 2018-09-24 | 2018-09-24 | 2018-09-24 | 2018-09-27 | 2018-10-08 | 2018-10-22 |  | Sep-18 | Oct-18 | MW22433-AYCA-4OJUJI-2GLB-04-20 Cathcart St Goulburn | Goulburn | 4404.14 | 3781.349 | 8185.489 | 9004.0379 |  |  | 0 | 8185.489 | 100% |  |  |  | Sogand Mohtat | 2018-05-15 | 2018-05-18 | 3 | 2018-06-20 | 33
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14203 | 2018-09-26 | 2018-08-08 | 2018-08-08 | 2018-08-16 | 2018-09-18 | 2018-08-22 | 2018-09-27 |  | Aug-18 | Sep-18 | MW417R000034-AYCA-44MH0G-2RYD-63-133-137 Bowden Street Meadowbank | Meadowbank | 3333.98 | 6685.2 | 10019.18 | 11021.098 | 5626.51 |  | 5626.51 | 4392.67 | 43.84% |  |  |  | Ertan Cicek | Direct Award | 2018-05-18 |  | 2018-08-01 | 75
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13506 | 2018-05-01 | 2018-05-21 | 2018-05-22 | 2018-05-22 | 2018-05-24 | 2018-05-31 | 2018-06-07 |  | May-18 | Jun-18 | MW22390-AYCA-4EE89M-2RIV-04-15 Boundary Rd Box Hill | Box Hill | 1635.31 | 845.6 | 2480.91 | 2729.001 | 976.93 |  | 976.93 | 1503.98 | 60.62% |  |  |  | Andrew Mahssy | Direct Award | 2018-05-08 |  | 2018-08-02 | 86
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14198 | 2018-09-26 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-09-18 | 2018-09-10 | 2018-09-27 |  | Aug-18 | Sep-18 | MW417R000052-AYCA-44H3AU-2STL-65-13 Marshall Avenue St Leonards | St Leonards | 1998.69 | 12541.45 | 14540.14 | 15994.154 | 10938.67 |  | 10938.67 | 3601.47 | 24.77% |  |  |  | Ertan Cicek | Direct Award | 2018-05-21 |  | 2018-08-05 | 76
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-03-17 | 2019-03-17 |  |  | 2019-03-31 | 2019-04-14 |  | Mar-19 | Apr-19 | MW22474-AYCA-4UE5JN-2LID-03-46-48 Beaumont St | Lidcombe | 1347.33 | 1862.3 | 3209.63 | 3530.593 | 1102.38 |  | 1102.38 | 2107.25 | 65.65% |  |  |  | Ertan Cicek | Direct Award | 2018-05-21 |  | 2018-08-06 | 77
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW22501-AYCA-4W183C-2WLG-02-71 Auburn St Wollongong | Wollongong | 1592.08 |  | 1592.08 | 1751.288 |  |  | 0 | 1592.08 | 100% |  |  |  | Nabeel Jaimon | Direct Award | 2018-05-22 |  | 2018-08-06 | 76
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R000712-AYCA-30GQWB-2ROU-02-16-20 Withers Rd, Kellyville | Kellyville | 1764.06 |  | 1764.06 | 1940.466 | 1979.12 |  | 1979.12 | -215.06 | -12.19% |  |  |  | Ertan Cicek | Direct Award | 2018-07-20 |  | 2018-10-17 | 89
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14104 | 2018-08-30 | 2018-06-29 | 2018-06-29 | 2018-07-02 | 2018-07-26 | 2018-07-13 | 2018-08-30 |  | Jun-18 | Aug-18 | MW22526-AYCA-4T7JU2-2MIR-25-13 Dudley Avenue Caringbah South | Carringbah | 1804.33 | 12670.33 | 14474.66 | 15922.126 | 3866.63 |  | 3866.63 | 10608.03 | 73.29% |  |  |  | Ertan Cicek | Direct Award | 2018-05-24 |  | 2018-05-30 | 6
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14202 | 2018-09-26 | 2018-07-30 | 2018-07-30 | 2018-08-29 | 2018-09-18 | 2018-08-13 | 2018-09-27 |  | Jul-18 | Sep-18 | MW22531-AYCA-413Z64-2PAR-64-2B Darcy Rd Westmead | Westmead | 1987.42 | 5857.75 | 7845.17 | 8629.687 | 4357.68 |  | 4357.68 | 3487.49 | 44.45% |  |  |  | Ertan Cicek | Direct Award | 2018-05-25 |  | 2018-06-15 | 21
A417 Greenfield MDU | Sth Coast | Marshell Antonio | Inv 13866 | 2018-07-03 | 2018-06-19 | 2018-06-19 | 2018-07-02 | 2018-07-04 | 2018-07-03 | 2018-07-17 |  | Jun-18 | Jul-18 | MW22420 - AYCA-4RFDRV - 2KIA-03 - 58 Old Saddleback Road Kiama | Kiama | 11050.52 | 9243.712 | 20294.232 | 22323.6552 | 5530.26 | 3905.8593 | 9436.1192 | 10858.1128 | 53.5% |  |  |  | Andrew Mahassy | Direct Award | 2018-05-11 |  | 2018-05-23 | 12
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14717 | 2019-02-15 | 2018-12-14 | 2018-12-14 | 2018-12-17 | 2019-01-30 | 2018-01-07 | 2019-02-15 |  | Dec-18 | Feb-19 | MW22470-AYCA-2XJBL7-2SIL-02-3 Olympic Blvd Sydney Olympic Park | Olympic Park | 5102.55 | 9554.26 | 14656.81 | 16122.491 | 2299.5 |  | 2299.5 | 12357.31 | 84.31% |  |  |  | Ertan Cicek | Direct Award | 2018-05-28 |  | 2018-08-05 | 69
A401/Greenfield | Sydney | Mickey Tran | Inv 13751 | 2018-06-20 | 2018-05-29 | 2018-05-29 | 2018-05-31 | 2018-06-05 | 2018-06-14 | 2018-06-28 |  | May-18 | Jun-18 | MW22478 - AYCA-501QN5 - 2CAS-23 - 30 Pentonville Parade, Castle Hill | Castle Hill | 2549.45 | 1147.33 | 3696.78 | 4066.458 | 1826.69 |  | 1826.69 | 1870.09 | 50.59% |  |  |  | Dave Yoemans | 2018-05-22 | 2018-05-30 |  | 2018-07-30 | 61
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14214 | 2018-10-05 | 2018-07-16 | 2018-07-17 | 2018-09-07 | 2018-09-25 | 2018-07-31 | 2018-10-09 |  | Jul-18 | Oct-18 | MW22548-AYCA-48V6NM-2PTH-05-Lord Sheffield Circuit Penrith | Penrith | 6541.61 | 28541.26 | 35082.87 | 38591.157 | 25943.58 |  | 25943.58 | 9139.29 | 26.05% |  |  |  | Ertan Cicek | Direct Award | 2018-05-30 |  | 2018-09-13 | 106
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14003 | 2018-08-09 | 2018-07-13 | 2018-07-13 | 2018-07-17 | 2018-07-31 | 2018-07-27 | 2018-08-09 |  | Jul-18 | Aug-18 | MW22505-AYCA-4KBL5R-2KNS-03-14-18 Primrose Ave & 27-29 Roseberry Ave Rosberry | Rosberry | 1091.81 | 12377.6246 | 13469.4346 | 14816.378 | 4029.22 |  | 4029.22 | 9440.2146 | 70.09% |  |  |  | Ertan Cicek | Direct Award | 2018-05-30 |  | 2018-08-18 | 80
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14622 | 2019-01-16 | 2018-10-31 | 2018-10-31 | 2018-11-14 | 2018-12-18 | 2018-11-14 | 2019-01-15 |  | Oct-18 | Jan-19 | MW417R000243-AYCA-56I886-2ASH-64-47 Cecil St, Ashfield | Ashfield | 2864.22 | 24700.93 | 27565.15 | 30321.665 | 3453.83 |  | 3453.83 | 24111.32 | 87.47% |  |  |  | Ertan Cicek | Direct Award | 2018-06-13 |  | 2018-09-28 | 107
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW22513 - AYCA-4JW63S - 2CRO-21 - 25-29 Tonkin St Cronulla | Cronulla | 4221.51 |  | 4221.51 | 4643.661 | 2685.67 |  | 2685.67 | 1535.84 | 36.38% |  |  |  | Ertan Cicek | Direct Award | 2018-05-29 |  | 2018-07-29 | 61
A401/Greenfield | Nth Coast | Mickey Tran | Inv 14006 | 2018-08-09 | 2018-07-16 | 2018-07-16 | 2018-07-16 | 2018-07-26 | 2018-07-27 | 2018-08-09 |  | Jul-18 | Aug-18 | MW22483-AYCA-4IEHVB-2CAH-21-Bottlebrush Place, Lakewood | Lakewood | 6677.56 | 1824.46 | 8502.02 | 9352.222 |  |  | 0 | 8502.02 | 100% |  |  |  | Mark Leal | 2018-05-21 | 2018-05-29 | 8 | 2018-06-29 | 31
A417 Greenfield MDU | Sydney East | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW22520-AYCA-48OYT0-2EDG-65-240 New South Head Road Edgecliff | Edgecliffe | 1411.72 |  | 1411.72 | 1552.892 | 285 |  | 285 | 1126.72 | 79.81% |  |  |  | Ertan Cicek | Direct Award | 2018-05-30 |  | 2018-09-05 | 98
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14260 | 2018-10-15 | 2018-09-17 | 2018-09-17 | 2018-09-18 | 2018-09-27 | 2018-10-01 | 2018-10-16 |  | Sep-18 | Oct-18 | MW22575-AYCA-4LHC6F-2DBB-01-30 Ritz Pl Dubbo | Dubbo | 4042.34 | 3454 | 7496.34 | 8245.974 | 2737.54 |  | 2737.54 | 4758.8 | 63.48% |  |  |  | Ertan Cicek | Direct Award | 2018-05-30 |  | 2018-08-23 | 85
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14384 | 2018-11-14 | 2018-10-10 | 2018-10-10 | 2018-10-16 | 2018-10-25 | 2018-10-24 | 2018-11-13 |  | Oct-18 | Nov-18 | MW417R000757-AYCA-59CA2X-2PTH-02-13 Stafford St, Kingswood | Kingswood | 450.05 | 4778.86 | 5228.91 | 5751.801 |  |  | 0 | 5228.91 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-23 |  | 2018-12-01 | 131
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14764 | 2019-03-05 | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-02-04 | 2019-02-07 | 2019-02-28 |  | Jan-19 | Feb-19 | MW22574 - AYCA-4BBYMK - 2ROU-01 - 184 & 186 Old Pitt Town Rd Box Hill | Box Hill | 3453.15 | -1955.27 | 1497.88 | 1647.668 |  |  | 0 | 1497.88 | 100% |  |  |  | Mark Leal | Direct Award | 2018-05-30 |  | 2018-08-23 | 85
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14055 | 2018-08-22 | 2018-07-30 | 2018-07-30 | 2018-08-03 | 2018-08-14 | 2018-08-13 | 2018-08-22 |  | Jul-18 | Aug-18 | MW22547-AYCA-547JTQ-2DBB-04-1D Rawson St Dubbo | Dubbo | 1056.4 | 6998.45 | 8054.85 | 8860.335 |  |  | 0 | 8054.85 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-05-31 |  | 2018-08-22 | 83
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14279 | 2018-10-17 | 2018-09-28 | 2018-09-28 |  |  | 2018-10-12 | 2018-10-18 |  | Sep-18 | Oct-18 | MW22579-AYCA-4R1C1M-2RIV-07-William St Riverstone | Riverstone | 923.71 |  | 923.71 | 1016.081 |  | 267.93 | 267.93 | 655.78 | 70.99% |  |  |  | Mark Leal | Direct Award | 2018-06-01 |  | 2018-08-23 | 83
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14036 | 2018-08-21 | 2018-07-30 | 2018-07-30 | 2018-08-01 | 2018-08-10 | 2018-08-13 | 2018-08-22 |  | Jul-18 | Aug-18 | MW22580-AYCA-52S52D-2BTH-01-18 Hobson Cl Eglinton | Eglinton | 2924.92 | 2414.0287 | 5338.9487 | 5872.8436 |  |  | 0 | 5338.9487 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-01 |  | 2018-08-24 | 84
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R000099-AYCA-577BDS-2BLK-07-36 Huntingwood Drive Huntingwood | Huntingwood | 856.8 |  | 856.8 | 942.48 |  |  | 0 | 856.8 | 100% |  |  |  | Richard Huffadine | Direct Award | 2018-06-01 |  | 2018-08-08 | 68
A401/Greenfield | Sth NSW | Marshell Antonio | Inv 13913 | 2018-07-24 | 2018-06-18 | 2018-06-30 |  |  | 2018-07-02 | 2018-07-24 |  | Jun-18 | Jul-18 | MW22493 - AYCA-4VG4KY - 2LTO-20 - 23-25 Chelmsford Place Leeton | Leeton | 4293.874 |  | 4293.874 | 4723.2614 |  |  | 0 | 4293.874 | 100% |  |  |  | Dave Yoemans | 2018-05-23 | 2018-07-17 | 55 | 2018-10-12 | 87
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14201 | 2018-09-27 | 2018-08-03 | 2018-08-03 | 2018-08-16 | 2018-09-18 | 2018-08-17 | 2018-09-27 |  | Aug-18 | Sep-18 | MW417R000065- AYCA-59DV6W-2CRR-72-Nelson St, Fairfield | Fairfield | 1156.75 | 6676.88 | 7833.63 | 8616.993 | 1502.68 |  | 1502.68 | 6330.95 | 80.82% |  |  |  | Ertan Cicek | Direct Award | 2018-06-05 |  | 2018-06-28 | 23
A417 Greenfield MDU | Newcastle | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R000077-AYCA-5A2Y34-2MAI-03-100 George St East Maitland | East Maitland | 926.02 |  | 926.02 | 1018.622 | 980.9 |  | 980.9 | -54.88 | -5.926% |  |  |  | Ertan Cicek | Direct Award | 2018-06-05 |  | 2018-08-29 | 85
A401/Greenfield | ACT | Marshell Antonio | Inv 14008 | 2018-08-09 | 2018-07-03 | 2018-07-23 |  |  | 2018-08-06 | 2018-08-09 |  | Jul-18 | Aug-18 | MW417R000671-9SCU-20-AYCA-52JYBU 7 Buggy Crescent McKellar | Mckellar | 20864.64 |  | 20864.64 | 22951.104 | 5714.37 |  | 5714.37 | 15150.27 | 72.61% |  |  |  | Dave Yoemans | 2018-07-02 | 2018-07-23 | 55 | 2018-07-30 | 7
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14004 | 2018-08-09 | 2018-07-05 | 2018-07-05 | 2018-07-23 | 2018-07-31 | 2018-07-19 | 2018-08-09 |  | Jul-18 | Aug-18 | MW417R000070-AYCA-52UC2N-2WRO-63-Beech Rd Casula | Casula | 19385.47 | -5701.87 | 13683.6 | 15051.96 | 7183.72 |  | 7183.72 | 6499.88 | 47.5% |  |  |  | Ertan Cicek | Direct Award | 2018-06-07 |  | 2018-08-29 | 83
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14142 | 2018-09-11 | 2018-08-01 | 2018-08-01 | 2018-08-03 | 2018-08-30 | 2018-08-15 | 2018-09-11 |  | Aug-18 | Sep-18 | MW22469-AYCA-4PQO3D-2EPP-62-12/6 Maida Road Epping | Epping | 1077.58 | 4821.08 | 5898.66 | 6488.526 | 2546.16 |  | 2546.16 | 3352.5 | 56.83% |  |  |  | Ertan Cicek | Direct Award | 2018-05-23 |  | 2018-08-05 | 74
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13975 | 2018-08-01 | 2018-06-22 | 2018-06-22 | 2018-06-25 | 2018-07-18 | 2018-07-18 | 2018-07-31 |  | Jun-18 | Jul-18 | MW417R000124-AYCA-58BKNK-2RYD-66-2-6 Junction St Ryde | Ryde | 1064.32 | 5366.589 | 6430.909 | 7073.9999 | 3823.6 |  | 3823.6 | 2607.309 | 40.54% |  |  |  | Ertan Cicek | Direct Award | 2018-06-06 |  | 2018-08-30 | 85
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13924 | 2018-07-27 | 2018-06-18 | 2018-06-19 | 2018-06-27 | 2018-07-18 | 2018-07-03 | 2018-07-31 |  | Jun-18 | Jul-18 | MW417R000098-AYCA-4TC0MT-2QUA-65-50 Farnham Rd, Quakers Hill | Quakers Hill | 8779.84 | 16441.63 | 25221.47 | 27743.617 | 17562.26 |  | 17562.26 | 7659.21 | 30.37% |  |  |  | Ertan Cicek | Direct Award | 2018-06-08 |  | 2018-08-30 | 83
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R000132-AYCA-4L3R6E-2MIR-26-4-6 Ventura Ave Miranda | Miranda | 5800.56 |  | 5800.56 | 6380.616 |  |  | 0 | 5800.56 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-07 |  | 2018-08-31 | 85
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R000139-AYCA-4IIZWC-2STL-60-22-28 Albany St St Leonards | St.Leonards | 781.39 |  | 781.39 | 859.529 |  |  | 0 | 781.39 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-07 |  | 2018-08-31 | 85
A417 Greenfield MDU | ACT | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R000123-AYCA-523PM8-9MNK-01-8 Beaconsfield St Fyshwick ACT | Fyshwick | 6863.96 |  | 6863.96 | 7550.356 |  |  | 0 | 6863.96 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-07 |  | 2018-08-30 | 84
A417 Greenfield MDU | Sydney East | Dane Harrington |  |  | 2019-03-05 | 2019-03-05 |  |  | 2019-03-19 | 2019-04-02 |  | Mar-19 | Apr-19 | MW417R000161-AYCA-3D0J11-2ROC-02-15-21 Willis St Wolli Creek | Wolli Creek | 1641.98 |  | 1641.98 | 1806.178 | 2301.72 |  | 2301.72 | -659.74 | -40.18% |  |  |  | Ertan Cicek | Direct Award | 2018-06-08 |  | 2018-08-31 | 84
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13993 | 2018-08-07 | 2018-07-06 | 2018-07-06 | 2018-07-09 | 2018-07-30 | 2018-07-20 | 2018-08-07 |  | Jul-18 | Aug-18 | MW417R000222-AYCA-4VFYJV-2BAN-64-27-37 Percy St, Bankstown | Bankstown | 4388.94 | 14761.99 | 19150.93 | 21066.023 | 11092.64 |  | 11092.64 | 8058.29 | 42.08% |  |  |  | Ertan Cicek | Direct Award | 2018-06-08 |  | 2018-09-29 | 113
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14616 | 2019-01-16 | 2018-11-08 | 2018-11-08 | 2018-11-14 | 2018-12-18 | 2018-11-23 | 2019-01-10 |  | Nov-18 | Jan-19 | MW417R001737-YCA-5L49UP-2PEN-64-A4 Water Street, Wentworthville | Wentworthville | 896.52 | 12354.3 | 13250.82 | 14575.902 |  |  | 0 | 13250.82 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-09 |  | 2018-11-30 | 52
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14515 | 2018-12-05 | 2018-10-18 | 2018-10-18 | 2018-10-23 | 2018-11-27 | 2018-11-01 | 2018-12-06 |  | Oct-18 | Dec-18 | MW417R000091-AYCA-57S6JD-2REV-20-50/42 Violet St Revesby | Revesby | 2570.53 | 10352.24 | 12922.77 | 14215.047 | 3384.13 | 380.1827 | 3764.3128 | 9158.4572 | 70.87% |  |  |  | Ertan Cicek | Direct Award | 2018-06-08 |  | 2018-08-29 | 82
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14005 | 2018-08-09 | 2018-06-15 | 2018-06-15 | 2018-06-15 | 2018-06-20 | 2018-08-01 | 2018-08-09 |  | Jun-18 | Aug-18 | MW417R000217-AYCA-5ENHJH-2MIL-01-Browning and Colenso Cct Edmondson Park | Edmondson Park | 2924.92 | -2087.42 | 837.5 | 921.25 |  |  | 0 | 837.5 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-08 |  | 2018-09-04 | 88
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14383 | 2018-11-14 | 2018-09-17 | 2018-09-17 | 2018-09-18 | 2018-10-26 | 2018-10-01 | 2018-11-13 |  | Sep-18 | Nov-18 | MW417R001249-AYCA-5FHVE5-2ORG-06-71 Bletchington Street, Orange Ext | Orange | 2583.8 | 5218.46 | 7802.26 | 8582.486 |  |  | 0 | 7802.26 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-08-27 |  | 2018-11-22 | 87
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 13742 | 2018-06-14 | 2018-06-14 | 2018-06-14 |  |  |  | 2018-06-14 |  | Jun-18 | Jun-18 | MW417R000157-2PAR-63-AYCA-4A46K7-208-210 Great Western Hwy, Westmead DFN Design & Construct, Mob payment | Westmead | 10733.39 |  | 10733.39 | 11806.729 |  |  | 0 | 10733.39 | 100% |  |  |  | Mark Leal | Direct Award | 2018-06-08 |  | 2018-08-31 | 84
A401/Greenfield | Sth Coast | Mickey Tran | Inv 14770 | 2019-03-04 | 2019-02-01 | 2019-02-01 | 2019-02-01 | 2019-02-08 | 2019-02-15 | 2019-03-05 |  | Feb-19 | Mar-19 | MW417R000044-AYCA-4YZZ1I-2ABN-03-149 The Boulevarde, Oak Flats | Oak Flats | 7574.8 | 19815.88 | 27390.68 | 30129.748 |  |  | 0 | 27390.68 | 100% |  |  |  | Andrew Mahassy | 2018-05-22 | 2018-05-25 | 3 | 2018-06-28 | 34
A401/Greenfield | Sth Coast | Mickey Tran | inv 13994 | 2018-08-07 | 2018-07-04 | 2018-07-04 | 2018-07-11 | 2018-07-27 | 2018-07-18 | 2018-08-07 |  | Jul-18 | Aug-18 | MW417R000063-AYCA-52381N-2SUX-01-284 River Rd Sussex Inlet | Sussex Inlet | 9332.53 | 1389.86 | 10722.39 | 11794.629 |  |  | 0 | 10722.39 | 100% |  |  |  | Ertan Cicek | 2018-05-31 | 2018-06-12 | 12 | 2018-07-04 | 22
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R000159-AYCA-4EZRCH-2MIR-26-1-3 Higherdale Ave Miranda | Miranda | 299.36 |  | 299.36 | 329.296 |  |  | 0 | 299.36 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-12 |  | 2018-08-31 | 80
A401/Greenfield | Sydney | Mickey Tran | Inv 13925 | 2018-07-26 | 2018-06-25 | 2018-06-25 | 2018-07-09 | 2018-07-11 | 2018-07-09 | 2018-07-26 |  | Jun-18 | Jul-18 | MW22455 -AYCA-3LT1P4 - 2KEL-08 - Sub of 123 Arnold Ave, Kellyville - 2 | Kellyville | 7140.73 | 3918.18 | 11058.91 | 12164.801 | 3510 |  | 3510 | 7548.91 | 68.26% |  |  |  | Sogand Mohtat | 2018-05-22 | 2018-06-12 | 21 | 2018-06-26 | 14
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13972 | 2018-08-01 | 2018-07-05 | 2018-07-06 | 2018-07-09 | 2018-07-26 | 2018-07-20 | 2018-08-02 |  | Jul-18 | Aug-18 | MW417R000223 - AYCA-5ALZB0 - 2BLK-07 - 6 Woods CL, Huntingwood Ext | Huntingwood | 5802.97 | 5801.3048 | 11604.2748 | 12764.7022 | 5337.83 |  | 5337.83 | 6266.4448 | 54% |  |  |  | Ertan Cicek | Direct Award | 2018-06-12 |  | 2018-09-28 | 108
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13995 | 2018-08-07 | 2018-07-06 | 2018-07-06 | 2018-07-10 | 2018-07-30 | 2018-07-20 | 2018-08-07 |  | Jul-18 | Aug-18 | MW417R000354-AYCA-57CAFW-2CRO-01-KURNELL 2 | Kurnell | 1791.95 | 1609.79 | 3401.74 | 3741.914 | 3351 |  | 3351 | 50.74 | 1.492% |  |  |  | Ertan Cicek | Direct Award | 2018-06-26 |  | 2018-09-28 | 94
A401/Greenfield | Sth Coast | Marshell Antonio | Inv 13971 | 2017-08-01 | 2018-07-11 | 2018-07-11 | 2018-07-11 | 2018-07-13 | 2018-07-25 | 2018-08-02 |  | Jul-18 | Aug-18 | MW417R000149-AYCA-4M2GZ2-2ABN-01-2 Pine Street, Albion Park Rail | Albion Park | 7206.99 | 2158.71 | 9365.7 | 10302.27 |  |  | 0 | 9365.7 | 100% |  |  |  | Mark Leal | 2018-06-04 | 2018-06-12 |  | 2018-06-29 | 17
NBN FttC Drops | Sydney | Rob Panovski | Inv 14271 | 2018-10-16 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-13 | 2018-09-24 | 2018-10-18 |  | Sep-18 | Oct-18 | MW417R000553-2NDS-01-STELLAR NPDL_MWR (A417)-Nords Wharf | Nords Wharf | 7432 | 40377.195 | 47809.195 | 52590.1145 | 25665.5 |  | 25665.5 | 22143.695 | 46.32% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13862 | 2018-07-17 | 2018-07-17 | 2018-07-14 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000553-2NDS-01-STELLAR NPDL_MWR (A417)-Nords Wharf | Nords Wharf | 3185.14 |  | 3185.14 | 3503.654 |  |  | 0 | 3185.14 | 100% |  |  |  | Kirsty Doyle | Direct Award
A417 Greenfield MDU | Sth Coast | Marshell Antonio | Inv 14617 | 2019-01-16 | 2018-11-16 | 2018-11-16 | 2018-11-16 | 2018-12-18 | 2018-11-30 | 2019-01-10 |  | Nov-18 | Jan-19 | MW417R000773-AYCA-4P6YWU- 2SHH-05-11 Kite Pl, Blackbutt Externals | Blackbutt | 2235.65 | 6499.245 | 8734.895 | 9608.3845 | 3921.9 |  | 3921.9 | 4812.995 | 55.1% |  |  |  | Nabeel Jaimon | Direct Award | 2018-07-25 |  | 2018-10-20 | 87
NBN FttC Drops | Sydney | Rob Panovski | Inv 14325 | 2018-10-25 | 2018-09-20 | 2018-09-20 | 2018-10-05 | 2018-10-11 | 2018-10-04 | 2018-10-30 |  | Sep-18 | Oct-18 | MW417R000554-2NYG-20-STELLAR NPDL_MWR (A417)-Nyngan | Nyngan | 7014.97 | 29930.19 | 36945.16 | 40639.676 | 5204 |  | 5204 | 31741.16 | 85.91% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13861 | 2018-07-17 | 2018-07-17 | 2018-07-14 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000554-2NYG-20-STELLAR NPDL_MWR (A417)-Nyngan | Nyngan | 3006.41 |  | 3006.41 | 3307.051 |  |  | 0 | 3006.41 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14588 | 2018-12-19 | 2018-11-23 | 2018-11-23 | 2018-11-27 | 2018-12-06 | 2018-11-28 | 2018-12-20 |  | Nov-18 | Dec-18 | MW417R000556-2ORC-21-STELLAR NPDL_MWR (A417)-Orchard Hills | Orchard Hills | 8943.739 | 58402.84 | 67346.579 | 74081.2369 | 43445 |  | 43445 | 23901.579 | 35.49% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13868 | 2018-07-18 | 2018-07-18 | 2018-07-14 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000556-2ORC-21-STELLAR NPDL_MWR (A417)-Orchard Hills | Orchard Hills | 3833.031 |  | 3833.031 | 4216.3341 |  |  | 0 | 3833.031 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14326 | 2018-10-26 | 2018-09-20 | 2018-09-20 | 2018-10-05 | 2018-10-11 | 2018-10-04 | 2018-10-30 |  | Sep-18 | Oct-18 | MW417R000557-2POR-20-STELLAR NPDL_MWR (A417)-Portland | Portland | 2042.58 | 20329.53 | 22372.11 | 24609.321 | 9152.5 |  | 9152.5 | 13219.61 | 59.09% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14690 | 2019-02-01 | 2018-12-20 | 2018-12-20 | 2019-01-14 | 2019-01-17 | 2019-01-11 | 2019-02-05 |  | Dec-18 | Feb-19 | MW417R000558 - 2SPW-20 - STELLAR NPDL_MWR (A417)-Springwood | Springwood | 13114.06 | 40775.74 | 53889.8 | 59278.78 | 27605 |  | 27605 | 26284.8 | 48.78% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13869 | 2018-07-18 | 2018-07-18 | 2018-07-14 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000558 - 2SPW-20 - STELLAR NPDL_MWR (A417)-Springwood | Springwood | 5620.31 |  | 5620.31 | 6182.341 |  |  | 0 | 5620.31 | 100% |  |  |  | Kirsty Doyle | Direct Award
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13864 | 2018-07-03 | 2018-06-29 | 2018-06-29 |  |  | 2018-07-13 | 2018-07-17 |  | Jun-18 | Jul-18 | MW417R000218-AYCA-34MTV2-2BUR-07-133 Parramatta Rd, Homebush | Homebush | 4296.81 |  | 4296.81 | 4726.491 | 2484.25 |  | 2484.25 | 1812.56 | 42.18% |  |  |  | Ertan Cicek | Direct Award | 2018-06-13 |  | 2018-09-28 | 107
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  | 2019-02-22 | 2019-02-22 | 2019-02-22 |  | 2019-03-08 | 2019-03-22 |  | Feb-19 | Mar-19 | MW417R000238-AYCA-52OEM0-2MON-25-33 Darley St, East, Mona Vale | Mona Vale | 1832.88 | 6717.27 | 8550.15 | 9405.165 |  |  | 0 | 8550.15 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-14 |  | 2018-09-28 | 106
A401/Greenfield | Nth Coast | Mickey Tran | Inv 14154 | 2018-09-17 | 2018-08-16 | 2018-08-17 | 2018-08-17 | 2018-08-31 | 2018-08-31 | 2018-09-14 |  | Aug-18 | Sep-18 | MW417R000148-AYCA-4Z992M-2LIS-21-2A Napier St Goonellabah; 17 Blue Hills Ave Goonellabah | Goonellabah | 16470.774 | 6157.91 | 22628.684 | 24891.5524 | 10881.5 | 3005 | 13886.5 | 8742.184 | 38.63% |  |  |  | Mark Leal | 2018-06-04 | 2018-06-19 | 15 | 2018-06-29 | 10
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13830 | 2018-07-06 | 2018-06-18 | 2018-06-18 |  |  | 2018-07-02 | 2018-07-05 |  | Jun-18 | Jul-18 | MW22264-AYCA-4YPT3F-145/129 - 2WAG-05-145 Hammond Ave East Wagga Wagga | Wagga Wagga | 1065 |  | 1065 | 1171.5 |  |  | 0 | 1065 | 100% |  |  |  | Nabeel Jaimon | 2018-04-19 | 2018-06-14 | 56 | 2018-06-29 | 15
A417 Greenfield MDU | Central West | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R000280-AYCA-481ES7-2BTH-09-65 George St Bathurst Ext | Bathurst | 1194.07 |  | 1194.07 | 1313.477 |  |  | 0 | 1194.07 | 100% |  |  |  | Nabeel Jaimon | Direct Award | 2018-06-14 |  | 2018-09-20 | 98
A417 Greenfield MDU | Sydney East | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R000126-2HMK-02-AYCA-56Z0PS-37-49 O'Connor St Chippendale | Chippendale | 3328.23 |  | 3328.23 | 3661.053 |  |  | 0 | 3328.23 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-15 |  | 2018-08-30 | 76
A417 Greenfield MDU | Sth NSW | Marshell Antonio | Inv 14244 | 2018-10-11 | 2018-09-17 | 2018-09-17 | 2018-09-18 | 2018-09-27 | 2018-10-01 | 2018-10-11 |  | Sep-18 | Oct-18 | MW22573-AYCA-LYHJJ-2MTT-02-10 Cardigan St Mittagong | Mittagong | 1458.46 | 603.36 | 2061.82 | 2268.002 | 986 |  | 986 | 1075.82 | 52.18% |  |  |  | Ertan Cicek | Direct Award | 2018-06-15 |  | 2018-08-28 | 74
A401/Greenfield | Sydney | Mickey Tran | Inv 13927 | 2018-07-26 | 2018-06-27 | 2018-06-27 |  |  | 2018-07-11 | 2018-07-12 |  | Jun-18 | Jul-18 | MW417R000151-AYCA-4PBBAI-2RYD-01-6,8,10,12 Anderson Avenue Ryde | Ryde | 4848.55 |  | 4848.55 | 5333.405 |  |  | 0 | 4848.55 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-15 |  | 2018-06-29 | 14
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14140 | 2018-09-11 | 2018-07-31 | 2018-07-31 | 2018-08-02 | 2018-08-30 | 2018-08-14 | 2018-09-13 |  | Jul-18 | Sep-18 | MW417R000299-AYCA-5AZ97T-2BTH-02-1 Wark Parade, Windradyne | Windradyne | 6779.46 | 2681.11 | 9460.57 | 10406.627 |  |  | 0 | 9460.57 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-15 |  | 2018-09-28 | 105
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13982 | 2018-08-03 | 2018-07-04 | 2018-07-04 | 2018-07-09 | 2018-07-26 | 2018-07-18 | 2018-08-02 |  | Jul-18 | Aug-18 | MW417R000298-AYCA-5CSK69-2LIV-03-94 Flowerdale Rd, Liverpool | Liverpool | 3687.45 | 2280.35 | 5967.8 | 6564.58 |  |  | 0 | 5967.8 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-15 |  | 2018-09-28 | 105
A401/Greenfield | Sydney | Mickey Tran | Inv 13833 | 2018-07-06 | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-20 | 2018-07-02 | 2018-07-05 |  | Jun-18 | Jul-18 | MW22481 - AYCA-4R2N0H - 2KEL-08 -6,8,9,11 John Hillas Avenue Kellyville | Kellyville | 3239.95 | 3749.57 | 6989.52 | 7688.472 |  | 1627.8535 | 1627.8535 | 5361.6665 | 76.71% |  |  |  | Dave Yoemans | 2018-06-05 | 2018-06-13 |  | 2018-07-02 | 19
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14240 | 2018-10-11 | 2018-08-23 | 2018-08-29 | 2018-09-06 | 2018-09-25 | 2018-09-12 | 2018-10-16 |  | Aug-18 | Oct-18 | MW417R000301-AYCA-5AVN4W-2EPP-62-23-25 Forest Grove, Epping | Epping | 1648 | 15728.34 | 17376.34 | 19113.974 | 8298.32 |  | 8298.32 | 9078.02 | 52.24% |  |  |  | Ertan Cicek | Direct Award | 2018-06-18 |  | 2018-09-28 | 102
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14152 | 2018-09-18 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-08-30 | 2018-08-07 | 2018-09-13 |  | Jul-18 | Sep-18 | MW417R000300-AYCA-57KT5A-2PTH-02-153 Jamison Rd, Penrith | Penrith | 958.19 | 10874.166 | 11832.356 | 13015.5916 | 852.56 |  | 852.56 | 10979.796 | 92.79% |  |  |  | Ertan Cicek | Direct Award | 2018-06-18 |  | 2018-08-28 | 71
A401/Greenfield | Central Coast | Mickey Tran | Inv 14157 | 2018-08-17 | 2018-08-24 | 2018-08-24 | 2018-08-28 | 2018-08-31 | 2018-09-07 | 2018-09-18 |  | Aug-18 | Sep-18 | MW417R000246 - AYCA-4RTZSH - 2WOY-07 - 25 Phegan Street Woy Woy | Woy Woy | 9674.98 | 6664.6 | 16339.58 | 17973.538 | 9666.42 |  | 9666.42 | 6673.16 | 40.84% |  |  |  | Ertan Cicek | 2018-06-18 | 2018-06-28 | 10 | 2018-07-05 | 7
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14022 | 2018-08-14 | 2018-07-23 | 2018-07-24 | 2018-07-24 | 2018-07-31 | 2018-08-07 | 2018-08-14 |  | Jul-18 | Aug-18 | MW417R000310--AYCA-5DPOWN-2APN-01-13 Technology Dr, Appin EXT | Appin | 7171.07 | 11234.14 | 18405.21 | 20245.731 | 15580.43 | 487.3053 | 16067.7352 | 2337.4747 | 12.7% |  |  |  | Ertan Cicek | Direct Award | 2018-06-20 |  | 2018-09-28 | 100
A401/Greenfield | Sth NSW | Marshell Antonio | Inv 13920 | 2018-07-26 | 2018-06-21 | 2018-06-21 |  |  | 2018-07-05 | 2018-07-12 |  | Jun-18 | Jul-18 | MW22430-AYCA-5667HJ-2WAG-01-12-16 Beetson Street Boorooma | Boorooma | 2717.54 |  | 2717.54 | 2989.294 |  |  | 0 | 2717.54 | 100% |  |  |  | Sogand Mohtat | 2018-05-17 | 2018-05-22 | 5 | 2018-06-20 | 29
NBN FttC Drops | Sydney | Rob Panovski | Inv 14728 | 2019-02-15 | 2019-01-08 | 2019-01-08 | 2019-01-10 | 2018-01-15 | 2019-01-22 | 2019-02-15 |  | Jan-19 | Feb-19 | MW417R000559 - 2SPW-21 - STELLAR NPDL_MWR (A417)-Springwood | Springwood | 11393.802 | 72682.835 | 84076.637 | 92484.3007 | 50110 |  | 50110 | 33966.637 | 40.4% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13873 | 2018-07-18 | 2018-07-18 | 2018-07-14 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000559 - 2SPW-21 - STELLAR NPDL_MWR (A417)-Springwood | Springwood | 4883.058 |  | 4883.058 | 5371.3638 |  |  | 0 | 4883.058 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14589 | 2018-12-19 | 2018-11-23 | 2018-11-23 | 2018-11-26 | 2018-12-06 | 2018-12-07 | 2018-12-20 |  | Nov-18 | Dec-18 | MW417R000560 - 2SPW-28 - STELLAR NPDL_MWR (A417)-Springwood | Springwood | 21350.44 | 109618.14 | 130968.58 | 144065.438 | 78690 |  | 78690 | 52278.58 | 39.92% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13867 | 2018-07-18 | 2018-07-18 | 2018-07-14 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000560 - 2SPW-28 - STELLAR NPDL_MWR (A417)-Springwood | Springwood | 9150.19 |  | 9150.19 | 10065.209 |  |  | 0 | 9150.19 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14210 | 2018-10-04 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-13 | 2018-09-24 | 2018-10-04 |  | Sep-18 | Oct-18 | MW417R000561-2WWA-20-STELLAR NPDL_MWR (A417)-Wee Waa | Wee Waa | 5294.71 | 14243.93 | 19538.64 | 21492.504 | 5148.5 |  | 5148.5 | 14390.14 | 73.65% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 13874 | 2018-07-18 | 2018-07-18 | 2018-07-14 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000561-2WWA-20-STELLAR NPDL_MWR (A417)-Wee Waa | Wee Waa | 2269.16 |  | 2269.16 | 2496.076 |  |  | 0 | 2269.16 | 100% |  |  |  | Kirsty Doyle | Direct Award
A417 Greenfield MDU | Sydney | Dane Harrington |  |  | 2018-11-30 | 2018-11-30 | [5 empty] | Nov-18 | Jan-00 | MW417R000348 - AYCA-5F1RYP - 2EDG-66 - 114 New South Head Road, Edgecliff | Edgecliffe | 3323.69 | -2063.69 | 1260 | 1386 |  |  | 0 | 1260 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-22 |  | 2018-09-28 | 98
A417 Greenfield MDU | Central Coast | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R000347-AYCA-397TA7-2TGL-02-6-8 Painters Lane Terrigal | Terrigal | 4185.9 |  | 4185.9 | 4604.49 |  |  | 0 | 4185.9 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-25 |  | 2018-09-19 | 86
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14023 | 2018-08-14 | 2018-07-23 | 2018-07-24 |  |  | 2018-08-07 | 2018-08-14 |  | Jul-18 | Aug-18 | MW417R000381-2APN-01-AYCA-5DPOWN-13 Technology Drive Appin INT | Appin | 1592.08 |  | 1592.08 | 1751.288 |  |  | 0 | 1592.08 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-25 |  | 2018-10-30 | 127
A401/Greenfield | Central Coast | Mickey Tran | Inv 14155 | 2018-09-17 | 2018-08-08 | 2018-08-08 | 2018-08-14 | 2018-09-03 | 2018-08-22 | 2018-09-05 |  | Aug-18 | Sep-18 | MW417R000141-AYCA-4UXA3J-2ERN-03-1 and 4 Fox Glove Close, Green | Green Point | 6603.41 | 10528.2 | 17131.61 | 18844.771 | 9198.2 |  | 9198.2 | 7933.41 | 46.31% |  |  |  | Dave Yoemans | 2018-06-04 | 2018-06-19 | 15 | 2018-06-29 | 10
NBN FttC Drops | Nth Coast | Rob Panovski | Inv 14724 | 2019-02-15 | 2018-12-20 | 2018-12-20 | 2019-01-10 | 2009-01-15 | 2009-01-11 | 2019-02-15 |  | Dec-18 | Feb-19 | MW417R001124-2ALS-01 - Alstonville | Alstonville | 23724.68 | 45166.885 | 68891.565 | 75780.7215 | 42821.75 |  | 42821.75 | 26069.815 | 37.84% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Nth Coast | Rob Panovski | Inv 14053 | 2018-08-22 | 2018-08-21 | 2018-08-21 |  |  |  | 2018-08-23 |  | Aug-18 | Aug-18 | MW417R001124-2ALS-01 - Alstonville | Alstonville | 10167.72 |  | 10167.72 | 11184.492 |  |  | 0 | 10167.72 | 100% |  |  |  | Kirsty Doyle | Direct Award
A401/Greenfield | Sth Coast | Mickey Tran | Inv 13926 | 2018-07-26 | 2018-07-03 | 2018-07-05 |  |  | 2018-07-19 | 2018-07-26 |  | Jul-18 | Jul-18 | MW417R000364-2ABN-03-AYCA-5DBDK2 -8 Werrang St, Albion Park Rail | Albion Park | 2852.73 |  | 2852.73 | 3138.003 |  |  | 0 | 2852.73 | 100% |  |  |  | Ertan Cicek | 2018-06-26 | 2018-07-04 | 8 | 2018-09-12 | 70
A417 Greenfield MDU | ACT | Marshell Antonio | Inv 14009 | 2018-08-09 | 2018-07-23 | 2018-07-23 | 2018-07-23 | 2018-07-31 | 2018-08-06 | 2018-08-09 |  | Jul-18 | Aug-18 | MW417R000383-AYCA-3MEHNA-9BLC-04-Nevertire St, Lawson | Lawson | 8900.22 | 4282.44 | 13182.66 | 14500.926 |  |  | 0 | 13182.66 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-28 |  | 2018-09-28 | 92
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14000 | 2018-08-09 | 2018-07-06 | 2018-07-06 | 2018-07-10 | 2018-07-30 | 2018-07-20 | 2018-08-09 |  | Jul-18 | Aug-18 | MW417R000346-AYCA-57CH4J-2CRO-01-8/268A Captain Cook Dr, Kurnell | Kurnell | 3154.72 | 4773.34 | 7928.06 | 8720.866 | 2498.5 |  | 2498.5 | 5429.56 | 68.49% |  |  |  | Ertan Cicek | Direct Award | 2018-06-28 |  | 2018-09-28 | 92
A417 Greenfield MDU | ACT | Marshell Antonio |  |  | 2018-09-18 | 2018-09-30 | 2018-09-18 | 2018-10-26 | 2018-10-14 | 2018-11-06 |  | Sep-18 | Nov-18 | MW417R001447-AYCA-5A2PE8-9CRC-06-35 Pademelon St, Throsby, ACT | Thorsby | 4429.15 | 1301.24 | 5730.39 | 6303.429 |  |  | 0 | 5730.39 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-09-11 |  | 2018-10-31 | 50
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14466 | 2018-11-29 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-11-14 | 2018-10-30 | 2018-11-29 |  | Oct-18 | Nov-18 | MW417R001525-AYCA-4NOC4P-2MIR-22-40 Cawarra Road, Caringbah | Caringbah | 616.6 | 857.91 | 1474.51 | 1621.961 |  |  | 0 | 1474.51 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-09-18 |  | 2018-11-30 | 73
A401/Greenfield | Sth Coast | Marshell Antonio | Inv 13928 | 2018-07-27 | 2018-07-05 | 2018-07-05 | 2018-07-10 | 2018-07-18 | 2018-07-19 | 2018-07-31 |  | Jul-18 | Jul-18 | MW22519 - AYCA-4V3JM3 - 2COR-01 - 69 High Street, Thirroul | Thirroul | 9249 | 5339.41 | 14588.41 | 16047.251 |  |  | 0 | 14588.41 | 100% |  |  |  | Dave Yoemans | 2018-05-31 | 2018-06-13 | 13 | 2018-06-29 | 16
NBN Assurance Sydney | NSW | Damien Marov | Inv 13781 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-24 |  | Jul-18 | Jul-18 | MW417R000504-2KTB-04-166 Great Western Highway, Wentworth Falls | Wentworth Falls | 2434.66 |  | 2434.66 | 2678.126 |  | 1008 | 1008 | 1426.66 | 58.6% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Sydney | NSW | Damien Marov | Inv 13782 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000569-2KTB-02-INC000007293986-Lot 22, 33 Foy Avenue, Medlow Bath | Medlow Bath | 1537.68 |  | 1537.68 | 1691.448 |  | 560 | 560 | 977.68 | 63.58% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Andrew McPherson | Inv 13784 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-08-16 |  | Jul-18 | Aug-18 | MW417R000570-2YAS-01-INC000007561589-Lot 102, 51 Mount St, Yass | Yass | 1819.54 |  | 1819.54 | 2001.494 |  | 976 | 504 | 1315.54 | 72.3% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Andrew McPherson | Inv 13785 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000520-2WWY-20-34 Church St, West Wyalong, NSW | West Wyalong | 768.84 |  | 768.84 | 845.724 |  | 224 | 224 | 544.84 | 70.87% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Andrew McPherson | Inv 13786 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-08-07 |  | Jul-18 | Aug-18 | MW417R000510-2CON-20-74-76 Orange St, Condobolin, NSW-INC000007693413 | Condobolin | 961.05 |  | 961.05 | 1057.155 |  | 308 | 308 | 653.05 | 67.95% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Andrew McPherson | Inv 13787 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-19 |  | Jul-18 | Jul-18 | MW417R000508-2WAG-06-Lot 220, 23 Crisp Dr, Ashmont, NSW | Ashmont | 962.813 |  | 962.813 | 1059.0943 |  | 168 | 168 | 794.813 | 82.55% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Andrew McPherson | Inv 13788 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-19 |  | Jul-18 | Jul-18 | MW417R000503-2CON-20-Lot 11, 15 Busby Street, Condobolin | Condobolin | 962.813 |  | 962.813 | 1059.0943 |  | 112 | 112 | 850.813 | 88.37% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Andrew McPherson | Inv 13789 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-19 |  | Jul-18 | Jul-18 | MW417R000507-2ALB-04-Lot 4, 2 Bunker Ct, Albury, NSW-INC000007471430 | Albury | 2947.22 |  | 2947.22 | 3241.942 |  | 1226 | 1226 | 1721.22 | 58.4% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Andrew McPherson | Inv 13790 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000511-2LTO-21-Lot 1, 45 Gossamer St, Leeton | Leeton | 3655.39 |  | 3655.39 | 4020.929 |  | 1690 | 1690 | 1965.39 | 53.77% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Sydney | NSW | Damien Marov | Inv 13794 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-08-16 |  | Jul-18 | Aug-18 | MW417R000542-2KTB-02-51 DELMONTE AV, MEDLOW BATH-INC000008346619 | Medlow Bath | 1422.33 |  | 1422.33 | 1564.563 |  | 600 | 600 | 822.33 | 57.82% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Damien Marov | Inv 13791 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000516-2HAY-20-Lot 7, 460 Orson St, Hay, NSW-INC000006971761 | Hay | 11144.61 |  | 11144.61 | 12259.071 |  | 6965.3813 | 6965.3813 | 4179.2288 | 37.5% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Sydney | NSW | Damien Marov | Inv 13792 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-03 |  | Jul-18 | Jul-18 | MW417R000587 - INC0000082632412KTB-01 - 24 NELSON RD, KATOOMBA | Katoomba | 3799.81 |  | 3799.81 | 4179.791 |  | 1522 | 2164 | 1635.81 | 43.05% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Sydney | NSW | Damien Marov | Inv 13795 | 2018-07-04 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000567-2BLK-05-INC000007924200-UNIT 501, LOT 1, 3 FIRST AV, SEVEN HILLS | Seven Hills | 4389.9073 |  | 4389.9073 | 4828.898 |  | 1980 | 1980 | 2409.9073 | 54.9% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Sydney | NSW | Damien Marov | Inv 13798 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000568-2KTB-05-INC000007742541-Lot 18, 30 Christabel Street, Lawson | Lawson | 1473.61 |  | 1473.61 | 1620.971 |  | 532 | 532 | 941.61 | 63.9% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Sydney | NSW | Damien Marov | Inv 13863 | 2018-07-04 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-26 |  | Jul-18 | Jul-18 | MW417R000521-2KTB-01-42-84 Martin St, Katoomba High School, Katoomba | Katoomba | 1409.54 |  | 1409.54 | 1550.494 |  | 504 | 504 | 905.54 | 64.24% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Andrew McPherson | Inv 13815 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000576-2NMN-20-INC000007557971-113 WATTLE CR, NARROMINE | Narromine | 1153.26 |  | 1153.26 | 1268.586 |  | 392 | 392 | 761.26 | 66.01% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Sydney | NSW | Andrew McPherson | Inv 13796 | 2018-07-04 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-26 |  | Jul-18 | Jul-18 | MW417R000577-2KTB-03-INC000007929584-127 Craigend St, Leura | Leura | 3651.99 |  | 3651.99 | 4017.189 |  | 1484 | 1484 | 2167.99 | 59.36% |  | 2018-07-17 |  | Tony Gabriel
NBN Assurance Wagga | NSW | Damien Marov | inv 13783 | 2018-07-03 | 2018-07-03 | 2018-07-03 |  |  |  | 2018-07-17 |  | Jul-18 | Jul-18 | MW417R000514-2WWY-20-12-20 BARNADO ST, WEST WYALONG | West Wyalong | 512.56 |  | 512.56 | 563.816 |  | 280 | 280 | 232.56 | 45.37% |  | 2018-07-17 |  | Tony Gabriel
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14151 | 2018-09-11 | 2018-07-23 | 2018-07-24 | 2018-07-25 | 2018-08-30 | 2018-08-07 | 2018-09-13 |  | Jul-18 | Sep-18 | MW417R000454 -AYCA-4V7F3M - 2LAK-22 - 23 Willeroo St, Lakemba | Lakemba | 2111.65 | 6124.44 | 8236.09 | 9059.699 | 3227.26 |  | 3227.26 | 5008.83 | 60.82% |  | 2018-08-07 |  | Ertan Cicek | Direct Award | 2018-07-05 |  | 2018-08-03 | 29
A417 Greenfield MDU | Sth Coast | Marshell Antonio | Inv 14518 | 2018-12-05 | 2018-10-30 | 2018-10-30 | 2018-10-31 | 2018-11-27 | 2018-11-13 | 2018-12-06 |  | Oct-18 | Dec-18 | MW417R000494-AYCA-21R8AP-2WLG-07-12-14 New Dapto Rd Wollongong | Wollongong | 1022.88 | 1599.58 | 2622.46 | 2884.706 | 680.69 | 302.51 | 983.2 | 1639.26 | 62.51% |  | 2018-11-13 |  | Ertan Cicek | Direct Award | 2018-07-05 |  | 2018-09-28 | 85
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R000495-AYCA-4X1Z9M-2MIR-26-58/60 Karimbla Rd, Miranda | Miranda | 680.91 |  | 680.91 | 749.001 |  |  | 0 | 680.91 | 100% |  | 2019-06-13 |  | Ertan Cicek | Direct Award | 2018-07-05 |  | 2018-09-28 | 85
A417 Greenfield MDU | Central Coast | Dane Harrington | Inv 14472 | 2018-11-29 | 2018-09-21 | 2018-09-21 | 2018-10-05 | 2018-11-14 | 2018-10-05 | 2018-11-29 |  | Sep-18 | Nov-18 | MW22435-AYCA-5576QH-2TGL-02-3 Ghersi Ave Wambera | Wamberal | 1596.49 | 8753.25 | 10349.74 | 11384.714 | 7118.33 |  | 7118.33 | 3231.41 | 31.22% |  |  |  | Ertan Cicek | Direct Award | 2018-05-14 |  | 2018-05-26 | 12
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R000462-AYCA-328OYF-2CBT-05-37-41 Chamberlain St, Campbelltown | Campbelltown | 1821.28 |  | 1821.28 | 2003.408 | 415.2 |  | 415.2 | 1406.08 | 77.2% |  | 2019-04-13 |  | Ertan Cicek | Direct Award | 2018-07-05 |  | 2018-09-28 | 85
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  | 2019-03-17 | 2019-03-17 | 2019-03-19 |  | 2019-03-31 | 2019-04-14 |  | Mar-19 | Apr-19 | MW417R000518-AYCA-2V9V2D-2HOR-63-2 Cowan Road & 540A-542 Pacific Highway, Mount Colah | Mount Colah | 1606.42 | 2515.82 | 4122.24 | 4534.464 | 1303.35 |  | 1303.35 | 2818.89 | 68.38% |  | 2019-03-31 |  | Ertan Cicek | Direct Award | 2018-07-05 |  | 2018-09-28 | 85
A401/Greenfield | Central West | Marshell Antonio | Inv 13742 | 2018-06-13 | 2018-05-23 | 2018-05-23 | 2018-05-23 | 2018-05-31 | 2018-06-06 | 2018-06-13 |  | May-18 | Jun-18 | MW22196 - AYCA-4VVND3 - 2ORG-01 - 258 CLERGATE RD, ORANGE | Orange | 6657.74 | 4284.1551 | 10941.8951 | 12036.0846 | 8266.83 |  | 8266.83 | 2675.0651 | 24.45% |  | 2018-06-06 |  | Dave Yoemans | 2018-04-11 | 2018-04-16 | 5 | 2018-06-08 | 53
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 13983 | 2018-08-03 | 2018-07-10 | 2018-07-12 |  |  | 2018-07-27 | 2018-08-02 |  | Jul-18 | Aug-18 | MW417R000529-AYCA-5ALZB0-2BLK-07-6 Woods Cl Huntingwood Int | Huntingwood | 285.6 |  | 285.6 | 314.16 |  |  | 0 | 285.6 | 100% |  | 2018-07-26 |  | Ertan Cicek | Direct Award | 2018-07-09 |  | 2018-07-18 | 9
A401/Greenfield | Central West | Marshell Antonio | Inv 14192 | 2018-09-28 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-09-13 | 2018-09-10 | 2018-09-25 |  | Aug-18 | Sep-18 | MW417R000543-2PKS-21-AYCA-5866DJ-2 Cecile Street, Parkes | Parkes | 7336.89 | 446.39 | 7783.28 | 8561.608 |  |  | 0 | 7783.28 | 100% |  | 2018-09-10 |  | Mark Leal | 2018-07-06 | 2018-07-10 | 4 | 2018-09-27 | 79
A401/Greenfield | Sth NSW | Marshell Antonio | Inv 14161 | 2018-09-21 | 2018-08-24 | 2018-08-24 | 2018-08-27 | 2018-09-13 | 2018-09-07 | 2018-09-20 |  | Aug-18 | Sep-18 | MW417R000059-AYCA-59JUMX - 2WAG-02-J83 Trail Street, Wagga Wagga | Wagga Wagga | 3012.97 | 4673.6 | 7686.57 | 8455.227 |  |  | 0 | 7686.57 | 100% |  | 2018-09-07 |  | Mark Leal | 2018-05-31 | 2018-07-11 | 41 | 2018-09-06 | 57
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R000625-AYCA-4QDZCA-2STL-61-31-33 Albany St, Crows Nest | Crows Nest | 1576.32 |  | 1576.32 | 1733.952 |  |  | 0 | 1576.32 | 100% |  | 2019-05-14 |  | Ertan Cicek | Direct Award | 2018-07-13 |  | 2018-10-10 | 89
A417 Greenfield MDU | Central Coast | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R000606-AYCA-56PJ6I-2GRK-01-645 Pacific Hwy, Kanwal | Kanwal | 5378 |  | 5378 | 5915.8 |  |  | 0 | 5378 | 100% |  | 2019-04-13 |  | Ertan Cicek | Direct Award | 2018-07-12 |  | 2018-10-10 | 90
A401/Greenfield | Central West | Marshell Antonio | Inv 14164 | 2018-09-21 | 2018-08-27 | 2018-08-27 |  |  | 2018-09-10 | 2018-09-20 |  | Aug-18 | Sep-18 | MW417R000468‐2PKS‐20‐AYCA‐4VRIOS‐37 High Street Parkes | Parkes | 9404.63 |  | 9404.63 | 10345.093 |  |  | 0 | 9404.63 | 100% |  |  |  | Mark Leal | 2018-07-05 | 2018-07-17 | 12 | 2018-09-26 | 71
A401/Greenfield | Sth NSW | Marshell Antonio | Inv 14520 | 2018-12-05 | 2018-11-06 | 2018-11-06 | 2018-11-13 | 2018-11-23 | 2018-11-20 | 2018-12-06 |  | Nov-18 | Dec-18 | MW417R000460 - AYCA-58DKIW - 2GFT-20 - 43 Jondaryan Avenue, Griffith | Griffith | 12959.63 | 9226.871 | 22186.501 | 24405.1511 |  |  | 0 | 22186.501 | 100% |  |  |  | Mark Leal | 2018-06-26 | 2018-07-17 | 21 | 2018-09-21 | 66
A401/Greenfield | ACT | Marshell Antonio | Inv 14265 | 2018-10-15 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-27 | 2018-10-02 | 2018-10-16 |  | Sep-18 | Oct-18 | MW417R000338-AYCA-54NU37-9KBA-20-427-177 Newman-Morris Circuit, Oxley, ACT | Oxley | 15828.41 | 7165.57 | 22993.98 | 25293.378 | 9054.28 | 3403.2501 | 12457.5301 | 10536.4499 | 45.82% |  |  |  | Mark Leal | 2018-06-20 | 2018-07-19 | 29 | 2018-09-11 | 54
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R000602 - AYCA-49DBF5 - 2CRO-21 - 33-39 Croydon St, Cronulla | Cronulla | 1557.5 |  | 1557.5 | 1713.25 |  |  | 0 | 1557.5 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-17 |  | 2018-10-10 | 85
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R000611-AYCA-4Z6R8L-2DAL-28-148-160 King St, Sydney | Sydney CBD | 1838.89 |  | 1838.89 | 2022.779 |  |  | 0 | 1838.89 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-17 |  | 2018-10-10 | 85
A401/Greenfield | Central Coast | Mickey Tran |  |  | 2018-07-17 | 2018-07-30 | Project Cancelled by NBN |  |  | 2018-08-30 |  | Jul-18 | Aug-18 | MW417R000209-AYCA-44H5DT-2GRK-02-44 Hakone Rd Woongarrah | Woongarrah | 7622.05 | -4533.29 | 3088.76 | 3397.636 | 2011.12 |  | 2011.12 | 1077.64 | 34.89% |  |  |  | Sogand Mohtat | 2018-06-06 | 2018-06-19 |  | 2018-07-17 | 28
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R000627-AYCA-4VSW7K-2PTH-05-10-12 Vista St, Penrith | Penrith | 1745.46 |  | 1745.46 | 1920.006 |  |  | 0 | 1745.46 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-18 |  | 2018-10-10 | 84
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R000616-AYCA-4VH4MG-2PTH-02-36 Barber Ave, Penrith | Penrith | 1863.78 |  | 1863.78 | 2050.158 |  |  | 0 | 1863.78 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-18 |  | 2018-10-10 | 84
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R000629-AYCA-4OCM1V-2UND-60-260-264 Wardell Rd | Marrickville | 875.62 |  | 875.62 | 963.182 |  |  | 0 | 875.62 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-18 |  | 2018-10-10 | 84
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R000605 - AYCA-4XR9F8 -2ROU-02 - 320 Annangrove Rd, Rouse Hill | Rouse Hill | 4072.98 |  | 4072.98 | 4480.278 |  |  | 0 | 4072.98 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-18 |  | 2018-10-10 | 84
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14247 | 2018-10-11 | 2018-08-23 | 2018-08-23 | 2018-08-26 | 2018-09-18 | 2018-09-06 | 2018-10-11 |  | Aug-18 | Oct-18 | MW417R000669-AYCA-4QID92-2EAS-63-153-165 Brougham St, Woolloomooloo | Potts Point | 4517.93 | 9364.678 | 13882.608 | 15270.8688 | 5869.67 |  | 5869.67 | 8012.938 | 57.72% |  |  |  | Ertan Cicek | Direct Award | 2018-07-19 |  | 2018-10-12 | 85
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14474 | 2018-11-29 | 2018-10-05 | 2018-10-05 | 2018-10-10 | 2018-11-14 | 2018-10-19 | 2018-11-29 |  | Oct-18 | Nov-18 | MW417R000211-AYCA-56B97M-2SEF-61-1 Tangerine St, Fairfield East | Fairfield | 2424.06 | 3717.23 | 6141.29 | 6755.419 | 2694.03 |  | 2694.03 | 3447.26 | 56.13% |  |  |  | Ertan Cicek | Direct Award | 2018-06-12 |  | 2018-09-28 | 108
A417 Greenfield MDU | Newcastle | Dane Harrington | Inv 14627 | 2019-01-18 | 2018-11-02 | 2018-11-05 | 2018-11-20 | 2018-11-21 | 2018-11-19 | 2019-01-17 |  | Nov-18 | Jan-19 | MW417R000707-AYCA-4QHVO8-2CHL-07-13-15 Pacific Hwy, Gateshead | Gateshead | 10653.74 | 12707.51 | 23361.25 | 25697.375 | 11292.03 | 1856.5901 | 13148.6201 | 10212.6299 | 43.72% |  |  |  | Ertan Cicek | Direct Award | 2018-07-20 |  | 2018-10-17 | 89
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R000716-AYCA-3S7B4B-2HMK-02-University of Technology Sydney | Sydney | 1753.73 |  | 1753.73 | 1929.103 | 3947.98 |  | 3947.98 | -2194.25 | -125.1% |  |  |  | Ertan Cicek | Direct Award | 2018-07-20 |  | 2018-10-17 | 89
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-07-30 | [5 empty] | Jul-19 | Jan-00 | MW417R000706-AYCA-3O2CEB-2GBE-62-5 Elger St, Glebe | Glebe | 1044.69 |  | 1044.69 | 1149.159 |  |  | 0 | 1044.69 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-20 |  | 2018-10-17 | 89
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14638 | 2019-01-18 | 2018-11-15 | 2018-11-16 | 2018-11-21 | 2018-12-21 | 2018-11-30 | 2019-01-22 |  | Nov-18 | Jan-19 | MW22094-AYCA-4LM7HH-2UND-61-590-602 New Canterbury Rd, Hurlstone Park | Hurlestone Park | 2574.51 | 11918.41 | 14492.92 | 15942.212 | 8104.13 |  | 8104.13 | 6388.79 | 44.08% |  | 2018-11-30 |  | Ertan Cicek | Direct Award | 2018-03-28 |  | 2018-04-24 | 27
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R000710-AYCA-55RMFH-2WET-23-1521 The Horsley Dr, Abbotsbury | Abbotsbury | 5325.25 |  | 5325.25 | 5857.775 |  |  | 0 | 5325.25 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-20 |  | 2018-10-27 | 99
A417 Greenfield MDU | Sth NSW | Marshell Antonio | Inv 14209 | 2018-09-26 | 2018-09-07 | 2018-09-07 | 2018-09-07 | 2018-09-17 | 2018-09-21 | 2018-09-27 |  | Sep-18 | Sep-18 | MW417R000743-AYCA-4K6VYT-2JNB-20-30 Twynam St, Jindabyne | Jindabyne | 1942.23 | 1545.48 | 3487.71 | 3836.481 |  |  | 0 | 3487.71 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-20 |  | 2018-11-03 | 106
NBN FttC Drops | Sth Coast | Rob Panovski | Inv 14544 | 2018-12-14 | 2018-10-31 | 2018-10-31 | 2018-11-14 | 2018-11-23 | 2018-11-14 | 2018-12-14 |  | Oct-18 | Dec-18 | MW417R001125-2BMG-20-STELLAR NPDL Bermagui | Bermigui | 16521.4 | 103826.76 | 120348.16 | 132382.976 | 79409.25 |  | 79409.25 | 40938.91 | 34.02% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sth Coast | Rob Panovski | Inv 14052 | 2018-08-22 | 2018-08-20 | 2018-08-20 |  |  |  | 2018-08-23 |  | Aug-18 | Aug-18 | MW417R001125-2BMG-20-STELLAR NPDL Bermagui | Bermigui | 7080.6 |  | 7080.6 | 7788.66 |  |  | 0 | 7080.6 | 100% |  |  |  | Kirsty Doyle | Direct Award
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-12-30 | [5 empty] | Dec-19 | Jan-00 | MW417R000713-AYCA-4LT337-2WET-23-457-463 Victoria Street, Wetherill | Wetherill Park | 5138.95 |  | 5138.95 | 5652.845 |  |  | 0 | 5138.95 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-20 |  | 2018-10-17 | 89
A401/Greenfield | Nth Coast | Mickey Tran | Inv 14216 | 2018-10-09 | 2018-09-12 | 2018-09-12 |  |  | 2018-09-26 | 2018-10-09 |  | Sep-18 | Oct-18 | MW417R000595 - 2PTM-09 - AYCA-4OQ160 - 2PTM-09 - 3 Ocean Ridge Terrace, Port Macquarie | Port Macquarie | 12541.16 |  | 12541.16 | 13795.276 | 4994.35 | 1160 | 6154.35 | 6386.81 | 50.93% |  |  |  | Mark Leal | 2018-07-16 | 2018-07-23 | 7 | 2018-08-08 | 16
A417 HFC DFN | Sydney | Mickey Tran | Inv 14579 | 2019-01-02 | 2018-10-19 | 2018-10-19 | 2018-10-24 | 2018-12-10 | 2018-11-02 | 2019-01-03 |  | Oct-18 | Jan-19 | MW417R000157-AYCA-4A46K7-2PAR-63-208-210 Great Western Hwy, Westmead DFN Design & Construct | Westmead | 25044.57 | 53952.1065 | 78996.6765 | 86896.3441 | 48798.2019 | 6825.1603 | 55623.3622 | 23373.3143 | 29.59% |  |  |  | Mark Leal | Direct Award | 2018-06-08 |  | 2018-08-31 | 84
A417 Greenfield MDU | ACT | Marshell Antonio | Inv 14208 | 2018-09-26 | 2018-09-07 | 2018-09-07 | 2018-09-07 | 2018-09-13 | 2018-09-21 | 2018-09-27 |  | Sep-18 | Sep-18 | MW417R000756-AYCA-593AE3-9QBN-03-12 Uriarra Rd, Queanbeyan | Queanbeyan | 3146.07 | 7941.2842 | 11087.3542 | 12196.0897 |  |  | 0 | 11087.3542 | 100% |  |  |  | Mark Leal | Direct Award | 2018-07-23 |  | 2018-11-01 | 101
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14264 | 2018-10-15 | 2018-09-07 | 2018-09-07 |  |  | 2018-10-05 | 2018-10-19 |  | Sep-18 | Oct-18 | MW417R000741-AYCA-4BC75L-2BLK-11-Fairwater Boulevard, Blacktown | Blacktown | 901.08 |  | 901.08 | 991.188 |  | 178.6217 | 178.6217 | 722.4583 | 80.18% |  |  |  | Mark Leal | Direct Award | 2018-07-23 |  | 2018-10-08 | 77
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R000739-AYCA-3AVVT5-2BRG-01-70 Seventeenth Avenue, Austral | Austral | 5335.07 |  | 5335.07 | 5868.577 |  |  | 0 | 5335.07 | 100% |  |  |  | Mark Leal | Direct Award | 2018-07-23 |  | 2018-11-02 | 102
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14636 | 2019-01-18 | 2018-11-20 | 2018-11-20 | 2018-11-21 | 2018-12-21 | 2018-12-04 | 2019-01-22 |  | Nov-18 | Jan-19 | MW417R000708-AYCA-57DG41-2BTH-01-93 Stanley St, Bathurst Ext | Bathurst | 4097 | 6315.449 | 10412.449 | 11453.6939 | 2929.97 |  | 2929.97 | 7482.479 | 71.86% |  |  |  | Richard Huffadine | Direct Award | 2018-07-20 |  | 2018-10-17 | 89
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14200 | 2018-09-26 | 2018-08-31 | 2018-08-31 | 2018-09-04 | 2018-09-17 | 2018-09-14 | 2018-09-27 |  | Aug-18 | Sep-18 | MW417R000745-AYCA-4LISRC-2BRG-03-62 Jamboree Ave, Leppington | Leppington | 3386.21 | 180.24 | 3566.45 | 3923.095 |  |  | 0 | 3566.45 | 100% |  |  |  | Mark Leal | Direct Award | 2018-07-25 |  | 2018-10-26 | 93
A417 Greenfield MDU | Central Coast | Mickey Tran | Inv 14239 | 2018-10-11 | 2018-09-14 | 2018-09-14 | 2018-09-19 | 2018-09-27 | 2018-09-28 | 2018-10-16 |  | Sep-18 | Oct-18 | MW417R000748-AYCA-4SQA1N-2GRK-06-Eleanor Close, Hamlyn Terrace | Hamlyn Terrace | 1126.73 | 2824.192 | 3950.922 | 4346.0142 |  |  | 0 | 3950.922 | 100% |  |  |  | Mark Leal | Direct Award | 2018-07-25 |  | 2018-11-16 | 114
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14245 | 2018-10-11 | 2018-09-04 | 2018-09-04 | 2018-09-19 | 2018-09-27 | 2018-09-18 | 2018-10-11 |  | Sep-18 | Oct-18 | MW417R000750-AYCA-4W3F0S- 51-53 Foxall Road, Kellyville | Kellyville | 2438.62 | 7436.94 | 9875.56 | 10863.116 | 3547.88 |  | 3547.88 | 6327.68 | 64.07% |  |  |  | Ertan Cicek | Direct Award | 2018-07-25 |  | 2018-12-05 | 133
A417 Greenfield MDU | ACT | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R000774-AYCA-5ECAGW-9QBN-09-79 Sawmill Circuit, Hume | Hume | 8978.73 |  | 8978.73 | 9876.603 |  |  | 0 | 8978.73 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-07-25 |  | 2018-10-20 | 87
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R000763-AYCA-5BXBTE-2MIR-27-41 Langer Ave, Caringbah | Carringbah | 3084.32 |  | 3084.32 | 3392.752 | 2061.17 |  | 2061.17 | 1023.15 | 33.17% |  |  |  | Ertan Cicek | Direct Award | 2018-07-25 |  | 2018-10-19 | 86
A417 Greenfield MDU | Central Coast | Mickey Tran | Inv 14162 | 2018-09-21 | 2018-08-28 | 2018-08-28 | 2018-08-29 | 2018-09-13 | 2018-09-11 | 2018-09-20 |  | Aug-18 | Sep-18 | MW417R000755-AYCA-56GK8A-2BLR-03-79 Marmong St, Booragul | Booragul | 1609.29 | 3905.92 | 5515.21 | 6066.731 | 2321.16 |  | 2321.16 | 3194.05 | 57.91% |  |  |  | Ertan Cicek | Direct Award | 2018-07-25 |  | 2018-10-05 | 72
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14522 | 2018-12-05 | 2018-10-05 | 2018-10-05 | 2018-10-08 | 2018-11-14 | 2018-10-19 | 2018-12-06 |  | Oct-18 | Dec-18 | MW417R000395 - AYCA-56PP6W-2BAN-67-55-57 Chelmsford Ave, Bankstown | Bankstown | 6228.33 | 5347.31 | 11575.64 | 12733.204 | 4454.87 |  | 4454.87 | 7120.77 | 61.52% |  |  |  | Ertan Cicek | Direct Award | 2018-06-29 |  | 2018-09-28 | 91
A417 Business Segment | Sth NSW | Mickey Tran | Inv 14504 | 2018-12-05 | 2018-10-29 | 2018-10-29 | 2018-11-09 | 2018-11-20 | 2018-11-26 | 2018-12-04 |  | Oct-18 | Dec-18 | MW417R000847-AYCA-5I9AIZ-BS-2GFT-21-11 Fairfax Demand Fibre Griffith | Griffith | 16698.66 | 5659.37 | 22358.03 | 24593.833 |  |  | 0 | 22358.03 | 100% |  |  |  | Dave Yoemans | 2018-07-26 | 2018-08-01 | 6 | 2018-11-05 | 96
A401/Greenfield NSB | Sydney West | Mickey Tran |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R000877-AYCA-54DAGS-2PTH-07-29 Park Ave Kingswood NSB | Kingswood | 960 |  | 960 | 1056 |  |  | 0 | 960 | 100% |  |  |  | Mark Leal | 2018-07-30 | 2018-08-06 | 7 | 2018-09-03 | 28
A401/Greenfield | ACT | Marshell Antonio | inv 14278 | 2018-10-18 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-10-11 | 2018-10-12 | 2018-10-18 |  | Sep-18 | Oct-18 | MW417R000844-AYCA-5K7QBN - 9QBN-03-74 Uriarra Road NSB | Queanbeyan | 960 | 1390.8064 | 2350.8064 | 2585.887 |  | 465.84 | 465.84 | 1884.9664 | 80.18% |  |  |  | Mark Leal | 2018-07-30 | 2018-08-03 | 4 | 2018-11-19 | 108
A401/Greenfield NSB | Central West | Mickey Tran |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R000845-AYCA-5KAX1D -2MDG-01- 20 Burrundulla Ave Mudgee NSB | Mudgee | 960 |  | 960 | 1056 | 4934.31 |  | 4934.31 | -3974.31 | -414% |  |  |  | Mark Leal | 2018-07-30 | 2018-08-06 | 7 | 2018-11-19 | 105
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14474 |  | 2018-10-10 | 2018-10-10 | 2018-10-16 | 2018-11-14 | 2018-10-24 | 2018-11-28 |  | Oct-18 | Nov-18 | MW417R000461-AYCA-5AXHNZ-2SIL-02-4 Murray Rose Ave, Sydney Olympic Park | Sydney Olympic Park | 2123.65 | 8407.02 | 10530.67 | 11583.737 |  |  | 0 | 10530.67 | 100% |  | 2018-10-24 |  | Ertan Cicek | Direct Award | 2018-07-05 |  | 2018-09-28 | 85
A417 Greenfield MDU | Sth Coast | Mickey Tran | Inv 14471 | 2018-11-29 | 2018-10-08 | 2018-10-08 | 2018-10-09 | 2018-11-14 | 2018-10-22 | 2018-11-29 |  | Oct-18 | Nov-18 | MW417R000704-AYCA-57Y170-2BRY-01-17 Hitchcocks Ln, Berry | Berry | 172.2 | 8427.44 | 8599.64 | 9459.604 | 2472.8 |  | 2472.8 | 6126.84 | 71.25% |  |  |  | Ertan Cicek | Direct Award | 2018-07-19 |  | 2018-10-17 | 90
A417 Greenfield MDU | Sth Coast | Mickey Tran | Inv 14470 | 2019-11-29 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-11-14 | 2018-10-29 | 2018-11-29 |  | Oct-18 | Nov-18 | MW417R000775-AYCA-5A18P2-2PKE-04-249 Shellharbour Rd Warrawong | Warrawong | 2786.87 | 4481.6041 | 7268.4741 | 7995.3216 | 3640 |  | 3640 | 3628.4741 | 49.92% |  |  |  | Ertan Cicek | Direct Award | 2018-07-25 |  | 2018-10-20 | 87
A417 Greenfield MDU | Sth NSW | Marshell Antonio |  |  | 2018-10-15 | 2018-10-15 | 2018-10-16 | 2018-10-24 | 2018-10-26 | 2018-11-06 |  | Oct-18 | Nov-18 | MW417R000742-AYCA-4E9HF0-2MTT-03--Mittagong | Mittagong | 970.55 | -153.99 | 816.56 | 898.216 |  | 390 | 390 | 426.56 | 52.24% |  |  |  | Ertan Cicek | Direct Award | 2018-07-31 |  | 2018-11-08 | 100
A417 Greenfield MDU | Newcastle | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R000968-AYCA-5CMO2F-2TAR-01-6 Parish Dr, Beresfield | Beresfield | 2014.04 |  | 2014.04 | 2215.444 | 1609.84 |  | 1609.84 | 404.2 | 20.07% |  |  |  | Ertan Cicek | Direct Award | 2018-08-06 |  | 2018-10-30 | 85
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-09-30 | [5 empty] | Sep-19 | Jan-00 | MW417R001044-03-AYCA-41DSOU-2ROU-38 Hezlett Road, Kellyville | Kellyville | 6449.44 |  | 6449.44 | 7094.384 |  |  | 0 | 6449.44 | 100% |  |  |  | Mark Leal | Direct Award | 2018-08-07 |  | 2018-11-02 | 87
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14197 | 2018-09-26 | 2018-08-31 | 2018-08-31 | 2018-09-03 | 2018-09-17 | 2018-09-14 | 2018-09-27 |  | Aug-18 | Sep-18 | MW417R001022 - AYCA-45LS90 - 2ROU-03 - 8 Withers Rd, Kellyville | Kellyville | 1481.08 | 400.91 | 1881.99 | 2070.189 |  |  | 0 | 1881.99 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-08-07 |  | 2018-11-02 | 87
A417 Greenfield MDU | Central Coast | Mickey Tran | Inv 14163 | 2018-09-21 | 2018-08-28 | 2018-08-28 |  |  | 2018-09-11 | 2018-09-20 |  | Aug-18 | Sep-18 | MW417R001023-AYCA-4KNB05-2BLR-03-20 Myrtle St, Teralba | Teralba | 3760.18 |  | 3760.18 | 4136.198 | 1040.76 | 202.868 | 1243.628 | 2516.552 | 66.93% |  |  |  | Ertan Cicek | Direct Award | 2018-08-07 |  | 2018-11-02 | 87
A417 Greenfield MDU | ACT | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R001077-AYCA-5A3CT0 - 9MNK-01- 1 Beaconsfield St, Fyshwick | Fyshwick | 3855.46 |  | 3855.46 | 4241.006 |  |  | 0 | 3855.46 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-08-09 |  | 2018-10-31 | 83
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14205 | 2018-09-26 | 2018-09-04 | 2018-09-04 | 2018-09-06 | 2018-09-17 | 2018-09-18 | 2018-09-27 |  | Sep-18 | Sep-18 | MW417R001042-AYCA-4KKMW0-2ROU-03-AYCA-4KKMW0- 55 Foxall Road – 3 | Kellyville | 638.4 | 16565.93 | 17204.33 | 18924.763 | 706 |  | 706 | 16498.33 | 95.9% |  |  |  | Ertan Cicek | Direct Award | 2018-08-09 |  | 2018-11-02 | 85
A417 Greenfield MDU | Newcastle | Dane Harrington |  |  |  | 2019-08-30 | [5 empty] | Aug-19 | Jan-00 | MW417R001040 - AYCA-4RJS2D - 2CHL-05 - 5 Edge St, Boolaroo | Boolaroo | 1668.12 |  | 1668.12 | 1834.932 |  |  | 0 | 1668.12 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-08-09 |  | 2018-11-02 | 85
NBN Assurance Sydney | NSW |  | Inv 13856 | 2018-07-17 | 2018-07-17 | 2018-07-17 |  |  |  | 2018-08-09 |  | Jul-18 | Aug-18 | MW417R000728- LOC000008822657 - Lot 4, 43 Wentworth St, Blackheath | Blackheath | 2191.17 |  | 2191.17 | 2410.287 |  | 868 | 868 | 1323.17 | 60.39% |  |  |  | Tony Gabriel
NBN Assurance Wagga | NSW |  | Inv 13857 | 2018-07-17 | 2018-07-17 | 2018-07-17 |  |  |  | 2018-08-09 |  | Jul-18 | Aug-18 | MW417R000725-INC000007511350 - Lot 17, 12 Weemilah St, Yass | Yass | 5351.03 |  | 5351.03 | 5886.133 |  | 1642 | 1642 | 3709.03 | 69.31% |  | 2018-07-31 |  | Tony Gabriel
NBN Assurance Wagga | NSW |  | Inv 13858 | 2018-07-17 | 2018-07-17 | 2018-07-17 |  |  |  | 2018-08-09 |  | Jul-18 | Aug-18 | MW417R000727-INC000008070266 - Lot 129, 21 Bruce Street, Tolland | Tolland | 640.7 |  | 640.7 | 704.77 |  | 140 | 140 | 500.7 | 78.15% |  |  |  | Tony Gabriel
NBN Assurance Wagga | NSW |  | Inv 13859 | 2018-07-17 | 2018-07-17 | 2018-07-17 |  |  |  | 2018-08-09 |  | Jul-18 | Aug-18 | MW417R000730-INC000008281172 - 21 AWABA AV, TOLLAND | Tolland | 640.7 |  | 640.7 | 704.77 |  | 168 | 168 | 472.7 | 73.78% |  |  |  | Tony Gabriel
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R001041-AYCA-4H9191-2COR-03-208-210 Princes Highway, Bulli | Bulli | 620.65 |  | 620.65 | 682.715 | 328 |  | 328 | 292.65 | 47.15% |  |  |  | Mark Leal | Direct Award | 2018-08-10 |  | 2018-11-02 | 84
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14698 | 2019-02-04 | 2019-01-10 | 2019-01-10 | 2019-01-10 | 2019-01-22 | 2019-01-24 | 2019-02-07 |  | Jan-19 | Feb-19 | MW417R001085-AYCA-583XDD-17-2PTH-02-119 Jamison Rd South Penrith | Penrith | 1061.38 | 2278.84 | 3340.22 | 3674.242 | 1740 |  | 1740 | 1600.22 | 47.91% |  |  |  | Ertan Cicek | Direct Award | 2018-08-14 |  | 2018-11-08 | 86
A401/Greenfield | Sth NSW | Marshell Antonio | Inv 14277 | 2018-10-17 | 2018-09-27 | 2018-09-27 |  |  | 2018-10-12 | 2018-10-18 |  | Sep-18 | Oct-18 | MW417R001036 - AYCA-4QEPUO - 2YAS-01 - 23 Rossi St, Yass | Yass | 5445.8 |  | 5445.8 | 5990.38 |  |  | 0 | 5445.8 | 100% |  |  |  | Mark Leal | 2018-08-08 | 2018-08-14 | 6 | 2018-10-30 | 77
A401/Greenfield | Sydney | Mickey Tran | Inv 14144 | 2018-09-11 | 2018-08-24 | 2018-08-24 |  |  | 2018-09-07 | 2018-09-11 |  | Aug-18 | Sep-18 | MW417R000974-AYCA-5F0TZX- 2AVA-01-6 Bangalley Way, Avalon Beach | Avalon | 2431 |  | 2431 | 2674.1 |  |  | 0 | 2431 | 100% |  |  |  | Ertan Cicek | 2018-08-09 | 2018-08-14 | 5 | 2018-10-25 | 72
A417 HFC DFN | Sydney | Mickey Tran | Inv 14722 | 2019-02-15 | 2018-12-03 | 2018-12-04 | 2018-12-11 | 2019-01-30 | 2018-12-18 | 2019-02-15 |  | Dec-18 | Feb-19 | MW417R001136-AYCA-33L9HP-2BAN-64-Restwell & Leonard St, Bankstown DFN Design | Bankstown | 17326.2 | 101443.9714 | 118770.1714 | 130647.1886 | 70426.27 | 4354.3705 | 74780.6405 | 43989.5309 | 37.04% |  |  |  | Mark Leal | Direct Award | 2018-08-14 |  | 2018-10-30 | 77
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14085 | 2018-08-29 | 2018-08-24 | 2018-08-24 |  |  |  | 2018-08-28 |  | Aug-18 | Aug-18 | MW417R001136-AYCA-33L9HP-2BAN-64-Restwell & Leonard St, Bankstown DFN Design | Bankstown | 7425.51 |  | 7425.51 | 8168.061 |  |  | 0 | 7425.51 | 100% |  |  |  | Mark Leal | Direct Award
A417 HFC DFN | Sydney | Mickey Tran | Inv 14632 | 2018-09-18 | 2018-10-05 | 2018-10-05 | 2018-10-12 | 2018-12-21 | 2018-10-19 | 2019-01-22 |  | Oct-18 | Jan-19 | MW417R000893-AYCA-59DV6W - 2CRR-72-Carramar HFC DFN | Carramar | 12087.24 | 34613.252 | 46700.492 | 51370.5412 | 24352.12 |  | 24352.12 | 22348.372 | 47.85% |  |  |  | Mark Leal | Direct Award | 2018-07-03 |  | 2018-09-28 | 87
A417 Greenfield MDU | Sydney | Dane Harrington |  |  | 2019-01-16 | 2019-01-16 | 2019-01-16 | 2019-03-12 | 2019-01-30 | 2019-02-13 |  | Jan-19 | Feb-19 | MW417R001116-AYCA-5FE5LS-2LIV-03-Hoxton Park Road, Liverpool | Liverpool | 3385.02 | 6075.565 | 9460.585 | 10406.6435 | 1551.05 |  | 1551.05 | 7909.535 | 83.61% |  |  |  | Ertan Cicek | Direct Award | 2018-08-14 |  | 2018-11-10 | 88
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R001121-AYCA-5BOGUQ-2PYM-61-2-6 Womerah Turramurra | Turramurra | 2718.92 |  | 2718.92 | 2990.812 |  |  | 0 | 2718.92 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-08-14 |  | 2018-11-10 | 88
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14281 | 2018-08-17 | 2018-08-23 | 2018-08-23 | 2018-08-27 | 2018-10-05 | 2018-09-06 | 2018-10-18 |  | Aug-18 | Oct-18 | MW417R001092-AYCA-5GPSWE-2CAM-20-100A- 100B Northcote Street, Canterburry | Canterbury | 4434.64 | 1312.58 | 5747.22 | 6321.942 | 1070.25 |  | 1070.25 | 4676.97 | 81.38% |  |  |  | Ertan Cicek | Direct Award | 2018-08-15 |  | 2018-11-02 | 79
A401/Greenfield | Hunter | Mickey Tran | Inv 14145 | 2018-09-11 | 2018-08-20 | 2018-08-20 | 2018-08-21 | 2018-08-31 | 2018-09-03 | 2018-09-11 |  | Aug-18 | Sep-18 | MW417R000067 - AYCA-51V8JL - 2MUS-03 - 11 Thomas Mitchell Dr, Muswellbrook | Muswellbrook | 6073.04 | 7558.75 | 13631.79 | 14994.969 | 3305.72 | 2070 | 5375.72 | 8256.07 | 60.56% |  |  |  | Mark Leal | 2018-07-24 | 2018-08-03 | 10 | 2018-08-31 | 28
A401/Greenfield | Central West | Marshell Antonio | Inv 14581 | 2018-12-21 | 2018-11-20 | 2018-11-20 | 2018-11-21 | 2018-12-04 | 2018-12-04 | 2018-12-31 |  | Nov-18 | Dec-18 | MW417R001078-AYCA-4WVWPI-2ORG-04-31 Molong Road, Orange | Orange | 4573.02 | 3890.4674 | 8463.4874 | 9309.8361 |  |  | 0 | 8463.4874 | 100% |  |  |  | Mark Leal | 2018-08-09 | 2018-08-17 | 8 | 2018-10-31 | 75
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14234 | 2018-10-09 | 2018-09-13 | 2018-09-13 | 2018-09-18 | 2018-09-27 | 2018-09-27 | 2018-10-09 |  | Sep-18 | Oct-18 | MW417R001147-AYCA-4T8B52-2ROU-04-3 Edwards Road, Box Hill | Box Hill | 3014.78 | -1566.77 | 1448.01 | 1592.811 |  | 419 | 419 | 1029.01 | 71.06% |  |  |  | Ertan Cicek | Direct Award | 2018-08-20 |  | 2018-11-13 | 85
NBN FttC Drops | Central West | Rob Panovski | Inv 14727 | 2019-02-15 | 2018-12-20 | 2018-12-20 | 2019-01-18 | 2019-01-23 | 2019-01-11 | 2019-02-15 |  | Dec-18 | Feb-19 | MW417R001126-2GUN-01-STELLAR NPDL-Gunnedah | Gunnedah | 13678 | 34432.98 | 48110.98 | 52922.078 | 28348.75 |  | 28348.75 | 19762.23 | 41.08% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Central West | Rob Panovski | Inv 14038 | 2018-08-21 | 2018-08-20 | 2018-08-20 |  |  |  | 2018-08-22 |  | Aug-18 | Aug-18 | MW417R001126-2GUN-01-STELLAR NPDL-Gunnedah | Gunnedah | 5862 |  | 5862 | 6448.2 |  |  | 0 | 5862 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney CBD | Rob Panovski | Inv 14266 | 2018-10-16 | 2018-09-18 | 2018-09-18 |  |  | 2018-09-29 | 2018-10-13 |  | Sep-18 | Oct-18 | MW417R001128 - 2HMK-04 - STELLAR NPDL_Haymarket | Haymarket | 11687.62 |  | 11687.62 | 12856.382 | 5745 |  | 5745 | 5942.62 | 50.85% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney CBD | Rob Panovski | Inv 14037 | 2018-08-21 | 2018-08-20 | 2018-08-20 |  |  |  | 2018-08-22 |  | Aug-18 | Aug-18 | MW417R001128 - 2HMK-04 - STELLAR NPDL_Haymarket | Haymarket | 5008.98 |  | 5008.98 | 5509.878 |  |  | 0 | 5008.98 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Newcastle | Rob Panovski | Inv 14645 | 2018-01-21 | 2018-11-23 | 2018-11-23 | 2018-11-29 | 2018-12-07 | 2018-12-07 | 2019-01-22 |  | Nov-18 | Jan-19 | MW417R001129 - 2KRI-01 - STELLAR NPDL-Kurri Kurri | Kurri Kurri | 16142.28 | 23026.65 | 39168.93 | 43085.823 | 25891.5 |  | 25891.5 | 13277.43 | 33.9% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Newcastle | Rob Panovski | Inv 14039 | 2018-08-21 | 2018-08-17 | 2018-08-17 |  |  |  | 2018-08-22 |  | Aug-18 | Aug-18 | MW417R001129 - 2KRI-01 - STELLAR NPDL-Kurri Kurri | Kurri Kurri | 6918.12 |  | 6918.12 | 7609.932 |  |  | 0 | 6918.12 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Nth Coast | Rob Panovski | Inv 14725 | 2019-02-15 | 2018-12-20 | 2018-12-20 | 2019-01-10 | 2019-01-15 | 2019-01-11 | 2019-02-15 |  | Dec-18 | Feb-19 | MW417R001130-2MAC-20-STELLAR NPDL-Macksville | Macksville | 37183.44 | 79437.365 | 116620.805 | 128282.8855 | 26620 |  | 26620 | 90000.805 | 77.17% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Nth Coast | Rob Panovski | Inv 14050 | 2018-08-22 | 2018-08-20 | 2018-08-20 |  |  |  | 2018-08-23 |  | Aug-18 | Aug-18 | MW417R001130-2MAC-20-STELLAR NPDL-Macksville | Macksville | 15935.76 |  | 15935.76 | 17529.336 |  |  | 0 | 15935.76 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sth NSW | Rob Panovski | inv 14524 | 2018-11-10 | 2018-10-31 | 2018-10-31 | 2018-11-14 | 2018-11-23 | 2018-11-14 | 2018-12-11 |  | Oct-18 | Dec-18 | MW417R001131-2MYA-01-STELLAR NPDL-Moruya | Moruya | 23061.22 | 27144.99 | 50206.21 | 55226.831 | 26655.5 |  | 26655.5 | 23550.71 | 46.91% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sth NSW | Rob Panovski | Inv 14040 | 2018-08-21 | 2018-08-20 | 2018-08-20 |  |  |  | 2018-08-22 |  | Aug-18 | Aug-18 | MW417R001131-2MYA-01-STELLAR NPDL-Moruya | Moruya | 9883.38 |  | 9883.38 | 10871.718 |  |  | 0 | 9883.38 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Central West | Rob Panovski | Inv 14723 | 2019-02-11 | 2018-12-20 | 2018-12-20 | 2019-01-10 | 2019-01-15 | 2019-01-11 | 2019-02-11 |  | Dec-18 | Feb-19 | MW417R001132-2WRD-20-STELLAR NPDL-Warialda | Warialda | 19270.02 | 87068.445 | 106338.465 | 116972.3115 | 70491.75 |  | 70491.75 | 35846.715 | 33.71% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Central West | Rob Panovski | Inv 14051 | 2018-08-22 | 2018-08-21 | 2018-08-21 |  |  |  | 2018-08-23 |  | Aug-18 | Aug-18 | MW417R001132-2WRD-20-STELLAR NPDL-Warialda | Warialda | 8258.58 |  | 8258.58 | 9084.438 |  |  | 0 | 8258.58 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | ACT | Rob Panovski |  |  | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-31 | 2019-02-06 |  |  | Jan-19 | Jan-00 | MW417R001133-9BLC-04-STELLAR NPDL-Belconnen | Belconnen | 7083.2 | -4050 | 3033.2 | 3336.52 | 1512.25 |  | 1512.25 | 1520.95 | 50.14% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | ACT | Rob Panovski | Inv 1468 | 2019-02-27 | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-01-31 | 2019-02-06 | 2019-03-05 |  | Jan-19 | Mar-19 | MW417R001134-9DKI-23-STELLAR NPDL-Deakin | Deakin | 2760.2 | 1360 | 4120.2 | 4532.22 | 1882.25 |  | 1882.25 | 2237.95 | 54.32% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Central West | Rob Panovski | Inv 14273 | 2018-10-16 | 2018-09-12 | 2018-09-12 | 2018-10-04 | 2018-10-09 | 2018-09-26 | 2018-10-18 |  | Sep-18 | Oct-18 | MW417R001247-2WLH-20-STELLAR NPDL_MWR (A417)-Walcha | Walcha | 7043.4 | 20906.775 | 27950.175 | 30745.1925 | 11702.5 |  | 11702.5 | 16247.675 | 58.13% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Central West | Rob Panovski | Inv 14086 | 2018-08-29 | 2018-08-27 | 2018-08-27 |  |  |  | 2018-08-28 |  | Aug-18 | Aug-18 | MW417R001247-2WLH-20-STELLAR NPDL_MWR (A417)-Walcha | Walcha | 3018.6 |  | 3018.6 | 3320.46 |  |  | 0 | 3018.6 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney | Rob Panovski | Inv 14165 | 2018-09-21 | 2018-08-27 | 2018-08-27 | 2018-08-27 | 2018-08-30 | 2018-09-10 | 2018-09-24 |  | Aug-18 | Sep-18 | MW417R001248-2MIR-21-STELLAR NPDL_MWR (A417)-Miranda | Miranda | 1121.45 | 15716.44 | 16837.89 | 18521.679 | 7252 |  | 7252 | 9585.89 | 56.93% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Central West | Rob Panovski | Inv 14324 | 2018-10-26 | 2018-09-20 | 2018-09-20 | 2018-10-05 | 2018-10-11 | 2018-10-04 | 2018-10-25 |  | Sep-18 | Oct-18 | MW417R001252-2KYO-20-STELLAR NPDL_MWR (A417)- Kyogle | Kyogle | 1812.4 | 8968.03 | 10780.43 | 11858.473 |  |  | 0 | 10780.43 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | ACT | Rob Panovski | Inv 14272 | 2018-10-16 | 2018-09-18 | 2018-09-18 |  |  | 2018-10-02 | 2018-10-18 |  | Sep-18 | Oct-18 | MW417R001255-9DKI-04-STELLAR NPDL_MWR (A417)-Deakin | Deakin | 31875.76 |  | 31875.76 | 35063.336 | 21354 |  | 21354 | 10521.76 | 33.01% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | ACT | Rob Panovski | Inv 14101 | 2018-08-30 | 2018-08-28 | 2018-08-28 |  |  |  | 2018-08-30 |  | Aug-18 | Aug-18 | MW417R001255-9DKI-04-STELLAR NPDL_MWR (A417)-Deakin | Deakin | 13661.04 |  | 13661.04 | 15027.144 |  |  | 0 | 13661.04 | 100% |  |  |  | Kirsty Doyle | Direct Award
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14246 | 2018-10-11 | 2018-09-12 | 2018-09-12 | 2018-09-18 | 2018-09-27 | 2018-09-26 | 2018-10-11 |  | Sep-18 | Oct-18 | MW417R001164-AYCA-1WRX9J -2ROU-03- 20 Foxall Road, Kellyville | Kellyville | 708.6 | 1766.46 | 2475.06 | 2722.566 |  | 312.4395 | 312.4395 | 2162.6205 | 87.38% |  |  |  | Ertan Cicek | Direct Award | 2018-08-23 |  | 2018-11-14 | 83
A401/Greenfield | Sydney | Mickey Tran | Inv 14275 | 2018-10-15 | 2018-09-21 | 2018-09-21 | 2018-09-24 | 2018-09-27 | 2018-10-05 | 2018-10-19 |  | Sep-18 | Oct-18 | MW417R001195--AYCA-5D4EG4-2CAS-238 Totness Court, Castle Hill | Castle Hill | 6198.97 | 1439.14 | 7638.11 | 8401.921 | 3490.36 |  | 3490.36 | 4147.75 | 54.3% |  |  |  | Mark Leal | 2018-08-20 | 2018-08-24 | 4 | 2018-11-02 | 70
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14467 | 2018-11-29 | 2018-10-02 | 2018-10-02 | 2018-10-16 | 2018-11-14 | 2018-10-16 | 2018-11-28 |  | Oct-18 | Nov-18 | MW417R000970 - AYCA-4Q27NU - 2BRG-03 - 50 Raby Rd, Gledswood Hills | Gledswood Hills | 1881.87 | 4671.38 | 6553.25 | 7208.575 | 4043.06 |  | 4043.06 | 2510.19 | 38.3% |  |  |  | Ertan Cicek | Direct Award | 2018-08-06 |  | 2018-10-31 | 86
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R001253-AYCA-5BRJ2L-2CBT-01-93-97 Broughton St, Campbelltown | Campbelltown | 589.81 |  | 589.81 | 648.791 | 3111.48 |  | 3111.48 | -2521.67 | -427.5% |  |  |  | Ertan Cicek | Direct Award | 2018-08-27 |  | 2018-11-22 | 87
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14542 | 2018-12-14 | 2018-11-16 | 2018-11-16 |  |  | 2018-11-30 | 2018-12-13 |  | Nov-18 | Dec-18 | MW417R000875-AYCA-4P6YWU-2SHH-05-11 Kite Pl Blackbutt Internals | Blackbutt | 1990.1 |  | 1990.1 | 2189.11 |  |  | 0 | 1990.1 | 100% |  |  |  | Nabeel Jaimon | Direct Award | 2018-08-06 |  | 2018-11-02 | 88
A417 Greenfield MDU | Newcastle | Mickey Tran | Inv 14159 | 2018-09-17 | 2018-08-28 | 2018-08-28 |  |  | 2018-09-12 | 2018-09-18 |  | Aug-18 | Sep-18 | MW417R000747-AYCA-4SM3QD-2MAI-09-63 Melrose St, Lorn | Lorn | 6367.25 |  | 6367.25 | 7003.975 |  | 715.424 | 715.424 | 5651.826 | 88.76% |  |  |  | Mark Leal | 2018-07-27 | 2018-08-01 | 5 | 2018-10-12 | 72
NBN FttC Drops | Newcastle | Rob Panovski | Inv 14580 | 2018-12-21 | 2018-11-23 | 2018-11-23 | 2018-11-29 | 2018-12-07 | 2018-12-07 | 2018-12-31 |  | Nov-18 | Dec-18 | MW417R001257-2KRI-20-STELLAR NPDL_MWR (A417)-Kurri kurri | Kurri Kurri | 19175.24 | 30129.185 | 49304.425 | 54234.8675 | 25797.5 |  | 25797.5 | 23506.925 | 47.68% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Newcastle | Rob Panovski | Inv 14099 | 2018-08-30 | 2018-08-28 | 2018-08-28 |  |  |  | 2018-08-30 |  | Aug-18 | Aug-18 | MW417R001257-2KRI-20-STELLAR NPDL_MWR (A417)-Kurri kurri | Kurri Kurri | 8217.96 |  | 8217.96 | 9039.756 |  |  | 0 | 8217.96 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney West | Rob Panovski | Inv 14736 | 2018-02-18 | 2019-01-21 | 2019-01-21 | 2019-01-21 | 2019-01-23 | 2019-02-04 | 2019-02-21 |  | Jan-19 | Feb-19 | MW417R001258-2ORC-22-STELLAR NPDL_MWR (A417)-Orchard Hills | Orchard Hills | 5985.315 | 3064.67 | 9049.985 | 9954.9835 | 3530 |  | 3530 | 5519.985 | 60.99% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Sydney West | Rob Panovski | Inv 14103 | 2018-08-30 | 2018-08-28 | 2018-08-28 |  |  |  | 2018-08-30 |  | Aug-18 | Aug-18 | MW417R001258-2ORC-22-STELLAR NPDL_MWR (A417)-Orchard Hills | Orchard Hills | 2565.135 |  | 2565.135 | 2821.6485 |  |  | 0 | 2565.135 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Nth Coast | Rob Panovski | Inv 14721 | 2019-02-07 | 2018-12-20 | 2018-12-20 | 2019-01-08 | 2019-01-15 | 2019-01-11 | 2019-02-07 |  | Dec-18 | Feb-19 | MW417R001260-2SWR-20-STELLAR NPDL_MWR (A417)-South West Rocks | South West Rocks | 17090.056 | 47973.16 | 65063.216 | 71569.5376 | 35510.25 |  | 35510.25 | 29552.966 | 45.42% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Nth Coast | Rob Panovski | Inv 14100 | 2018-08-30 | 2018-08-28 | 2018-08-28 |  |  |  | 2018-08-30 |  | Aug-18 | Aug-18 | MW417R001260-2SWR-20-STELLAR NPDL_MWR (A417)-South West Rocks | South West Rocks | 7324.344 |  | 7324.344 | 8056.7784 |  |  | 0 | 7324.344 | 100% |  |  |  | Kirsty Doyle | Direct Award
VPL New Devs | Hunter |  | Inv 13847 | 2018-07-10 | 2018-06-07 | 2018-06-07 |  |  | 2018-06-21 | 2018-08-03 |  | Jun-18 | Aug-18 | 2BRX-01-AYCA-41AL6Q | Branxton | 139911.2432 |  | 139911.2432 | 153902.3675 | 104665.7 |  | 104665.7 | 35245.5432 | 25.19% |  | 2018-06-21 |  | Adnan Khabbaz | Direct Award | 2018-04-20 |  | 2018-06-06 | 47
NBN FttC Drops | Nth Coast | Rob Panovski | Inv 14691 | 2019-02-05 | 2018-12-20 | 2018-12-20 | 2019-01-08 | 2019-01-14 | 2018-01-07 | 2019-02-05 |  | Dec-18 | Feb-19 | MW417R001261-2TTF-20-STELLAR NPDL_MWR (A417)-Tenterfield | Tenterfield | 31022.74 | 138446.125 | 169468.865 | 186415.7515 | 121750.75 |  | 121750.75 | 47718.115 | 28.16% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Nth Coast | Rob Panovski | Inv 10498 | 2018-08-30 | 2018-08-28 | 2018-08-28 |  |  |  | 2018-08-30 |  | Aug-18 | Aug-18 | MW417R001261-2TTF-20-STELLAR NPDL_MWR (A417)-Tenterfield | Tenterfield | 13295.46 |  | 13295.46 | 14625.006 |  |  | 0 | 13295.46 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Nth Coast | Rob Panovski | Inv 14102 | 2018-08-30 | 2018-08-28 | 2018-08-28 |  |  |  | 2018-08-30 |  | Aug-18 | Aug-18 | MW417R001262-2WAL-20-STELLAR NPDL_MWR (A417)-Wallerawang | Wallerawang | 3790.38 |  | 3790.38 | 4169.418 |  |  | 0 | 3790.38 | 100% |  |  |  | Kirsty Doyle | Direct Award
NBN FttC Drops | Nth Coast | Rob Panovski | Inv 14503 | 2018-12-05 | 2018-11-14 | 2018-11-14 | 2018-11-19 | 2018-11-23 | 2018-11-27 | 2018-12-04 |  | Nov-18 | Dec-18 | MW417R001262-2WAL-20-STELLAR NPDL_MWR (A417)-Wallerawang | Wallerawang | 8844.22 | 33294.28 | 42138.5 | 46352.35 | 23171.5 |  | 23171.5 | 18967 | 45.01% |  |  |  | Kirsty Doyle | Direct Award
A401/Greenfield | Sydney Sth | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R001188-AYCA-48QOI8-2NRN-05-Lodges Road, Elderslie | Elderslie | 3135.13 |  | 3135.13 | 3448.643 |  |  | 0 | 3135.13 | 100% |  |  |  | Mark Leal | 2018-08-20 | 2018-08-28 | 8 | 2018-11-09 | 73
A401/Greenfield | Sydney | Mickey Tran | Inv 14261 | 2018-10-15 | 2018-09-21 | 2018-09-21 |  |  | 2018-10-05 | 2018-10-16 |  | Sep-18 | Oct-18 | MW417R001196-AYCA-5CYZU8-2ROU-02-12 Highgate Circuit, Kellyville | Kellyville | 5572.19 |  | 5572.19 | 6129.409 |  | 1389.0101 | 1389.0101 | 4183.1799 | 75.07% |  |  |  | Mark Leal | 2018-08-24 | 2018-08-28 | 4 | 2018-11-29 | 93
A401/Greenfield | Sth NSW | Marshell Antonio | Inv 14683 | 2019-01-24 | 2018-12-20 | 2018-12-20 | 2018-12-20 | 2019-01-09 | 2019-01-11 | 2019-01-29 |  | Dec-18 | Jan-19 | MW417R001274 - AYCA-5FK9G7 - 2TEM-20 - 113-115 Baker Street Temora NSB | Temora | 960 | 6687.41 | 7647.41 | 8412.151 |  |  | 0 | 7647.41 | 100% |  |  |  | Mark Leal | 2018-08-27 | 2018-08-31 | 4 | 2018-09-28 | 28
A401/Greenfield | Sydney | Dane Harrington | Inv 14519 | 2018-12-05 | 2018-11-07 | 2018-11-09 | 2018-11-19 | 2018-11-28 | 2018-11-23 | 2018-12-06 |  | Nov-18 | Dec-18 | MW417R001266-AYCA-56GQ2L-2RCH-02-62 Argyle Street South Windsor NSB | Windsor | 960 | 3479.04 | 4439.04 | 4882.944 |  |  | 0 | 4439.04 | 100% |  |  |  | Mark Leal | 2018-08-24 | 2018-08-31 |  | 2018-11-16 | 77
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R001267-AYCA-55JR8W-2NEW-21-228 King Street, Newtown | Newtown | 1601.74 |  | 1601.74 | 1761.914 |  |  | 0 | 1601.74 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-08-28 |  | 2018-11-22 | 86
A417 Greenfield MDU | Sydney East | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R001264-AYCA-4ND19Q-2ROC-22- Chapel Street Rockdale | Rockdale | 656.58 |  | 656.58 | 722.238 |  |  | 0 | 656.58 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-08-29 |  | 2018-11-22 | 85
A401/Greenfield NSB | Nth Coast | Mickey Tran | Inv 14785 | 2019-03-06 | 2019-02-14 | 2019-02-14 | 2019-02-14 | 2019-02-25 | 2019-02-28 | 2019-03-07 |  | Feb-19 | Mar-19 | MW417R001310-AYCA-5N0IF2-2CFS-03-30 Park Ave Coffs Harbour NSB | Coffs Harbour | 960 | 8050.44 | 9010.44 | 9911.484 | 1836.35 |  | 1836.35 | 7174.09 | 79.62% |  |  |  | Mark Leal | 2018-08-30 | 2018-09-04 | 5 | 2018-11-02 | 59
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14441 | 2018-11-22 | 2018-09-21 | 2018-09-21 | 2018-09-25 | 2018-10-31 | 2018-10-05 | 2018-11-22 |  | Sep-18 | Nov-18 | MW417R001115-AYCA-591MZC-2CRO-21-CRONULLA 88 DEVELOPMENTS | Cronulla | 2268.3 | 17859.46 | 20127.76 | 22140.536 | 4513.41 | 10153.16 | 14666.57 | 5461.19 | 27.13% |  |  |  | Mark Leal | Direct Award | 2018-08-14 |  | 2018-11-10 | 88
A401/Greenfield | Central West | Marshell Antonio | Inv 14521 | 2018-12-05 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-20 | 2018-11-26 | 2018-12-06 |  | Nov-18 | Dec-18 | MW417R001216 - AYCA-56GE93 - 2NMN-20 -10 Dandaloo St, Narromine | Narromine | 10643.11 | 2969.86 | 13612.97 | 14974.267 | 3074.22 |  | 3074.22 | 10538.75 | 77.42% |  |  |  | Mark Leal | 2018-08-24 | 2018-08-30 | 6 | 2018-11-12 | 74
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R001256 - AYCA-Y8UNL - 2BUR-03 - Burwood Grand - 1 | Burwood | 5774.95 |  | 5774.95 | 6352.445 |  |  | 0 | 5774.95 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-08-30 |  | 2018-11-22 | 84
A401/Greenfield | Sydney | Mickey Tran |  |  | 2019-01-25 | 2019-01-25 | 2019-02-09 |  | 2019-02-08 | 1900-01-13 |  | Jan-19 | Jan-00 | MW417R001241-AYCA-5MNUDQ-2KNS-03-221 Queen Street Beaconsfield NSB | Beaconsfield | 960 | 4091.97 | 5051.97 | 5557.167 | 975.27 |  | 975.27 | 4076.7 | 80.7% |  |  |  | Mark Leal | 2018-08-24 | 2018-08-31 | 7 | 2018-10-30 | 60
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14468 | 2018-11-29 | 2018-10-11 | 2018-10-12 | 2018-10-16 | 2018-11-14 | 2018-10-26 | 2018-11-29 |  | Oct-18 | Nov-18 | MW417R001246-AYCA-5FA5OM-2MIR-24-4-6 Crammond Boulevard, Caringbah Ext | Caringbah | 972.94 | 6718.14 | 7691.08 | 8460.188 | 1298.91 |  | 1298.91 | 6392.17 | 83.11% |  |  |  | Ertan Cicek | Direct Award | 2018-08-27 |  | 2018-11-22 | 87
A417 Greenfield MDU | Sydney | Dane Harrington |  |  | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-03-18 | 2019-02-06 | 2019-03-30 |  | Jan-19 | Mar-19 | MW417R001352-AYCA-3JJIX9-2MIR-28-13-21 University Rd and 1-5 Pinnacle St, Miranda | Miranda | 1513.96 | 5411.69 | 6925.65 | 7618.215 |  |  | 0 | 6925.65 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-09-04 |  | 2018-10-31 | 57
A401/Greenfield NSB | Central West | Mickey Tran |  |  | 2019-02-26 | 2019-02-26 | 2019-03-05 |  | 2019-03-12 | 2019-03-26 |  | Feb-19 | Mar-19 | MW417R001369 - AYCA-5DL8UH - 2MRE-02 - Boland Drive Moree NSB | Moree | 960 | 24580.357 | 25540.357 | 28094.3927 | 15299.87 |  | 15299.87 | 10240.487 | 40.1% |  |  |  | Mark Leal | 2018-09-03 | 2018-09-05 | 2 | 2018-09-08 | 3
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R001351-AYCA-2LCFXK-2BUR-65-Skyview | Burwood | 4568.74 |  | 4568.74 | 5025.614 | 800 |  | 800 | 3768.74 | 82.49% |  |  |  | Ertan Cicek | Direct Award | 2018-09-06 |  | 2018-10-31 | 55
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  | 2019-02-22 | 2019-02-22 | 2019-02-22 |  | 2019-03-08 | 2019-03-22 |  | Feb-19 | Mar-19 | MW417R001366-AYCA-5FA5OM-2MIR-24-4-6 Crammond Boulevard Caringbah Int | Caringbah | 1713.6 | 813 | 2526.6 | 2779.26 |  |  | 0 | 2526.6 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-09-05 |  | 2018-09-29 | 24
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14475 | 2018-11-23 | 2018-10-04 | 2018-10-04 | 2018-10-08 | 2018-11-13 | 2018-10-18 | 2018-11-27 |  | Oct-18 | Nov-18 | MW417R001335-AYCA-4RH5YY-2ROU-01-32 George St Box Hill | Box Hill | 1333.44 | 2606.44 | 3939.88 | 4333.868 | 1787.25 |  | 1787.25 | 2152.63 | 54.64% |  |  |  | Ertan Cicek | Direct Award | 2018-08-30 |  | 2018-11-28 | 90
A417 Business Segment | Central West | Mickey Tran | Inv 14586 | 2019-01-04 | 2018-11-26 | 2018-11-26 | 2018-11-30 | 2018-12-10 | 2018-12-11 | 2019-01-08 |  | Nov-18 | Jan-19 | MW417R001610-AYCA-5NNV14-2NBR-20-30 Barwan Street, Narrabri | Narrabri | 16366.01 | 8634.78 | 25000.79 | 27500.869 | 6990.56 |  | 6990.56 | 18010.23 | 72.04% |  |  |  | Dave Yoemans | 2018-09-05
Business Segment | Sydney West | Mickey Tran |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R001919-AYCA-5OZYD0-2ERP-20-204-214 Chandos St Horsley Park | Horsley Park | 5810.57 |  | 5810.57 | 6391.627 |  |  | 0 | 5810.57 | 100% |  |  |  | David Yeomans | 2018-09-24 | 2018-10-24 | 30 | 2018-11-15 | 22
A417 Business Segment | Sydney | Mickey Tran | Inv 14741 | 2019-02-27 | 2019-01-10 | 2019-01-10 | 2019-01-10 | 2019-01-17 | 2019-02-04 | 2019-02-26 |  | Jan-19 | Feb-19 | MW417R001920-AYCA-5OZYGU-2ERP-20-194-204 Chandos Rd Horsley Park | Horsley Park | 8293.08 | 18946.46 | 27239.54 | 29963.494 | 1348.57 |  | 1348.57 | 25890.97 | 95.05% |  |  |  | David Yeomans | 2018-09-24 | 2018-10-24 | 30 | 2018-11-15 | 22
A417 Business Segment | Sydney | Mickey Tran | inv 14494 | 2018-12-05 | 2018-10-29 | 2018-11-05 | 2018-11-11 | 2018-11-19 | 2018-11-23 | 2018-12-04 |  | Nov-18 | Dec-18 | MW417R001948-2LIV-04-AYCA-5BV5Z8-SHOP M4, LEVEL 2, WESTFIELD LIVERPOOL | Liverpool | 19198.9 | 1293.94 | 20492.84 | 22542.124 | 7903.248 |  | 7903.248 | 12589.592 | 61.43% |  |  |  | Dave Yoemans | Direct Award
A417 Business Segment | Sydney | Mickey Tran | Inv 14575 | 2018-12-20 | 2018-11-07 | 2018-11-07 | 2018-11-09 | 2018-11-19 | 2018-12-04 | 2018-12-18 |  | Nov-18 | Dec-18 | MW417R001950-2LIV-04-AYCA-5BV5ZG-SHOP DDS1, LEVEL 2, WESTFIELD LIVERPOOL | Liverpool | 5960.27 | 5746.39 | 11706.66 | 12877.326 | 5106.138 |  | 5106.138 | 6600.522 | 56.38% |  |  |  | Dave Yoemans | Direct Award
A417 Business Segment | Sydney | Mickey Tran | Inv 14495 | 2018-12-05 | 2018-11-05 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-21 | 2018-12-04 |  | Nov-18 | Dec-18 | MW417R001951-2PTH-05-AYCA-5BXC7Q-SHOP 01A2, LEVEL 1, 585 HIGH STREET | Penrith | 2914.87 | 11413.77 | 14328.64 | 15761.504 | 5927.9 |  | 5927.9 | 8400.74 | 58.63% |  |  |  | Dave Yoemans | Direct Award
A417 Business Segment | Sydney | Mickey Tran | Inv 14469 | 2018-11-29 | 2018-11-05 | 2018-11-05 | 2018-11-14 | 2018-11-22 | 2018-11-21 | 2018-11-29 |  | Nov-18 | Nov-18 | MW417R001952-2PTH-05-AYCA-5BXC7I-SHOP A5, FLOOR 2, 585 HIGH STREET, PENRITH | Penrith | 13865.48 | 8228.31 | 22093.79 | 24303.169 | 12998.037 |  | 12998.037 | 9095.753 | 41.17% |  |  |  | Dave Yoemans | Direct Award
A417 Business Segment | Sydney | Mickey Tran | Inv 14496 | 2018-12-05 | 2018-11-05 | 2018-11-06 | 2018-11-12 | 2018-11-19 | 2018-11-21 | 2018-12-04 |  | Nov-18 | Dec-18 | MW417R001953-2ROC-02-AYCA-5BXC86-DAN MURPHYS, 78-98 ARNCLIFFE STREET | Wolli Creek | 1499.14 | 3398.74 | 4897.88 | 5387.668 | 2437.05 |  | 2437.05 | 2460.83 | 50.24% |  |  |  | Dave Yoemans | Direct Award
A417 Business Segment | Sydney | Mickey Tran | Inv 14497 | 2018-12-05 | 2018-11-05 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-21 | 2018-12-04 |  | Nov-18 | Dec-18 | MW417R001954-2ROC-02-AYCA-5BXC8E-WOOLWORTHS, SHOP 1, 78-98 ARNCLIFFE STREET | Wolli Creek | 4744.32 | 2556.18 | 7300.5 | 8030.55 | 3577.12 |  | 3577.12 | 3723.38 | 51% |  |  |  | Dave Yoemans | Direct Award
A417 Business Segment | Sydney | Mickey Tran | Inv 14498 | 2018-12-05 | 2018-10-31 | 2018-11-05 | 2018-11-15 | 2018-11-22 | 2018-11-21 | 2018-12-04 |  | Nov-18 | Dec-18 | MW417R001955-2NRN-02-AYCA-5GNS0T-SHOP 1, 11-13 MAIN STREET, MOUNT ANNAN | Mt Annan | 13113.23 | 3137.48 | 16250.71 | 17875.781 | 10825.0826 |  | 10825.0826 | 5425.6274 | 33.39% |  |  |  | Dave Yoemans | Direct Award
A401/Greenfield | Sth NSW | Marshell Antonio | Inv 14386 | 2018-11-14 | 2018-10-16 | 2018-10-16 | 2018-10-16 | 2018-10-24 | 2018-10-30 | 2018-11-13 |  | Oct-18 | Nov-18 | MW417R001276-AYCA-50T2L6-2TUM-20-76 Capper St, Tumut | Tumut | 9572.93 | -2348.963 | 7223.967 | 7946.3637 |  |  | 0 | 7223.967 | 100% |  |  |  | Mark Leal | 2018-08-26 | 2018-08-31 | 5 | 2018-11-16 | 77
A417 Business Segment | Sydney | Mickey Tran | Inv 14499 | 2018-12-05 | 2018-10-29 | 2018-11-05 | 2018-11-09 | 2018-11-19 | 2018-11-21 | 2018-12-05 |  | Nov-18 | Dec-18 | MW417R001956-2CBT-02-AYCA-5GNRZH-WOOLWORTHS, SHOP MO1, MARKETFAIR | Campbelltown | 5791.37 | 2892.16 | 8683.53 | 9551.883 | 6773.2364 |  | 6773.2364 | 1910.2936 | 22% |  |  |  | Dave Yoemans | Direct Award
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14336 | 2018-10-29 | 2018-10-10 | 2018-10-10 |  |  | 2018-10-24 | 2018-10-29 |  | Oct-18 | Oct-18 | MW417R001487-AYCA-55ZVL2-2ROU-03-45 Foxall Rd Kellyville | Kellyville | 668.28 |  | 668.28 | 735.108 |  | 267.9325 | 267.9325 | 400.3475 | 59.91% |  |  |  | Ertan Cicek | Direct Award | 2018-09-14 |  | 2018-12-11 | 88
A401/Greenfield | Central West | Marshell Antonio | Inv 14335 | 2018-11-07 | 2018-09-17 | 2018-09-17 | 2018-09-18 | 2018-10-26 | 2018-09-27 | 2018-11-06 |  | Sep-18 | Nov-18 | MW417R001420-AYCA-5FHVE5-2ORG-06-71 Bletchington Street Orange Int | Orange | 1990.1 | 910.59 | 2900.69 | 3190.759 |  |  | 0 | 2900.69 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-09-07 |  | 2018-10-02 | 25
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-03-18 | 2019-02-06 | 2019-03-30 |  | Jan-19 | Mar-19 | MW417R001530 - AYCA-5CXXCR - 2BTM-21 - 30 Golf Links Dr, Batemans Bay | Batemans Bay | 2919.49 | 5874.364 | 8793.854 | 9673.2394 | 1770.88 |  | 1770.88 | 7022.974 | 79.86% |  |  |  | Ertan Cicek | Direct Award | 2018-09-18 |  | 2018-11-20 | 63
A417 Greenfield MDU | Sydney | Mickey Tran | Inv 14262 | 2018-10-15 | 2018-09-20 | 2018-09-20 |  |  | 2018-10-04 | 2018-10-18 |  | Sep-18 | Oct-18 | MW417R001497-AYCA-4BC964-2BLK-11-Fairwater Boulevard Blacktown | Blacktown | 5336.12 |  | 5336.12 | 5869.732 | 1105.82 |  | 1105.82 | 4230.3 | 79.28% |  |  |  | Ertan Cicek | Direct Award | 2018-09-17 |  | 2018-12-12 | 86
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  | 2019-02-20 | 2019-02-20 | 2019-02-15 |  | 2019-03-06 | 2019-03-20 |  | Feb-19 | Mar-19 | MW417R001524-AYCA-45U68U-2PTH-12-5 CULLEN AV, JORDAN SPRINGS | Jordan Springs | 10684.8 | -4767.64 | 5917.16 | 6508.876 |  |  | 0 | 5917.16 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-09-18 |  | 2018-11-30 | 73
A401/Greenfield | Sth NSW | Marshell Antonio | Inv 14637 | 2019-01-18 | 2018-12-10 | 2018-12-10 | 2018-12-10 | 2018-12-18 | 2018-12-24 | 2019-01-22 |  | Dec-18 | Jan-19 | MW417R001290 - AYCA-50OJVS - 2DNQ-22 - 419 Kelly St, Deniliquin | Deniliquin | 24419.13 | 15576.51 | 39995.64 | 43995.204 |  | 28099.7819 | 28099.7819 | 11895.8581 | 29.74% |  |  |  | Mark Leal | 2018-08-29 | 2018-09-17 | 19 | 2018-11-21 | 65
A417 Greenfield MDU | Sydney | Dane Harrington |  |  | 2019-01-23 | 2019-01-23 | 2019-01-23 | 2019-03-18 | 2019-02-06 | 2019-03-30 |  | Jan-19 | Mar-19 | MW417R001526-AYCA-2RG791-2PEN-61-5-19 Toongabbie Rd , Toongabbie | Toongabbie | 1207.53 | 7192.05 | 8399.58 | 9239.538 |  |  | 0 | 8399.58 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-09-18 |  | 2018-11-30 | 73
A417 HFC DFN | Sydney | Mickey Tran |  |  | 2019-01-31 | 2019-01-31 | 2019-02-01 | 2019-02-11 | 2019-02-14 |  |  | Jan-19 | Jan-00 | MW417R001505-AYCA-4ZNBL1-2EPP-60-The Gateway on Pembroke Epping DFN | Epping | 32019.38 | 127924.42 | 159943.8 | 175938.18 | 110714.9 |  | 110714.9 | 49228.9 | 30.78% |  |  |  | Mark Leal | Direct Award | 2018-09-19 |  | 2018-11-30 | 72
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14195 | 2018-09-28 | 2018-09-24 | 2018-09-24 |  |  |  | 2018-09-25 |  | Sep-18 | Sep-18 | MW417R001505-AYCA-4ZNBL1-2EPP-60-The Gateway on Pembroke Epping DFN | Epping | 13722.59 |  | 13722.59 | 15094.849 |  |  | 0 | 13722.59 | 100% |  |  |  | Mark Leal | Direct Award | 2018-09-19 |  | 2018-11-30 | 72
A417 Greenfield MDU | ACT | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R001664-AYCA-587UWZ-9CVI-22-7 Lowrie Street Dickson ACT | Dickson | 2220.41 |  | 2220.41 | 2442.451 |  |  | 0 | 2220.41 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-09-28 |  | 2018-10-31 | 33
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14585 | 2019-01-07 | 2018-12-03 | 2018-12-03 |  |  | 2018-12-17 | 2019-01-08 |  | Dec-18 | Jan-19 | MW417R001652 - AYCA-5ML96W -2LIV-61 - 24 Blackwood Avenue Casula | Casula | 1428 |  | 1428 | 1570.8 |  |  | 0 | 1428 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-09-28 |  | 2018-10-23 | 25
A417 Greenfield MDU | ACT | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R001665-AYCA-53R6D6-9BLC-04-Nest 3 | Gungarlin | 7628.33 |  | 7628.33 | 8391.163 | 150 |  | 150 | 7478.33 | 98.03% |  |  |  | Ertan Cicek | Direct Award | 2018-10-02 |  | 2018-10-30 | 28
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14516 | 2018-12-05 | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-11-27 | 2018-11-06 | 2018-12-06 |  | Oct-18 | Dec-18 | MW417R001659-AYCA-54E9AY-2MER-21-RESIDENTIAL ESTATE - 4 (Block A & B), Picton | Picton | 9350.37 | 2343.823 | 11694.193 | 12863.6123 |  |  | 0 | 11694.193 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-02 |  | 2018-10-30 | 28
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R001667 - AYCA-55XM3V - 2HBD-20 -10-12 Roger St, Brookvale | Brookvale | 2347.15 |  | 2347.15 | 2581.865 | 3167.34 |  | 3167.34 | -820.19 | -34.94% |  |  |  | Ertan Cicek | Direct Award | 2018-10-02 |  | 2018-10-31 | 29
A401/Greenfield NSB | Hunter | Mickey Tran |  |  | 2019-03-04 | 2019-03-04 | 2019-03-04 |  | 2019-03-18 | 2019-04-01 |  | Mar-19 | Apr-19 | MW417R001630 - AYCA-5PBMZD - 2URL-20 - 14 SALISBURY ST URALLA NSB | Uralla | 960 | 13772.91 | 14732.91 | 16206.201 | 5458.9 |  | 5458.9 | 9274.01 | 62.95% |  |  |  | Mark Leal | 2018-09-27 | 2018-10-02 | 5 | 2018-10-31 | 29
A417 Greenfield MDU | ACT | Marshell Antonio | Inv 14517 | 2018-12-05 | 2018-10-22 | 2018-10-22 | 2018-10-24 | 2018-11-27 | 2018-11-05 | 2018-12-06 |  | Oct-18 | Dec-18 | MW417R001661-AYCA-5JRURV-9BLC-20-37 Belconnen Way, Weetangera, ACT Ext | Weetangera | 5878.2 | 3447.03 | 9325.23 | 10257.753 | 300 |  | 300 | 9025.23 | 96.78% |  |  |  | Ertan Cicek | Direct Award | 2018-10-03 |  | 2018-10-31 | 28
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14769 | 2019-03-06 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 2019-02-11 | 2019-02-14 | 2019-03-05 |  | Jan-19 | Mar-19 | MW417R001687-AYCA-4DQ6PX-2NRN-06-Estate-Cobbitty Rd Cobbitty | Cobbitty | 1391.35 | 376.46 | 1767.81 | 1944.591 |  |  | 0 | 1767.81 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-04 |  | 2018-11-01 | 28
A417 Greenfield MDU | Nth Coast | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R001688-2AYCA-4MFJ6I-CFS-03-65 Victoria Street Coffs Harbour | Coffs Harbour | 593.24 |  | 593.24 | 652.564 |  |  | 0 | 593.24 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-09 |  | 2019-01-28 | 111
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14635 | 2019-01-18 | 2018-11-20 | 2018-11-20 | 2018-11-21 | 2018-12-21 | 2018-12-04 | 2019-01-22 |  | Nov-18 | Jan-19 | MW417R001770 - AYCA-5N4YCV - 2BTH-02 - 5 Watt Drive, Robin Hill Ext | Bathurst | 1946.85 | 3741.196 | 5688.046 | 6256.8506 | 1912.6 |  | 1912.6 | 3775.446 | 66.38% |  |  |  | Ertan Cicek | Direct Award | 2018-10-11 |  | 2019-01-10 | 91
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R001721-AYCA-5M7EQR-2NWR-01-40 Basil Street South Nowra | Sth Nowra | 2977.15 |  | 2977.15 | 3274.865 |  |  | 0 | 2977.15 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-09 |  | 2018-11-19 | 41
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R001729 - AYCA-5KIP6Y - 2WLG-07 - 45 Rosemont Street West Wollongong | Wollongong | 1592.08 |  | 1592.08 | 1751.288 |  |  | 0 | 1592.08 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-09 |  | 2018-12-28 | 80
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14761 | 2019-03-05 | 2019-01-31 | 2019-01-31 | 2019-01-31 | 2019-02-11 | 2019-02-14 | 2019-02-28 |  | Jan-19 | Feb-19 | MW417R001750-AYCA-4DQ9I8-2NRN-06-Cobbitty Rd Cobbitty | Cobbitty | 669.27 | 225.95 | 895.22 | 984.742 |  |  | 0 | 895.22 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-09 |  | 2019-01-17 | 100
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  | 2019-02-27 | 2019-02-27 | 2019-02-27 | 2019-03-12 | 2019-03-13 | 2019-03-27 |  | Feb-19 | Mar-19 | MW417R001563-AYCA-5FHXRP-2HUH-22-75 Park Road, Hunters Hill | Hunters Hill | 3629.09 | 15596.83 | 19225.92 | 21148.512 | 2011.3 |  | 2011.3 | 17214.62 | 89.54% |  |  |  | Ertan Cicek | Direct Award | 2018-10-09 |  | 2018-12-11 | 63
A417 HFC DFN | Sydney West | Mickey Tran |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R001755-AYCA-5FEXSP-2PEN-61-103-105 Metella Road, Toongabbie DFN | Toongabbie | 43870.722 |  | 43870.722 | 48257.7942 | 95465.67 |  | 95465.67 | -51594.948 | -117.6% |  |  |  | Mark Leal | Direct Award | 2018-10-10 |  | 2018-12-28 | 79
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14263 | 2018-10-15 | 2018-10-11 | 2018-10-11 |  |  |  | 2018-10-15 |  | Oct-18 | Oct-18 | MW417R001755-AYCA-5FEXSP-2PEN-61-103-105 Metella Road, Toongabbie DFN | Toongabbie | 18801.738 |  | 18801.738 | 20681.9118 |  |  | 0 | 18801.738 | 100% |  |  |  | Mark Leal | Direct Award | 2018-10-10 |  | 2018-12-28 | 79
A417 Greenfield MDU | Sth Coast | Marshell Antonio | Inv 14584 | 2019-01-07 | 2018-11-30 | 2018-11-30 | 2018-12-30 | 2018-12-10 | 2018-12-14 | 2019-01-08 |  | Nov-18 | Jan-19 | MW417R001786 - AYCA-5B4OYT - 2ULL-04 - The Lakes - 9A | Burrill Lake | 2926.47 | 2282.6 | 5209.07 | 5729.977 | 2538 |  | 2538 | 2671.07 | 51.28% |  |  |  | Ertan Cicek | Direct Award | 2018-10-11 |  | 2019-01-08 | 89
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14583 | 2019-01-07 | 2018-11-28 | 2018-11-29 |  |  | 2018-12-13 | 2019-01-08 |  | Nov-18 | Jan-19 | MW417R001787 - AYCA-57Y4AJ - 2MIL-02 - 2140 Camden Valley Way - 1 | Camden | 772.06 |  | 772.06 | 849.266 |  |  | 0 | 772.06 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-11 |  | 2019-01-08 | 89
A417 Greenfield MDU | Sth Coast | Marshell Antonio | Inv 14634 | 2019-01-18 | 2018-11-28 | 2018-11-28 | 2018-11-29 | 2018-12-21 | 2018-12-12 | 2019-01-22 |  | Nov-18 | Jan-19 | MW417R002015-AYCA-568KCW-2GER-01-Mayflower Gerringong | Gerringong | 2351.63 | 4251.26 | 6602.89 | 7263.179 | 2911.43 | 657.2995 | 3568.7295 | 3034.1605 | 45.95% |  |  |  | Ertan Cicek | Direct Award | 2018-10-29 |  | 2019-01-15 | 78
A401/Greenfield | Sth NSW | Marshell Antonio | inv 14502 | 2018-12-05 | 2018-11-08 | 2018-11-08 | 2018-11-14 | 2018-11-23 | 2018-11-22 | 2018-12-04 |  | Nov-18 | Dec-18 | MW417R001768-AYCA-5GWBTB-2TAH-01-4 Davies Place, Picton | Picton | 6488.73 | 785.91 | 7274.64 | 8002.104 | 3333.25 |  | 3333.25 | 3941.39 | 54.18% |  |  |  | Mark Leal | 2018-10-10 | 2018-10-11 | 1 | 2019-01-01 | 82
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14633 | 2019-01-18 | 2018-11-21 | 2018-11-22 | 2018-12-07 | 2018-12-21 | 2018-12-06 | 2019-01-22 |  | Nov-18 | Jan-19 | MW417R001785-AYCA-5ML96W-2LIV-61- Blackwood Avenue Casula | Casula | 1357.13 | 5471.92 | 6829.05 | 7511.955 | 1761.8 |  | 1761.8 | 5067.25 | 74.2% |  |  |  | Ertan Cicek | Direct Award | 2018-10-12 |  | 2019-01-11 | 91
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14720 | 2019-02-15 | 2018-12-05 | 2018-12-05 | 2018-12-17 | 2019-01-30 | 2018-12-19 | 2019-02-13 |  | Dec-18 | Feb-19 | MW417R001805-AYCA-5DVB9M-2ROC-02-4 Magdalene Terrace, Wolli Creek | Wolli Creek | 2319.78 | 13164.05 | 15483.83 | 17032.213 | 3184.85 |  | 3184.85 | 12298.98 | 79.43% |  |  |  | Ertan Cicek | Direct Award | 2018-10-12 |  | 2018-11-01 | 20
NBN Assurance Wagga | Sth NSW | Andrew McPherson | Inv 14251 | 2018-10-16 | 2018-10-16 | 2018-10-16 |  |  |  | 2019-01-22 |  | Oct-18 | Jan-19 | MW417R002566 - 2WAG-02 -INC000008944090 - Lot 57, 18 Incarnie Cr, Wagga Wagga | Wagga Wagga | 256.28 |  | 256.28 | 281.908 |  | 97.66 | 97.66 | 158.62 | 61.89% |  |  |  | Tony Gabriel
NBN Assurance Wagga | Sth NSW | Andrew McPherson | Inv 14250 | 2018-10-16 | 2018-10-16 | 2018-10-16 |  |  |  | 2019-01-22 |  | Oct-18 | Jan-19 | MW417R002567-2WAG-06 INC000008340723 - UNIT 3, 12 WEWAK ST, ASHMONT | Ashmont | 384.42 |  | 384.42 | 422.862 |  | 146.49 | 146.49 | 237.93 | 61.89% |  |  |  | Tony Gabriel
A417 Greenfield MDU | ACT | Marshell Antonio | Inv 14643 | 2019-01-18 | 2018-12-08 | 2018-12-08 | 2018-12-08 | 2018-12-21 | 2018-12-22 | 2019-01-22 |  | Dec-18 | Jan-19 | MW417R001864-AYCA-5MT9Y3-9BON-03-Bon Scott Crescent, Moncrieff , ACT Ext | Moncrieff | 9092.68 | 2989.5674 | 12082.2474 | 13290.4721 |  |  | 0 | 12082.2474 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-16 |  | 2018-12-03 | 48
A417 HFC DFN | Sydney Nth | Mickey Tran |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R001793-AYCA-4WB37J-2FRE-61-36 Pringle Ave, Belrose HFC DFN | Frenchs Forest | 35728.259 |  | 35728.259 | 39301.0849 | 41108.89 |  | 41108.89 | -5380.631 | -15.06% |  |  |  | Mark Leal | Direct Award | 2018-10-16 |  | 2018-12-20 | 65
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14323 | 2018-10-26 | 2018-10-17 | 2018-10-17 |  |  |  | 2018-10-23 |  | Oct-18 | Oct-18 | MW417R001793-AYCA-4WB37J-2FRE-61-36 Pringle Ave, Belrose HFC DFN | Frenchs Forest | 15312.111 |  | 15312.111 | 16843.3221 |  |  | 0 | 15312.111 | 100% |  |  |  | Mark Leal | Direct Award | 2018-10-16 |  | 2018-12-20 | 65
A401/Greenfield | Hunter | Dane Harrington |  |  | 2019-01-18 | 2019-01-18 | 2019-01-18 |  | 2019-01-29 | 1900-01-13 |  | Jan-19 | Jan-00 | MW417R001670-AYCA-5ETO6E - 2TAM-07-7 Jack Smyth Drive, Hillvue | Tamworth | 13588.63 | 18400.565 | 31989.195 | 35188.1145 | 20142.57 | 4437.6215 | 24580.1915 | 7409.0035 | 23.16% |  |  |  | Mark Leal | 2018-10-09 | 2018-10-16 | 7 | 2018-12-21 | 66
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R001887-AYCA-41FBT3-2NSY-02-231 Miller St, North Sydney | North Sydney | 1375.53 |  | 1375.53 | 1513.083 | 300 |  | 300 | 1075.53 | 78.19% |  |  |  | Ertan Cicek | Direct Award | 2018-10-16 |  | 2018-12-02 | 47
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14712 | 2019-02-15 | 2018-12-21 | 2018-12-21 | 2018-12-20 | 2019-01-30 | 2019-01-11 | 2019-02-15 |  | Dec-18 | Feb-19 | MW417R001876-2AYCA-4R1E3Q-PTH-02-144-148 High Street & 35-37 Barber Avenue, Penrith |  | 932.59 | 6243.01 | 7175.6 | 7893.16 | 2141.26 |  | 2141.26 | 5034.34 | 70.16% |  |  |  | Ertan Cicek | Direct Award | 2018-10-16 |  | 2018-12-04 | 49
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R001892-AYCA-5LC14Q-2NSY-21-100 Mount street, North sydney | North Sydney | 1224.43 |  | 1224.43 | 1346.873 | 300 |  | 300 | 924.43 | 75.5% |  |  |  | Ertan Cicek | Direct Award | 2018-10-17 |  | 2018-12-04 | 48
A401/Greenfield NSB | Sydney West | Mickey Tran |  |  | 2019-03-14 | 2019-03-14 | 2019-03-14 |  | 2019-03-28 | 2019-04-11 |  | Mar-19 | Apr-19 | MW417R001868 -AYCA-5QTMEE - 2KEL-07 - 68-82 Fairway Drive Kellyville NSB | Kellyville | 960 | 3408.15 | 4368.15 | 4804.965 |  |  | 0 | 4368.15 | 100% |  |  |  | Mark Leal | 2018-10-16 | 2018-10-18 | 2 | 2018-11-26 | 39
A417 Greenfield MDU | Sydney | Dane Harrington |  |  | 2019-01-16 | 2019-01-16 | 2019-01-16 | 2019-03-12 | 2019-01-30 | 2019-02-13 |  | Jan-19 | Feb-19 | MW417R001859-AYCA-5NM0LP-2BUR-65-118 Burwood Road, Croydon Park | Croydon Park | 6061.73 | 12246.352 | 18308.082 | 20138.8902 | 6847.32 | 4150.2493 | 10997.5693 | 7310.5127 | 39.93% |  |  |  | Ertan Cicek | Direct Award | 2018-10-18 |  | 2018-12-03 | 46
A417 Business Segment | Sydney | Mickey Tran | Inv 14545 | 2018-12-14 | 2018-11-13 | 2018-11-13 | 2018-11-13 | 2018-11-22 | 2018-11-28 | 2018-12-14 |  | Nov-18 | Dec-18 | MW417R001958-2SHH-04-AYCA-5GNS19-SHOP 1097, 211 LAKE ENTRANCE ROAD | ShellHarbour | 9278.44 | 5236.06 | 14514.5 | 15965.95 | 7245.8956 |  | 7245.8956 | 7268.6044 | 50.08% |  |  |  | Dave Yoemans | Direct Award
A417 Business Segment | Sydney | Mickey Tran | Inv 14493 | 2018-12-05 | 2018-10-29 | 2018-11-05 | 2018-11-09 | 2018-11-19 | 2018-11-21 | 2018-12-04 |  | Nov-18 | Dec-18 | MW417R001961-2ABN-02-AYCA-5GN6MZ-SHOP 2, 1 RUSSELL STREET, ALBION PARK | Albion Park | 6802.6 | 5870.02 | 12672.62 | 13939.882 | 4841.6216 |  | 4841.6216 | 7830.9984 | 61.79% |  |  |  | Dave Yoemans | Direct Award
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14719 | 2019-02-15 | 2018-12-05 | 2018-12-05 | 2018-12-17 | 2019-01-30 | 2018-12-19 | 2019-02-15 |  | Dec-18 | Feb-19 | MW417R001910-2AYCA-2M3M8J-PTH-05-72-84 Empire Circuit, Penrith | Penrith | 1915.96 | 5533.73 | 7449.69 | 8194.659 | 3749.57 |  | 3749.57 | 3700.12 | 49.67% |  |  |  | Ertan Cicek | Direct Award | 2018-10-19 |  | 2018-12-07 | 49
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R001878-AYCA-1XN8L5-2KEL-07-9 Affleck Circuit, 9 Affleck Circuit | Kellyville | 4049.37 |  | 4049.37 | 4454.307 |  |  | 0 | 4049.37 | 100% |  |  |  | Nabeel Jaimon | Direct Award | 2018-10-19 |  | 2018-12-04 | 46
A417 Greenfield MDU | ACT | Marshell Antonio | Inv 14623 | 2019-01-16 | 2018-12-07 | 2018-12-07 |  |  | 2018-12-21 | 2019-01-15 |  | Dec-18 | Jan-19 | MW417R001903-AYCA-5JRURV-9BLC-20-Estate-37 Belconnen Way Weetangera ACT Int | Weetangera | 1592.08 |  | 1592.08 | 1751.288 |  | 342 | 342 | 1250.08 | 78.52% |  |  |  | Nabeel Jaimon | Direct Award | 2018-10-22 |  | 2018-12-12 | 51
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R001914 - AYCA-4DBFGM - 2NEW-20 - 87 Parramatta Rd, Camperdown | Camperdown | 1743.13 |  | 1743.13 | 1917.443 |  |  | 0 | 1743.13 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-22 |  | 2018-10-08 | -14
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R001917-AYCA-2L9FVY-2HOR-02-117-119 Pacific Hwy, Hornsby | Hornsby | 1415.68 |  | 1415.68 | 1557.248 | 300 |  | 300 | 1115.68 | 78.81% |  |  |  | Ertan Cicek | Direct Award | 2018-10-23 |  | 2018-12-08 | 46
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R001916-AYCA-4DW3WX-2HOR-62-18-22 Lords Ave + 421-425 Pacific Hwy, Asquith | Asquith | 1922.68 |  | 1922.68 | 2114.948 | 300 |  | 300 | 1622.68 | 84.4% |  |  |  | Ertan Cicek | Direct Award | 2018-10-23 |  | 2018-12-08 | 46
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-03-05 | 2019-03-05 | 2019-03-05 |  | 2019-03-19 | 2019-04-02 |  | Mar-19 | Apr-19 | MW417R001913-AYCA-35V4R1-2HOM-03-208-214 Parramatta Rd, Homebush | Homebush | 1037.08 | 13389.36 | 14426.44 | 15869.084 | 8936.65 |  | 8936.65 | 5489.79 | 38.05% |  |  |  | Ertan Cicek | Direct Award | 2018-10-23 |  | 2018-12-08 | 46
A401/Greenfield | ACT | Marshell Antonio | inv 14500 | 2018-12-05 | 2018-11-05 | 2018-11-05 | 2018-11-07 | 2018-11-22 | 2018-11-19 | 2018-12-04 |  | Nov-18 | Dec-18 | MW417R001847-AYCA-5K3OHQ-9KBA-23-93 Ivo Whitton Circuit, Kambah | Kambah | 3248.5 | 357.12 | 3605.62 | 3966.182 |  | 541.8342 | 541.8342 | 3063.7858 | 84.97% |  |  |  | Mark Leal | 2018-10-12 | 2018-10-23 | 11 | 2019-01-03 | 72
A401/Greenfield | Sydney | Dane Harrington | Inv 14615 | 2019-01-16 | 2018-11-21 | 2018-11-21 | 2018-11-29 | 2018-12-18 | 2018-12-05 | 2019-01-10 |  | Nov-18 | Jan-19 | MW417R001760-AYCA-5JYO3A-2KNS-03-1B Maddox Street, Alexandria | Alexandria | 9442.59 | -6319.07 | 3123.52 | 3435.872 | 693.05 | 860.379 | 1553.429 | 1570.091 | 50.27% |  |  |  | Ertan Cicek | 2018-10-16 | 2018-10-23 | 7 | 2018-12-31 | 69
A401/Greenfield | Central Coast | Shankar Acharya | Inv 14640 | 2019-01-18 | 2018-12-13 | 2018-12-13 |  |  | 2018-12-27 | 2019-01-22 |  | Dec-18 | Jan-19 | MW417R001874 - AYCA-512UVL - 2WYO-03 - Marineres Centre of Excellence | Tuggerah | 4847.75 |  | 4847.75 | 5332.525 | 3032.6 |  | 3032.6 | 1815.15 | 37.44% |  |  |  | Mark Leal | 2018-10-16 | 2018-10-23 |  | 2019-01-07 | 76
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14631 | 2019-01-18 | 2018-11-29 | 2018-11-29 | 2018-12-07 | 2018-12-21 | 2018-12-13 | 2019-01-22 |  | Nov-18 | Jan-19 | MW417R000463-AYCA-48HHL8-2MIR-28-2-22 University Rd & 660-664 | Miranda | 957.85 | 13993.23 | 14951.08 | 16446.188 | 4336.41 |  | 4336.41 | 10614.67 | 71% |  | 2018-12-13 |  | Ertan Cicek | Direct Award | 2018-07-05 |  | 2018-09-28 | 85
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-03-19 | 2019-03-19 |  |  | 2019-04-02 | 2019-04-16 |  | Mar-19 | Apr-19 | MW417R001980-AYCA-5M4R4N-2SHA-64-76 Irwin Street, Werrington | Werrington | 8939.74 |  | 8939.74 | 9833.714 | 9605.94 |  | 9605.94 | -666.2 | -7.452% |  |  |  | Ertan Cicek | Direct Award | 2018-10-25 |  | 2018-12-11 | 47
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R001992-AYCA-4UF84M--2LIV-04-52 Copeland Street, Liverpool | Liverpool | 904.4 |  | 904.4 | 994.84 | 300 |  | 300 | 604.4 | 66.83% |  |  |  | Ertan Cicek | Direct Award | 2018-10-25 |  | 2018-12-11 | 47
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R001994-AYCA-3CIGB0-2WRO-63-1-3 Balmoral St, Waitara | Waitara | 1318.69 |  | 1318.69 | 1450.559 |  |  | 0 | 1318.69 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-25 |  | 2018-12-11 | 47
A417 Greenfield MDU | ACT | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R001990-AYCA-YGLEJ-9CVI-03-RSL Head quarter and Residential - 1 | Civic | 1884.19 |  | 1884.19 | 2072.609 |  |  | 0 | 1884.19 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-26 |  | 2018-12-11 | 46
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R001986-AYCA-52VCLT-2NEW-20-Annandale Place - | Newtown | 2136.35 |  | 2136.35 | 2349.985 | 1001.75 |  | 1001.75 | 1134.6 | 53.11% |  |  |  | Ertan Cicek | Direct Award | 2018-10-26 |  | 2018-12-11 | 46
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14642 | 2019-01-18 | 2018-12-03 | 2018-12-03 | 2018-12-11 | 2018-12-21 | 2018-12-17 | 2019-01-22 |  | Dec-18 | Jan-19 | MW417R001982-AYCA-4EITU0-2LIV-02-10 Norfolk St, Liverpool | Liverpool | 2551.68 | 13471.6 | 16023.28 | 17625.608 | 5010.42 |  | 5010.42 | 11012.86 | 68.73% |  |  |  | Ertan Cicek | Direct Award | 2018-10-26 |  | 2018-12-11 | 46
A417 Greenfield MDU | Nth Coast | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002016-AYCA-5K2YBV-2CFS-03-Victoria Terrace | Coffs Harbour | 3268.06 |  | 3268.06 | 3594.866 |  |  | 0 | 3268.06 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-29 |  | 2019-01-15 | 78
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14577 | 2018-12-20 | 2018-11-20 | 2018-11-20 |  |  | 2018-12-04 | 2018-12-18 |  | Nov-18 | Dec-18 | MW417R000790-AYCA-57DG41 -2BTH-01-93 Stanley St Bathurst Int | Bathurst | 1592.08 |  | 1592.08 | 1751.288 |  |  | 0 | 1592.08 | 100% |  |  |  | Richard Huffadine | Direct Award | 2018-07-25 |  | 2018-10-28 | 95
NBN FttC MDUs | Sydney | Rob Panovski | Inv 14641 | 2019-01-18 | 2018-11-30 | 2018-11-30 | 2018-11-17 | 2019-01-07 | 2018-12-14 | 2019-01-22 |  | Nov-18 | Jan-19 | MW417R001946-2HOR-20-MELLAR NPDL_MWR (A417) | Hornsby | 16800 | -5883 | 10917 | 12008.7 | 1495 |  | 1495 | 9422 | 86.31% |  |  |  | Greg Mouller | Direct Award | 2018-10-29 |  | 2018-12-02 | 34
NBN FttC MDUs | Sydney | Rob Panovski | Inv 14682 | 2019-02-05 | 2018-12-20 | 2018-12-20 | 2019-01-07 | 2019-01-14 | 2019-01-11 | 2019-01-29 |  | Dec-18 | Jan-19 | MW417R001947-2HOR-02-MELLAR NPDL_MWR (A417) | Hornsby | 37960 | 19731.49 | 57691.49 | 63460.639 | 21285 |  | 21285 | 36406.49 | 63.11% |  |  |  | Greg Mouller | Direct Award | 2018-10-29 |  | 2018-12-02 | 34
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002005-AYCA-4BA1DQ-2SEF-01-Hillside | Hillside | 1037.36 |  | 1037.36 | 1141.096 |  |  | 0 | 1037.36 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-29 |  | 2018-12-11 | 43
A417 HFC DFN | Sydney Nth | Mickey Tran |  |  | 2019-02-15 | 2019-02-15 | 2019-02-25 |  | 2019-03-01 | 2019-03-15 |  | Feb-19 | Mar-19 | MW417R002021-AYCA-4IIZWC-2STL-66-28 Albany St, St Leonards DFN HFC | St Leonards | 14469.76 | 83735.01 | 98204.77 | 108025.247 | 64035.56 |  | 64035.56 | 34169.21 | 34.79% |  |  |  | Ertan Cicek | Direct Award | 2018-10-30 |  | 2018-12-27 | 58
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14393 | 2018-11-15 | 2018-11-12 | 2018-11-12 |  |  |  | 2018-11-15 |  | Nov-18 | Nov-18 | MW417R002021-AYCA-4IIZWC-2STL-66-28 Albany St, St Leonards DFN HFC | St Leonards | 6201.33 |  | 6201.33 | 6821.463 |  |  | 0 | 6201.33 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-30 |  | 2018-12-27 | 58
A401/Greenfield | Newcastle | Dane Harrington | Inv 14501 | 2018-12-05 | 2018-11-09 | 2018-11-09 | 2018-11-14 | 2018-11-23 | 2018-11-23 | 2018-12-04 |  | Nov-18 | Dec-18 | MW417R001461-AYCA-5IWI3A-2WLL-20-26 Queen St, Stockton | Stockton | 8284.33 | 20596.11 | 28880.44 | 31768.484 | 18460.98 | 1714.9701 | 20175.9501 | 8704.4899 | 30.14% |  |  |  | Mark Leal | 2018-09-18 | 2018-09-25 | 7 | 2018-12-03 | 69
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14576 | 2018-12-20 | 2018-11-20 | 2018-11-20 |  |  | 2018-12-04 | 2018-12-18 |  | Nov-18 | Dec-18 | MW417R001968 - AYCA-5N4YCV - 2BTH-02 - 5 Watt Drive Robin Hill Int | Robin Hill | 398.02 |  | 398.02 | 437.822 |  |  | 0 | 398.02 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-25 |  | 2018-11-15 | 21
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  | 2019-01-21 | 2019-01-21 | 2019-01-21 | 2019-03-18 | 2019-02-04 | 2019-03-30 |  | Jan-19 | Mar-19 | MW417R002070 - AYCA-5M7EQR - 2NWR-01 - 40 Basil Street, South Nowra | South Nowra | 1269.63 | 2015.14 | 3284.77 | 3613.247 |  |  | 0 | 3284.77 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-31 |  | 2018-12-20 | 50
A417 Greenfield MDU | ACT | Marshell Antonio |  |  | 2019-03-15 | 2019-03-15 | 2019-03-15 |  | 2019-03-29 | 2019-04-12 |  | Mar-19 | Apr-19 | MW417R002071 - AYCA-5L8461 -9CVI-21 -14 Holder Street, Turner | Turner | 2984.36 | 4182.53 | 7166.89 | 7883.579 |  |  | 0 | 7166.89 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-31 |  | 2018-12-20 | 50
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002072 - AYCA-5G4WE4 - 2MON-20 - 1473 Pittwater Road, North Narrabeen | Nth Narrabeen | 3686.86 |  | 3686.86 | 4055.546 |  |  | 0 | 3686.86 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-31 |  | 2018-12-20 | 50
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14514 | 2018-12-05 | 2018-11-13 | 2018-11-13 |  |  | 2018-11-28 | 2018-12-06 |  | Nov-18 | Dec-18 | MW417R002023 - AYCA-5PIVSY -2BTH-02 - 11 Lombard Drive, Robin Hill Int | Robin Hill | 3184.17 |  | 3184.17 | 3502.587 |  |  | 0 | 3184.17 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-10-31 |  | 2018-12-20 | 50
A417 Greenfield MDU | ACT | Marshell Antonio | Inv 14644 | 2019-01-18 | 2018-12-08 | 2019-02-28 | 2018-12-08 | 2018-12-21 | 2018-12-22 | 2019-01-22 |  | Feb-19 | Jan-19 | MW417R002106-AYCA-53Y6BS-9BON-03-Bon Scott Crescent, Moncrieff, ACT | Moncrieff | 5290.57 | 8298.28 | 13588.85 | 14947.735 |  | 3869.1222 | 3869.1222 | 9719.7278 | 71.53% |  |  |  | Ertan Cicek | Direct Award | 2018-11-05 |  | 2019-01-22 | 78
A401/Greenfield NSB | Nth Coast | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R001691 - AYCA-5PYJJF - 2KCL-02 - Sailfish Way & Seaside Drive Kingscliff NSB | Kingscliff | 960 | 6645.6 | 7605.6 | 8366.16 | 10236.04 |  | 10236.04 | -2630.44 | -34.59% |  |  |  | Mark Leal | 2018-10-04 | 2018-10-10 |  | 2018-11-07 | 28
A401/Greenfield | Hunter | Dane Harrington |  |  | 2019-02-21 | 2019-02-21 | 2019-02-21 | 2019-02-27 | 2019-03-07 | 2019-03-21 |  | Feb-19 | Mar-19 | MW417R001962 - AYCA-4W844H- 2DNM-20 - Grey Gum Road, Denman - 1 | Denman | 3509.86 | -370.128 | 3139.732 | 3453.7052 | 1456 |  | 1456 | 1683.732 | 53.63% |  |  |  | Mark Leal | 2018-10-26 | 2018-11-05 | 10 | 2018-12-04 | 29
A417 Greenfield MDU | ACT | Marshell Antonio |  |  | 2019-03-05 | 2019-03-05 | 2019-03-05 |  | 2019-03-19 | 2019-04-02 |  | Mar-19 | Apr-19 | MW417R002112-AYCA-4UFUW5-9MNS-25-Block 15, Section 56, Monash | Monash | 4646.57 | 5024.7892 | 9671.3592 | 10638.4951 | 2972.37 |  | 2972.37 | 6698.9892 | 69.27% |  |  |  | Ertan Cicek | Direct Award | 2018-11-06 |  | 2019-01-23 | 78
A417 Greenfield MDU | ACT | Marshell Antonio | Inv 14639 | 2019-01-18 | 2018-12-10 | 2018-12-10 | 2018-12-10 | 2018-12-21 | 2018-12-24 | 2019-01-22 |  | Dec-18 | Jan-19 | MW417R002121-AYCA-5JF564-9BLC-21-9 Braybrooke Street, Bruce | Bruce | 6491.62 | 4182.236 | 10673.856 | 11741.2416 | 700 |  | 700 | 9973.856 | 93.44% |  |  |  | Ertan Cicek | Direct Award | 2018-11-06 |  | 2019-01-24 | 79
A417 Greenfield MDU | Nth Coast | Dane Harrington |  |  | 2019-02-20 | 2019-02-20 | 2019-02-20 | 2019-02-26 | 2019-03-06 | 2019-03-20 |  | Feb-19 | Mar-19 | MW417R002154-AYCA-5MWJQ4-2MAC-22-222 Wallace St Macksville | Macksville | 1559.44 | 5238.77 | 6798.21 | 7478.031 | 3584.43 |  | 3584.43 | 3213.78 | 47.27% |  |  |  | Ertan Cicek | Direct Award | 2018-11-06 |  | 2018-12-04 | 28
A401/Greenfield | Sydney West | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R001939 - AYCA-56YY5F - 2CRR-65 - 120-122 Hume Highway, Canley Vale | Canley Vale | 5646.2 |  | 5646.2 | 6210.82 | 300 |  | 300 | 5346.2 | 94.69% |  |  |  | Mark Leal | 2018-10-24 | 2018-11-09 | 16 | 2019-01-14 | 66
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-02-22 | 2019-02-22 | 2019-02-22 |  | 2019-03-08 | 2019-03-22 |  | Feb-19 | Mar-19 | MW417R002155-AYCA-5KDIAQ-2ERP-60-67 Newleaf Parade, Bonnyrigg | Bonnyrigg | 2743.66 | 1870.77 | 4614.43 | 5075.873 | 2049.8 |  | 2049.8 | 2564.63 | 55.58% |  |  |  | Ertan Cicek | Direct Award | 2018-11-12 |  | 2019-01-25 | 74
A417 Greenfield MDU | Sydney | Dane Harrington | Inv 14718 | 2019-02-15 | 2018-12-14 | 2018-12-14 | 2018-12-14 | 2019-01-30 | 2018-01-08 | 2019-02-15 |  | Dec-18 | Feb-19 | MW417R002169-AYCA-55AZ5J-2ASH-63-2 Smith st, Summer Hill | Summer Hill | 1560.28 | 3867.02 | 5427.3 | 5970.03 | 2289.32 |  | 2289.32 | 3137.98 | 57.82% |  |  |  | Ertan Cicek | Direct Award | 2018-11-12 |  | 2019-01-29 | 78
A417 Greenfield MDU | Nth Coast | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002160-AYCA-4L1IJG-2SWR-20-19 Gregory Street | South West Rocks | 3540.82 | 280.8 | 3821.62 | 4203.782 |  |  | 0 | 3821.62 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-13 |  | 2019-01-25 | 73
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002170-AYCA-5OO3VM-2WLG-01- Victoria Street, Wollongong | Wollongong | 986.64 |  | 986.64 | 1085.304 |  |  | 0 | 986.64 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-13 |  | 2019-01-29 | 77
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002159-AYCA-5PIMJX-2STL-66-36A Park Road, Naremburn | Naremburn | 4936.16 |  | 4936.16 | 5429.776 | 1866.83 |  | 1866.83 | 3069.33 | 62.18% |  |  |  | Ertan Cicek | Direct Award | 2018-11-13 |  | 2019-01-25 | 73
A417 Business Segment | Sth NSW | Mickey Tran | Inv 14760 | 2019-03-05 | 2019-02-04 | 2019-02-04 | 2019-02-05 | 2019-02-08 | 2019-02-18 | 2019-02-28 |  | Feb-19 | Feb-19 | MW417R002173-AYCA-5S2CD6-2GFT-21-40 Dunn Avenue, Leeton | Leeton | 14914.04 | 4406.93 | 19320.97 | 21253.067 |  |  | 0 | 19320.97 | 100% |  |  |  | David Yeomans | 2018-10-17 | 2018-11-14 | 28 | 2018-12-07 | 23
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002182-AYCA-4PRYRR-2PAR-63-161-163 Great Western Hwy, Mays Hill | Mays Hill | 1272.51 |  | 1272.51 | 1399.761 |  |  | 0 | 1272.51 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-14 |  | 2019-01-30 | 77
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-02-18 | 2019-02-19 | 2019-02-19 |  | 2019-03-05 | 2019-03-19 |  | Feb-19 | Mar-19 | MW417R002172-AYCA-5MHAO7-2SIL-02-NSWRL Centre of Excellence - 1 | Silverwater | 9772.01 | -417.18 | 9354.83 | 10290.313 |  |  | 0 | 9354.83 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-14 |  | 2018-12-29 | 45
A417 Greenfield MDU | ACT | Marshell Antonio |  |  | 2019-03-04 | 2019-03-04 | 2019-03-04 |  | 2019-03-18 | 2019-04-01 |  | Mar-19 | Apr-19 | MW417R002018-AYCA-5MCPUX-9SCU-23-151 Drake-Brockman Drive Higgins ACT | Higgins | 5746.08 | 2587.46 | 8333.54 | 9166.894 |  |  | 0 | 8333.54 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-14 |  | 2019-01-16 | 63
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002241-AYCA-43APKG-2HOM-20-6-14 Cosgrove Road, Strathfield | Strathfield | 1727.14 |  | 1727.14 | 1899.854 |  |  | 0 | 1727.14 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-14 |  | 2019-01-30 | 77
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002246-AYCA-4P3YPZ-2BAN-67-107 Chapel Road South, Bankstown | Bankstown | 5523.45 |  | 5523.45 | 6075.795 | 1995.77 |  | 1995.77 | 3527.68 | 63.87% |  |  |  | Ertan Cicek | Direct Award | 2018-11-14 |  | 2019-01-30 | 77
A417 Greenfield MDU | Sth NSW | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002156-AYCA-5F1MOI-2MSV-03-Martha Street, Bowral | Bowral | 4334.94 |  | 4334.94 | 4768.434 |  |  | 0 | 4334.94 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-14 |  | 2019-01-25 | 72
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002183 - AYCA-5KIP6Y -2WLG-07-45 Rosemont Street, West Wollongong | Wollongong | 469.92 |  | 469.92 | 516.912 |  |  | 0 | 469.92 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-14 |  | 2019-01-30 | 77
A401/Greenfield | Sth NSW | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002120-AYCA-5FILA6-2BOW-20--12 Marsden Street, Boorowa | Boorowa | 9721.02 |  | 9721.02 | 10693.122 |  |  | 0 | 9721.02 | 100% |  |  |  | Mark Leal | 2018-11-08 | 2018-11-15 |  | 2019-01-28 | 74
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002221 - AYCA-54A0VP - 2PYM-62 - 7 Cherry St, Warrawee | Warrawee | 1328.35 |  | 1328.35 | 1461.185 |  |  | 0 | 1328.35 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-15 |  | 2018-12-31 | 46
A417 HFC DFN | Sydney West | Mickey Tran |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002226-AYCA-4PEEEK - 2RYD-63- 17-21 Ryedale Rdm West Ryde HFC DFN | West Ryde | 24022.14 |  | 24022.14 | 26424.354 | 44669.64 |  | 44669.64 | -20647.5 | -85.95% |  |  |  | Mark Leal | Direct Award | 2018-11-16 |  | 2018-12-21 | 35
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14799 | 2019-03-14 | 2019-03-12 | 2019-03-12 |  |  |  | 2019-03-14 |  | Mar-19 | Mar-19 | MW417R002226-AYCA-4PEEEK - 2RYD-63- 17-21 Ryedale Rdm West Ryde HFC DFN | West Ryde | 10295.2 |  | 10295.2 | 11324.72 |  |  | 0 | 10295.2 | 100% |  |  |  | Mark Leal | Direct Award | 2018-11-16 |  | 2018-12-21 | 35
A417 Greenfield MDU | ACT | Marshell Antonio |  |  | 2019-02-19 | 2019-02-19 | 2019-02-21 |  | 2019-03-05 | 2019-03-19 |  | Feb-19 | Mar-19 | MW417R002299-AYCA-5MVKQ1-9BON-03-1 O'Keefe Avenue, Moncrieff, ACT | Moncrieff | 1682.01 | 2839.13 | 4521.14 | 4973.254 |  |  | 0 | 4521.14 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-19 |  | 2018-12-06 | 17
A417 Greenfield MDU | ACT | Marshell Antonio |  |  | 2019-03-08 | 2019-03-08 | 2019-03-08 |  | 2019-03-22 | 2019-04-05 |  | Mar-19 | Apr-19 | MW417R002295-AYCA-5AZA4J-9SCU-08-BLOCK 26 SECTION 124, Holt, ACT | Holt | 1671.26 | 3401.598 | 5072.858 | 5580.1438 |  |  | 0 | 5072.858 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-19 |  | 2019-02-02 | 75
A417 Greenfield MDU | Sydney East | Dane Harrington |  |  | 2019-03-07 | 2019-03-07 | 2019-03-12 |  | 2019-03-21 | 2019-04-04 |  | Mar-19 | Apr-19 | MW417R002292-AYCA-49OZC4-2EAS-65-257 Oxford St - 1 | Paddington | 2337.72 | 14000.67 | 16338.39 | 17972.229 | 1747.74 |  | 1747.74 | 14590.65 | 89.3% |  |  |  | Ertan Cicek | Direct Award | 2018-11-19 |  | 2019-02-06 | 79
A417 Greenfield MDU | Sydney East | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002291-AYCA-42HX6R-2BON-61-34-42 Spring St, Bondi Junction, | Bondi Junction | 1007.09 |  | 1007.09 | 1107.799 |  |  | 0 | 1007.09 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-19 |  | 2019-02-06 | 79
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-03-14 | 2019-03-14 | 2019-03-14 |  | 2019-03-28 | 2019-04-11 |  | Mar-19 | Apr-19 | MW417R002312-AYCA-5KPEKH-2NRN-06-Estate-Olive Hill Drvie Cobbitty | Cobbitty | 536.97 | 208.16 | 745.13 | 819.643 |  |  | 0 | 745.13 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-20 |  | 2019-01-15 | 56
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002301-AYCA-578FAA-2NSY-02-229 MILLER STREET, NORTH SYDNEY | North Sydney | 748.98 |  | 748.98 | 823.878 |  |  | 0 | 748.98 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-22 |  | 2019-02-06 | 76
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2019-02-28 | 2019-03-14 |  | Feb-19 | Mar-19 | MW417R002329-AYCA-5MG99P-2MEN-62-593 Old Illawarra Road, Menai EXT | Menai | 1631.42 | 2960.56 | 4591.98 | 5051.178 | 3261.51 |  | 3261.51 | 1330.47 | 28.97% |  |  |  | Ertan Cicek | Direct Award | 2018-11-22 |  | 2019-02-08 | 78
NBN FttC MDUs | Sydney | Rob Panovski | Inv 14763 | 2019-03-05 | 2019-01-16 | 2019-01-16 | 2019-02-07 | 2019-02-15 | 2019-01-31 | 2019-01-28 |  | Jan-19 | Jan-19 | MW417R002345 - 2MIR-21 - MELLAR NPDL_MWR (A417) - Miranda | Miranda | 30623 | 18285 | 48908 | 53798.8 | 17225 |  | 17225 | 31683 | 64.78% |  |  |  | Greg Mouller | 2018-11-22 | 2018-11-29 |  | 2018-12-21 | 22
NBN FttC MDUs | Sydney | Rob Panovski | Inv 14737 | 2019-02-18 | 2019-01-16 | 2019-01-16 | 2019-01-16 | 2019-01-23 | 2019-01-31 | 2019-02-18 |  | Jan-19 | Feb-19 | MW417R002346 - 2MIR-22 - MELLAR NPDL_MWR (A417)-Miranda | Miranda | 13451 | 9540 | 22991 | 25290.1 | 6370 |  | 6370 | 16621 | 72.29% |  |  |  | Greg Mouller | 2018-11-22 | 2018-11-29 |  | 2018-12-14 | 15
A401/Greenfield NSB | Nth Coast | Mickey Tran |  |  |  | 2019-03-30 | 2019-03-11 |  | 2019-04-13 | 2019-04-27 |  | Mar-19 | Apr-19 | MW417R002209-AYCA-5T4J9J-2WAU-21-39 - 41 Production Ave Wauchope NSB | Wauchope | 3522.8 | 5222.724 | 8745.524 | 9620.0764 | 1395.3 |  | 1395.3 | 7350.224 | 84.05% |  |  |  | Mark Leal | 2018-11-16 | 2018-11-23 | 7 | 2018-12-26 | 33
A417 Business Segment | Hunter | Dane Harrington |  |  | 2019-02-18 | 2019-02-18 | 2019-02-18 | 2019-02-26 | 2019-03-04 | 2019-03-18 |  | Feb-19 | Mar-19 | MW417R002406-2SIN-22-AYCA-5ST32Q-42-44 ENTREPRISE CRE, MCDOUGALLS HILL | McDougalls Hill | 35556.08 | 46751.81 | 82307.89 | 90538.679 | 38337.51 |  | 38337.51 | 43970.38 | 53.42% |  |  |  | Dave Yoemans | 2018-11-08 | 2018-12-10 | 32 | 2018-12-24 | 14
A417 Business Segment | Sydney | Mickey Tran | Inv 14759 | 2019-03-05 | 2019-02-04 | 2019-02-04 | 2019-02-05 | 2019-02-09 | 2019-02-18 | 2019-02-28 |  | Feb-19 | Feb-19 | MW417R002426 - 2LIV-68 - AYCA-5ST336 - 78-82 RIVERSIDE RD, CHIPPING NORTON Chipping Norton |  | 15453.91 | 3990.99 | 19444.9 | 21389.39 | 9611.86 |  | 9611.86 | 9833.04 | 50.57% |  |  |  | Dave Yoemans | 2018-11-08 | 2018-12-10 | 32 | 2018-12-24 | 14
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002367-AYCA-4PPBEB-2RYD-63-8 Sherbrooke Rd, West Ryde | West Ryde | 2919.27 |  | 2919.27 | 3211.197 |  |  | 0 | 2919.27 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-26 |  | 2019-02-12 | 78
A417 Greenfield MDU | Sydney East | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002375-AYCA-5BOGUB-2RED-01-11B Lachlan St Waterloo INT | Waterloo | 13668 |  | 13668 | 15034.8 |  |  | 0 | 13668 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-26 |  | 2019-01-25 | 60
A417 Greenfield MDU | Sydney East | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002435-AYCA-5BOGUB-2RED-01-11B Lachlan St, Waterloo EXT | Waterloo | 3070.2 |  | 3070.2 | 3377.22 |  |  | 0 | 3070.2 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-29 |  | 2019-02-18 | 81
A417 Greenfield MDU | ACT | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002390-AYCA-5RXMK0-9QBN-08-96 Bayldon Road, Queanbeyan West | Queanbeyan West | 636.87 |  | 636.87 | 700.557 |  |  | 0 | 636.87 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-27 |  | 2019-02-13 | 78
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002384 - AYCA-5N4NUW- 2HBD-23 - 36 Wyndora Avenue, Freshwater | Harbord | 5278.64 |  | 5278.64 | 5806.504 | 2805.2 |  | 2805.2 | 2473.44 | 46.86% |  |  |  | Ertan Cicek | Direct Award | 2018-11-27 |  | 2019-02-13 | 78
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002360 - AYCA-54N6L7 - 2PAR-60 - 104 - 108 Bridge Rd, Westmead | Westmead | 1106.42 |  | 1106.42 | 1217.062 | 353.76 |  | 353.76 | 752.66 | 68.03% |  |  |  | Ertan Cicek | Direct Award | 2018-11-27 |  | 2019-02-13 | 78
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  | 2019-03-11 | 2019-03-11 | 2019-03-11 |  | 2019-03-25 | 2019-04-08 |  | Mar-19 | Apr-19 | MW417R002412 - AYCA-47STWW - 2CYS-11 -130 Elizabeth St, Sydney | Sydney CBD | 665 | 2614.56 | 3279.56 | 3607.516 |  |  | 0 | 3279.56 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-28 |  | 2019-02-14 | 78
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2018-03-30 | [5 empty] | Mar-18 | Jan-00 | MW417R002383-AYCA-5DHKDD -2CRO-22-36 Rawson Parade, Caringbah South | Caringbah South | 681.82 |  | 681.82 | 750.002 | 300 |  | 300 | 381.82 | 56% |  |  |  | Ertan Cicek | Direct Award | 2018-11-28 |  | 2019-02-19 | 83
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  | 2019-02-21 | 2019-02-21 | 2019-02-21 | 2019-02-27 | 2019-03-07 | 2019-03-21 |  | Feb-19 | Mar-19 | MW417R002399-AYCA-EV5EP-2DAP-01-Smiths Lane Wongawilli | Wongawilli | 3147.58 | 1887.34 | 5034.92 | 5538.412 | 2617.08 |  | 2617.08 | 2417.84 | 48.02% |  |  |  | Ertan Cicek | Direct Award | 2018-11-28 |  | 2019-01-15 | 48
NBN FttC MDUs | Sydney | Rob Panovski | Inv 14762 & 14798 | 2019-03-05 | 2019-01-16 | 2019-01-16 | 2019-02-17 | 2019-02-15 | 2009-01-31 | 2019-02-28 |  | Jan-19 | Feb-19 | MW417R002347-2MIR-29-MELLAR NPDL_MWR (A417) | Miranda | 71327 | 21052 | 92379 | 101616.9 | 39195 |  | 39195 | 53184 | 57.57% |  |  |  | Greg Mouller | 2018-11-23 | 2018-11-29 | 6 | 2019-01-11 | 43
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002400-AYCA-41DY76-2ROU-03-38 Hezlett Road Kellyville | Kellyville | 2372.08 |  | 2372.08 | 2609.288 |  |  | 0 | 2372.08 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-11-29 |  | 2019-01-15 | 47
A417 Greenfield MDU | Sydney | Dane Harrington |  |  | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-03-18 | 2019-02-07 | 2019-03-30 |  | Jan-19 | Mar-19 | MW417R002437-AYCA-4LVG38-2MIL-20-9-11 Edgeworth Place, Cartwright | Cartwright | 1737.94 | 2937.87 | 4675.81 | 5143.391 | 2271.88 |  | 2271.88 | 2403.93 | 51.41% |  |  |  | Ertan Cicek | Direct Award | 2018-11-29 |  | 2019-02-18 | 81
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002436-AYCA-5RHH4X-2PNN-68-68 Beecroft Road, Beecroft | Beecroft | 727.36 |  | 727.36 | 800.096 | 300 |  | 300 | 427.36 | 58.75% |  |  |  | Ertan Cicek | Direct Award | 2018-11-29 |  | 2019-02-18 | 81
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002457-AYCA-4YHOA0-2PAR-63-8-12 Robilliard St, Mays Hill | Mays Hill | 664.04 |  | 664.04 | 730.444 |  |  | 0 | 664.04 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-03 |  | 2019-02-19 | 78
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002455-AYCA-3GG3CO-2MIR-31-1-13 Dianella St, Caringbah | Carringbah | 1434.48 |  | 1434.48 | 1577.928 | 1650.08 |  | 1650.08 | -215.6 | -15.03% |  |  |  | Ertan Cicek | Direct Award | 2018-12-03 |  | 2019-02-19 | 78
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  | 2019-02-14 | 2019-02-14 | 2019-02-14 |  | 2019-02-28 | 2019-03-14 |  | Feb-19 | Mar-19 | MW417R002453-62-AYCA-5MGOY8-2MEN-589 Old Illawarra Road, Menai Ext | Menai | 5140.98 | 581.85 | 5722.83 | 6295.113 | 3773.26 |  | 3773.26 | 1949.57 | 34.07% |  |  |  | Ertan Cicek | Direct Award | 2018-12-03 |  | 2019-02-19 | 78
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002451-AYCA-4WGB20-2STL-60-64-66 Chandos St, St Leonards | St Leonards | 969.02 |  | 969.02 | 1065.922 |  |  | 0 | 969.02 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-03 |  | 2019-02-19 | 78
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002449-AYCA-40TCKL-2NSY-02-221 Miller St, North Sydney | Nth Sydney | 808.49 |  | 808.49 | 889.339 |  |  | 0 | 808.49 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-03 |  | 2019-02-19 | 78
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002450-AYCA-5I8I8D-2PNN-63-27-31 Thornleigh Street, Thornleigh | Thornleigh | 2812.91 |  | 2812.91 | 3094.201 |  |  | 0 | 2812.91 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-04 |  | 2019-02-19 | 77
A417 HFC DFN | Sydney Sth | Mickey Tran |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002470-AYCA-5E7TWE-2MEN-60-37-39 Barden Rd, Barden Ridge HFC DFN | Menia | 33375.965 |  | 33375.965 | 36713.5615 | 25056.88 |  | 25056.88 | 8319.085 | 24.93% |  |  |  | Mark Leal | Direct Award | 2018-12-04 |  | 2019-01-31 | 58
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14523 | 2018-12-05 | 2018-12-05 | 2018-12-05 |  |  |  | 2018-12-11 |  | Dec-18 | Dec-18 | MW417R002470-AYCA-5E7TWE-2MEN-60-37-39 Barden Rd, Barden Ridge HFC DFN | Menia | 14303.985 |  | 14303.985 | 15734.3835 |  |  | 0 | 14303.985 | 100% |  |  |  | Mark Leal | Direct Award | 2018-12-04 |  | 2019-01-31 | 58
A417 Greenfield MDU | Central West | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002504-AYCA-5ALAXU-2ORG-02-104 Lysterfield Rd Orange | Orange | 193.64 |  | 193.64 | 213.004 |  |  | 0 | 193.64 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-10 |  | 2019-02-01 | 53
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002546 - AYCA-4ULUDH -2MIR-26 - 5-7 Higherdale Ave., Miranda | Miranda | 1105.88 |  | 1105.88 | 1216.468 |  |  | 0 | 1105.88 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-10 |  | 2019-02-27 | 79
A417 HFC DFN | Sydney East | Mickey Tran |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002533-AYCA-2PNFXD-2ROS-66 -Corner Old South Road & Hamilton Street HFC DFN | Rose Bay | 24694.061 |  | 24694.061 | 27163.4671 | 20557.64 |  | 20557.64 | 4136.421 | 16.75% |  |  |  | Mark Leal | Direct Award | 2018-12-10 |  | 2019-02-27 | 79
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14578 | 2018-12-20 | 2018-12-11 | 2018-12-11 |  |  |  | 2018-12-18 |  | Dec-18 | Dec-18 | MW417R002533-AYCA-2PNFXD-2ROS-66 -Corner Old South Road & Hamilton Street HFC DFN | Rose Bay | 10583.169 |  | 10583.169 | 11641.4859 |  |  | 0 | 10583.169 | 100% |  |  |  | Mark Leal | Direct Award | 2018-12-10 |  | 2019-02-27 | 79
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  | 2019-02-18 | 2019-02-20 |  |  | 2019-03-06 | 2019-03-20 |  | Feb-19 | Mar-19 | MW417R002507 - AYCA-5MG99P - 2MEN-62 - 593 Old Illawarra Road Menai INT | Menia | 1428 |  | 1428 | 1570.8 |  |  | 0 | 1428 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-10 |  | 2019-02-19 | 71
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002545 - AYCA-52UVXU - 2HOM-20 -The Christian, Strathfield South | Strathfield Sth | 675.26 |  | 675.26 | 742.786 | 2034.82 |  | 2034.82 | -1359.56 | -201.3% |  |  |  | Ertan Cicek | Direct Award | 2018-12-10 |  | 2019-02-27 | 79
A417 Greenfield MDU | Nth Coast | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002554 - AYCA-5M84RG - 2CFS-02 - 72 Boultwood Street, Coffs Harbour | Coffs Harbour | 1098.34 |  | 1098.34 | 1208.174 |  |  | 0 | 1098.34 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-12 |  | 2019-02-27 | 77
A417 Greenfield MDU | Sth NSW | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002550-AYCA-58PGFK-2MSV-03-25 Ascot Rd, Bowral | Bowral | 4436.08 |  | 4436.08 | 4879.688 |  |  | 0 | 4436.08 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-12 |  | 2019-02-27 | 77
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002551 - AYCA-5M7O7M - 9BON-03 - Shugg St, Taylor, ACT | Taylor | 1844.58 |  | 1844.58 | 2029.038 |  |  | 0 | 1844.58 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-12 |  | 2019-02-27 | 77
A417 Greenfield MDU | Sydney East | Dane Harrington |  |  | 2019-02-07 | 2019-02-08 | 2019-02-08 |  | 2019-02-22 | 2019-03-08 |  | Feb-19 | Mar-19 | MW417R002544 - AYCA-55AQIZ - 2ASH-63 - 3 Mungo Scott Place, Summer Hill | Summer Hill | 505.61 | 2254.949 | 2760.559 | 3036.6149 | 516 |  | 516 | 2244.559 | 81.31% |  |  |  | Ertan Cicek | Direct Award | 2018-12-12 |  | 2019-02-27 | 77
A417 HFC DFN | Sydney West | Mickey Tran |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002570-AYCA-4XIVYZ-HFC DFN-2UND-62-236-238 ILLAWARRA RD, MARRICKVILLE | Marrickville | 30651.5 |  | 30651.5 | 33716.65 | 17579.85 |  | 17579.85 | 13071.65 | 42.65% |  |  |  | Mark Leal | Direct Award | 2018-12-12 |  | 2019-02-27 | 77
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14621 | 2019-01-16 | 2019-01-16 | 2019-01-16 |  |  |  | 2019-01-17 |  | Jan-19 | Jan-00 | MW417R002570-AYCA-4XIVYZ-HFC DFN-2UND-62-236-238 ILLAWARRA RD, MARRICKVILLE | Marrickville | 9195.45 |  | 9195.45 | 33716.65 |  |  | 0 | 9195.45 | 100% |  |  |  | Mark Leal | Direct Award | 2018-12-12 |  | 2019-02-27 | 77
A417 Greenfield MDU | Central West | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002548-AYCA-5JIMDQ-2DBB-02-166 Brisbane Street Dubbo | Dubbo | 1713.6 |  | 1713.6 | 1884.96 |  |  | 0 | 1713.6 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-12 |  | 2019-01-30 | 49
NBN FttC MDUs | Sydney West | Rob Panovski |  |  | 2019-02-06 | 2018-02-17 | 2019-02-17 | 2019-02-25 | 2018-03-03 | 2018-03-17 |  | Feb-18 | Mar-18 | MW417R002582-2ERP-20 - Erskine Park | Erskine Paark | 11861 | 1749 | 13610 | 14971 | 2600 |  | 2600 | 11010 | 80.9% |  |  |  | Greg Mouller | Direct Award | 2018-12-12 |  | 2019-01-22 | 41
NBN FttC MDUs | Sydney West | Rob Panovski |  |  | 2019-02-06 | 2018-02-17 | 2019-02-17 | 2019-02-25 | 2018-03-03 | 2018-03-17 |  | Feb-18 | Mar-18 | MW417R002583-2ORC-06 - Orchid Hills | Orchid Hills | 12974 | 28938 | 41912 | 46103.2 | 14230.68 |  | 14230.68 | 27681.32 | 66.05% |  |  |  | Greg Mouller | 2018-12-21 | 2019-01-03 | 13 | 2019-01-22 | 19
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  | 2019-02-18 | 2019-02-18 |  |  | 2019-03-04 | 2019-03-18 |  | Feb-19 | Mar-19 | MW417R002524-AYCA-5MGOY8-2MEN-62-589 Old Illawarra Road Menai Int | Menai | 856.8 |  | 856.8 | 942.48 |  |  | 0 | 856.8 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-11 |  | 2019-01-18 | 38
A417 Greenfield MDU | Central West | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002540-AYCA-5JIMDQ2DBB-02-166 Brisbane Street, Dubbo Ext | Dubbo | 2107.76 |  | 2107.76 | 2318.536 | 300 |  | 300 | 1807.76 | 85.77% |  |  |  | Ertan Cicek | Direct Award | 2018-12-11 |  | 2019-02-27 | 78
A401/Greenfield | Sydney Nth | Mickey Tran |  |  | 2019-03-07 | 2019-03-07 | 2019-03-11 |  | 2019-03-21 | 2019-04-04 |  | Mar-19 | Apr-19 | MW417R002429 - AYCA-5MQHDT - 2AVA-02 - 32 Ruskin Rowe, Avalon Beach | Avalon | 8594.65 | 3796.15 | 12390.8 | 13629.88 | 474.4 |  | 474.4 | 11916.4 | 96.17% |  |  |  | Ertan Cicek | 2018-11-30 | 2018-12-11 | 11 | 2019-02-19 | 70
A401/Greenfield | Sydney East | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002552-AYCA-4C0Z5Y - 2ROS-66-554-564 Old South Head Rd, Rose Bay | Rose Bay | 964.26 |  | 964.26 | 1060.686 |  |  | 0 | 964.26 | 100% |  |  |  | Mark Leal | Direct Award | 2018-12-11 |  | 2019-02-27 | 78
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002590-AYCA-5072G6-2LIV-02-123 CASTLEREAGH STREET, LIVERPOOL | Liverpool | 1421.68 |  | 1421.68 | 1563.848 | 300 |  | 300 | 1121.68 | 78.9% |  |  |  | Ertan Cicek | Direct Award | 2018-12-15 |  | 2019-03-05 | 80
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14765 | 2019-05-05 | 2019-01-24 | 2019-01-24 |  |  | 2019-02-07 | 2019-02-28 |  | Jan-19 | Feb-19 | MW417R002527-AYCA-5H49UT-2BTH-20-132 Piper Street, Bathurst | Bathurst | 4608.26 |  | 4608.26 | 5069.086 |  |  | 0 | 4608.26 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-15 |  | 2019-02-26 | 73
A417 Greenfield MDU | ACT | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002598-AYCA-44HH3F-9BLC-22-31-49 Warrego Circuit, Kaleen, ACT | Kaleen | 2863.75 |  | 2863.75 | 3150.125 |  |  | 0 | 2863.75 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-15 |  | 2019-03-05 | 80
A417 Greenfield MDU | Central Coast | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002595 - AYCA-5NXLZB - 2TGL-02 -158 Terrigal Drive, Terrigal | Terrigal | 1092.78 |  | 1092.78 | 1202.058 |  |  | 0 | 1092.78 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-13 |  | 2019-03-05 | 82
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002581 - AYCA-5CQHIP -2PTH-02 - 24 Barber Ave, Penrith | Penrith | 2028.08 |  | 2028.08 | 2230.888 |  |  | 0 | 2028.08 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-13 |  | 2019-03-04 | 81
A417 Greenfield MDU | Nth Coast | Dane Harrington | Inv 14672 | 2019-01-23 | 2018-12-19 | 2018-12-19 | 2018-12-19 | 2018-12-21 | 2019-01-10 | 2019-01-24 |  | Dec-18 | Jan-19 | MW417R002148 - AYCA-5D2DU0 - 2LCT-01 - Seawide Estate - 4 | Lake Cathie | 4713.07 | 7330.69 | 12043.76 | 13248.136 | 6070.13 |  | 6070.13 | 5973.63 | 49.6% |  |  |  | Mark Leal | Direct Award | 2018-11-08 |  | 2019-02-04 | 88
A417 Greenfield MDU | Sth NSW | Marshell Antonio |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002606-AYCA-58PGFK-2MSV-03-25 Ascot Rd Bowral | Bowral | 1592.08 |  | 1592.08 | 1751.288 |  |  | 0 | 1592.08 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-18 |  | 2019-02-11 | 55
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002640 - AYCA-5SX5PK - 2CRO-23 - 51-55 Burraneer Bay Road, Burraneer | Burraneer | 1115.6 |  | 1115.6 | 1227.16 |  |  | 0 | 1115.6 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-19 |  | 2019-03-13 | 84
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002626 - AYCA-4LZWVS - 2PNN-63 -266-268 Pennant Hills Rd, Thornleigh | Thronleigh | 2082.54 |  | 2082.54 | 2290.794 |  |  | 0 | 2082.54 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-19 |  | 2019-03-12 | 83
A401/Greenfield NSB | Central Coast | Mickey Tran |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002564-AYCA-512UVL-2WYO-03-Marineres Centre of Excellence - BUILD | Tuggerah | 21515.28 |  | 21515.28 | 23666.808 |  |  | 0 | 21515.28 | 100% |  |  |  | Mark Leal | 2018-12-07 | 2018-12-20 |  | 2019-03-06 | 76
NBN FttC MDUs | ACT | Rob Panovski |  |  | 2019-02-06 | 2018-02-17 | 2019-02-17 | 2019-02-25 | 2019-03-04 | 2019-03-18 |  | Feb-18 | Mar-19 | MW417R002601-9DKI-05-ACT | Deakin | 5381 | 2540 | 7921 | 8713.1 | 1358.5 |  | 1358.5 | 6562.5 | 82.85% |  |  |  | Greg Mouller | 2018-12-17 | 2019-01-02 |  | 2019-01-14 | 12
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002689 -AYCA-5HNMQ4-2CRO-26-2 - 4 Marlo Road Cronulla | Cronulla | 1655.36 |  | 1655.36 | 1820.896 |  |  | 0 | 1655.36 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-04 |  | 2019-03-01 | 56
A401/Greenfield | Sydney Sth | Marshell Antonio |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002563 - 2NRN-05 - AYCA-5FCHOB - 23 Grahams Hill Road, Narellan | Narellan | 13650.26 |  | 13650.26 | 15015.286 | 4831.84 |  | 4831.84 | 8818.42 | 64.6% |  |  |  | Ertan Cicek | 2018-12-18 | 2019-01-03 | 16 | 2019-03-06 | 62
NBN FttC MDUs | ACT | Rob Panovski |  |  | 2019-02-05 | 2018-02-17 | 2019-02-17 | 2019-02-25 | 2018-03-03 | 2018-03-17 |  | Feb-18 | Mar-18 | MW417R002600 - 9DKI-04 - Deakin | Deakin | 13451 | 15603 | 29054 | 31959.4 | 8930 |  | 8930 | 20124 | 69.26% |  |  |  | Greg Mouller | 2018-12-17 | 2019-01-02 | 16 | 2019-01-14 | 12
NBN FttC MDUs | ACT | Rob Panovski |  |  | 2019-02-05 | 2018-02-17 | 2019-02-17 | 2019-02-26 | 2018-03-03 | 2018-03-17 |  | Feb-18 | Mar-18 | MW417R002602 - 9DKI-21- Deakin | Deakin | 10430 | 12967 | 23397 | 25736.7 | 6663.5 |  | 6663.5 | 16733.5 | 71.52% |  |  |  | Greg Mouller | 2018-12-17 | 2019-01-02 | 16 | 2019-01-14 | 12
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  | 2019-02-25 | 2019-02-25 | 2019-02-25 |  | 2019-03-11 | 2019-03-25 |  | Feb-19 | Mar-19 | MW417R002683-AYCA-5UQX4I-2HUH-20-29 Moorefield Avenue, Hunters Hill | Hunter Hill | 1545.49 | 131.638 | 1677.128 | 1844.8408 |  |  | 0 | 1677.128 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-02 |  | 2019-03-13 | 70
A417 Greenfield MDU | Sth Coast | Marshell Antonio | Inv 14766 | 2019-02-27 | 2019-01-21 | 2019-01-21 | 2019-01-21 | 2019-01-29 | 2019-02-04 | 2019-02-28 |  | Jan-19 | Feb-19 | MW417R002684-AYCA-5SK61D- 2NWR-03-38 Cumberland Avenue, South Nowra | South Nowra | 1069.03 | 1341.389 | 2410.419 | 2651.4609 |  |  | 0 | 2410.419 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-02 |  | 2019-03-13 | 70
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002673 - AYCA-4WQIL0 - 2PTH-05 - 13-15 Vista St, Penrith | Penrith | 540.68 |  | 540.68 | 594.748 |  |  | 0 | 540.68 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-02 |  | 2019-03-12 | 69
A401/Greenfield | ACT | Marshell Antonio |  |  | 2019-03-11 | 2019-03-11 | 2019-03-11 |  | 2019-03-25 | 2019-04-08 |  | Mar-19 | Apr-19 | MW417R002213-9BLC-20-AYCA-5SMBZ7-54 Arndell Street Macquarie ACT NSB | Macquarie | 19923.24 | 9901.4643 | 29824.7043 | 32807.1747 | 18001.95 |  | 18001.95 | 11822.7543 | 39.64% |  |  |  | Mark Leal | 2018-11-27 |  |  |  | 0 | email go ahead from Vipin on the 2/1/19
A417 Greenfield MDU | Sth Coast | Marshell Antonio | Inv 14742 | 2019-02-27 | 2019-01-21 | 2019-01-21 |  |  | 2019-02-04 | 2019-02-26 |  | Jan-19 | Feb-19 | MW417R002652-AYCA-5SK61D-2NWR-03-39 Cumberland Avenue South Nowra | Nowra | 398.02 |  | 398.02 | 437.822 |  |  | 0 | 398.02 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-21 |  | 2019-01-11 | 21
NBN FttC MDUs | Sydney West | Rob Panovski |  |  | 2019-02-06 | 2018-02-17 | 2019-02-17 | 2019-02-25 | 2018-03-03 | 2018-03-17 |  | Feb-18 | Mar-18 | MW417R002584-2ORC-22-Orchard Hills | Orchard Hills | 11702 | -795 | 10907 | 11997.7 |  |  | 0 | 10907 | 100% |  |  |  | Greg Mouller | 2018-12-17 | 2018-12-21 | 4 | 2019-01-22 | 32
NBN FttC MDUs | Sydney East | Rob Panovski |  |  | 2019-02-06 | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002740-2HMK-01 Haymarket | Haymarket | 6017 |  | 6017 | 6618.7 | 995 |  | 995 | 5022 | 83.46% |  |  |  | Greg Mouller | 2019-01-09
NBN FttC MDUs | Sydney East | Rob Panovski |  |  | 2019-02-06 | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002740-2HMK-22 - Haymarket | Haymarket | 4586 |  | 4586 | 5044.6 | 260 |  | 260 | 4326 | 94.33% |  |  |  | Greg Mouller | 2019-01-09
NBN FttC MDUs | Sydney East | Rob Panovski |  |  | 2019-02-06 | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002740-2HMK-02 - Haymarket | Haymarket | 25694 |  | 25694 | 28263.4 | 7540 |  | 7540 | 18154 | 70.65% |  |  |  | Greg Mouller | 2019-01-09
A417 Greenfield MDU | ACT | Marshell Antonio |  |  | 2019-01-29 | 2019-01-29 |  |  | 2019-02-12 | 2019-02-26 |  | Jan-19 | Feb-19 | MW417R002676-AYCA-5I62CV-9BON-03-Block 9 Section 39 Taylor | Taylor | 5787.21 | 709.33 | 6496.54 | 7146.194 |  |  | 0 | 6496.54 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-24 |  | 2019-03-12 | 78
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002672-AYCA-54OULE-2MIL-62-HILL ROAD LURNEA | Lurnea | 1956.37 |  | 1956.37 | 2152.007 |  |  | 0 | 1956.37 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-24 |  | 2019-03-12 | 78
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2018-04-30 | [5 empty] | Apr-18 | Jan-00 | MW417R002667-AYCA-2I98H3-2PAR-61-Hassall View Pty Ltd | Parramatta | 1949.48 |  | 1949.48 | 2144.428 |  |  | 0 | 1949.48 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-24 |  | 2019-03-12 | 78
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002731-AYCA-5M5JQ0-2HUH-21-23A Mars Road, Lane Cove West | Lane Cove | 1746.76 |  | 1746.76 | 1921.436 |  |  | 0 | 1746.76 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-07 |  | 2019-03-27 | 79
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002723-AYCA-3O1ZGP-2GBE-62-4-6 Elger St, Glebe | Glebe | 1752.98 |  | 1752.98 | 1928.278 |  |  | 0 | 1752.98 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-07 |  | 2019-03-27 | 79
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002725-AYCA-57JCRY-2GRA-63-27a, 31, 33 & 35 Louis Street,Granville | Granville | 1715.62 |  | 1715.62 | 1887.182 |  |  | 0 | 1715.62 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-07 |  | 2019-03-27 | 79
A417 Greenfield MDU | ACT | Marshell Antonio |  |  | 2019-03-08 | 2019-03-08 | 2019-03-08 |  | 2019-03-22 | 2019-04-05 |  | Mar-19 | Apr-19 | MW417R002720-AYCA-5LTSYB-9BLC-20-12 Shumack Street, Weetangera ACT Ext | Weetangera | 1514.73 | 2375.21 | 3889.94 | 4278.934 |  |  | 0 | 3889.94 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-08 |  | 2019-03-27 | 78
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002739 - AYCA-5U1ZX9 - 2CRO-26 -32 Seaview Street, Cronulla | Cronulla | 1174.26 |  | 1174.26 | 1291.686 |  |  | 0 | 1174.26 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-08 |  | 2019-03-28 | 79
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002744-AYCA-4SBJVB-2BLK-01-9-11 SWINSON ROAD BLACKTOWN | Blacktown | 811.16 |  | 811.16 | 892.276 |  |  | 0 | 811.16 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-08 |  | 2019-03-27 | 78
A417 HFC DFN | Sydney West | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002737-AYCA-5HZXRM-2SHA-64-88 Reid Street, Werrington County HFC DFN | Shalvey | 65014.866 |  | 65014.866 | 71516.3526 | 47610.9 |  | 33072.8 | 31942.066 | 49.13% |  |  |  | Mark Leal | Direct Award | 2019-01-11 |  | 2019-03-31 | 79
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14628 | 2019-01-18 | 2019-01-14 | 2019-01-14 |  |  |  | 2019-01-17 |  | Jan-19 | Jan-19 | MW417R002737-AYCA-5HZXRM-2SHA-64-88 Reid Street, Werrington County HFC DFN | Shalvey | 27863.514 |  | 27863.514 | 30649.8654 |  |  | 0 | 27863.514 | 100% | Mark Leal | Direct Award | 2019-01-11 | Mark Leal | Direct Award | 2019-01-11 |  | 2019-03-31 | 79
A417 Greenfield MDU | Central West | Marshell Antonio | Inv 14743 | 2019-02-27 | 2019-01-23 | 2019-01-23 |  |  | 2019-02-06 | 2019-02-26 |  | Jan-19 | Feb-19 | MW417R002662-AYCA-5KEC98-2NMN-20-41 Third Avenue North, Narromine | Narromine | 3730.72 |  | 3730.72 | 4103.792 |  |  | 0 | 3730.72 | 100% |  |  |  | Ertan Cicek | 2019-01-07 | 2019-01-15 |  | 2019-03-13 | 57
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  | 2019-03-06 | 2019-03-08 |  |  | 2019-03-22 | 2019-04-05 |  | Mar-19 | Apr-19 | MW417R002694-AYCA-5FCMYJ-2BAN-60-117 Rookwood Road, Yagoona | Bankstown | 4493.28 |  | 4493.28 | 4942.608 | 2046.14 |  | 2046.14 | 2447.14 | 54.46% |  |  |  | Ertan Cicek | Direct Award | 2019-01-15 |  | 2019-03-28 | 72
A417 HFC DFN | Sydney West | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R002790-AYCA-5QBJSS-2PAR-62-7 Morton Street, Parramatta HFC DFN | Parramatta | 24092.07 |  | 24092.07 | 26501.277 | 1500 |  | 1500 | 22592.07 | 93.77% |  |  |  | Mark Leal | Direct Award | 2019-01-16 |  | 2019-04-15 | 89
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14646 | 2019-01-22 | 2019-01-18 | 2019-01-18 |  |  |  | 2019-01-22 |  | Jan-19 | Jan-19 | MW417R002790-AYCA-5QBJSS-2PAR-62-7 Morton Street, Parramatta HFC DFN | Parramatta | 10325.18 |  | 10325.18 | 33716.65 |  |  | 0 | 10325.18 | 100% |  |  |  | Mark Leal | Direct Award | 2019-01-16 |  | 2019-04-15 | 89
A417 HFC DFN | Sydney West | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R002789-AYCA-53VL4I-2PNN-68-116a-118-castle-hill- HFC DFN | Castle Hill | 38814.94 |  | 38814.94 | 42696.434 | 12281.92 |  | 12281.92 | 26533.02 | 68.36% |  |  |  | Mark Leal | Direct Award | 2019-01-16 |  | 2019-04-15 | 89
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14647 | 2019-01-22 | 2019-01-18 | 2019-01-18 |  |  |  | 2019-01-22 |  | Jan-19 | Jan-19 | MW417R002789-AYCA-53VL4I-2PNN-68-116a-118-castle-hill- HFC DFN | Castle Hill | 16635.1 |  | 16635.1 | 18298.61 |  |  | 0 | 16635.1 | 100% |  |  |  | Mark Leal | Direct Award | 2019-01-16 |  | 2019-04-15 | 89
A401/Greenfield | Sth Coast | Marshell Antonio |  |  | 2019-02-18 | 2019-02-18 |  |  | 2019-03-04 | 2019-03-18 |  | Feb-19 | Mar-19 | MW417R002735-AYCA-5TDBKQ-2EDN-20-44 Hopkins Street, EDEN | Eden | 6815.77 | 2647.61 | 9463.38 | 10409.718 |  |  | 0 | 9463.38 | 100% |  |  |  | Mark Leal | 2019-01-08 | 2019-01-17 |  | 2019-04-01 | 74
A401/Greenfield | Nth Coast | Dane Harrington |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002745-AYCA-5HY3IQ-2KYO-20-Stratheden Street, Kyogle | Kyogle | 10117.98 |  | 10117.98 | 11129.778 |  |  | 0 | 10117.98 | 100% |  |  |  | Mark Leal | 2019-01-08 | 2019-01-17 |  | 2019-04-01 | 74
A417 HFC DFN | Sydney West | Mickey Tran |  |  |  | 2019-02-28 | [5 empty] | Feb-19 | Jan-00 | MW417R002792-AYCA-5JQV6N 2BAN-62-265 Hume Highway, Greenacre HFC DFN-Design NDD | Greenacre | 1640 |  | 1640 | 1804 | 1500 |  | 1500 | 140 | 8.537% |  |  |  | Mark Leal | 2019-01-15 | 2019-01-18 | 3 | 2019-02-11 | 24
A417 HFC DFN | Sydney West | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002899-AYCA-2WNBI8-2PEN-64-31,33,37B Garfield-HFC DFN | Pendale Hill | 43034.404 |  | 43034.404 | 47337.8444 | 24753.26 |  | 24753.26 | 18281.144 | 42.48% |  |  |  | Mark Leal | Direct Award | 2019-01-24 |  | 2019-03-29 | 64
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14684 | 2019-01-31 | 2019-01-25 | 2019-01-25 |  |  |  | 2019-01-31 |  | Jan-19 | Jan-19 | MW417R002899-AYCA-2WNBI8-2PEN-64-31,33,37B Garfield-HFC DFN | Pendale Hill | 18443.316 |  | 18443.316 | 20287.6476 |  |  | 0 | 18443.316 | 100% |  |  |  | Mark Leal | Direct Award | 2019-01-24 |  | 2019-03-29 | 64
A417 Greenfield MDU Transformation | Sydney West | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002878-AYCA-53IJ1X-2PIT-01-21 Hall St Pitt Town Transformation | Pitt Town | 973.92 |  | 973.92 | 1071.312 |  |  | 0 | 973.92 | 100% |  |  |  |  | Direct Award | 2019-01-24 |  | 2019-03-06 | 41
A417 HFC DFN | Sydney Nth | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002898-AYCA-4Y3W7O-2PYM-60-1017 Pacific Hwy, Pymble, HFC DFN | Pymble | 35210.014 |  | 35210.014 | 38731.0154 | 1500 |  | 1500 | 33710.014 | 95.74% |  |  |  | Mark leal | Direct Award | 2019-01-25 |  | 2019-03-29 | 63
A417 HFC DFN Comm | Sydney | Damien Marov | Inv 14685 | 2019-01-31 | 2019-01-29 | 2019-01-29 |  |  |  | 2019-01-31 |  | Jan-19 | Jan-19 | MW417R002898-AYCA-4Y3W7O-2PYM-60-1017 Pacific Hwy, Pymble, HFC DFN | Pymble | 15090.006 |  | 15090.006 | 16599.0066 |  |  | 0 | 15090.006 | 100% |  |  |  | Mark leal | Direct Award | 2019-01-25 |  | 2019-03-29 | 63
A417 HFC DFN | Sydney East | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R002917-AYCA-4LKVQJ - 2ROC-61-551 Gardeners Road -HFC DFN | Rockdale | 33171.719 |  | 33171.719 | 36488.8909 | 9278.24 |  | 9278.24 | 23893.479 | 72.03% |  |  |  | Mark leal | Direct Award | 2019-01-25 |  | 2019-04-15 | 80
A417 HFC DFN Comm | Sydney East | Damien Marov | Inv 14816 | 2019-03-15 | 2019-01-29 | 2019-01-29 |  |  |  | 2019-03-15 |  | Jan-19 | Mar-19 | MW417R002917-AYCA-4LKVQJ - 2ROC-61-551 Gardeners Road -HFC DFN | Rockdale | 14216.451 |  | 14216.451 | 15638.0961 |  |  | 0 | 14216.451 | 100% |  |  |  | Mark leal | Direct Award | 2019-01-25 |  | 2019-04-15 | 80
A417 HFC DFN | Sydney East | Mickey Tran |  |  |  | 2019-01-29 | [5 empty] | Jan-19 | Jan-00 | MW417R002916-AYCA-49ZOSX - 2ROC-60-CIE GROUP HK-HFC DFN | Rockdale | 75390.693 |  | 75390.693 | 82929.7623 | 18197.78 |  | 18197.78 | 57192.913 | 75.86% |  |  |  | Mark leal | Direct Award | 2019-01-25 |  | 2019-04-15 | 80
A417 HFC DFN Comm | Sydney East | Damien Marov | Inv 14817 | 2019-03-14 | 2019-01-29 | 2019-01-29 |  |  |  | 2019-03-14 |  | Jan-19 | Mar-19 | MW417R002916-AYCA-49ZOSX - 2ROC-60-CIE GROUP HK-HFC DFN | Rockdale | 32310.297 |  | 32310.297 | 35541.3267 |  |  | 0 | 32310.297 | 100% |  |  |  | Mark leal | Direct Award | 2019-01-25 |  | 2019-04-15 | 80
A417 Greenfield MDU | ACT | Marshell Antonio |  |  |  | 2019-01-29 | [5 empty] | Jan-19 | Jan-00 | MW417R002927-AYCA-44HH3F-31-9BLC-22-49 Warrego Circuit Kaleen ACT | Kaleen | 1990.1 |  | 1990.1 | 2189.11 |  |  | 0 | 1990.1 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-25 |  | 2019-04-30 | 95
A417 Greenfield MDU | ACT | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002936-AYCA-3L3HR8-9CVI-01-32 Mort St, Braddon, ACT | Braddon | 1115.6 |  | 1115.6 | 1227.16 |  |  | 0 | 1115.6 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-25 |  | 2019-04-17 | 82
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R002945-AYCA-5ANVTS-2MIR-26-293 Port Hacking Rd, Miranda - 1 | Miranda | 1226.04 |  | 1226.04 | 1348.644 |  |  | 0 | 1226.04 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-01-31 |  | 2019-04-18 | 77
A417 HFC DFN | Sydney Nth | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R002938-AYCA-52ZW78-2STL-60-Atchison Street HFC DFN | St Leonards | 7131.2 |  | 7131.2 | 7844.32 | 1500 |  | 1500 | 5631.2 | 78.97% |  |  |  | Ertan Cicek | Direct Award | 2019-01-31 |  | 2019-04-23 | 82
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R002972-AYCA-5WOZHL-2PEN-66--18 Rawson Road, South Wentworthville | Wentworthville | 1966.52 |  | 1966.52 | 2163.172 | 300 |  | 300 | 1666.52 | 84.74% |  |  |  | Ertan Cicek | Direct Award | 2019-02-01 |  | 2019-04-19 | 77
A417 Greenfield MDU | Newcastle | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R002896-AYCA-5NB7OP-2CHL-08-83 Redhead Road, Redhead | Redhead | 6306.89 |  | 6306.89 | 6937.579 |  |  | 0 | 6306.89 | 100% |  |  |  | Ertan Cicek |  | 2019-02-05 |  | 2019-04-17 | 71
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R000326-AYCA-2T05DV-2RCH-04-752 George St South Windsor | Windsor | 1339.96 |  | 1339.96 | 1473.956 |  |  | 0 | 1339.96 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-06-21 |  | 2018-09-14 | 85
A417 Business Segment | Central West | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002948-AYCA-5XOE8H-2ORG-06-4 ELWIN DR, ORANGE | Orange | 16268.92 |  | 16268.92 | 17895.812 |  |  | 0 | 16268.92 | 100% |  |  |  | Dave Yoemans | 2018-12-20 | 2019-02-07 | 49 | 2019-04-09 | 61
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R003005-AYCA-5OO3VM-2WLG-01-2 Victoria Street Wollongong | Wollongong | 1990.11 |  | 1990.11 | 2189.121 |  |  | 0 | 1990.11 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-12 |  | 2019-03-19 | 35
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003051-AYCA-587BWC-2RAM-20-218-222 Railway Parade, Kogarah | Kogarah | 1006.06 |  | 1006.06 | 1106.666 |  |  | 0 | 1006.06 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-12 |  | 2019-04-29 | 76
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003053-AYCA-5FWMQ5 -2WRO-63-14-18 Neringah Avenue South, Wahroonga | Wahroonga | 1611.29 |  | 1611.29 | 1772.419 |  |  | 0 | 1611.29 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-12 |  | 2019-04-29 | 76
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003054-AYCA-4Z8X0L-2COR-07-34-44 Underwood St, Corrimal | Corrimal | 1742.49 |  | 1742.49 | 1916.739 |  |  | 0 | 1742.49 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-14 |  | 2019-04-29 | 74
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003119-AYCA-3G1TZ6-2PYM-62-9-17 Eastern Rd, Turramurra | Turramurra | 3453.05 |  | 3453.05 | 3798.355 |  |  | 0 | 3453.05 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-14 |  | 2019-05-03 | 78
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003106-AYCA-5E4D09-2PEN-01- 2-6 Dolerite Way Pemulwuy Int | Pemulwuy | 856.8 |  | 856.8 | 942.48 |  |  | 0 | 856.8 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-15 |  | 2019-05-31 | 105
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  | 2019-03-18 | 2019-03-18 |  |  | 2019-04-01 | 2019-04-15 |  | Mar-19 | Apr-19 | MW417R003149-AYCA-5V4B6P-2COR-09-53 Russell Street Balgownie Int | Balgownie | 3980.2 |  | 3980.2 | 4378.22 |  |  | 0 | 3980.2 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-19 |  | 2019-05-01 | 71
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  | 2019-02-20 | 2019-02-20 | 2019-02-20 | 2019-02-26 | 2019-03-06 | 2019-03-20 |  | Feb-19 | Mar-19 | MW417R001849 - AYCA-562Y8R - 2APN-01 - 900 Wilton Rd, Appin | Appin | 4527.39 | 19099.377 | 23626.767 | 25989.4437 | 3510.43 |  | 3510.43 | 20116.337 | 85.14% |  |  |  | Mark Leal | 2018-10-15 | 2018-11-08 | 24 | 2019-01-01 | 54
Minor Works Maximo | Sth NSW | Marshell Antonio |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | ND-2KRG-03-AYCA-2GRL7A-Tatton 12B-Estate | Tatton | 3529.87 |  | 3529.87 | 3882.857 |  |  | 0 | 3529.87 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-27 |  | 2019-06-01 | 94
Minor Works Maximo | Newcastle | Mickey Tran |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | 2NAB-20-AYCA-5KDV96-43,45,47,49 Eastern Valley Way, Tallwood-FTTN | Tallwood | 11768.29 |  | 11768.29 | 12945.119 |  |  | 0 | 11768.29 | 100% | [7 empty] | 2019-06-01 | 43617
Minor Works Maximo | Sydney Sth | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | ND-2BRG-01-AYCA-4Z5838-10 & 20 Seventeenth Ave, Austral - 2 | Austral | 2307.6 |  | 2307.6 | 2538.36 |  |  | 0 | 2307.6 | 100% |  |  |  |  | Direct Award | 2019-03-04 |  | 2019-04-30 | 57
Minor Works Maximo | Sth Coast | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | ND-2DAP-02-AYCA-5XRS1Z-7-9 Princes Highway, Dapto - 1- TTFN | Dapto | 1656.01 |  | 1656.01 | 1821.611 |  |  | 0 | 1656.01 | 100% |  |  |  |  | Direct Award | 2019-02-21 |  | 2019-05-14 | 82
A417 Business Segment | Sydney Nth | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003296-2PNN-62-AYCA-5V8GGB-70 YARRARA RD, PENNANT HILLS | Pennant Hills | 7526.78 |  | 7526.78 | 8279.458 | 859.38 |  | 859.38 | 6667.4 | 88.58% |  |  |  | Dave Yoemans | 2019-02-18 | 2019-02-27 | 9 | 2019-05-01 | 63
A417 Business Segment | Sydney Nth | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003298-2PNN-60-AYCA-5V8GAT-1A DARTFORD RD, THORNLEIGH | Thornleigh | 10927.04 |  | 10927.04 | 12019.744 |  |  | 0 | 10927.04 | 100% |  |  |  | Dave Yoemans | 2019-02-18 | 2019-02-26 | 8 | 2019-05-01 | 64
A417 Business Segment | Sydney Nth | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003299-2PNN-60-AYCA-5V8GEZ-31-33 SEFTON RD, THORNLEIGH | Thornleigh | 8156.46 |  | 8156.46 | 8972.106 | 1405.52 |  | 1405.52 | 6750.94 | 82.77% |  |  |  | Dave Yoemans | 2019-02-18 | 2019-02-26 | 8 | 2019-05-01 | 64
A417 Greenfield MDU | ACT | Marshell Antonio |  |  | 2019-03-08 | 2019-03-08 | 2019-03-08 |  | 2019-03-22 | 2019-04-05 |  | Mar-19 | Apr-19 | MW417R003254-AYCA-5LTSYB-9BLC-20-12 Shumack Street Weetangera ACT Int | Weetangera | 2388.13 |  | 2388.13 | 2626.943 |  |  | 0 | 2388.13 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-21 |  | 2019-06-01 | 100
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003339-AYCA-4XC850-2PTH-05-50-54 Rodley Ave, Penrith | Penrith | 528.9 |  | 528.9 | 581.79 | 300 |  | 300 | 228.9 | 43.28% |  |  |  | Ertan Cicek | Direct Award | 2019-02-22 |  | 2019-05-09 | 76
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003220-AYCA-4WLRNG-2ROU-03-51-53 Foxall road,Kellyville | Kellyville | 1187.6 |  | 1187.6 | 1306.36 |  |  | 0 | 1187.6 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-22 |  | 2019-06-01 | 99
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R003241-AYCA-52CPTI-2HOR-63--6-8 Cowan Rd, Mount Colah | Mount Colah | 4495.32 |  | 4495.32 | 4944.852 |  |  | 0 | 4495.32 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-22 |  | 2019-04-10 | 47
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003248-AYCA-5QX4TH-2EAS-60-164 Cathedral Street, Woolloomooloo | Woolloomooloo | 2211.62 |  | 2211.62 | 2432.782 |  |  | 0 | 2211.62 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-22 |  | 2019-05-15 | 82
A417 HFC DFN | Sydney Nth | Mickey Tran |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003233-AYCA-4ZHXIF-2KIL-62-8 Buckingham-HFC DFN | Killara | 52009.209 |  | 52009.209 | 57210.1299 |  |  | 0 | 52009.209 | 100% |  |  |  | Mark Leal | Direct Award | 2019-02-22 |  | 2019-06-01 | 99
A417 HFC DFN Comm | Sydney Nth | Mickey Tran | Inv 14786 | 2019-03-06 | 2019-03-04 | 2019-03-04 |  |  |  | 2019-03-07 |  | Mar-19 | Mar-19 | MW417R003233-AYCA-4ZHXIF-2KIL-62-8 Buckingham-HFC DFN | Killara | 22289.661 |  | 22289.661 | 24518.6271 |  |  | 0 | 22289.661 | 100% |  |  |  | Mark Leal | Direct Award | 2019-02-22 |  | 2019-06-01 | 99
A417 HFC DFN | Sydney Sth | Mickey Tran |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003246-AYCA-5SPCV6-2BOT-61-51 Chester Avenue Maroubra HFC DFN | Maroubra | 65302.692 |  | 65302.692 | 71832.9612 | 1500 |  | 1500 | 63802.692 | 97.7% |  |  |  | Mark Leal | Direct Award | 2019-02-22 |  | 2019-06-01 | 99
A417 HFC DFN Comm | Sydney Sth | Mickey Tran | Inv 14787 | 2019-03-07 | 2019-03-04 | 2019-03-04 |  |  |  | 2019-03-07 |  | Mar-19 | Mar-19 | MW417R003246-AYCA-5SPCV6-2BOT-61-51 Chester Avenue Maroubra HFC DFN | Maroubra | 27986.868 |  | 27986.868 | 30785.5548 |  |  | 0 | 27986.868 | 100% |  |  |  | Mark Leal | Direct Award | 2019-02-22 |  | 2019-06-01 | 99
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003284-AYCA-5T15312-NEW-60-293 Princes Highway, Saint Peters | St Peters | 662.58 |  | 662.58 | 728.838 |  |  | 0 | 662.58 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-22 |  | 2019-05-13 | 80
A417 Greenfield MDU Transformation | Sydney CBD | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003224-AYCA-5G1AHP-2RED-01-2-14 Amelia Street, Waterloo Transformation | Waterloo | 1472.75 |  | 1472.75 | 1620.025 | 650 |  | 650 | 822.75 | 55.86% |  |  |  | Ertan Cicek | Direct Award | 2019-02-25 |  | 2019-04-10 | 44
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  | 2019-03-18 | 2019-03-18 |  |  | 2019-04-01 | 2019-04-15 |  | Mar-19 | Apr-19 | MW417R003247-AYCA-5V4B6P-2COR-09-53 Russell Street, Balgownie Ext | Balgownie | 6205.77 |  | 6205.77 | 6826.347 |  |  | 0 | 6205.77 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-25 |  | 2019-05-15 | 79
A417 Greenfield MDU | Sth Coast | Marshell Antonio |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003204-AYCA-4Q4RLG-2NRN-01-MacArthur Rd Spring Farm | Spring Farm | 1040.04 |  | 1040.04 | 1144.044 |  |  | 0 | 1040.04 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-25 |  | 2019-06-01 | 96
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003294-AYCA-2HEWWI-2CAM-02-337-339 Beamish Street, Campsie | Campsie | 739.75 |  | 739.75 | 813.725 | 300 |  | 300 | 439.75 | 59.45% |  |  |  | Ertan Cicek | Direct Award | 2019-02-25 |  | 2019-05-13 | 77
A417 HFC DFN | Sydney Sth | Mickey Tran |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003230-AYCA-5MELWX-2BOT-62-Lot 3,4,5 & 6 Denison Street Banksmeadow HFC DFN | Banksmedow | 25782.008 |  | 25782.008 | 28360.2088 | 1500 |  | 1500 | 24282.008 | 94.18% |  |  |  | Mark Leal | Direct Award | 2019-02-25 |  | 2019-06-01 | 96
A417 HFC DFN Comm | Sydney Sth | Mickey Tran | Inv 14801 | 2019-03-14 | 2019-03-05 | 2019-03-05 |  |  |  | 2019-03-14 |  | Mar-19 | Mar-19 | MW417R003230-AYCA-5MELWX-2BOT-62-Lot 3,4,5 & 6 Denison Street Banksmeadow HFC DFN | Banksmedow | 11049.432 |  | 11049.432 | 12154.3752 |  |  | 0 | 11049.432 | 100% |  |  |  | Mark Leal | Direct Award | 2019-02-25 |  | 2019-06-01 | 96
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003288 - AYCA-5L1XWG - 2LIV-67 - 365 Hume Highway, Liverpool | Liverpool | 800.08 |  | 800.08 | 880.088 |  |  | 0 | 800.08 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-25 |  | 2019-05-13 | 77
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003328-AYCA-4W57Z3 -2BAN-64-11+17 Cross St Bankstown | Bankstown | 1178.5 |  | 1178.5 | 1296.35 |  |  | 0 | 1178.5 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-25 |  | 2019-05-10 | 74
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003326-AYCA-5JO5XA-2BAN-70-5-9 White Avenue, Bankstown - 1 | Bankstown | 1478.7 |  | 1478.7 | 1626.57 |  |  | 0 | 1478.7 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-25 |  | 2019-05-10 | 74
A417 Greenfield MDU | Sydney Nth | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003287-AYCA-4KZ9TH-2HOR-62-457-459 Pacific Highway, Asquith | Asquith | 789.4 |  | 789.4 | 868.34 |  |  | 0 | 789.4 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-25 |  | 2019-05-13 | 77
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003285-AYCA-5NKJJY-2CRO-24-25 Judd Street, Cronulla | Cornulla | 1943.76 |  | 1943.76 | 2138.136 |  |  | 0 | 1943.76 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-25 |  | 2019-05-13 | 77
NBN FttC MDUs | Nth Coast | Rob Panovski |  |  | 2019-03-14 | 2019-03-15 |  |  | 2019-03-29 | 2019-04-12 |  | Mar-19 | Apr-19 | MW417R003263-2SWR-20-South West Rock | South West Rocks | 6176 |  | 6176 | 6793.6 | 1085.95 |  | 1085.95 | 5090.05 | 82.42% |  |  |  | Greg Moeller | Direct Award | 2019-02-26 |  | 2019-03-19 | 21
Minor Works Maximo | Sth NSW | Marshell Antonio |  |  |  | 2019-05-01 | [5 empty] | May-19 | Jan-00 | 2KRG-03-AYCA-58NL54 | Koringal | 0 |  | 0 | 0 | 1150 |  | 1150 | -1150 | #DIV/0! |  |  |  | Richard Huffidine
NBN FttC MDUs | Nth Coast | Rob Panovski |  |  | 2019-03-14 | 2019-03-15 |  |  | 2019-03-29 | 2019-04-12 |  | Mar-19 | Apr-19 | MW417R003266-2WRD-20-Warialda | Warrialda | 4427 |  | 4427 | 4869.7 | 1168.95 |  | 1168.95 | 3258.05 | 73.59% |  |  |  | Greg Moeller | Direct Award | 2019-02-27 |  | 2019-03-19 | 20
NBN FttC MDUs | Sth Coast | Rob Panovski |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R003265-2TUH-20-MELLAR | Tursso Heads | 11702 |  | 11702 | 12872.2 |  |  | 0 | 11702 | 100% |  |  |  | Greg Moeller | Direct Award | 2019-02-27 |  | 2019-03-19 | 20
NBN FttC MDUs | Nth Coast | Rob Panovski |  |  | 2019-03-14 | 2019-03-15 |  |  | 2019-03-29 | 2019-04-12 |  | Mar-19 | Apr-19 | MW417R003264-2TTF-20-MELLAR NPDL-Tenterfield | Tenterfield | 6653 |  | 6653 | 7318.3 | 1600.55 |  | 1600.55 | 5052.45 | 75.94% |  |  |  | Greg Moeller | Direct Award | 2019-02-27 |  | 2019-03-19 | 20
NBN FttC MDUs | Sth Coast | Rob Panovski |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R003262-2MYA-01-MELLAR NPDL-Moruya | Morouya | 15995 |  | 15995 | 17594.5 |  |  | 0 | 15995 | 100% |  |  |  | Greg Moeller | Direct Award | 2019-02-27 |  | 2019-03-19 | 20
NBN FttC MDUs | Newcastle | Rob Panovski |  |  | 2019-03-14 | 2019-03-15 |  |  | 2019-03-29 | 2019-04-12 |  | Mar-19 | Apr-19 | MW417R003261-2KRI-01-MELLAR NPDL_MWR (A417) | Kurri Kurri | 6653 |  | 6653 | 7318.3 |  |  | 0 | 6653 | 100% |  |  |  | Greg Moeller | Direct Award | 2019-02-27 |  | 2019-03-19 | 20
NBN FttC MDUs | Nth Coast | Rob Panovski |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R003260-2DRG-20-MELLAR NPDL-Dorrigo- | Dorrigo | 12497 |  | 12497 | 13746.7 | 2197.3 |  | 2197.3 | 10299.7 | 82.42% |  |  |  | Greg Moeller | Direct Award | 2019-02-27 |  | 2019-03-19 | 20
A417 Greenfield MDU | Newcastle | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003363- AYCA-52924C-2TRT-24-38 French Rd, Wangi Wangi | Wangi Wangi | 1316.22 |  | 1316.22 | 1447.842 |  |  | 0 | 1316.22 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-28 |  | 2019-05-10 | 71
A417 Greenfield MDU Transformation | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003366-AYCA-4QNRBL-2KEL-03-822 Windsor Road Rouse Hill Transformation | Rouse Hill | 881.93 |  | 881.93 | 970.123 | 650 |  | 650 | 231.93 | 26.3% |  |  |  | Ertan Cicek | Direct Award | 2019-02-28 |  | 2019-05-10 | 71
A417 HFC DFN | Sydney Nth | Mickey Tran |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003379-AYCA-4HLUIU-2PYM-62-1454 Pacific Hwy Turramurra HFC DFN | Turramurra | 31179.281 |  | 31179.281 | 34297.2091 | 1500 |  | 1500 | 29679.281 | 95.19% |  |  |  | Mark Leal | Direct Award | 2019-02-25 |  | 2019-06-01 | 96
A417 HFC DFN Comm | Sydney Nth | Mickey Tran | Inv 14802 | 2019-03-14 | 2019-03-09 | 2019-03-09 |  |  |  | 2019-03-14 |  | Mar-19 | Mar-19 | MW417R003379-AYCA-4HLUIU-2PYM-62-1454 Pacific Hwy Turramurra HFC DFN | Turramurra | 13362.549 |  | 13362.549 | 14698.8039 |  |  | 0 | 13362.549 | 100% |  |  |  | Mark Leal | Direct Award | 2019-02-25 |  | 2019-06-01 | 96
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003367-AYCA-4RS6QG-2KNS-03-William Street Alexandria | Alexandria | 10719.51 |  | 10719.51 | 11791.461 |  |  | 0 | 10719.51 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-02-28 |  | 2019-05-10 | 71
A417 Greenfield MDU Transformation | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003365-AYCA-4F75OS-2BLK-12-66-68 Cambridge St, Blacktown Transformation | Blacktown | 363.5 |  | 363.5 | 399.85 | 650 |  | 650 | -286.5 | -78.82% |  |  |  | Ertan Cicek | Direct Award | 2019-02-28 |  | 2019-05-10 | 71
A401/Greenfield | Sth Coast | Marshell Antonio |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003243-AYCA-5WHZHM-2SUX-01-Jacobs Dr Sussex-NSB | Sussex Inlet | 1961 |  | 1961 | 2157.1 |  |  | 0 | 1961 | 100% |  |  |  | Mark Leal | 2019-02-21 | 2019-02-28 | 7 | 2019-06-01 | 93
A401/Greenfield | Nth Coast | Mickey Tran |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002747-AYCA-5FJLCJ-2KMS-20-476 Macleay Valley Way, South Kempsey | South Kempsey | 17140.81 |  | 17140.81 | 18854.891 | 7685.34 |  | 7685.34 | 9455.47 | 55.16% |  |  |  | Mark Leal | 2019-01-07 | 2019-01-23 | 16 | 2019-10-01 | 251
A417 Greenfield MDU | ACT | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003355-AYCA-5O866G-9CVI-22-113 Dooring Street, Dickson | Dickson | 2918.46 |  | 2918.46 | 3210.306 |  |  | 0 | 2918.46 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-03-01 |  | 2019-05-10 | 70
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003370-AYCA-5LZJ26-2BAN-70-72 Canterbury Road, Bankstown | Bankstown | 1655.36 |  | 1655.36 | 1820.896 |  |  | 0 | 1655.36 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-03-01 |  | 2019-05-10 | 70
A417 Greenfield MDU | Sydney CBD | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003418 - AYCA-5EJRTN - 2CAM-02 - 31-31A Perry St, Campsie | Campsie | 453.66 |  | 453.66 | 499.026 |  |  | 0 | 453.66 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-03-01 |  | 2019-06-01 | 92
A417 Greenfield MDU Transformation | Sydney West | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003415 - AYCA-5IOF6P - 2BAN-60 - 120 Hume Highway, Chullora Transformation | Chullora | 2661.23 |  | 2661.23 | 2927.353 |  |  | 0 | 2661.23 | 100% |  |  |  | Ertan Cicek | Direct Award | 2019-03-01 |  | 2019-06-01 | 92
A401/Greenfield | Nth Coast | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R002892-AYCA-45502V-2CTW-20-127 Prince St Clarence Town | Clarence Town | 5886.29 |  | 5886.29 | 6474.919 |  |  | 0 | 5886.29 | 100% |  |  |  | Mark Leal | 2019-01-24 | 2019-03-07 | 42 | 2019-09-23 | 200
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003487-AYCA-57OBUB-2RAM-63-399-403 Princes Hwy, Carlton | Carlton | 9565.27 |  | 9565.27 | 10521.797 |  |  | 0 | 9565.27 | 100% |  |  |  | Mark Leal |  |  |  |  | 0
A417 Greenfield MDU | Nth Coast | Dane Harrington |  |  |  | 2019-03-30 | [5 empty] | Mar-19 | Jan-00 | MW417R002554 - AYCA-5M84RG - 2CFS-02 - 72 Boultwood Street, Coffs Harbour | Coffs Harbour | 1098.34 |  | 1098.34 | 1208.174 | 632.75 |  | 632.75 | 465.59 | 42.39% |  |  |  | Ertan Cicek | Direct Award | 2018-12-12 |  | 2019-02-27 | 77
A417 Greenfield MDU | Sydney Sth | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | MW417R003422-AYCA-63B4XW-2MIR-27-65A PARTHENIA ST, DOLANS BAY | Dolans Bay | 12234.39 |  | 12234.39 | 13457.829 |  |  | 0 | 12234.39 | 100% |  |  |  | Mark Leal | 2019-03-05 | 2019-03-12 | 7 | 2019-04-22 | 41
A417 Greenfield MDU | Sydney West | Dane Harrington |  |  |  | 2019-06-30 | [5 empty] | Jun-19 | Jan-00 | MW417R003508-AYCA-2LID-07-5K1HTP-18 Gibbons Street, Auburn | Auburn | 1374.96 |  | 1374.96 | 1512.456 |  |  | 0 | 1374.96 | 100% |  |  |  | Ertan Cicek | Direct Award | 2018-12-12 |  | 2019-06-01 | 171
Minor Works Maximo Comm | Newcastle | Mickey Tran | Inv 14789 | 2019-03-06 | 2019-03-06 | 2019-03-06 |  |  |  | 2019-03-07 |  | Mar-19 | Mar-19 | 2NAB-20-AYCA-5KDV96-43,45,47,49 Eastern Valley Way, Tallwood-FTTN | Tallwood | 5043.55 |  | 5043.55 | 5547.905 |  |  | 0 | 5043.55 | 100% |  |  |  | Ertan Cicek | Direct Award
A401/Greenfield | Nth Coast | Mickey Tran |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R003080-AYCA-5PAIM1-2CHL-073 Jarrod Close, Charlestown | Charlestown | 4049.06 |  | 4049.06 | 4453.966 |  |  | 0 | 4049.06 | 100% |  |  |  | Mark leal | 2019-02-13 | 2019-03-13 | 28 | 2019-04-01 | 19
A401/Greenfield | Sth NSW | Marshell Antonio |  |  |  | 2019-04-30 | [5 empty] | Apr-19 | Jan-00 | MW417R002994-AYCA-3R9RDG-2GLB-04-193 & 205 Wheeo Road Goulburn | Goulburn | 11164.4 |  | 11164.4 | 12280.84 |  |  | 0 | 11164.4 | 100% |  |  |  | Mark leal |  | 2019-02-01
Minor Works Maximo |  | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | ND-2BUP-05-AYCA-5KIM5I-19 Clarence Street, Lake Munmorah-Estate+TTFN | Lake Munmorah | 2642.39 |  | 2642.39 |  |  |  | 0 | 2642.39 | 100%
Minor Works Maximo |  | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | ND-2GLB-04-AYCA-5T6RSW-Clinton Street, Goulburn - 1 | Goulburn | 10171 |  | 10171 |  |  |  | 0 | 10171 | 100%
Minor Works Maximo |  | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | ND-2GOS-20-AYCA-5OJCT8-Lot 51,155 Woy Woy Road Kariong NSW-Estate+TTFN | Karriong | 8931.74 |  | 8931.74 |  |  |  | 0 | 8931.74 | 100%
Minor Works Maximo |  | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | ND-2MSV-02-AYCA-5NR7GA-Non Standard Build - 12 Berrima Road, Mo-Estate+TTFN | Moss Val | 7156.36 |  | 7156.36 |  |  |  | 0 | 7156.36 | 100%
Minor Works Maximo |  | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | ND-2SHH03-AYCA-5V8X5D-TECH CHOICE-1 Arcadia Street Warilla | Warilla | 8769.04 |  | 8769.04 |  |  |  | 0 | 8769.04 | 100%
Minor Works Maximo |  | Marshell Antonio |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | ND-2YON-02-AYCA-5HUUR7-5 Forsythe Avenue, Young -1-FTTN | Young |  |  | 0 |  |  |  | 0 | 0 | #DIV/0!
Minor Works Maximo HFC DFN |  | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | ND-2KNS-62-AYCA-5E2I7I-4-6 Grosvenor St, Kensington - 1-HFC-DFN | Kensington | 2920.97 |  | 2920.97 |  | 1500 |  | 1500 | 1420.97 | 48.65% |  |  |  | Mark leal | Direct Award | 2019-03-15
Minor Works Maximo Transformation |  | Mickey Tran |  |  |  | 2019-05-30 | [5 empty] | May-19 | Jan-00 | ND-2ASH-62-AYCA-5ZUB5A-Cardinal Freeman Village-3B-TTFN | Ashfield
[16 empty] | 4650055.7923 | 4410820.0787 | 9060875.8711 | 9968273.4152 | 3769215.6938 | 162369.7728 | 3917217.3666 | 5143658.5045 | 69.48%
#REF!
Formulas:
PC Due = [PC Request Date Submitted]+14
PC Due = [Variation Request submitted]+14
Date Expected Payment = [PC Request Date Submitted]+14
Payment Date = [PC Due]+14
Payment Date = [Variation Approval]+14
Customer required date = [Project Quote Submitted]+(12*7)
Note on Y55: Damien Marov: Variation booked to another project
Note on R91: Damien Marov: Includes the following Ertan Projects in the variation. Ertan - AYCA-4GJAAH - MEZZO, 87 Bay Street, Glebe - SP2 - Faulty PON Ertan - AYCA-4RB8MD-2 Clarke St, Berala Ertan - AYCA-5576QH - Wamerbal Ertan - AYCA-5576QH-3 GHERSI
Note on V178: Damien Marov: Brendan and Alex half a day
Note on V218: Damien Marov: Brendan wages 3 days $910 @ $28 per hour for 32 .5 hrs. Alex Jones: $715 wages Vehicle cost $255 TA $720 Test Equipment $255 Fuel $150
Note on O244: Damien Marov:
Note on V301: Damien Marov: Brendan and Alex 14.5 hr day on the 6/9/18 and tehn 4 hrs travel on the 7/9/19
Note on V302: Damien Marov: Karsten and Bassam by 8 days at 2hrs OT per day
Note on V304: Damien Marov: Brendan and Alex for 3 hrs each
Note on R339: Damien Marov: Additionlal flushes Afetr Hours work for haulers Altus traffic control
Note on V366: Damien Marov: Phil for the day + 1 hr to install Earthing for Mak Leal> need toa dd Brnedan's time in this as well..
Note on V384: Damien Marov: Karsten and Bassam 9hr day and Brendan and Alex normal day each
Note on V417: Damien Marov:
Note on V453: Damien Marov: Greg and Phil there for 3 days, Karsten and Bass there for 1 night
Note on R495: Damien Marov: LASA component