## Datateks
RequestID | Application Name | Project Type | Build Type | FSAM | NBN PM | EFSCD | EFSCD by Month | Project Leader | Project Status | Site Contact | Lead-in Ready | Comms Room Ready | Internal Pathway Ready | Test & Coiled | LAAN Commence | FORECAST DESIGN SUBMISSION | ACTUAL DESIGN SUBMISSION | FORECAST CONSTRUCTION START | ACTUAL CONSTRUCTION START | FORECAST: CONSTRUCTION COMPLETE | WS 18/02/2019 | WS 25/02/2019 | WS 04/03/2019 | WS 11/03/2019 | ACTUAL: CONSTRUCTION COMPLETE | Actual: Construction Complete by Month | Follow up Date | Comments: | FORECAST: PC SUBMIT | WS 24/09/18 | WS 01/10/18 | WS 08/10/2018 | WS 15/10/2018 | ACTUAL: PC SUBMIT | Actual PC Submit by Month | Comments:
AYCA-117I3H | 34 Station Street Schofields | SDU | FTTP – Type 2 | 2RIV-01 | Andrew Mahasay | #N/A | #N/A |  | Completed | [10 empty] | 2018-05-22 |  |  |  |  | 2018-05-22 | May-18 |  |  | 2018-05-24 |  |  |  |  | 2018-05-24 | May-18
AYCA-1L7010 | 18 Harrow Road - Mixed Use Development - Tower A and B | MDU Externals | FTTP – Type 2 | 2LID-08 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-09-07 |  |  |  |  | 2018-09-04 | Sep-18 |  | 18/05 - Internal PDH Dependent - waiting on PDH 06/08 - No change 10/08- Ertan advises PDH to be installed late August | 2018-09-12 |  |  |  |  | 2018-05-09 | May-18
AYCA-1SQ3K5 | Macquarie St - 1, 189 Macquarie St | MDU Externals | FTTP – Type 2 | 2PAR-01 | Ertan Cicek | 2019-02-28 | Feb-19 | Dane | Heritage Delay |  | X | X | X | [6 empty] | TBC | [7 empty] | On hold per Heritage issue 26/07: No change 03/08 - no change 25/10- NBN to meet with council next week 06/12- Soon to commence 28/03- Hauling and splicing remaining, waiting for LAANs 28/05- Waiting for new LAANs to haul and splice 31/05- No change | TBC
AYCA-1WRX9J | 20 Foxall Road - 2 | SDU | FTTP - Type 2 | 2ROU-03 | Mark Leal | #N/A | #N/A |  | Completed | [5 empty] | 2018-09-06 |  |  |  |  | 2018-09-14 |  |  |  |  | 2018-09-03 | Sep-18 |  | 31/08 - Require site visit - check road crossings if linked and FDH pon patching only | 2018-09-05 |  |  |  |  | 2018-09-07 | Sep-18
AYCA-21PVTM | 5 Second Avenue | MDU Externals | FTTP – Type 2 | 2BLK-03 | Ertan Cicek | 2019-04-06 | Apr-19 | Dane | Developer Delay | Moey 04 811 949 66 | TBC | TBC | TBC | [6 empty] | TBC | [6 empty] | 2019-01-07 | 06/07 foreman thinks he will start building comms room next week, pathway not started, he is unsure of LIC location and needs to speak with electrician. contact Moey 0481194966. 17/07- Could not contact developer 18/07- Developer advised call in another two weeks 03/08- Developer advised call in another 2 weeks 23/08- Developer advises atleast another 2 weeks. 05/09- Unable to contact 07/09 - Another 2 weeks 21/09 - Developer confirmed will be ready by 16/10 19/10- Unable to contact 14/03- Unable to contact 28/03- Requested alternate contact, developer being non-responsive | TBC
AYCA-33L9HP | Restwell & Leonard St | MDU Externals | FTTP – Type 3 (MT-LFN) | 2BAN-64 | Ertan Cicek | #N/A | #N/A | Dane | Developer Delay |  | X | X | X | [6 empty] | TBC | [7 empty] | 29/06 - Site not ready, still few months out per dev from 04/05. 6 pit require upgrade, badly damage and requires to be linked up. Follow up required 26/07: No change 03/08 - no change 15/08- Requires follow up 31/08 - Advised site lead-in will be ready to commence WS 03/09. Require to confirm Monday. Splicing schedule WS 10/09 07/09 - Scheduled civils WS 10/09 and splicing later in week 14/09 - Concrete slab, no structure... postponed by dev 09/11- likely to be terminated 16/11- Still awaiting a response from Ertan 22/11- On hold 14/03- Project possibly terminated, waiting for confirmation | 2018-09-19 |  | X
AYCA-24QAXK | 10 Martin Avenue, Arncliffe | MDU Externals | FTTP – Type 2 | 2ROC-03 | Ertan Cicek | 2019-05-10 | May-19 | Dane | Completed |  | X | X | X | [6 empty] | TBC | [7 empty] | 06/07 - Waiting for PDH Installation to complete haul, hauled to lead-in pit 26/07: No change 03/08 - no change | 2019-01-05 |  |  |  |  | 2019-01-05
AYCA-35DF0W | 1A & 1B President Road | MDU Externals | FTTP – Type 2 | 2KEL-07 | Ertan Cicek | #N/A | #N/A | Dane | Developer Delay | [10 empty] | TBC | [7 empty] | 06/07 - Site fenced with no building, base or structure per visit 04/04. Not ready. Incorrect EFSCD 16/07 - RRP and hauled cable from A END up to lead-in pit outside, left 100m coil for internal haul. 26/07: No change 03/08 - no change 28/03- Project on hold | TBC
AYCA-2CVKCU | 60 Wallgrove Road Eastern Creek | SDU | FTTP - Type 2 |  | Andrew Mahasay | #N/A |  |  | Completed | [10 empty] | 2018-05-28 |  |  |  |  | 2018-05-28 | May-18 |  |  | 2018-05-30 |  |  |  |  | 2018-05-30 | May-18
AYCA-2EBL4P | 7-15 Conder Street | MDU Externals | FTTP – Type 2 |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-04-27 |  |  |  |  | 2018-04-26 | Apr-18 |  |  | 2018-05-01 |  |  |  |  | 2018-04-29 | Apr-18
AYCA-2HEWWI | 337-339 Beamish Street, Campsie, NSW 2194 | MDU Externals | FTTP - Type 2 | 2CAM-02 | Ertan Cicek | 30/04/2019 |  | Dane | Completed | [5 empty] | 18/03/2019 | [12 empty] | 12/03- Developer has installed lead in not to depth 22/03- Scheduled for splicing WS 01/04 | [5 empty] | 2019-10-04
AYCA-4SBJVB | 9-11 SWINSON ROAD BLACKTOWN, NSW 2148 | MDU | FTTP- Type 2 | 2BLK-01 | Ertan Cicek | #N/A |  | Dane | Site Visit | [18 empty] | 15/04- Site not even demolished yet
AYCA-52UVXU | The Christian, Strathfield South | MDU | FTTP- Type 2 | 2HOM-20 | Ertan Cicek | #N/A |  | Dane | Site Visit | 0401 957 310 |  |  |  |  | 21/12/2018 | [12 empty] | 11/12- Dependent project in service date 29/03/2019 02/03- Civils complete, waiting on A end 28/05- PC pushed to mid June for dependent site
AYCA-2LIFV6 | 4 Stringer Road | SDU |  |  | Andrew Mahasay | #N/A |  |  | Completed | [10 empty] | 2018-05-04 |  |  |  |  | 2018-05-04 | May-18 |  |  | 2018-05-04 |  |  |  |  | 2018-05-04 | May-18
AYCA-2M3M8J | 72-84 Empire Circuit, Penrith, NSW 2750 | MDU | FTTP - Type 2 | 2PTH-05 | Ertan Cicek | #N/A |  | Dane | Completed | Andrew 0409 696 964 | X | X | X |  | Waived |  |  |  |  | 2018-07-12 | X |  |  |  | 2018-12-03 |  |  | 26/10- Need to attend site again once developer moves spoil to prove road crossing. Likely to drop a pit over existing in front of development 08/11- Scheduled for Monday 16/11- LAANs submitted, waiver applied for 01/12- Amy Dunbar 047327958 0402105874amy.dunbar@penrith.city | 2018-07-12 |  |  |  |  | 2018-12-05
AYCA-2Q0B3G | 148-150 Great Western Hwy, Westmead, NSW, 2145 | MDU Externals | FTTP – Type 2 | 2PAR-63 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-08-17 |  |  |  |  | 2018-08-17 | Aug-18 | 2018-08-03 | 06/07 - Cancelled due to condition of lead-in, scaffold in the way. Waiting for dev to remove scaffolding before lead-in complete. Should be within 2 weeks from 29/06 12/07- Developer has not answered phone calls the last 2 attempts 13/07- Developer still not answering or returning calls 17/07 - Developer advises scaff down early next week and will call as soon as it happens 24/07- Developer has pushed out the end date again. could not give me a time frame 26/07: scaffolding should be down end of this week. Waiting for contact from the developer. assuming start construction 01/08 27/07- ROL extended 02/08 - no change. waiting for developer to give us confirmation 09/08- Developer double booked work in our area, could not start civils until lunch time 10/08- Splicing scheduled week starting 13/08 15/08- Developer renigged on parking access, further delay for splicing | 2018-08-22 |  |  |  |  | 21/08/2018 | Aug-18
AYCA-2RG791 | 15-19 Toongabbie Rd , Toongabbie, NSW, 2146 - Mixed used | MDU Externals | FTTP- Type 2 | 2PEN-61 | Ertan Cicek | 2019-01-19 |  | Dane | Completed |  | X | X | X |  | 2018-10-22 |  |  |  |  | TBC | [7 empty] | 19/09- Dependant on Visionstream project. with EFSCD 28/09/2018 20/09 - Emailed Ertan regarding dependency site, ordered materials 26/09 - Issue with dependency site, Ertan requested to tap from different A END 04/10 - Require new materials ordered, LAANs start 22/10 05/10 - Ordered materials additional due to new scope plus LAANs commencement 22/10 25/10- Give Ertan dates as soon as we RRP 09/11- Cables hauled, DJL installed, waiting on NBN confirmation of CTL location, and what to do about lead in installed by developer 15/11- No change, Advised to leave pit as is 22/11- Internal contract not yet released. 29/11- ETA for internals 2 weeks 14/12- Internals complete 18/01- Complete, pending new workbook | TBC |  |  |  |  | 22/01/2019
AYCA-26L0VY | LOT 20 Caddies Boulevard Rouse Hill, NSW 2155 | MDU Externals | FTTP - Type 2 | 2ROU-02 | Ertan Cicek | 2020-11-04 |  | Dane | Site Visit | [5 empty] | 17/05/2019 | [12 empty] | 08/05- Council response to LAANs stipulates need ROL, not give out until after 31st July.
AYCA-2V9V2D | 2 Cowan Road & 540A-542 Pacific Highway, Mount Colah, 2079 | New Devs - MDU | FTTP - Type 2 | 2HOR-63 | Ertan Cicek | 29/03/2019 | Mar-19 | Dane | Completed | Michael 0417 415 337 | TBC | TBC | TBC |  | 2018-01-08 |  |  |  |  | TBC | X | [6 empty] | 06/07 - Ordered materials, require site visit 26/07: No change 03/08 - no change 12/10- Developer will contact next week with a progress update 18/10- Developer advises hopefully ready in two weeks. follow up next friday 25/10- Still not ready advised to call back tomorrow for update 26/10- Unable to contact 08/11- Still a while away from internal pathways being ready 14/12- Scope first week back next year to organise lead in with developer 18/01- Civils complete 15/02- Scheduled week starting 18/02 01/03 - Booked in Monday 04/03 for hauling alt. route, splicing all ready after | [5 empty] | 17/03/2019
AYCA-2XJBL7 | 3 Olympic Blvd Sydney Olympic Park | MDU Externals | FTTP – Type 3 (MT-LFN) | 2SIL-02 | Ertan Cicek | 2019-01-18 | Jan-19 | Dane | Completed |  | X | X | X |  | 20/06/2018 |  |  |  |  | 2018-07-12 | X |  |  |  | 2018-10-12 |  |  | 06/07 - Advised by developer site not ready till 2 months away from 20/06. 26/07: Follow up on the 20th of August 03/08 - no change 23/08- Unable to contact 30/08- Awaiting SOPA permits, will schedule as soon as received - submitted on 30/08 21/09 - Pending SOPA, but schedule WS 01/10 28/09- Sopa permit valid until November 30 28/09- Awaiting PDH 04/10 - Blockages outside and inside development. Require further investigation and possible civils dig down. Possibly breakout of pavers 05/10 - Blockages, require dig down and further investigation WS 08/10 11/10- Confirm we can use alternate DJL 17/10- no response from NBN, SOPA permit clause does not allow us to work in this area from 17/10-28/10 02/11/- PDH to be installed soon 08/11- Link up not actually done, haul complete | 2018-12-12 |  |  |  |  | 13/12/2018
AYCA-2Y5DX4 | Bridgeland Investment – 1, 3 & 16 Hazlewood Pl | MDU Externals | FTTP – Type 2 |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | X | [5 empty] | 2018-05-02 |  |  |  |  | 2018-04-30 | Apr-18 |  |  | 2018-05-02 |  |  |  |  | 2018-05-02 | May-18
AYCA-56Z0PS | 37-49 O'Connor Street Chippendale | MDU Externals | FTTP - Type 3 (MT-LFN) | 2HMK-20 | Ertan Cicek | 30/08/2019 | Aug-19 | Dane | Developer Delay | David Cummins 0423623268 | TBC | TBC | TBC |  | 19/06/2018 | [12 empty] | 07/07 - Site not ready until few months from 06/07. Requires link up between pits. 26/07: No change. Follow up on early September 03/08 - No change 14/09 - Site on-hold because builder is fired, pushed out 11/10- Unable to contact 12/10- Site has been on hold during handover period to new construction company. Looking at completing inside by late December 23/11- Unable to contact 30/11-Unable to contact
AYCA-31DCKF | 18-20 Neild Avenue, Darlinghurst | MDU Externals | FTTP – Type 2 | 2EAS-64 | Ertan Cicek | 2019-01-31 | Jan-19 | Dane | Completed |  | X | X | X | [6 empty] | 2018-08-08 |  |  |  |  | 2018-08-08 | Aug-18 |  | 06/07 - Lead in conduit to be brought out within next week, comms room possibly ready in two weeks. lead in has been changed to Boundary Rd not Neild Av. 09/07 ready 16/07 17/07- Civils and splicing booked in for tomorrow 19/07- Blockages to be flushed 23/07, link up completed 25/07 - Blockage rectified and cable hauled, waiting on developer internal pathways 26/07- Scheduled for splicing next week 03/08 - Pushed out to next week, week starting 06/08 | 20/08/2018 |  |  |  |  | 20/08/2018 | Aug-18
AYCA-3O2CEB | 5 Elger St, Glebe, NSW- 2037 | MDU Externals | FTTP - Type 2 | 2GBE-62 | Ertan Cicek | 30/07/2019 | Jul-19 | Dane | Developer Delay |  | TBC | TBC | TBC |  | 2018-03-08 |  |  |  |  | TBC | [7 empty] | 22/07 - Material order request sent, site visit required 26/07- Clarify with NBN regarding one cable for two building developments 17/08 - Request for clarity on 10/08
AYCA-34MTV2 | 133 Parramatta Rd, Homebush, NSW, 2140 | MDU Externals | FTTP - Type 2 | 2BUR-07 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-07-04 |  |  |  |  | 2018-06-29 | Jun-18 |  |  | 2018-06-07 |  |  |  |  | 2018-06-29 | Jun-18
AYCA-57JCRY | 27a, 31, 33 & 35 Louis Street,Granville, NSW 2142 | MDU | FTTP- Type 2 | 2GRA-63 | Ertan Cicek | 30/07/2019 |  | Dane | Site Visit | John Obeid 0410 486 112 | [17 empty] | 01/03- A month away frtom bringig out LIC 07/03- Uable to rope through congested conduit, requires extensive new build, or alternate route with road crossing
AYCA-35V4R1 | 208-214 Parramatta Rd, Homebush, NSW 2140 | MDU | FTTP - Type 2 | 2HOM-03 | Ertan Cicek | 2019-01-31 |  | Dane | Completed | Jaffar 0423548839 |  |  |  |  | 2018-01-11 | [11 empty] | 2019-01-07 | 09/11- Check LAANs, may have to submit ROP 10 days before construction 15/11- Internals commenced 01/12- Still awaiting ROL 11/01- No change, requested to put a new application in | [5 empty] | 2019-05-03
AYCA-3O8ECI | 170-178 Bondi Road, Bondi | MDU externals | FTTP - Type 2 | 2BON-67 | Ertan Cicek | 30/06/2019 | Dec-18 | Dane | Site Visit | [5 empty] | 2019-04-19 | [12 empty] | 05/04 - Work order received yesterday
AYCA-39AB50 | JAAN – 1 12-14 Bouvardia St | MDU Externals | FTTP – Type 2 | 2HOR-62 | Ertan Cicek | #N/A | #N/A | Dane | Completed | [10 empty] | 2018-07-30 |  |  |  |  | 2018-08-02 | Aug-18 |  | 06/07 - Waiting on developer to link up to our pipe at boundary, unable to haul cable yet. 19/07- scheduled for splicing and haul week starting 23/07. 26/07 - Scheduled for splicing and haul week starting 30/07 | 2018-08-06 |  |  |  |  | 2018-08-03 | Aug-18
AYCA-39XZGZ | 23 Nelson Road | SDU | FTTP - Type 3 (MT-LFN) |  | VPL | #N/A |  |  | Completed | [10 empty] | 2018-04-24 |  |  |  |  | 2018-04-24 | Apr-18 |  |  | 2018-04-27 |  |  |  |  | 2018-04-27 | Apr-18
AYCA-3A485K | Lidbury Street Berala - 1 - EXTERNAL | MDU Externals | FTTP – Type 2 |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-05-08 |  |  |  |  | 2018-05-08 | May-18 |  |  | 2018-05-17 |  |  |  |  | 2018-05-17 | May-18
AYCA-3AVVT5 | 70 seventeenth Avenue, Austral, NSW 2179 | SDU | FTTP - Type 3 | 2BRG-01 | Andrew Mahasay | 2018-11-16 | Nov-18 | Dane | Completed | [5 empty] | Waived |  |  |  |  | 2018-10-12 | [7 empty] | 06/08- Requires site visit 28/08- A end FJL is not currently built. FSD cable is in the pit 30/08- VPL forecasted to complete FJL construction 25/09 05/10 - No response from NBN regarding confirmation of Parent site. Hauling has been completed, pending splicing 09/10 - FJL still not built, followed up with NBN 12/10- Still awaiting response from NBN regarding A end 17/10- Dealayed for road works, awaiting NBN response regarding VPL new schedule 27/11- Still no word on parent site 11/12- No change 06/01- No change 18/01- No change 22/03- Splicing completed 28/03- Waiting for new Workbook |  |  |  | X |  | 28/03/2019
AYCA-3BBGCI | 737 Windsor Road Box Hill | SDU | FTTP – Type 2 | 2RIV-04 | Andrew Mahasay | #N/A | #N/A |  | Completed | [10 empty] | 2018-04-07 |  |  |  |  | 2018-06-01 | Jun-18 |  |  | 2018-04-07 |  |  |  |  | 2018-04-07 | Apr-18
AYCA-3CFI3W | 120 Herring Road | MDU Externals | FTTP – Type 2 | 2EPP-05 | Ertan Cicek | 2019-02-02 | Feb-19 |  | Completed |  | X | X | X | [6 empty] | 20/08/2018 |  |  |  |  | 2018-08-22 | Aug-18 |  | 18/05 - Internal PDH Dependent - waiting on PDH 26/07 - Internal started this week, PDH will be installed 27/07 03/08 - awaiting for advise from Ertan in regards to PDH installation 09/08- PDH Installed, splicing scheduled week starting 13/08. 10/08- Splicing scheduled to be completed week starting 13/08 15/08- Complete internal haul and insert into PDH outstanding | 2018-08-22 |  |  |  |  | 2018-08-23 | Aug-18
AYCA-4DBFGM | 87 Parramatta Rd, Camperdown, NSW 2050 | MDU | FTTP- Type 2 | 2NEW-20 | Ertan Cicek | 28/06/2019 |  | Dane | Site Visit | [18 empty] | 14/03- Just at framing stage 31/05- Scaff down in 6 weeks
AYCA-3D0J11 | 15-21 Willis St, Wolli Creek | MDU Externals | FTTP - Type 2 | 2ROC-02 | Ertan Cicek | 2019-02-18 | Feb-19 | Dane | Completed | Paul 0405220639 | TBC | TBC | TBC |  | 18/06/2018 |  |  |  |  | TBC | X | [5 empty] | 30/11/2018 | 06/07 - Developer advised 3 months from 13/06 until LPC ready. Follow up 6 weeks from 13/06 26/07: No change 10/08- Comms room expected to be built in 6 weeks time. 26/10- Hoarding to come down in a month or two 23/11- Unable to contact 01/12- Unable to contact, crew sent out to rod and rope and discovered public domain works already complete 06/01- Upon discussion with developere, advised that public domain works were from site next door. They have poured ashpalt footpath over telstra pits 15/02- Scheduled WS 18/02 | [5 empty] | 2019-06-03
AYCA-42HX6R | 34-42 Spring St, Bondi Junction, NSW2022 | MDU | FTTP- Type 2 | 2BON-61 | Ertan Cicek | 23/10/2019 |  | Dane | Site Visit | [5 empty] | 2018-03-12 | [12 empty] | 07/12- Developer unwilling to give any information. Only wants to speak to Ertan
AYCA-5M5JQ0 | 23A Mars Road, Lane Cove West, NSW 2066 | MDU Externals | FTTP - Type 2 | 2HUH-21 | Ertan Cicek | 22/08/2019 |  | Dane | Site Visit | [5 empty] | 2019-01-04
AYCA-3G34XT | 51 Norton St - Stage 1 | MDU Externals | FTTP – Type 2 |  | VPL | #N/A |  |  | Completed | [10 empty] | 2018-05-22 |  |  |  |  | 2018-05-22 | May-18 |  |  | 2018-05-25 |  |  |  |  | 2018-05-25 | May-18
AYCA-3I8XUO | Highgardens - 1 - EXTERNAL - 7 Rutledge St | MDU Externals | FTTN | 2RDL-60 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-04-16 |  |  |  |  | 2018-04-16 | Apr-18 |  |  | 2018-04-17 |  |  |  |  | 2018-04-17 | Apr-18
AYCA-3JJIX9 | 13-21 University Rd and 1-5 Pinnacle St, Miranda, NSW, 2228 | MDU Externals | FTTP - Type 2 | 2MIR-28 | Ertan Cicek | 2019-02-28 | Feb-19 | Dane | Completed |  | X | X |  |  | 19/09/2018 |  |  |  |  | 21/01/2019 | X | [6 empty] | 31/08 - Lead-in is ready, revise civil plans to send to Saman and Ertan. Connection back to comms not ready 07/09 - Confirmed all ready for link up and haul for WS 10/09 14/09 - Pit install and link up today 27/09- Awaiting PDH 14/12- PDH installed | 25/01/2019 |  |  |  |  | 23/01/2019
AYCA-3K4RCM | Marsden Park Tonzat Development - 2 - 861 Richmond Rd - EXTERNALS | c | FTTP – Type 2 |  | Andrew Mahasay | #N/A |  |  | Completed | [10 empty] | 2018-03-29 |  |  |  |  | 2018-03-29 | Mar-18 |  |  | 2018-04-04 |  |  |  |  | 2018-04-04 | Apr-18
AYCA-3L48XJ | Mercedes Benz - 2 Anella Avenue | MDU Externals | FTTP – Type 3 (MT-LFN) | 2CAS-23 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-05-18 |  |  |  |  | 2018-05-18 | May-18 |  |  | 2018-05-21 |  |  |  |  | 2018-05-21 | May-18
AYCA-3LT1P4 | 6A Arnold Avenue, Kellyville | SDU | FTTN | 2KEL-08 | Sogand Mohtat | #N/A | #N/A |  | Completed | [10 empty] | 2018-06-22 |  |  |  |  | 2018-06-22 | Jun-18 |  |  | 25/06/2018 |  |  |  |  | 25/06/2018 | Jun-18
AYCA-3NFID7 | Tench Ave Jamisontown – 1 | MDU Externals | FTTP - Type 2 | 2PTH-04 | Ertan Cicek | 2019-01-31 | Jan-19 | Dane | Completed | Robert 0419427459 | TBC | X | X | [6 empty] | TBC | [6 empty] | 23/11/2018 | 06/07 - Approx 2 months away (29/07) 25/07- Comms room ready, waiting for lead in conduit 03/08 - No change 09/08- Waiting for construction conmpany to call back 15/08- Third message left with construction company, no return calls 22/08 - Site visit from crew attended today, waiting for feedback on progress/details 23/08 - Still concrete slab, obtained contact details, still approx 2 months away 07/09 - 4 weeks away and developer is bringing trenching lead-in plus power same time to bring to boundary, follow up in 2 weeks - Clarify if P100 or P50 - P100 will require pit upgrade 10/10- Could not contact 11/10- Developer advises another two weeks, pushed out due to rain 25/10- Call next friday, trenching to commence next week, requires closing down a coffee shop to bring conduit to front 02/11- Coffee shop closing 07/11, aiming to be ready 12/11 09/11- Advised the coffee shop is now closed and escavation has begun, hopefully next friday LIC will be complete 15/11- Advises it will be ready next week 23/11- Developer advises it will be ready next week again. He will call to confirm. 30/11- With NBN, possibility of redesign. waiting for comms cupboard to be built. 13/12- Civils and haul completed, waiting on internals 06/01- No change | 2019-06-03 |  |  |  |  | 27/02/2019
AYCA-4P3YPZ | 107 Chapel Road South, Bankstown,NSW 2200 | MDU | FTTP- Type 2 | 2BAN-67 | Ertan Cicek | 22/02/2019 |  | Dane | Completed | Steven Saad |  |  |  |  | 29/11/2018 | [12 empty] | 11/02- LIC brought out in middle of developement at around 100mm cover. ACM 4 pit ok to link into. Construction 2-3 weeks away 22/03- Blockage on route in footpath 11/04- Civils and haul complete, splicing commencing WS 15/04 | 2019-10-05 |  |  |  |  | 2019-10-05
AYCA-5CQHIP | 24 Barber Ave, Penrith, NSW 2750 | MDU | FTTP- Type 2 | 2PTH-02 | Ertan Cicek | 21/12/2019 |  | Dane | Site Visit
AYCA-3G1TZ6 | 9-17 Eastern Rd, Turramurra, NSW 2074 | MDU | FTTP- Type 2 | 2PYM-62 | Ertan Cicek | 21/06/2019 |  | Dane | Site Visit | Robert 0400 101 897 | [17 empty] | 24/05- Civils scheduled next week
AYCA-3TBATE | Skyrise - 11 Hassall Street | MDU Externals | FTTP – Type 2 |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-04-30 |  |  |  |  | 2018-04-30 | Apr-18 |  |  | 2018-05-04 |  |  |  |  | 2018-05-04 | May-18
AYCA-3TP6RP | 8 Hilly Rd - Majors Bay | MDU Externals | FTTN | 2SIL-04 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-04-13 |  |  |  |  | 2018-04-21 | Apr-18 |  |  | 2018-04-18 |  |  |  |  | 2018-04-18 | Apr-18
AYCA-3V5BM6 | 197-199 Lyons Rd | MDU Externals | FTTP – Type 2 | 2DRU-61 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | X | [5 empty] | 2018-06-29 |  |  |  |  | 26/06/2018 | Jun-18 |  |  | 2018-07-03 |  |  |  |  | 27/06/2018 | Jun-18
AYCA-413V2N | 16-20 Smallwood St | MDU Externals | FTTP – Type 2 |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-04-13 |  |  |  |  | 2018-04-05 | Apr-18 |  |  | 2018-04-16 |  |  |  |  | 2018-04-06 | Apr-18
AYCA-413Z64 | 2B Darcy Road, Westmead | MDU Externals | FTTP – Type 2 | 2PAR-64 | Ertan Cicek | 2018-11-30 | Nov-18 | Dane | Completed | Joe 0472720221 | X | X | X | [6 empty] | 2018-07-23 |  |  |  |  | 24/07/2018 | Jul-18 | 2018-07-11 | 06/07 - further developer delay due to weather and builder not running on schedule, no escavator on site still, at least another 2 weeks. 09/11- Should be ready 16/07 17/07- Scheduled in tonight | 2018-07-27 |  |  |  |  | 2018-07-30 | Jul-18
AYCA-41AL6Q | 63 Water Street, Greta | SDU |  |  | VPL | #N/A |  |  | Completed | [10 empty] | 2018-06-06 |  |  |  |  | 2018-06-06 | Jun-18 |  |  | 2018-06-15 |  |  |  |  | 2018-06-08 | Jun-18
AYCA-47OO3O | 188 Moore Street | MDU Externals | FTTP – Type 2 | 2LIV-03 | Ertan Cicek | 20/06/2019 | Jun-19 | Dane | Developer Delay | Phoi 93541836 | [9 empty] | TBC | [7 empty] | 06/07 - Site had no structure, only temp fencing at time of inspection 27/03 26/07: No change 03/08 - no change 02/05- Need to locate buried pits out the front to determine which to link into | TBC
AYCA-5K1HTP | 18 Gibbons Street, Auburn NSW 2144 | MDU Externals | FTTP - Type 2 | 2LID-07 | Ertan Cicek | 20/06/2019 |  | Dane | Site Visit | [18 empty] | 26/05- Developer to pour footpath soon
AYCA-5NXLZB | 158 Terrigal Drive, Terrigal , NSW 2260 | MDU | FTTP- Type 2 | 2TGL-02 | Ertan Cicek | 19/06/2019 |  | Dane | Site Visit | Aiden 0405 164 705 | [17 empty] | 07/03- Unable to contact
AYCA-42N8QF | 38 Macklin Street | MDU Externals | FTTP – Type 2 | 2PEN-67 | Ertan Cicek | 2019-04-01 | Apr-19 | Dane | Completed |  | TBC | TBC | TBC | [6 empty] | TBC | [7 empty] | 06/07 - Site had old buildings not knocked down yet, fencing at time of inspection 03/04. Incorrect EFSCD 26/07 - no change. scheduled second site visit on the 13th of August 03/08 - no change 11/10- Call in two months for follow up as advised by developer 07/09- Scheduled to scope WS 11/03 08/03- LIC brought out to pit, left 200m away. 1 bend and a 1m piece of conduit required. | TBC |  |  |  |  | 29/03/2019
AYCA-5L4YBN | 13a Locosi Street, Schofields | SDU | FTTP - Type 2 | 2RIV-01 | Mark Leal | 15/03/2019 |  | Dane | Completed | [18 empty] | 12/04- Requires CRQ, MPT upgrade and patching only 16/04- CRQ booked for 06/05 | [5 empty] | 15/05/2019
AYCA-442ZEA | 2 Good Street - Pinnancle 1 | MDU Externals | FTTP – Type 2 | 2PAR-63 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-06-22 |  |  |  |  | 20/06/2018 | Jun-18 |  |  | 25/06/2018 |  |  |  |  | 2018-06-22 | Jun-18
AYCA-44H3AU | 13 Marshall Avenue St Leonards NSW 2065 | MDU Externals | FTTP - Type 2 | 2STL-65 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 24/08/2018 |  |  |  |  | 2018-08-24 | Aug-18 |  | 06/07 - everything ready to go excpet PDH. Will need to be night works due to being infront of site entry 19/07- Civils week starting 06/08 26/07 : PDH planned to be installed week ending 03/08 30/07- PDH installed, schedule civils and haul 03/08 03/08 - Civil and haul scheduled for week starting 06/08 09/08- Civils completed, site meeting with NBN on 13/08 to discuss new build. 15/08- New build scheduled week starting 20/08 22/08 - Civils and haul complete. Splicing 24/08 | 29/08/2018 |  |  |  |  | 27/08/2018 | Aug-18
AYCA-44MH0G | 133-137 Bowden Street | MDU Externals | FTTP – Type 2 | 2RYD-63 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  |  | X | X | [6 empty] | TBC |  |  |  |  | 2018-06-08 | Jun-18 |  | 06/07 - Civils 100% complete up to boundary, hauling up to lead-in pit. Lead-in from developer not ready. Follow up developer when lead-in will be installed - Joe 0411121298 12/07- Check with Ertan that PDH has been installed before sending haulers out to complete, site 2 weeks away. 24/07- Site another week and a half away 26/07 - PDH was installed. Follow up with the developer on the 31st of July 27/07- Sceduled to complete week starting 30/07 03/08 - construction in progress. PDH is installed today, not as per the advise on the 26th of July | 2018-08-08 |  |  |  |  | 2018-08-08 | Aug-18
AYCA-45LS90 | 8 Withers Rd, Kellyville, NSW- 2155 | SDU | FTTP- Type 2 | 2ROU-03 | Mark Leal | #N/A | #N/A | Dane | Completed | [10 empty] | 2018-08-31 |  |  |  |  | 2018-08-30 | Aug-18 |  | 10/08 - LAANs 20/08 start date 15/08 - Confirm if civils is required 16/08 - No Civils required, ready for haul and splice 28/08- Scheduled for 29/08 | 2018-09-03 |  |  |  |  | 2018-08-31 | Aug-18
AYCA-45Q6J5 | 35 Oxford Street, Epping - Luxcom | MDU Externals | FTTP – Type 2 | 2EPP-62 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 24/08/2018 |  |  |  |  | 16/08/2018 | Aug-18 |  | 07/06 - Internal PDH Dependent 12/07 - No change 26/07 - PDH is installed 03/08 - No change 09/08- Splicing scheduled week starting 13/08 16/08 - Field completed, pending artefacts | 29/08/2018 |  |  |  |  | 24/08/2018 | Aug-18
AYCA-45U68U | 5 CULLEN AV, JORDAN SPRINGS, NSW, 2747 | MDU Externals | FTTP- Type 2 | 2PTH-12 | Ertan Cicek | 2019-01-07 |  | Dane | Completed |  | X | X | X |  | 2018-01-10 |  |  |  |  | 2019-01-02 | [7 empty] | 20/09 - Internals completed, require site visit 04/10 - Developer require jack hammer out front for us to get lead-in link up. Confirm with dev. Also require CRQ, dropping DJL on existing DSS run 05/10 - Require special CRQ for outage 11/10- Requires drill shot 19/10- Land M Trenchless to submit quote by Monday 22/10 25/10- Quote submitted on 23/10, awaiting response 02/11- No change 08/11- Still waiting on Opticom response on agreement 15/11- No change 23/11- Opticom agreement obtained, waiting for clarification on whether we can install lead in into pit as well as haul through conduit. 30/11- Looking into new plans with Opticom contact 14/12-OPticom site visit scheduled for today, but cannot contact rep 11/01- Scheduled civils and haul 14/01 18/01- Pushed out week starting 21/01 | 2019-06-02 |  |  |  |  | 14/02/2019 | Feb-19
AYCA-468RZY | 23 Railway Parade | MDU Externals | FTTP – Type 3 (MT-LFN) | 2LID-04 | Ertan Cicek | 2019-02-04 | Feb-19 | Dane | Completed | Musa 0404910121 Rahmi 0421 308 298 | X | X | X | [6 empty] | 2019-08-02 |  | X | [5 empty] | 06/07 - Developer advised end of July lead-in approx ready 25/07 - Site still 3-4 months away, 03/08 - No change 28/08- Unable to contact 11/10- Requires site visit to discuss where to bring conduit out 19/10- Developer to bring conduit out on side street, electrician to do this before footings are dug out 07/11- Jemena spotter booked for Monday 15/11- Civils complete, CRQ booked for 28-30 Nov 30/11- New CRQ raised for 17/12, unable to contact developer for update on internals 13/12- Awaiting internal pathways, MPT upgrade and civils complete. Will terminate external cable when we return for internals 18/01- Pathways certified, scheduled week starting 28/01 | TBC |  |  |  |  | 20/02/2019
AYCA-468RZY | 23 Railway Parade- Internals | MDU Internals | FTTP-Type 2 | 2LID-04 |  |  |  | Dane | Completed | [24 empty] | 20/02/2019 | Feb-19
AYCA-476RM9 | 87-91 Campbell Street Liverpool | SDU | FTTB | 2LIV-04 | Andrew Mahasay | 2017-02-15 | Feb-17 | Dane | Completed |  | X | X | X | [6 empty] | 19/10/2018 |  |  |  |  | 13/11/2018 |  |  | 27/07- CRQ from the 31/07, Scheduled in to complete work 03/08 - MPT upgrade completed. Integration scheduled in for Monday, 06/08 14/08 - Second integration due to faulty card. Scheduled today 15/08- Faulty equipment, new Chassis ordered on 17/08 - confirming material ETA 28/08 - Advised material should arrive today. Need to schedule with integration team etc, will need follow up on date 07/09 - Chasis did not resolve issue, require RANI card, ordered, pending ETA 14/09 - Materials received, scheduled works to commence WS 17/09 28/09- Still having issues with equipment 02/10 - Tech spoke to Mark Leal, waiting for update 09/10 - Reordered all new parts/cards. 613870 | 24/10/2018 |  | X
AYCA-47C97W | Kildare's Corner - 1 - 51 Kildare Road | MDU Externals | FTTN | 2BLK-01 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-06-05 |  |  |  |  | 2018-06-05 | Jun-18 |  |  | 2018-06-08 |  |  |  |  | 2018-06-08 | Jun-18
AYCA-Y8UNL | Belmore Street Burwood, NSW 2134 | MDU | FTTP - Type 2 | 2BUR-03 | Ertan Cicek | 14/09/2019 |  | Dane | Site Visit
AYCA-47STWW | 130 Elizabeth St, Sydney, NSW 2000 | MDU | FTTP- Type 2 | 2CYS-11 | Ertan Cicek | 2019-02-01 |  | Dane | Completed | [5 empty] | 2018-12-12 |  |  |  |  | 15/02/2019 | X | [6 empty] | 01/12- Waiting on PON Patching 07/12- Developer to install conduit for us, only need to corehole into manhole, need to send through SWMS 11/01- Develoepr to open trench for us on Thursday, we lay pipe on Friday | 20/02/2019 |  |  |  |  | 2019-04-03
AYCA-48280D | 906 Bourke Street - THE RESERVE | MDU Externals | FTTP – Type 2 | 2RED-03 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 13/07/2018 |  |  |  |  | 2018-07-12 | Jul-18 |  | 06/07 - Scheduled for splicing 09/07 | 2018-07-18 |  |  |  |  | 2018-07-12 | Jul-18
AYCA-48HHL8 | 22 University Rd & 660-664 Kingsway, Miranda | MDU Externals | FTTP - Type 2 | 2MIR-28 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X |  | 18/07/2018 |  |  |  |  | 23/11/2018 | X |  |  |  |  | 26/11/2018 |  | 06/07 - Ordered materials, require site visit 17/07- site visited, waiting on details 19/07- Waiting for lead in mark up to be sent through 26/07: second site visit 27/07 03/08 - Waiting to hear back from developer regarding whether we do the pit upgrade or not 15/08- Construction scheduled week starting 20/08 (Confirming PDH install date) 16/08 - Waiting for ROL to commence then civils can commence 30/08- Altus error in booking ROL, expecting to receive this by Friday 31/08 05/09- Scheduled Monday 10/09 14/09 - Civils completed 21/09 - Waiting on PDH to be installed 14/11- PDH installed, hauling on saturday, splicing next week | 28/11/2018 |  |  |  |  | 29/11/2018
AYCA-1XN8L5 | 9 Affleck Circuit, 9 Affleck Circuit, NSW 2155 | MDU | FTTP - Type 2 | 2KEL-07 | Ertan Cicek | 13/11/2019 |  | Dane | Site Visit | Sharbel 0413 638 490 Mormon Raad 0406 433 776 site manager |  |  |  |  | 2018-12-11 | [12 empty] | 02/11- Still awaiting LAANs 04/04- Advised site may be pushed out, develoepr to contact when LIC and comms room ready 18/04- Road crossing starter pipe finishes under road. May be better option to do new one with grundy
AYCA-4PPBEB | 8 Sherbrooke Rd, West Ryde, NSW | MDU | FTTP - Type 3 (MT-LFN) | 2RYD-63 | Ertan Cicek | 2020-03-04 |  | Dane | Site Visit | [5 empty] | 2018-11-12 | [12 empty] | 27/11/- Dependent on Datateks 2RYD-63 DFN 01/12- Scoped by Mick Gale, not ready until next year
AYCA-48V6NM | Lord Sheffield Circuit, Penrith | MDU Externals | FTTP – Type 2 | 2PTH-05 | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-07-20 |  |  |  |  | 2018-07-13 | Jul-18 |  | 06/07 - New LAANs received, schedule in 11/07 as LAAN date revised 12/07 - Civils complete 12/07, splicing 16/07 | 2018-07-25 |  |  |  |  | 16/07/2018 | Jul-18
AYCA-49OZC4 | 257 Oxford St – 1 | MDU | FTTP- Type 2 | 2EAS-65 | Ertan Cicek | 2019-01-28 |  | Dane | Completed | George 0409 470 398 |  |  |  |  | Requested |  |  |  |  | 15/02/2019 |  | X |  |  | 2019-01-03 |  |  | 15/02- Pending tunnell access approval, waiting on TUN number from NBN | 20/02/2019 |  |  |  |  | 2019-07-03
AYCA-49Z80V | 44 Wells Street | SDU |  |  | Andrew Mahasay | #N/A |  |  | Completed | [10 empty] | 2018-05-14 |  |  |  |  | 2018-05-14 | May-18 |  |  | 2018-05-18 |  |  |  |  | 2018-05-18 | May-18
AYCA-4A5XPU | 29 Norfolk Street Blacktown | SDU | FTTP – Type 2 | 2BLK-11 | Sogand Mohtat | #N/A | #N/A |  | Completed | [10 empty] | 2018-06-05 |  |  |  |  | 2018-05-30 | May-18 |  |  | 2018-06-08 |  |  |  |  | 2018-05-30 | May-18
AYCA-4B5K39 | Camden Day Hospital - 1 - Copper - 37 Hilder St | SDU |  |  | VPL | #N/A |  |  | Completed | [10 empty] | 2018-05-08 |  |  |  |  | 2018-05-08 | May-18 |  |  | 2018-05-14 |  |  |  |  | 2018-05-14 | May-18
AYCA-4Z6R8L | 148-160 King St, Sydney, NSW- 2000 | MDU Externals | FTTP - Type 2 | 2DAL-28 | Ertan Cicek | 2020-01-31 | Jan-20 | Dane | Site Visit |  | TBC | TBC | TBC |  | 2018-08-08 |  |  |  |  | TBC | [7 empty] | 18/07 - Materials ordered, needs site visit 27/07- Site visit organised week starting 30/07 03/08 - no change
AYCA-4BBYMK | 184 & 186 Old Pitt Town Rd Box Hill, NSW 2765 | SDU | FTTP - Type 3 (MT-LFN) | 2ROU-01 | Mark Leal | 2019-01-16 | Jan-19 | Dane | Completed | Completed |  |  |  |  | 2018-11-07 |  |  |  |  | 25/01/2019 | X | [6 empty] | 29/06 - Dependent site won't be built till mid August AYCA-4BBYMK 03/08 - no change 06/08- Dependant site pushed out until October 17/08 - no change 28/08- Dependant site forecast completion 16/10 16/10 - Mark advised pushed out to 27/11 17/12- Dependednt site due this week, schedule for first week back 11/01- Splicing remaining | 30/01/2019 |  |  |  |  | 24/01/2019
AYCA-4BC75L | Fairwater Boulevarde, Blacktown | SDU | FTTP - Type 2 | 2BLK-11 | Mark Leal | #N/A | #N/A | Dane | Completed | [10 empty] | 2018-09-06 |  |  |  |  | 2018-09-07 |  |  | 24/07 - Pending dependent site to be ready. Waiting for NBN PM to confirm 03/08 - No change 10/08- Waiting for information on dependant site 16/08 - NBN estimate MPT ready 08/10 20/08 - Mark leal advised: for construction once site ready 06/09 - perform patch and test, PC pack 2 days after | 2018-09-07 |  |  |  |  | 2018-09-07 | Sep-18
AYCA-4BT0OX | 66 Schofields Road, Schofields - Dark Moon | SDU |  |  | Andrew Mahasay | #N/A |  |  | Completed | [10 empty] | 2018-06-08 |  |  |  |  | 2018-06-08 | Jun-18 |  |  | 2018-06-08 |  |  |  |  | 2018-06-08 | Jun-18
AYCA-4C0Z5Y | Hamptons - Rose Bay - 1 | MDU | FTTP- Type 2 | 2ROS-66 | Ertan Cicek | 2019-03-15 |  | Dane | Completed | [18 empty] | 14/03- Scheduled 18/03, 3m trench and corehole into manhole 22/03- Haul and civils complete, waiting on A end | [5 empty] | 2019-10-04
AYCA-4CG9U4 | Dunning Avenue, Roseberry | MDU Externals | FTTP - Type 2 | 2KNS-04 | Ertan Cicek | 2018-12-13 | Dec-18 | Dane | Completed | Tony 0424892073 |  | X | X | [6 empty] | 2018-10-26 | X |  |  |  | 29/10/2018 |  | 15/10/2018 | 06/07 - boards come down when crane comes down in 2-3 weeks. Tony will call when this happens hopefully 18th july. contact 0424892073 23/07- Another 3-4 weeks 26/07: still waiting on developer 03/08 - No change 30/08- Unable to contact 05/09- Established contact, developer advised WS 24/09 hoarding down, require follow up before crew commences 20/09 - Advised Internals commencing soon, require follow up when hoarding down 27/09-Hoarding is down, starting Kerb and Gutter week starting 01/10/2018, developer to advise when he starts footpath as we will come in at that time to ensure the pit is upgraded to the correct level 04/10 - Require follow up regarding site access for WS 08/10 10/10- Kerb and gutter work pushed out due to weather, now looking at getting access for end of week starting 15/10 17/10- Civils scheduled for 18/10, developer advises we will have full access 18/10 - ACM Pit removal scheduled today - also internals have been completed | 2018-10-31 |  |  |  |  | 2018-01-11
AYCA-26KP9Q | Caddies Boulevarde and White Hart Drive | MDU Externals | FTTP – Type 2 | 2ROU-02 | Ertan Cicek | 2019-12-10 | Dec-19 | Dane | Developer Delay | [10 empty] | TBC | [7 empty] | 06/07 - EFSCD pushed out till 01/02/2019, developer advised nothing ready at this stage since visit 16/03 26/07: No Change 03/08 - no change | TBC
AYCA-4DQ6PX | 645 Cobbitty Road - 3 | Stage Application | FTTP - Type 3 (MT-LFN) | 2NRN-06 | Mark Leal | 2019-01-25 |  | Dane | Completed | [5 empty] | 19/10/2018 | [5 empty] | X | [6 empty] | 05/11- No a end 11/01- A end built, scheduled for construction week starting 14/01 | [5 empty] | 31/01/2019
AYCA-4DQ9I8 | 645 Cobbitty Road - 2 | Stage Application | FTTP - Type 3 (MT-LFN) | 2NRN-06 | Mark Leal | 2019-01-25 |  | Dane | Completed | [5 empty] | 19/10/2018 | [5 empty] | X | [6 empty] | 05/11- No a end 11/01- A end built, scheduled for construction week starting 14/01 | [5 empty] | 31/01/2019
AYCA-4DRN0U | 182 Raby Road | SDU |  |  | Andrew Mahasay | #N/A |  |  | Completed | [10 empty] | 2018-05-14 |  |  |  |  | 2018-05-14 | May-18 |  |  | 2018-05-16 |  |  |  |  | 2018-05-16 | May-18
AYCA-4EE89M | 15 Boundary Road | SDU |  |  | Andrew Mahasay | #N/A |  |  | Completed | [10 empty] | 2018-05-21 |  |  |  |  | 2018-05-21 | May-18 |  |  | 2018-05-21 |  |  |  |  | 2018-05-21 | May-18
AYCA-4EITU0 | The Pinnacle - 100 Castlereagh Street | MDU | FTTP - Type 2 | 2LIV-02 | Ertan Cicek | 2019-01-14 |  | Dane | Completed | [5 empty] | 2018-06-11 |  |  |  |  | 28/11/2018 |  |  |  |  | 26/11/2018 |  |  | 09/11- Awaiting Endeavour energy response regarding stand by 15/11- No standby needed, | 2018-03-12 |  |  |  |  | 2018-12-03
AYCA-4EOA07 | 298-300 Taren Point Rd | MDU Externals | FTTP – Type 2 | 2MIR-24 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | X | [5 empty] | 2018-04-30 |  |  |  |  | 2018-04-30 | Apr-18 |  |  | 2018-05-05 |  |  |  |  | 2018-05-04 | May-18
AYCA-4EZRCH | 1-3 Higherdale Avenue, Miranda | MDU Externals | FTTP - Type 2 | 2MIR-26 | Ertan Cicek | 2019-01-31 | Jan-19 | Dane | Completed | Joe 0451180087 Billy 0451 656 566 |  |  |  |  | 20/06/2018 |  |  |  |  | TBC | X | [5 empty] | 2019-07-01 | 06/07 - Developer advised 2 months until comms room ready, contact back in 6 weeks from 13/06 20/07- unable to contact 24/07- No change to site, call in 4 weeks for an update 03/08 - no change 30/08- Comms room to be built next week, LIC to be built in 4 weeks 23/11- Advised to call back in three weeks when the stormwater has been installed 11/01- Unable to contact 18/01- Stormwater being put in now, 15/02- Sceduled WS 18/02 01/03- Waiting to hear back from developer regarding damaged pit by Ausgrid 07/03- Pit has been replaced, ready for us 14/03- Civils complete | [5 empty] | 27/03/2019
AYCA-5QVLJR | 60 Veron Street, Wentwothville | MDU externals | FTTP - Type 2 | 2PAR-60 | Ertan Cicek | 2019-11-20 | Nov-19 | Dane | Design | [18 empty] | 05/04 - NDD to be submitted 08/04
AYCA-4GPKZN | Waterloo TQM - 713-717 Elizabeth Street | MDU Externals | FTTP – Type 2 |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-04-27 |  |  |  |  | 2018-04-27 | Apr-18 |  |  | 2018-05-01 |  |  |  |  | 2018-04-29 | Apr-18
AYCA-4IEHVB | Bottlebrush Place, Lakewood | SDU | FTTN |  | Mark Leal | #N/A | #N/A |  | Completed | [10 empty] | 16/07/2018 |  |  |  |  | 16/07/2018 | Jul-18 |  | 06/07 - Civils and hauling complete, confirming pairs, need 3 more pairs as pillar range 1-100 are taken | 16/07/2018 |  |  |  |  | 16/07/2018 | Jul-18
AYCA-4JM0L9 | CINQUE - 50-52 East St | MDU Externals |  | 2DRU-60 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-08-03 |  |  |  |  | 2018-08-01 | Aug-18 | 2018-07-30 | 06/07 - Civils completed, waiting on VPL installing the MPT at A END 16/07 - VPL schedule to build A END by end of week, potential to schedule next week 20/07- Advised VPL has pushed this back 25/07 - Lindy to advise latest update this week. Follow up with Lindy 30/07 31/07 - Lindy advised MPT is installed 01/08 - construction completed | 2018-08-06 |  |  |  |  | 2018-08-03 | Aug-18
AYCA-4KBL5R | 14-18 Primrose Ave & 27-29 Roseberry Ave Rosberry NSW 2018 | MDU Externals | FTTP – Type 2 | 2KNS-03 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-07-11 |  |  |  |  | 2018-07-11 | Jul-18 |  | 06/07 - Duct issues due to relocation of BMPT, not as per plan. Possibly rehaul required 10/07- Hauling completed | 2018-07-13 |  |  |  |  | 2018-07-13 | Jul-18
AYCA-4KKMW0 | 55 Foxall Road, Kellyville, NSW- 2155 | SDU | FTTP - Type 2 | 2ROU-03 | Mark Leal | #N/A | #N/A | Dane | Completed | [10 empty] | 2018-09-07 |  |  |  |  | 2018-09-03 | Sep-18 |  | 10/08 - Request to NBN when parent site will be completed to schedule work 10/08 - Parent site completed since 2016, should be ready to patch, complete 28/08- Attended site, incorrect MPT (not 12 but 8), request if need to upgrade MPT with outage to patch the remaining | 2018-09-14 |  |  | X |  | 2018-09-05 | Sep-18
AYCA-4KNB05 | 20 Myrtle St, Teralba, NSW- 2284 | SDU | FTTP - Type 2 | 2BLR-03 | Mark Leal | #N/A | #N/A | Dane | Completed | [10 empty] | 31/08/2018 |  |  |  |  | 2018-08-24 | Aug-18 |  | 13/08 - Materials ordered, site visit required, LAAN received 16/08 - LAAN - Access start date 22/08, RRP/Civils/Haul commencing 24/08, Splicing week commencing 27/08 20/08 - Hauling complete, ready for splicing schedule | 27/08/2018 |  |  |  |  | 27/08/2018 | Aug-18
AYCA-4KZ476 | 38-40 Doonmore St - Penrith 1 | MDU Externals | FTTP - Type 2 | 2PTH-02 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-09-19 |  |  |  |  | 2018-09-13 |  | 2018-08-27 | 06/07 - Site visit this week and site still same condition. LPC not ready 17/07 - Following up with developer, will return and advise of status 25/07 - Civil trench P50 external to build route, cannot use P20, developer still delay 17/08 - Developer site sheds still in way of lead-in, developer still delay 28/08- PDH Installed 30/08- Site visit this afternoon to organise a date and see what needs to be moved 05/09- Awaiting response from developer regarding possible change of design | 2018-09-21 |  |  |  |  | 2018-09-20 | Sep-18
AYCA-41DY76 | 38 Hezlett Road Kellyville NSW | SDU | FTTP- Type 2 | 2ROU-03 | Andrew Mahasey | 2019-10-18 |  | Dane | Site Visit | [5 empty] | 2018-12-12 | [12 empty] | 11/01- Sheduled week starting 21/01 18/01-EFSCD moved out
AYCA-4LISRC | 62 Jamboree Avenue, Leppington, NSW 2179 | SDU | FTTP- Type 2 | 2BRG-03 | Andrew Mahasay | #N/A | #N/A | Dane | Completed | [5 empty] | 2018-08-13 |  |  |  |  | 27/08/2018 |  |  |  |  | 2018-08-27 | Aug-18 |  | 06/08- LAANs received 17/08 - Planned site visit 17/08 to confirm build 28/08- Hauling completed, splicing scheduled 28/08 | 31/08/2018 |  |  |  |  | 31/08/2018 | Aug-18
AYCA-4LM7HH | 590-602 New Canterbury Rd | MDU Externals | FTTP – Type 2 | 2UND-61 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X |  | 2018-09-11 |  |  |  |  | 2018-12-11 | X |  |  |  | 2018-12-11 |  |  | 06/07 - Revisit, confirm road crossing exist, confirm corehole, ROL small window, require renew, night works, L/P/C not ready 26/07: No change 03/08 - no change 15/08- Need another site visit to guide developer where to corehole and shoring wall and HV is within work zone. 07/09 - Waiting on ROL, night works 14/09 - ROL received, night works to commence 18/09 05/10 - Link up completed 11/10- Second visit discovered a road crossing, proposal to come 12/10- Awaiting new LAANs and design 08/11- Awaiting cable tray from developer | 15/11/2018 |  |  |  |  | 15/11/2018
AYCA-4LQOVR | 25 Water Creek Boulevard Kellyville, NSW 2155 | SDU | FTTP - Type 2 |  | Sogand Mohtat | #N/A |  |  | Completed | [10 empty] | 2018-06-06 |  |  |  |  | 2018-06-06 | Jun-18 |  |  | 2018-06-06 |  |  |  |  | 2018-06-06 | Jun-18
AYCA-54WJL3 | Andrews Road , Cranebrook, NSW, 2749 | MDU Externals | AYCA-57Y170 | 2PTH-09 | Ertan Cicek | 2019-09-06 | Sep-19 | Dane | Developer Delay |  | TBC | TBC | TBC |  | 2018-03-07 |  |  |  |  | TBC | [7 empty] | 04/07 - Cable is hauled up to lead-in pit. Empty lot with no building and fenced off area. Incorrect EFSCD 26/07: Correct EFSCD obtained. Follow up site visit on the beginning of September 03/08 - No change 30/11- Contact details requested
AYCA-4LVG38 | 9-11 Edgeworth Place, Cartwright, NSW 2168 | MDU | FTTP- Type 2 | 2MIL-20 | Ertan Cicek | 2019-01-12 |  | Dane | Completed | [5 empty] | 2019-04-01 |  |  |  |  | 18/01/2019 | [7 empty] | 01/12- Waiting for LAANs 13/12- Internals submitted | 23/012019
AYCA-4M02LB | 401-405 Illawarra Road | MDU Externals | FTTP – Type 2 | 2UND-62 | Ertan Cicek | #N/A | #N/A | Dane | Completed | Joe 0407299633 | [9 empty] | TBC | [6 empty] | 26/11/2018 | 06/07 - Confirmed with builder lead-in won't be ready for at least few months. 26/07: Due for follow up on the 2nd of August 03/08 - no change 03/08- Follow up in 6 weeks - Lead-in was brought out NOT to spec 100mm cover through concrete slab 21/09 - Sent to Ertan to NBN field services, no response. NBN advised builder will have it resolved. 27/09- Developer advises another 2 months for comms room to be built 08/11- On hold as advised by NBN | TBC
AYCA-4MFJ6I | 65 Victoria Street Coffs Harbour, NSW, 2450 | SDU | FTTP- Type 2 | 2CFS-03 | Mark Leal | 2019-02-13 |  | Dane | Completed | [5 empty] | 15/10/2018 | [12 empty] | 19/10- Email sent to NBN to clarify scope 26/10- Scope confirmed, Vipin advises another project attached to this one will be sent through. 23/11- Sent to contractor, waiting to receive dates from them to scope 09/02- Requires new build, proposal to come 07/03- Waiting on response to quote 22/03- Scheduled WS 25/03 11/04- CRQ raised for MPT swap 12/04- New materials ordered 639900 | [5 empty] | 18/04/2019
AYCA-4MJ7W3 | 10 Park Avenue Waitara - Cubic Construction Management - 1 | MDU Externals | FTTP – Type 2 |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | X | [5 empty] | 2018-05-08 |  |  |  |  | 2018-05-08 | May-18 |  |  | 2018-05-08 |  |  |  |  | 2018-05-08 | May-18
AYCA-4MJKV1 | Lot 37 Springfields Drive, Green Hill | SDU | FTTN | 2KMS-21 | Mark Leal | #N/A |  |  | Completed | [10 empty] | 2018-06-21 |  |  |  |  | 2018-06-21 | Jun-18 |  |  | 2018-06-21 |  |  |  |  | 2018-06-21 | Jun-18
AYCA-4MNF1P | 11 & 15 Holborn Circuit - Gregory Hills Health Hub | MDU Externals | FTTP – Type 2 | 2NRN-10 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | X | [5 empty] | 2018-05-25 |  |  |  |  | 2018-05-25 | May-18 |  |  | 2018-05-30 |  |  |  |  | 2018-05-29 | May-18
AYCA-41DSOU | 38 Hezlett Road, Kellyville, NSW- 2155 | SDU | FTTP - Type 2 | 2ROU-03 | Mark Leal | 2019-09-02 | Sep-19 | Dane | Developer Delay | [5 empty] | 22/08/2018 |  |  |  |  | TBC | [7 empty] | 13/08 - Materials ordered, site visit required, LAAN received 16/08 - Site visit indicates pit and pipe after Halloway St is not ready. Earth moving machinery in place, unlikely will be ready before 05/11. Advised NBN 16/10 - Advised will schedule personnel to attend end of month 23/10- Advised EFSCD has been pushed out until late 2019 02/05- Haul complete, cable not labelled
AYCA-4NNOGX | 240-250 Great Western Hwy Kingswood NSW 2747 | MDU Externals | FTTP – Type 2 | 2PTH-02 | Ertan Cicek | 2019-02-28 |  | Dane | Completed | Avni 0481600 288 | [9 empty] | TBC | X | [5 empty] | 2018-02-11 | 06/07 - Not ready for at least 4 months time from 18/05, scaffolding, no lead-in 26/07: No change 03/08 - no change 11/10- Developer to follow up with electrician on progress 26/10- Corehole completed, waiting for conduit and cable tray 19/11- Corehole and cable tray comlplete, ready to schedule 30/11- ROL requested 06/01- ROL receieved and valid until 24/01 07/03- Unable to contact | TBC |  |  |  |  | 20/03/2019
AYCA-4NOC4P | 40 Cawarra Road, Caringbah, NSW, 2229 | MDU Externals | FTTP- Type 2 | 2MIR-22 | Ertan Cicek | 2018-11-30 |  | Dane | Completed | Pete 0438958457 | X | X | X |  | 2018-01-10 | [9 empty] | 17/10/2018 |  |  | 04/10 - Waiting on Comms room to be built, ETA waiting from builder 05/10 - Follow up with builder when hauling cable is available (link up completed) 11/10- Scheduled to complete week starting 15/10 | [5 empty] | 17/10/2018 | Oct-18
AYCA-4O03IQ | 17 Ryan Street | MDU Externals | FTTP – Type 2 | 2COR-09 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-08-29 |  |  |  |  | 2018-08-31 | Aug-18 |  | 06/07 - Site delayed a fourth time, driveway expected to be poured 17th July, comms cabinet at least a week away after driveway. follow up 12/07 to see if they are on track 12/07- Driveway to be poured 17/07, Meter box possibly week after 17/07-Driveway to be poured next week. Still a few weeks away from having meter box installed 25/07- Delayed another week. 03/08- Driveway to be poured next week, potentially ready the week after 10/08- Developer advises to schedule in 20/08 16/08- Confirm on Monday that meter box will be installed by Wednesday. 30/08 - Site in progress build, external and internal | 2018-08-31 |  |  |  |  | 2018-08-31 | Aug-18
AYCA-4O03IQ | 17 Ryan Street | MDU Internals | FTTP – Type 2 | 2COR-09 | Nabeel Jaimon | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-08-31 |  |  |  |  | 2018-08-31 | Aug-18 |  | 10/08- Waiting on externals | 2018-08-31 |  |  |  |  | 2018-08-31 | Aug-18
AYCA-4OHMS3 | 35 Holbeche Road - INTERNAL | MDU Internals | FTTP – Type 2 |  | Nabeel Jaimon | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-05-14 |  |  |  |  | 2018-05-14 | May-18 |  |  | 2018-05-14 |  |  |  |  | 2018-05-14 | May-18
AYCA-4OQ160 | 3 Ocean Ridge Terrace, Port Macquarie NSW 2444 | Tech Choice Type 3 | FTTP - Type 3 |  | Mark Leal | #N/A |  | Dane | Completed | [10 empty] | 2018-09-07 |  |  |  |  | 2018-09-07 | Sep-18 |  | 10/08- Start Construction week starting 20/08 17/08 - Haul completed 17/08, splicing to commence WS 20/08 20/08 - Project pushed out for splicing @ customer available is 06/09 up to 10AM or 07/09 anytime 05/09 - Confirmed with customer booked for 07/09 | 2018-09-12 |  |  |  |  | 2018-09-12 | Sep-18
AYCA-4RJS2D | 5 Edge St, Boolaroo, NSW- 2284 | SDU | FTTP - Type 3 | 2CHL-05 | Mark Leal | 2019-08-16 | Aug-19 | Dane | Developer Delay | Nathan West 0243554622 |  |  |  |  | 22/08/2018 |  |  |  |  | TBC | [6 empty] | 2019-01-07 | 13/08 - Materials ordered, site visit required, LAAN received 16/08 - LAAN - Access start date 22/08, RRP/Civils/Haul commencing 24/08, Splicing week commencing 27/08 20/08 - Site visit indicates not ready from the lead-in pit. Site doesn't seem level and no construction done 21/08 - Contacted developer, advised wont have lead-in ready for approx start of 2019 |  | X | X | X |  | `
AYCA-4PBBAI | 6,8,10,12 Anderson Avenue, Ryde | SDU | FTTP – Type 3 (MT-LFN) |  | Dave Yeomans | #N/A |  |  | Completed | [10 empty] | 2018-06-29 |  |  |  |  | 2018-06-27 | Jun-18 |  |  | 2018-07-04 |  |  |  |  | 2018-06-27 | Jun-18
AYCA-4PIIN5 | 101 Church Street (dependent - require 4 Junction St QUBE), Ryde | MDU Externals | FTTP – Type 2 | 2RYD-66 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | X | [5 empty] | 2018-07-13 |  |  |  |  | 2018-07-13 | Jul-18 |  | 06/07 - ready 11/07 12/07- Splicing today | 2018-07-18 |  |  |  |  | 16/07/2018 | Jul-18
AYCA-4LT337 | 457-463 Victoria Street, Wetherill Park | MDU Externals | FTTP - Type 3 (MT-LFN) | 2WET-23 | Ertan Cicek | 2019-08-08 |  | Dane | Site Visit | Vince Site manager 0419 711 811 Michael PM 0419 811 711 | TBC | TBC | TBC |  | 2018-06-08 |  |  |  |  | TBC | [6 empty] | 2019-08-03 | 22/07 - Material order request sent, site visit required 03/08 - no change 19/12- Still escavating, two year project, folllow up in a few months to check progress
AYCA-4PQO3D | 12/6 Maida Road, Epping | MDU Externals | FTTP – Type 2 | 2EPP-62 | Ertan Cicek | 2019-01-07 | Jan-19 | Dane | Completed |  | X | X | X | [6 empty] | TBC |  |  |  |  | 2018-07-30 | Jul-18 |  | 06/07 - Unable to locate lead-in pit, lead-in to be brought out next week from 04/07, need to confirm developer, lead-in pit may require upgrade and additional P50 trench due to capacity of P20 12-07 Scheduled in for 17/07 26/07- Civils haul and splice complete, waiting on PON Patching 27/07- PON Patching received, scheduled for week starting 30/07 30/07 - MW is not available in sharepoint. PC Pack sent to Ertan via email 02/08 - MW is in sharepoint. RFC submitted 01/08. PC Pack uploaded to sharepoint today | TBC |  |  |  |  | 2018-07-30 | Jul-18
AYCA-54OULE | 71 Hill Rd, Lurnea | MDU | FTTP- Type 2 | 2MIL-62 | Ertan Cicek | 2019-07-31 |  | Dane | Site Visit | Mohammed 0415 544 399 | [17 empty] | 07/03- Site being escavated
AYCA-4Q0G0C | 20 Scarborough Close, Port Macquarie | SDU |  |  | Dave Yeomans | #N/A |  |  | Completed | [10 empty] | 2018-05-22 |  |  |  |  | 2018-05-22 | May-18 |  |  | 2018-06-06 |  |  |  |  | 2018-06-06 | Jun-18
AYCA-4Q27NU | 50 Raby Rd, Gledswood Hills, NSW- 2557 | MDU | FTTP- Type 2 | 2BRG-03 | Ertan Cicek | 2019-01-11 | Jan-19 | Dane | Completed | Sam Nohra (elec) 0431552652 | TBC | TBC | TBC | [6 empty] | 2018-09-28 | X |  |  |  | 27/09/2018 | Sep-18 |  | 15/08 - Materials ordered, requires site visit, LAAN received 07/09 - Comms ready, pathways 99%, lead-in ready, but suggest to commence only if Test and Coil option OK | 2018-10-04 |  | X |  |  | 2018-02-10 | Feb-18
AYCA-4QBUIV | Letitia St | SDU | FTTN | 2KTB-02 | Ertan Cicek | #N/A | #N/A |  | Completed | [10 empty] | 2018-05-21 |  |  |  |  | 2018-05-21 | May-18 |  |  | 2018-05-21 |  |  |  |  | 2018-05-21 | May-18
AYCA-4QG9AV | 33 Shoalhaven Street, Kiama | SDU | FTTP - Type 2 | 2KIA-02 | Andrew Mahasay | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-06-14 |  |  |  |  | 2018-06-13 | Jun-18 |  |  | 2018-06-14 |  |  |  |  | 2018-06-14 | Jun-18
AYCA-4QHVO8 | 13-15 Pacific Hwy, Gateshead | MDU Externals | FTTP - Type 3 (MT-LFN) | 2CHL-07 | Ertan Cicek | #N/A | #N/A | Dane | Completed | Mckenzie 0400381297 Office 43653351 John Thomas 0407928428 electrician | X | X | X | [6 empty] | 2018-10-26 | X |  |  |  | 25/10/2018 | Oct-18 | 2018-10-08 | 22/07 - Material order request sent, site visit required 26/07- No change 03/08 - no change 11/10- Begin construction week starting 15/10 19/10- pushed out due to rain, now expecting to meet on site next Wednesday 2/11- Still waiting on correct workbook | 31/10/2018 |  |  |  |  | 2018-02-11
AYCA-4QID92 | 153-165 Brougham St, Woolloomooloo | MDU Externals | FTTP - Type 2 | 2EAS-63 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-08-21 |  |  |  |  | 2018-08-20 | Aug-18 |  | 22/07 - Material order request sent, site visit required 24/07- RRP to commence 30/07 26/07 - Civils and haul scheduled 27/07 02/08 - Lindy advised us that CTL will be installed early next week. Proposed field completion by Wednesday, 08/08 07/08- Waiting for Ertans response on CTL installation 16/04- CTLs installed, scheduled week starting 20/08 | 23/08/2018 |  |  |  |  | 23/08/2018 | Aug-18
AYCA-2T05DV | 752 George St South Windsor NSW 2756 | SDU | FTTP - Type 2 | 2RCH-04 | Andrew Mahasay | 2019-07-25 | Jul-19 | Dane | Developer Delay | Eliza 0411 418 898 | TBC | TBC | TBC | [6 empty] | TBC | [6 empty] | 18/01/2019 | 06/07 - Materials ordered, require raise CRQ 25/07- Site visit before Monday 26/07: CRQ is for 31/07-02-08 31/07 - MPT upgrade completed 03/08- Site in early stages of construction and waiting for DA approval 19/10- Unable to contact, left message 19/10- Site has been pushed out until next year 06/02- Read email regarding LAANs 02/05- Unable to contact 08/05- advised call back in 2 weeks 31/05- Unable to contact
AYCA-4R1C1M | William Street, Riverstone | SDU | FTTP - Type 2 | 2RIV-07 | Mark Leal | #N/A | #N/A | Dane | Completed | [10 empty] | 2018-09-20 |  |  |  |  | 2018-09-20 | Sep-18 |  | 29/06 - AJL not built yet. Confirming parent site AYCA-1WXP9R for completion. Waiting response since 12/06 26/07: no change. still waiting 03/08 - No change | 2018-09-24 | X |  |  |  | 2018-09-28 | Sep-18
AYCA-4R1E3Q | 144-148 High Street & 35-37 Barber Avenue | MDU Externals | FTTP- Type 2 | 2PTH-02 | Ertan Cicek | 2018-12-21 |  | Dane | Completed | Andrew 0450079393 |  |  |  |  | Waived | [9 empty] | 2018-12-17 |  | 16/11/2018 | 16/10- Requires material order 17/10- Comms room still being built, advised to call back in a month 08/11- Civils underway 09/11- Proposal sent to NBN, awaiting response 01/12- Requested ROL 14/12- ROL received, civils commenced, rain impacted schedule. | [5 empty] | 2018-12-21
AYCA-4R1HAL | Crown, Edmund, William St-7 Riverstone | SDU |  |  | Andrew Mahasay | #N/A |  |  | Completed | [10 empty] | 2018-05-22 |  |  |  |  | 2018-05-22 | May-18 |  |  | 2018-05-24 |  |  |  |  | 2018-05-24 | May-18
AYCA-4R1HNT | 6-8 Facey Cres | MDU Externals | FTTN | 2MIL-62 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | X | [5 empty] | 2018-05-30 |  |  |  |  | 2018-05-29 | May-18 |  |  | 2018-06-01 |  |  |  |  | 2018-06-01 | Jun-18
AYCA-4R2N0H | 6,8,9,11 John Hillas Avenue, Kellyville | SDU | FTTP - Type 2 | 2KEL-07 | Dave Yeomans | #N/A |  |  | Completed | [10 empty] | 2018-06-18 |  |  |  |  | 2018-06-18 | Jun-18 |  |  | 2018-06-18 |  |  |  |  | 2018-06-18 | Jun-18
AYCA-4R7UP6 | 40 Government Road | SDU | FTTP – Type 3 (MT-LFN) |  | Andrew Mahasay | #N/A | #N/A |  | Completed | [10 empty] | 2018-05-15 |  |  |  |  | 2018-05-15 | May-18 |  |  | 2018-05-18 |  |  |  |  | 2018-05-16 | May-18
AYCA-4RB8MD | 2 Clarke St | MDU Externals | FTTP – Type 2 | 2LID-03 | Ertan Cicek | #N/A | #N/A | Dane | Completed | Rob 0402068217 | [9 empty] | 2018-10-19 |  |  |  |  | 18/10/2018 |  |  | 06/07 - Followed up with developer, would like someone to come out visit to help discuss with nbn external works. Site visit required. 12/07 - Field staff heading out 13/07 to advise developer for lead-in conduit 13/07 - Builder advised 2 weeks time 09/08- Still not ready 10/08- Developer advises lead in to be constructed end of next week, require follow up on 20/08 23/08- Developer advises he has been pushed back 2 weeks, lead in will be complete 31/08 30/08 - Advised lead-in ready by next week. Confirmation required by contractor and if confirmed, schedule next week 31/08 - Awaiting CRQ date 27/09- CRQ scheduled for approval date is 11/10/2018 02/10 - Link up ready as per builder Rob. Require schedule 04/10 - Check CRQ if any issues 05/10 - CRQ good, booked in WS 08/10 for civils and MPT swap is 16/10 12/10- Civils and hauling completed, pending termination and testing, and MPT upgrade 17/10- Issues with cable damage, required rehaul of SDS cable and also MSS cable feeding MPT 18/10 - Rehaul MSS due to f2 damage inbetween. | 2018-10-24
AYCA-4RFDRV | 58 Old Saddleback Road, Kiama | SDU | FTTP – Type 3 (MT-LFN) |  | Andrew Mahasay | #N/A | #N/A |  | Completed | [10 empty] | 2018-06-01 |  |  |  |  | 2018-06-01 | Jun-18 |  |  | 2018-06-06 |  |  |  |  | 2018-06-01 | Jun-18
AYCA-4RGB2W | OMNIA - 111-139 Darlinghurst Rd | MDU Externals | FTTP - Type 2 | 2EAS-62 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-07-13 |  |  |  |  | 2018-07-12 | Jul-18 |  | 06/07 - A END DJL not existing delay 12/07 - Splicing finalising 12/07 | 2018-07-18 |  |  |  |  | 2018-07-13 | Jul-18
AYCA-4RH5YY | 32 George St Box Hill NSW 2765-High Grove - 3B | SDU | FTTP - Type 3 | 2ROU-01 | Mark Leal | #N/A | #N/A |  | Completed | [5 empty] | 14/09/2018 | [5 empty] | X |  | X |  | 27/09/2018 | Sep-18 |  | 05/09 - Materials ordered, LAAN requested 18/09- Scheduled to begin construction week starting 24/09/2018 21/09 - Not linked, requires civil link up. Need to advise Mark Leal mob civil crew | 2018-10-03 |  |  |  |  | 2018-04-10 | Apr-18
AYCA-4ND19Q | Chapel Street Rockdale - 1 | MDU Externals | FTTP - Type 2 | 2ROC-22 | Ertan Cicek | 2019-07-20 | Jul-19 | Dane | Developer Delay | Richard Edmonds 86654100 George Diakos 94371000 |  |  |  |  | 2018-07-09 | [12 empty] | 30/08 - Requested CLAAN and Contact details. Require Site Visit 14/09 - Site visit complete,. Currently hole in ground 04/04- Comms room to be built in August
AYCA-3O1ZGP | 4-6 Elger St, Glebe, NSW 2037 | MDU | FTTP- Type 2 | 2GBE-62 | Ertan Cicek | 2019-07-19 |  | Dane | Site Visit
AYCA-4RTZSH | 25 Phegan Street Woy Woy NSW 2256 | Tech Choice Type 3 | FTTP - Type 3 (MT-LFN) | 2WOY-07 | Mark Leal | #N/A |  |  | Completed | [10 empty] | 24/08/2018 |  |  |  |  | 2018-08-23 | Aug-18 |  | 06/07 - Quote for customer lead-in require to be sent to NBN 25-07- waiting for customer reply 03/08 - no change 10/08- Customer approved, require customer detail to confirm attending 15/08- Scheduled for construction of lead-in and remaining haul 16/08, splicing week commencing 20/08 | 29/08/2018 |  |  |  |  | 2018-08-24 | Aug-18
AYCA-4S0RD5 | 14 Argowan Rd | SDU | FTTP – Type 3 (MT-LFN) | 2RIV-03 | Andrew Mahasay | #N/A | #N/A |  | Completed | [10 empty] | 2018-05-04 |  |  |  |  | 2018-05-04 | May-18 |  |  | 2018-05-04 |  |  |  |  | 2018-05-04 | May-18
AYCA-55RMFH | 1521 The Horsley Dr, Abbotsbury, NSW- 2176 | MDU Externals | FTTP - Type 3 (MT-LFN) | 2WET-23 | Ertan Cicek | 2019-06-30 | Jun-19 | Dane | Developer Delay |  | TBC | TBC | TBC |  | 15/08/2018 |  |  |  |  | TBC | [7 empty] | 22/07 - Material order request sent, site visit required 21/07 from contractor 26/07: Site visit scheduled for next week 30/07- Site in very early stages , just a slab 11/10- Unable to contact 19/10- Requires another site visit to confirm NBN network
AYCA-4SM3QD | Melrose St and Belmore Road (Lorn 6 lots) | SDU | FTTN | 2MAI-09 | Mark Leal | #N/A | #N/A | Dane | Completed | [10 empty] | 29/08/2018 |  |  |  |  | 27/08/2018 | Aug-18 |  | 22/07 - Quote query on hauling sent to Andrew Mahasay 03/08 - job awarded. Awaiting for heritage 06/08- No civils required 14/08- Heritage approved, ready to schedule | 31/08/2018 |  |  |  |  | 28/08/2018 | Aug-18
AYCA-4SOX62 | R & S Investments NSW – 1 - 192 Moore Street | MDU Externals | FTTP – Type 2 | 2LIV-03 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-06-20 |  |  |  |  | 2018-06-15 | Jun-18 |  |  | 2018-06-22 |  |  |  |  | 2018-06-18 | Jun-18
AYCA-4SQA1N | Estate + TTFN-1 Eleanor Close | SDU | FTTP- Type 3 | 2GRK-06 | Mark Leal | #N/A | #N/A |  | Completed | [10 empty] | 2018-09-07 |  |  |  |  | 2018-09-07 |  |  | 16/08 - Scheduled to perform R&R and prove route and haul for week commencing 20/08 20/08 - Hauling complete. Ready for splicing schedule 27/08 - Unable to complete the testing, 4th splitter in FJL was not there, installed splitter but no power. 28/08 - Received PON patching, reschedule to mobilise crew up on | 14/09/2018 |  |  |  |  | 14/09/2018 | Sep-18
AYCA-4SRFAN | ALDI Store Development, Balgowlah | MDU Externals | FTTP – Type 2 | 2BAL-62 | Ertan Cicek | 2019-01-22 | Jan-19 | Dane | Completed | Cameron electrician 0425297171 | X | X | X | [6 empty] | 2019-01-02 | X | [6 empty] | 06/07 - Potenitally have slab poured in three weeks time, follow up on 11/07 12/07- Slab still not poured, Looking at another 6-7 weeks until comms room built 17/07- waiting to hear back from PM, could not contact site manager today 24/07-call in 5 weeks for update on lead in and comms room 03/08 - no change 05/09 - Unable to contact 14/09- Unable to contact 18/10 - ACM Pit replacement and new pit install 18/10. A END no FJL exist or cable going to the M/H 19/10- Civils complete, waiting on A end 06/01- Blockage identified 11/01- New pit to be installed over blockage week starting 14/01 | 2019-06-02 |  |  |  |  | 19/02/2019
AYCA-4SRFAN | ALDI Store Development, Balgowlah - INTERNAL | MDU Internals | FTTP – Type 2 | 2BAL-62 | Lindy Chan | 2019-01-22 | Jan-19 | Dane | Completed | Frank 0412120142 Aidan 0406517307 | TBC | TBC | TBC | [6 empty] | TBC | [7 empty] | 06/07 - Potenitally have slab poured in three weeks time, follow up on 11/07 12/07- Slab still not poured, Looking at another 6-7 weeks until comms room built 17/07- waiting to hear back from PM, could not contact site manager today 24/07-call in 5 weeks for update on lead in and comms room 03/08 - no change | TBC
AYCA-4SV0JO | 41-47 Stennett Road - INTERNAL | MDU Internals |  |  | Nabeel Jaimon | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-08-21 |  |  |  |  | 2018-08-20 | Aug-18 |  | 06/07 - NBN PM will advise when VPL complete the Externals 26/07 - External completed, ready for construction internal. Scheduled 30/07 31/07 - internal construction completed. PON reading cannot be performed due to external build not completed yet by others 06/08- Waiting to hear back from Richard Huffadine regarding VPL external completion 16/08- Externals complete, PON patching scheduled 20/08 | 2018-08-24 |  |  |  |  | 2018-08-21 | Aug-18
AYCA-4T7JU2 | 13 Dudley Avenue, Caringbah South | MDU Externals | FTTN | 2MIR-25 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 29/06/2018 |  |  |  |  | 2018-06-29 | Jun-18 |  |  | 2018-04-07 |  |  |  |  | 2018-06-29 | Jun-18
AYCA-4T8B52 | 3 Edwards Road, Box Hill, NSW- 2765 | SDU | FTTP - Type 2 | 2ROU-04 | Mark Leal | #N/A | #N/A | Dane | Completed | [5 empty] | 31/08/2018 |  |  |  |  | 2018-09-14 |  |  |  |  | 2018-09-05 | Sep-18 |  | 22/08 - LAAN Received | 2018-09-21 |  |  |  |  | 2018-09-07 | Sep-18
AYCA-4TBHNX | 125 Lake Entrance Road, Barrack Heights | SDU |  | 2SHH-05 | Andrew Mahasay | #N/A | #N/A |  | Completed | [10 empty] | 2018-07-27 |  |  |  |  | 2018-07-27 | Jul-18 |  |  | 2018-08-08 |  |  |  |  | 2018-08-08 | Aug-18
AYCA-4TC0MT | 50 Farnham Road, Quakers Hill | MDU Externals |  |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-06-15 |  |  |  |  | 2018-06-15 | Jun-18 |  |  | 2018-06-20 |  |  |  |  | 19/06/2018 | Jun-18
AYCA-4UE5JN | 46-48 Beaumont St | MDU Externals | FTTP – Type 3 (MT-LFN) | 2LID-03 | Ertan Cicek | 2019-02-28 | Feb-19 | Dane | Completed | Paul khouri office@tradelinkconstruction.com.au 0405 415 952 | X | X | X | [6 empty] | TBC | [7 empty] | 06/07 - 2 old buildings and fenced, not knocked down yet since 24/05. Incorrect EFSCD 26/07: No change 03/08 - no change 14/12- Unable to contact 06/01- Civils and haul completed 01/03- CRQ booked for 11/03 07/03- Approval to door knock | TBC |  |  |  |  | 17/03/2019
AYCA-4UKN6A | 727 The Horsley Drive | MDU Externals | FTTP – Type 2 |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | X | [5 empty] | 2018-04-27 |  |  |  |  | 2018-04-27 | Apr-18 |  |  | 2018-04-29 |  |  |  |  | 2018-04-29 | Apr-18
AYCA-4P5T6R | 723-731 Victoria Rd Ryde, NSW 2112 | MDU Externals | FTTP - Type 2 | 2RYD-01 | Ertan Cicek | 2019-06-09 |  | Dane | Site Visit | [5 empty] | 17/05/2019 | [12 empty] | 08/05- Materials ordered 31/05- LIC and comms room bout 2 months away. Follow up end of June
AYCA-4UMUPA | 21 Fairway Drive, Kellyville | MDU Externals | FTTP - Type 2 | 2KEL-07 | Ertan Cicek | 2019-01-29 | Jan-19 | Dane | Completed | Tim 0409490026 | X | X | X |  | Waived |  |  |  |  | 18/01/2019 | X | [5 empty] | 23/11/2018 | 06/07 - Ordered materials, site is in very early stages. 17/07- Can RRP when in area 18/07- Civils scheduled 19/07, comms room not ready, follow up in a months time 19/07- Power mains in work zone need spotter to complete link up to road crossing 25/07- Civils sheduled 27/07 27/07- Follow in a month for update on comms room 03/08 - no change 30/08- Pushed out another month 27/09- Unable to contact 28/09- Unable to contact 11/10- Unable to contact 12/10- Advised another two weeks for comms room to be built 18/10 - Ertan advised no progress in internals at this stage 19/10- Developer to send photo of comms room progress, waiting to receive 25/10- Comms room not sheeted yet 31/10- Comms room location changed 23/11- Unable to contact 23/11- Comms room built, waiting for door. will be done next week 30/11- Comms room ready, need to get SWMS approved and have inductions 01/12- SWMS submitted 13/12- Civils and haul completed, waiting on internals 06/01- Internals completed, scheduled for first week back pending SWMS and inductions | 30/01/2019 |  |  |  |  | 14/02/2019
AYCA-4UXA3J | 1 and 4 Fox Glove Close, Green Point | SDU | FTTP - Type 3 (MT-LFN) | 2ERN-03 | Dave Yeomans | #N/A |  |  | Completed | [10 empty] | 2018-07-13 | [7 empty] | 06/07 - Finalising splicing 09/07 | 2018-07-25 |  |  |  |  | 2018-07-13 | Jul-18
AYCA-4V7F3M | 23 Willeroo St, Lakemba, NSW, 2195 | MDU Externals | FTTP - Type 2 | 2LAK-22 | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | X | [5 empty] | 20/07/2018 |  |  |  |  | 19/07/2018 | Jul-18 |  | 18/07 - Splicing scheduled 19-20/07 | 25/07/2018 |  |  |  |  | 2018-07-23 | Jul-18
AYCA-4VCIKM | 2A Thorncraft Parade - Arrage Group | MDU Externals | FTTP - Type 3 (MT-LFN) |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-04-27 |  |  |  |  | 2018-04-26 | Apr-18 |  |  | 2018-05-02 |  |  |  |  | 2018-04-29 | Apr-18
AYCA-4VFYJV | 27-37 Percy St, Bankstown | MDU Externals | FTTP - Type 2 | 2BAN-64 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-07-04 |  |  |  |  | 2018-07-04 | Jul-18 |  |  | 2018-07-03 |  |  |  |  | 2018-06-07 | Jun-18
AYCA-30GQWB | 16-20 Withers Rd, Kellyville, NSW- 2155 | MDU Externals | FTTP - Type 2 | 2ROU-02 | Ertan Cicek | 2019-06-01 | Jun-19 | Dane | Developer Delay |  | TBC | TBC | TBC |  | 15/08/2018 |  |  |  |  | TBC | [7 empty] | 20/07 - Pending Material order, site visit required 26/07- Civils and haul scheduled week starting 30/07 30/07- Civils complete, haul scheduled for 31/07. Site only at the framing stage, comms room months away.
AYCA-4VJFPP | 19-21 Eve Street | MDU Externals | FTTP – Type 2 | 2NEW-22 | Ertan Cicek | 2019-01-09 | Jan-19 | Dane | Completed | James 0404663591 |  | X | X | [6 empty] | 30/11/2018 | [6 empty] | 15/10/2018 | 06/07 - Civils completed and brought pipe into boundary, lead-in not ready by developer, waiting for dev lead-in - Follow up required 25/07 - Obtained developer contact details and require follow up on when dev will link to lead-in 27/07- Advised link up will be performed in 2 weeks time 03/08 - no change 16/08 - Follow up and link up still not completed by electrician. Require further follow up directly with electrician 30/08- Developer unable to give a timeframe for the link up 11/10- Confirm Monday if link up has been completed | 2018-05-12 |  |  |  |  | 2018-11-12
AYCA-4WQIL0 | 13-15 Vista St, Penrith, NSW 2750 | MDU | FTTP- Type 2 | 2PTH-05 | Ertan Cicek | 2019-05-31 |  | Dane | Completed | Ling 0433 702 229 | [17 empty] | 15/03- Scaff due down in three weeks 15/04- Spoke to developer, Ling, LIC to beee brought out approx week starting 29/05. Agreed that i will call back for update that week. 07/05- LIC being trenched in today | [5 empty] | 2019-05-25
AYCA-4VVND3 | Clergate Road, Orange | SDU |  |  | Dave Yeomans | #N/A |  |  | Completed | [10 empty] | 2018-05-14 |  |  |  |  | 2018-05-14 | May-18 |  |  | 2018-05-23 |  |  |  |  | 2018-05-23 | May-18
AYCA-4W3F0S | 51-53 Foxall Road, Kellyville | SDU | FTTP - Type 2 | 2ROU-03 | Andrew Mahasay | #N/A | #N/A | Dane | Completed | [10 empty] | TBC |  |  |  |  | 2018-09-03 | Sep-18 |  | 03/08- LAANs received, 15th Aug start date 16/08 - Ready to schedule 28/08- Scheduled 29/08 31/08 - Construction proposal submitted, waiting for NBN FS and NBN PM for response to proceed with options | 2018-09-05 |  |  |  |  | 2018-09-04 | Sep-18
AYCA-4W4BKH | Strathfield Golf Club - 1 - 38 Weeroona Rd - EXTERNAL | MDU Externals | FTTP – Type 2 | 2HOM-02 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-06-22 |  |  |  |  | 20/06/2018 | Jun-18 |  |  | 22/06/2018 |  |  |  |  | 2018-06-22 | Jun-18
AYCA-4W4BKH | Strathfield Golf Club - 1 - 38 Weeroona Rd - INTERNAL | MDU Internals | FTTP – Type 2 | 2HOM-02 | Nabeel Jaimon | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-06-22 |  |  |  |  | 2018-06-21 | Jun-18 |  |  | 2018-06-25 |  |  |  |  | 2018-06-25 | Jun-18
AYCA-4VSW7K | 10-12 Vista St, Penrith, NSW- 2750 | MDU Externals | FTTP - Type 2 | 2PTH-05 | Ertan Cicek | 2019-05-25 | May-19 | Dane | Developer Delay | Rob 0411 363 678 | TBC | TBC | TBC |  | 27/07/2018 |  |  |  |  | TBC | [7 empty] | 20/07 - Materials ordered, pending site visit 24/07- Site in very early stages, still escavating 03/08 - no change 02/05- Haul complete, link up ready as advised by developer 07/05- Link up not yet complete, due in the next week or so. riser and cable tray also not complete
AYCA-4W7GEZ | 173-175 Norton St - Stage 2 | MDU Externals | FTTP – Type 2 |  | VPL | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-05-22 |  |  |  |  | 2018-05-22 | May-18 |  |  | 2018-05-25 |  |  |  |  | 2018-05-25 | May-18
AYCA-4W844H | 18A Grey Gum Rd, Denman, NSW 2328 | SDU | FTTN | 2DNM-20 | Mark leal | 2019-02-28 |  | Dane | Completed | Tammy Dever 02 6543 2475 admin@hbsurveys.com.au |  |  |  |  | 2018-06-11 | [12 empty] | 20/11- Copper jointer scheduled to scope week starting 03/12 14/12- Site scoped, trench dug for pit and pipe work to service back two lots, needs to be linked up | [5 empty] | 21/02/2019
AYCA-3CIGB0 | 1-3 Balmoral St, Waitara, NSW 2077 | MDU | FTTP - Type 2 | 2WRO-63 | Ertan Cicek | 2019-09-06 |  | Dane | Site Visit | Michael 0417 415 337 |  |  |  |  | 2018-07-11 | [12 empty] | 25/03- LIC to be brought out within next few weeks 28/03- Crane needs to be taken down, approx 2 months. Handover in July
AYCA-36XIQO | 9 Fairway Drive, Kellyville | SDU | FTTP - Type 2 | 2KEL-07 | Mark Leal | 2019-05-20 | May-19 | Dane | Completed | [5 empty] | 2019-06-05 | [12 empty] | 05/04 - NDD to be submitted 08/04 16/04- DDD submitted 15/04 29/04- DDD approved | [5 empty] | 22/05/2019
AYCA-4X6TWU | 43-47 Harrow Road - Omar Mosque - EXTERNAL | MDU Externals | FTTP – Type 3 (MT-LFN) | 2LID-08 | Ertan Cicek | 2019-02-15 | Feb-19 | Dane | Completed | Kassem 0405719942 Adel 0406987404 Nayes 0415340197 | [9 empty] | TBC | X | [6 empty] | 06/07 - Advised by NBN, site revised EFSCD in November, site pushed out 10/07 - No change 26/07: No change 03/08 - no change 28/09- Conduit has been brought to boundary, waiting for electrcians details to cofirm it has been linked 11/10- Advised call at end of month for follow up 26/10- Link up completed, waiting for cable tray and comms room, developer to advise dates for these to be ready 02/11- Main switch room a month away 14/12- Switch room ready 14/12- Advised internals wont be ready until late Feb | TBC |  |  |  |  | 21/02/2019
AYCA-4X6TWU | 43-47 Harrow Road - Omar Mosque - INTERNAL | MDU Internals | FTTP – Type 3 (MT-LFN) | 2LID-08 | Nabeel Jaimon | 2019-02-15 | Feb-19 | Dane | Completed | [10 empty] | TBC | [7 empty] | 06/07 - Advised by NBN, site revised EFSCD in November, site pushed out 10/07 - No change 26/07: No change 03/08 - no change 14/12- Advised internals wont be ready until late feb | TBC |  |  |  |  | 21/02/2019
AYCA-4XC850 | 50-54 Rodley Ave, Penrith, NSW 2750 | MDU Externals | FTTP - Type 2 | 2PTH-05 | Ertan Cicek | 2019-01-04 |  | Dane | Completed | [18 empty] | Civils complete, waiting on design 28/03- DDD submitted
AYCA-4XR9F8 | 320 Annangrove Rd, Rouse Hill, NSW- 2155 | MDU Externals | FTTP - Type 3 (MT-LFN) | 2ROU-02 | Ertan Cicek | 2019-02-28 | Feb-19 | Dane | Completed | Eric Long 0430088617 Guy 0422 384 166 Wayne Cash | TBC | TBC | TBC |  | 2018-01-08 |  |  |  |  | TBC | [6 empty] | 14/01/2019 | 20/07 - Materials ordered, pending site visit 26/07: No change 03/08 - no change 22/08 - Development very early stages. Slab at the moment. Require follow up later 19/10- LIC trenching starting next week 26/10- Unable to contact 16/11- LIC built, waiting on comms room 15/03- CVivils and splicing complete | 2019-10-04 |  |  |  |  | 2019-11-04
AYCA-4XTH50 | 31-35 Smallwood Ave | MDU Externals | FTTN | 2HOM-03 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | X | [5 empty] | 2018-05-29 |  |  |  |  | 2018-05-25 | May-18 |  |  | 2018-06-01 |  |  |  |  | 2018-05-30 | May-18
AYCA-4YHOA0 | 8-12 Robilliard St, Mays Hill, NSW 2145 | MDU | FTTP- Type 2 | 2PAR-63 | Ertan Cicek | 2019-03-16 |  | Dane | Completed | [5 empty] | 2018-12-19 | [12 empty] | 07/12- Lead in and comms room ready 02/03- Scoping week starrtting 04/03 07/03- Ready for link up, footpath not due for another month or so | [5 empty] | 17/04/2019
AYCA-4YJULB | 479 Henry Lawson Drive - INTERNAL | MDU Internals |  |  | Nabeel Jaimon | 2019-01-25 | Jan-19 | Dane | Completed | Electrician 0427 996 092 | TBC | TBC | TBC | [6 empty] | TBC | X | [6 empty] | 06/07 - Advised by Nabeel, site not ready for a while - Externals on this EFSCD 29/10 26/07: No change 03/08 - No change 16/11- Everything installed, waiting on externals and electrician to install power points for NTDs 23/11- Unable to contact | TBC |  |  |  |  | 2018-12-14
AYCA-4YPJJH | 62 Hume Highway | MDU Externals | FTTP – Type 2 | 2BAN-60 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-05-04 |  |  |  |  | 2018-05-04 | May-18 |  |  | 2018-05-04 |  |  |  |  | 2018-05-04 | May-18
AYCA-4YZGFK | 51 Boronia Street | MDU Externals | FTTP – Type 3 (MT-LFN) | 2PEN-66 | Ertan Cicek | 2019-01-25 | Jan-19 |  | Completed |  | X | X | X | X | [5 empty] | 2018-06-01 |  |  |  |  | 2018-05-25 | May-18 |  |  | 2018-06-06 |  |  |  |  | 2018-05-30 | May-18
AYCA-4Z4FSB | Mainfreight Logistics - 36B Kookaburra Rd N | MDU Externals | FTTN | 2MIL-20 | Ertan Cicek | #N/A | #N/A | Dane | Completed | Michael 0417675931 | [9 empty] | 2018-10-12 |  |  | X |  | 2018-10-05 |  |  | 06/07 - Followed up with developer, advised follow up in 1 months time from 20/06 to obtain update for us to perform drill shot - Michael 0417675931 20/07- Have not been able to contact 25/07 - Made contact, developer advised 4 weeks time for pathways and lead-in brought out. Street works also to commence that time. 03/08 - No change 15/08- Awaiting developer to build new kerb, estimated 2 weeks. Can then potentially book in a driller as soon as the developer confirms water lead in depths 16/08 - Provide heads up to driller about job coming up soon 30/08 - Waiting to confirm driller availability 03/09- Developer ready 05/09- Drill shot to be completed 15/09 14/09 - Drill shot done. 40m Trench to Cnr Yarrunga, install 8 pit, Link up 2 x P100s dev 04/10 - Completed | 2018-10-17 |  | X |  |  | 18/10/2018 | Oct-18
AYCA-4S2PFJ | 273-279 Sussex St, Sydney | MDU Externals | FTTP- Type 2 | 2CYS-03 | Ertan Cicek | 2019-05-17 | May-19 | Dane | PC | [18 empty] | 18/04- PDH installed
AYCA-4Z992M | 2A Napier St and 17 Blue Hills Ave Goonellabah | Tech Choice Type 3 | FTTP - Type 3 (MT-LFN) | 2LIS-21 | Mark Leal | #N/A |  | Dane | Completed | [10 empty] | 17/08/2018 |  |  |  |  | 16/08/2018 | Aug-18 |  | 06/07 - Waiting on 12F Double ended tether - 16/07 19/07- still waiting on materials, ETA 13/08 26/07: No change 03/08 - awaiting for 500m double ended tehter to schedule. Advised by Mark that material will be available to NBN warehouse on the 6th of August 07/08- Scheduled in for week starting 13/08 | 22/08/2018 |  |  |  |  | 2018-08-17 | Aug-18
AYCA-50FP2M | d | SDU | FTTP - Type 2 | 2ROU-03 | Sogand Mohtat | #N/A | #N/A | Dane | Completed | [10 empty] | 2018-09-28 | X |  |  |  | 27/09/2018 | Sep-18 |  | 04/07 - Awaiting for revised LAANs due to major chages in civil works 12/07 - Followed up on revised LAANs 17/07- LAANs approved, organising a driller for an early start 19/07- Civils started, pit upgrades and prep for driller. 26/07- Drill commencing 06/08 03/08 - Drilling pushed out 17/08 - Field completion by 28/09, PC by 08/10 | 2018-10-03 |  |  | X |  | 2018-10-03 | Oct-18
AYCA-51V8JL | 11 Thomas Mitchell Drive Muswellbrook NSW 2333 | MDU Externals | FTTP- Type 3 | 2MUS-03 | Ertan Cicek | #N/A |  | Dane | Completed |  | X | X | X | [6 empty] | 17/08/2018 |  |  |  |  | 2018-08-17 | Aug-18 |  | 06/08- Civils scheduled week starting 13/08 10/08 - Splicing scheduled likely 14/08 17/08 - Field completion 17/08 and PC 20/08 | 2018-08-20 |  |  |  |  | 2018-08-20 | Aug-18
AYCA-52950S | 147 Liverpool Road - United Apartments - 1 | MDU Externals | FTTP – Type 2 |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | X | [5 empty] | 2018-04-11 |  |  |  |  | 2018-04-10 | Apr-18 |  |  | 2018-04-17 |  |  |  |  | 2018-04-17 | Apr-18
AYCA-52OEM0 | 33 Darley Street East, Mona Vale | MDU Externals | FTTP - Type 3 (MT-LFN) | 2MON-25 | Ertan Cicek | 2019-02-04 | Feb-19 | Dane | Completed | [5 empty] | 22/06/2018 |  |  |  |  | TBC | X | [6 empty] | 06/07 - Site ready in late sept, need to confirm when LPC will be ready 26/07: No change. 03/08 - no change 16/08 Followed up - lead-in ready late Oct. Require 2 x ACM upgrade as pits are completely crushed/damaged. 1. Lead-in pit, 2. route pit 31/08 - Pending revised design of lead-in pit issue. Internal plans do not match original plan. Pending NBN internal plan 11/10- site follow up 12/10/2018 12/10- Developer advises another month until lead in conduit is built 30/11- Scheduled for 10/12 14/12- Civils complete, pending haul and splice | [5 empty] | 22/02/2019
AYCA-52UC2N | Beech Road, Casula | MDU Externals | FTTP - Type 3 (MT-LFN) | 2WRO-63 | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-03-07 |  |  |  |  | 2018-03-07 | Mar-18 |  |  | 2018-07-06 |  |  |  |  | 2018-07-05 | Jul-18
AYCA-4BA1DQ | 3 Rowe Drive Potts Hill, NSW 2143 | MDU | FTTP - Type 2 | 2SEF-01 | Ertan Cicek | 2019-05-04 |  | Dane | Site Visit | [5 empty] | 2018-07-11 | [12 empty] | 07/03- Vacant lot, advised it will not be built for another year
AYCA-52VCLT | Annandale Place - 1 - | MDU | FTTP - Type 2 | 2NEW-20 | Ertan Cicek | 2019-02-16 |  | Dane | Completed | Matthew site manager 04 210 432 24 Goktay TGB electrical 0405 692 915 |  |  |  |  | 2018-06-11 | [5 empty] | X | [5 empty] | 2019-01-07 | 09/11- LAANs and contact requested 14/12- Scaff still in the way, due to be taken down next week. Schedule for early in the new year 11/01- Telstra relocation works commencing 22/01, schedule our link up for 23rd 15/02- Blockages to be cleared week starting 18/02 22/03- Haul complete | [5 empty] | 2019-05-04
AYCA-52ZO0L | 32 Norval Street - EXTERNAL | MDU Externals | FTTP – Type 2 | 2LID-04 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 27/07/2018 |  |  |  |  | 23/07/2018 | Jul-18 |  | 06/07 - Lead-in accessibility wont be ready till 21/07 16/07 - Scheduled civils and hauling to be done 21/07, schedule splicing next week | 2018-08-01 |  |  |  |  | 2018-07-24 | Jul-18
AYCA-52ZO0L | 32 Norval Street - INTERNAL | MDU Internals | FTTP – Type 2 | 2LID-04 | Nabeel Jaimon | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 27/07/2018 |  |  |  |  | 23/07/2018 | Jul-18 |  | 06/07 - Lead-in accessibility wont be ready till 21/07 developer delay 16/07 - Internals physical devices installed, waiting on Externals to be completed to perform tests | 2018-08-01 |  |  |  |  | 2018-07-24 | Jul-18
AYCA-53063P | 23 Mayberry Cres, Liverpool | MDU Externals | FTTP – Type 2 |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | X | [5 empty] | 2018-04-11 |  |  |  |  | 2018-04-06 | Apr-18 |  |  | 2018-04-10 |  |  |  |  | 2018-04-09 | Apr-18
AYCA-53E534 | 25 Glenfield Road - Glenfield Gains - EXTERNAL | MDU Externals | FTTP – Type 2 |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-05-14 |  |  |  |  | 2018-05-14 | May-18 |  |  | 2018-05-16 |  |  |  |  | 2018-05-15 | May-18
AYCA-53E534 | 25 Glenfield Road - Glenfield Gains - INTERNAL | MDU Internals | FTTP – Type 2 |  | Nabeel Jaimon | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-06-08 |  |  |  |  | 2018-06-08 | Jun-18 |  |  | 2018-06-08 |  |  |  |  | 2018-06-08 | Jun-18
AYCA-541Y7O | 728-730 Beechwood | SDU | FTTP - Type 3 (MT-LFN) | 2WAU-20 | Mark Leal | #N/A |  |  | Completed | [10 empty] | 2018-06-18 |  |  |  |  | 2018-06-18 | Jun-18 |  |  | 2018-06-29 |  |  |  |  | 2018-06-29 | Jun-18
AYCA-54DAGS | 29 Park Ave, Kingswood, 2747 - NSB | NSB |  | 2PTH-07 | Mark Leal | 2018-03-01 | Mar-18 |  | In Design |  | TBC | TBC | TBC | [6 empty] | TBC | [7 empty] | 06/08- Under Design 31/08 - Survey completed, on-hold 18/01- On hold
AYCA-54N6L7 | 104-108 Bridge Road, Westmead, NSW 2145 | MDU | FTTP- Type 2 | 2PAR-60 | Ertan Cicek | 2019-03-08 |  | Dane | Completed | [5 empty] | 2018-06-12 | [12 empty] | 02/03- Scheduled WS 04/03 for civils 07/03- Civils complete, haul and splice outstanding | [5 empty] | 17/04/2019
AYCA-56PJ6I | 645 Pacific Hwy, Kanwal, NSW- 2259 | MDU Externals | FTTP - Type 3 (MT-LFN) | 2GRK-01 | Ertan Cicek | 2019-05-04 | May-19 | Dane | Completed | Darren 0417385199 | TBC | X | X |  | 2018-01-08 |  |  |  |  | TBC | [6 empty] | 23/11/2018 | 15/06 - Pending material order and Site Visit 17/07- Materials ordered, site visit 23/07 17/08 - no change 11/10- Building only at ground level, advised the site has been pushed ut until February 2019. Call for follow up late November as they will potentially be ready for us then 14/12- Still on first level, site pushed out to March, Comms room and pathways complete, lead in waiting on scaff to come down 02/03- Scoping WS 04/03 18/04- Civils and haul complete, splicing to commence 06/05 | [5 empty] | 17/05/2019
AYCA-54QSHT | 42A Kurrajong Rd, Prestons - INTERNAL | MDU Internals |  |  | Nabeel Jaimon | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-06-19 |  |  |  |  | 2018-06-19 | Jun-18 |  |  | 2018-06-19 |  |  |  |  | 2018-06-19 | Jun-18
AYCA-54SUCD | Warehouse Place, Berkeley | SDU | FTTP – Type 3 (MT-LFN) | 2PKE-06 | Mark Leal | #N/A | #N/A |  | Completed | [10 empty] | 2018-07-04 |  |  |  |  | 2018-07-03 | Jul-18 |  |  | 2018-07-09 |  |  |  |  | 2018-07-05 | Jul-18
AYCA-54VFA3 | 50 Squires Cres | SDU | FTTN |  | Sogand Mohtat | #N/A |  |  | Completed | [10 empty] | 2018-05-02 |  |  |  |  | 2018-05-02 | May-18 |  |  | 2018-05-07 |  |  |  |  | 2018-05-07 | May-18
AYCA-5SX5PK | 51-55 Burraneer Bay Road, Burraneer, NSW 2230 | MDU | FTTP - Type 3 (MT-LFN) | 2CRO-23 | Ertan Cicek | 2019-05-01 |  | Dane | Completed | Stuart 0403 024 052 | [17 empty] | 18/01- Advised to come in end of Feb, around the same time footpath will be getting repoured | 17/05/219 |  |  |  |  | 17/05/2019
AYCA-5576QH | Ghersi Avenue, Wamberal | MDU Externals | FTTP – Type 2 | 2TGL-02 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-09-07 |  |  |  |  | 2018-09-10 | Sep-18 |  | 06/07 - External route proven with civils completed, hauled cable up to lead-in pit. 2-3 weeks away from 28/06 until lead-in ready 12/07 - Developer advised should be ready by end of next week 20/07 20/07 - Developer not complete link to MDF. Still excavating power and telco conduits which not occured on Seaview Rd by dev. Pending dev 25/07 - Follow up with Comms Connect 26/07- link up by developer completion by next week 27/07- Advised lead in to be 3 weeks away 03/08 - no change 16/08 - Advised by foreman can attend to link dev pipe after 20/08, schedule civil/haul/splice week commencing 20/08 22/08 - Developer not ready yet, waiting on power conduit to be lowered.. require to confirm complete 31/08 - Advised power works happening today, dev was unaware require to bring lead-in to boundary, should have corehole and lead-in ready by Monday. Follow up Monday to confirm civil mobilisation 5/09- Unable to contact developer | 2018-09-21 |  |  |  |  | 2018-09-21 | Sep-18
AYCA-55AQIZ | 3 Mungo Scott Place, Summer Hill, NSW 2130 | MDU | FTTP- Type 2 | 2ASH-63 | Ertan Cicek | 2019-02-16 |  | Dane | Completed | [10 empty] | 2019-01-02 | X | [6 empty] | 11/01- Waiting for materials | 2019-06-02 |  |  |  |  | 2019-07-02 | Jul-19
AYCA-55AZ5J | 2 Smith st, Summer Hill, NSW 2130 | MDU | FTTP- Type 2 | 2ASH-63 | Ertan Cicek | 14/12/2018 |  | Dane | Completed | [5 empty] | 22/11/2018 | [5 empty] | X |  |  |  | 29/11/2018 |  |  | 14/11- Dependant project in service, materials ordered, waiting on LAANs 15/11- Ertan advises possible change of external design 23/11- Scheduled for RRP week starting 26/11 | 2018-12-12 |  |  |  |  | 13/12/2018
AYCA-55F4KR | Revesby Industrial Site - 1 | MDU Externals | FTTN |  | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-05-04 |  |  |  |  | 2018-05-04 | May-18 |  |  | 2018-05-04 |  |  |  |  | 2018-05-04 | May-18
AYCA-3S7B4B | University of Technology Sydney | MDU Externals | FTTP - Type 2 | 2HMK-02 | Ertan Cicek | 2019-04-30 | Apr-19 | Dane | Completed |  | TBC | TBC | TBC |  | 2018-06-08 |  |  |  |  | TBC | X | [6 empty] | 22/07 - Material order request sent, site visit required 26/07- Need to contact Sevices Manager 03/08 - no change 30/08- Site meeting 31/08 03/09 - Site visited, SWMS/Scope sent to UTS PM, LPC not ready, approx Sept/Oct, need also ROL-Night works 07/09 - Revising SWMS 21/09 - Mid Oct scheduled in for construction 27/09- Now aiming for November when the hoarding will be taken down 12/10- Another site meeting booked as Richard Crookes has lost our SWMS 09/11- Waiting on SWMS approval 30/11- Scheduled for 5th and 6th Dec 13/12- Civils completed, blockages identified, need a new ROL in order to investigate further 06/01- ROL receievd for week starting 07/01 02/03- Waiting for internals 07/03- No Change 18/04- Scheduled Wednesday 24/04 02/05- Unable to get red light through from DJL-002 and DJL-004, need to investigate further 09/05- Further investigation unsuccessful. Need to recieve full asbuilt of DSS-003. Requested | [5 empty] | 2019-05-27
AYCA-55JW1J | 188 Maroubra Road | MDU Externals | FTTP – Type 2 | 2BOT-01 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 14/09/2018 |  |  |  |  | 2018-09-18 | Sep-18 | 2018-08-06 | 06/06 - A END does not exist and waiting on PDH (approx 4 weeks from 20/07) 26/07 - PDH aimed to be installed by 03/08 03/08 - awaiting advise from Ertan in regards to PDH installation 06/08- PDH to be installed this week, Spicing scheduled for week starting 13/08 09/08 Awaiting NBN confirmation on PDH 13/08 - PDH confirmed installed. Forecast splicing week commencing 13/08 15/08- Waiting for confirmation of a end 06/09 - Confirmed A end built. Scheduling for WS 10/09 | 2018-09-20 |  |  |  |  | 2018-09-21 | Sep-18
AYCA-55KUFO | 31 Bay Road Taren Point NSW 2229 | MDU Externals |  |  | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-08-21 |  |  |  |  | 2018-08-23 | Aug-18 |  | 06/07 - Identified need to drop pit over P100 exist, link lead-in, booked in for gas spotter 21st july. 25/07 - Civils completed, haul and splice commenced 24/07. Civil delayed due to defects on the developer pit and pipe 26/07 - PC aimed by 31/07 10/08- Pit Relocation scheduled 13/08 16/08- PCD termination scheduled 21/08 22/08 - Civil build unexpected - additional 15-20m trench, removing trees out of way, PC docs in 24/08 | 2018-08-27 |  |  |  |  | 2018-08-27 | Aug-18
AYCA-55JR8W | 228 King Street, Newtown, NSW- 2042 | MDU Externals | FTTP - Type 3 | 2NEW-21 | Ertan Cicek | 2019-03-25 | Mar-19 | Dane | Site Visit | Peter 0411 694 959 |  |  |  |  | Requested | [12 empty] | 28/08 - Materials ordered, CLAAN requested, contact details requested 28/03- No LAANs, no A end, tunnel network 04/04- Advised LAANs will be received in 4-6 weeks 11/04- New design to be issues 09/05- Recieved new LAANs, waiting for heritage exemption 24/05- Waiting for confirmation on tunnel 28/05- Tunnel confirmed, waiting for Telstra plans
AYCA-55S741 | 116 Broken Bay, Ettalong Beach | SDU | FTTN | 2WOY-03 | Mark Leal | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-06-14 |  |  |  |  | 2018-06-13 | Jun-18 |  |  | 2018-06-14 |  |  |  |  | 2018-06-14 | Jun-18
AYCA-55XM3V | 10-12 Roger St, Brookvale, NSW,2100 | New Devs - MDU | FTTP - Type 2 | 2HBD-20 | Ertan Cicek | 28/02/2019 | Feb-19 | Dane | Completed | Chris 0435 829 566 | TBC | X | X | TBC | LAANs waived |  |  |  |  | TBC | X | [5 empty] | 23/11/2018 | 19/10- Materials ordered 08/11- Advised builder to bring his corehole out from corner, waiting for comfirmation this is complete 16/11- Advised to call back next Friday 13/12- Civils completed, haul outstanding, internals not yet complete 18/01- Haul scheduled week starting 21/01 19/02 - Hauling completed | [5 empty] | 2019-05-04
AYCA-55ZVL2 | 45 Foxall Road, Kellyville | SDU | FTTP - Type 2 | 2ROU-03 | Mark Leal | #N/A |  | Dane | Completed | [5 empty] | 2018-01-10 |  |  |  |  | 2018-10-08 |  |  |  |  | 2018-08-10 | Aug-18 |  | 18/09 - Requested if dependency site completed for commence of patching/testing only 25/09 - LAANs received, start 01/10 02/10 - Commence WS 02/10 05/10 - Weather pushed splicing, WS 08/10 ,Patching and testing only | 2018-11-10 |  |  |  |  | 2018-10-10 | Oct-18
AYCA-562Y8R | 900 Wilton Rd, Appin NSW | SDU | FTTP - Type 3 (MT-LFN) | 2APN-01 | Mark Leal | #N/A |  | Dane | Completed | [5 empty] | 2019-01-14 |  |  |  |  | 15/02/2019 |  | X |  |  | 15/02/2019 |  | 2019-01-07 | 13/11 - Crew attending today, possible internal SDS haul difficulty 16/11- Blockages identified, ACM pit upgrades required. link up to new LIC 20/11- To revise dates on Thursday after we RRP 23/11- new build proposal to come on Monday 01/12- New proposal sent 14/12- Waiting on new LAANs, driller scheduled for mid Jan 06/01- New LAANs commence 14/01 | 20/02/2019 |  |  |  |  | 20/02/2019
AYCA-56B97M | 1 Tangerine St, Fairfield East | MDU Externals | FTTP - Type 2 | 2SEF-61 | Ertan Cicek | 2019-01-30 | Jan-19 | Dane | Completed |  | X | X | X | [6 empty] | 2018-09-28 | X |  |  |  | 26/09/2018 |  |  | 06/07 - Civils and hauling complete, lead-in not ready from dev, brought to boundary 10/07 - Require follow up with developer when lead-in linked 13/07- Developer to call back with an update once he has spoken to eletrician, call george 0413726907 20/07- Developer has still not answered 25/07- Developer has still not answered 02/08 -Contacted developer waiting for electricians details 09/08- Have not been able to conact since 02/08 10/08- Contact Radi 041134411 (electrician) to confirm link up and schedule a date to commence work 17/08- Site still delayed, Bill 0401723071 thinks it will be up and running in another two weeks 29/08- Develoepr advisesd that they are getting a new electrician, will contact me when they are ready 05/09 Electrician to complete lead in conduit week starting 10/09 10/09 - Advised lead-in completed, ready to schedule 21/09 - To confirm with developer on Monday if ready | 2018-10-05 |  | X |  |  | 2018-05-10 | May-18
AYCA-56GK8A | 79 Marmon St, Booragul - Marmong Waters Retirement Village - 3 | SDU | FTTP - Type 3 (MT-LFN) | 2BLR-03 | Mark Leal | #N/A | #N/A |  | Completed | [10 empty] | 24/08/2018 |  |  |  |  | 2018-08-24 | Aug-18 |  | 26/07 - Material order request sent, site visit required. Request for LAAN and confirmation whether we are installing up to SC2. Dependant on other site, AYCA-2JGND9 26/07- Not hauling SDS, waiting on LAANs 27/07- LAANs received ready on 15/08 03/08 - No change 16/08 - Scheduled field work commence 17/08, splicing scheduled week commencing 20/08 20/08 - Civils and hauling completed, Ready for splicing schedule | 29/08/2018 |  |  |  |  | 27/08/2018 | Aug-18
AYCA-56GQ2L | 62 Argyle Street South Windsor NSW 2756 | NSB |  | 2RCH-02 | Mark Leal | #N/A | #N/A |  | Completed | [5 empty] | 22/10/2018 |  |  |  |  | 24/10/2018 |  |  |  |  | 2018-02-11 |  |  | 28/08 - Survey laan sent 27/09, 05/09 will be survey 11/09 - Rescheduled survey to complete yesterday, FIR to be sent today (few units were locked) 09/10 - CLAANs commence 22/10 26/10- Encountered issues with RRP as the internal conduit was not to spec | 26/10/2018 |  |  |  |  | 2018-07-11 | Jul-18
AYCA-56I886 | Cecil Ash - 47 Cecil St, Ashfield | MDU Externals | FTTP – Type 2 | 2ASH-64 | Ertan Cicek | #N/A | #N/A | Dane | Completed | Angelo 0400358308 | X | X | X | [6 empty] | 25/10/2018 |  |  |  |  | 29/10/2018 |  |  | 09/07 - further developer delay, call back in two weeks 19/07- further delay, waiting for scaff to come down, 2-3 weeks 26/07: Follow up on the 6th of August 02/08 - no change 03/08- Devloper advises another two weeks untill scaff is down 15/08- Scaffolding is down, developer advises another two weeks for lead in conduit to be brought out 30/08- Developer thinks end of next week he will be putting conduit in whilst doing the sewer. 07/09 - Follow up 12/09 to see if sewer complete 14/09 - Dev advised follow up on 20/09 20/09 - Dev advised follow up on 28/09 05/10 - Confirmed booked for 09/10 10/10- Civils completed, hauling scheduled pending rain 18/10- Pushed out due to Clarke street 25/10- Pushed out required new PON Patching | 31/10/2018 |  |  |  |  | 31/10/2018
AYCA-2I98H3 | 113-117A Wigram St23-29 Hassall St | MDU | FTTP- Type 2 | 2PAR-61 | Ertan Cicek | 2019-03-22 |  | Dane | NBN Internal Delay | William 04211 586 51 | [17 empty] | 01/03- Aboriginal importance issue 02/03- Awaitijng response 07/03- No channge, developer is restoring footpath in the next few weeks 22/03- Waiting for response from NBN 28/03- No change 09/05- Waiting for heritage exemption
AYCA-56PP6W | 55-57 Chelmsford Ave, Bankstown, NSW,2200 | MDU Externals | FTTP - Type 2 | 2BAN-67 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-10-05 |  | X |  |  | 2018-09-28 |  |  | 06/07 - Encountered blockage, require dig down repair, hauling commencing 06/07, B END TBC if lead-in ready etc 25/07- follow up on 02/08 27/07- Civils and haul scheduled for week starting 30/07 01/08 - Civil done 03/08 - blockages encountered. Hauling in progress 07/08- Splicing scheduled for week starting 06/08 09/08- A end does not exist, cannot splice, awaiting update from NBN regarding A end installation 24/08 - Still waiting and also damaged internal cable. Developer installed new lead-in and may have damaged pit. Require site visit. 05/09- A end has been built 07/09 - Waiting for Internals to be built | 2018-10-10 |  |  |  |  | 2018-10-05 | Oct-18
AYCA-56YKSC | 38 Wonga Street | MDU Externals | FTTP – Type 3 (MT-LFN) | 2CAM-02 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-05-09 |  |  |  |  | 2018-05-09 | May-18 |  |  | 2018-05-14 |  |  |  |  | 2018-05-14 | May-18
AYCA-56YY5F | 120-122 Hume Highway, Canley Vale NSW | Tech Choice | FTTP - Type 3 (MT-LFN) | 2CRR-65 | Mark Leal | #N/A |  | Dane | Completed | [5 empty] | 2018-05-11 |  |  |  |  | 15/02/2019 | X | [6 empty] | 13/11 - Scheduled for R&R prove crew WS 19/11. Materials ordered 16/11- waiting for response from developer on ETA for comms room and LIC to be built 23/11- RRP scheduled week starting 26/11 27/11- pushed out until 03/11/2018, waiting on ROL 14/12- ROL receievd, waiting on 2nd LIC 11/01- Still waiting on ETA for second LIC, new ROL applied for. 19/02- Meeting organised on Monday 25/02, commence build 04/03 02/03- Second site meeting 04/03, build to commence after 12/03- Waiting for developer to move dirt pile so we can trench to pit to link up | 20/02/2019 |  |  |  |  | 2019-10-04
AYCA-4PRYRR | 161 - 163 Great Western Hwy, Mays Hill, NSW 2145 | MDU | FTTP- Type 2 | 2PAR-63 | Ertan Cicek | 2019-03-22 |  | Dane | Completed | Michael 0420 942 413 |  |  |  |  | 2018-05-12 | [12 empty] | 23/11- Waiting for confirmation of dependent sites 19/12- LIC brought out to the 3 pit next to 6 pit, not visually confirmed. Footpath due to be repoured end of Jan/ early Feb, comms room nearly ready 11/01- Scaffolding due down end of Jan, follow up then 22/03- Waiting for an ROL 11/04- No change 18/04- ROL recieved, schedule WS 29/04 02/05- Civils and haul complete, splicing outstanding 09/05- Pushed out a week due to higherdale rework | 24/05/2019 |  |  |  |  | 22/05/2019
AYCA-577BDS | 36 Huntingwood Drive Huntingwood - INTERNAL | MDU Internals |  | 2BLK-07 | Richard Huffadine | 2019-01-31 | Jan-19 | Dane | Completed | [10 empty] | TBC | [7 empty] | 06/07 - Ordered materials 06/06 13/07 - Waiting for Externals to be ready 26/07: No change 03/08 - no change 15/08- Sent update request for externals 07/03- On track for FC WE 08/03 | TBC |  |  |  |  | 28/03/2019
AYCA-57CAFW | 262A Captain Cook Dr, Kurnell | MDU Externals | FTTP - Type 3 (MT-LFN) | 2CRO-01 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-06-07 |  |  |  |  | 2018-07-04 | Jul-18 |  |  | 2018-07-09 |  |  |  |  | 2018-07-05 | Jul-18
AYCA-57CH4J | 8/268A Captain Cook Dr, Kurnell, NSW,2231 | MDU Externals | FTTP - Type 3 (MT-LFN) | 2CRO-01 | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-06-07 |  |  |  |  | 2018-07-04 | Jul-18 |  |  | 2018-09-07 |  |  |  |  | 2018-07-05 | Jul-18
AYCA-48S696 | 3-7 Wallace Street | MDU Externals | FTTP – Type 2 | 2BLK-03 | Nabeel Jaimon | 2019-03-08 | Mar-19 | Dane | Developer Delay | [10 empty] | TBC | [7 empty] | 20/07 - Field obtained incorrect contact, was another site next door which was almost complete and done by VPL. Actual site is a hole in the ground, no one onsite. 26/07: No change 03/08 - no change | TBC
AYCA-57KT5A | 153 Jamison Rd, Penrith | MDU Externals | FTTP - Type 2 | 2PTH-02 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 2018-07-20 |  |  |  |  | 2018-07-20 | Jul-18 |  | 06/07 - Comms box should be built by 06/07, require follow up 09/07 12/07- Meter box should be built 13/07. follow up friday afternoon 13/07- Confirmed PCD installation, scheduled in week commencing 16/07 17/07- to be finished by end of week | 2018-07-25 |  |  |  |  | 2018-07-23 | Jul-18
AYCA-57S6JD | 50 Violet Street, Revesby | MDU Externals |  |  | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-10-17 |  |  |  |  | 17/10/2018 |  |  | 06/07 - Site still few months out. RRP attempted; identified require night works, too many vehicles parked onto pits, blockages, HP gas require standby 03/08 - No change 30/08 - Site rod and rope required on other side of road to determine to get to the end of development and propose road crossing. Will require gas standby 06/09 - Follow up with contractor re: other side route 07/09 - Alternate route been proven today 13/09 - Original route proven during after hours with blockages rectified 14/09 - Book in gas standby to schedule civil link up 20/09 - Speak to developer to see if macquarie gas can perform trench so we can lay conduit in to link with pit 20/09 - Jemena booked 27/09 1pm 04/10 - Substation very close to the PCDs, Splitter multiports also moved back down and ACM pit now required replacing, Gas standby require booking now 05/10 - Waiting for standby to respond and confirm date 09/10- Have tried calling Jemena with no success on the 05/10, 06/10, 09/10 10/10- Gas spotter booked in for 16/10 at 700 | 18/10/2018 |  |  |  |  | 18/10/2018 | Oct-18
AYCA-57Y4AJ | 2140 Camden Valley Way | SDU | FTTP- Type 2 | 2MIL-02 | Mark Leal | #N/A |  | Dane | Completed | [5 empty] | 25/10/2018 |  |  |  |  | 23/11/2018 |  |  |  |  | 23/11/2018 |  |  | 15/10- Request for CRQ 02/11- Just MPT upgrade and patching 09/11- Still awaiting CRQ 13/11- CRQ for 21st- 23rd | 28/11/2018 |  |  |  |  | 28/11/2018
AYCA-583XDD | 117-119 Jamison Rd South Penrith NSW 2750 | SDU | FTTP - Type 2 | 2PTH-02 | Mark Leal | 2019-02-01 | Feb-19 | Dane | Completed | [5 empty] | 28/08/2018 |  |  |  |  | TBC | [7 empty] | 15/08 - Materials ordered, site visit required 16/08 - Site not ready to perform civil link up, will revisit when performing 2 x MPT swaps. CRQ in for 04/09 07/09 - Reapply CRQ, require site visit for lead-in check if dev ready 21/09 - CRQ was rejected due to no forecast attend site date, reapply 24/09 28/09- CRQ booked for 16/10 17/10 - Completed MPT swaps, leadin and individual internal lead-ins not ready. 27/11- Requires follow up in Dec 14/12- Developer has completed link ups | TBC | X
AYCA-58BKNK | 4 Junction St, Ryde - QUBE | MDU Externals |  |  | Ertan Cicek | 2019-02-02 |  | Dane | Completed |  | X | X | X | X | [5 empty] | 2018-06-20 |  |  |  |  | 21/06/2018 | Jun-18 |  |  | 2018-06-22 |  |  |  |  | 2018-06-22 | Jun-18
AYCA-58QIXQ | 35 Scott Street | MDU Externals | FTTP – Type 2 | 2LIV-02 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | X | [5 empty] | 2018-06-08 |  |  |  |  | 2018-06-06 | Jun-18 |  |  | 2018-06-13 |  |  |  |  | 2018-06-08 | Jun-18
AYCA-591MZC | Cronulla 88 Developments - 6 Gerrale Street, Cronulla | MDU Externals | FTTP - Type 3 | 2CRO-21 | Ertan Cicek | #N/A | #N/A |  | Completed | Charlie 0401838342 | X | X | X |  | 28/08/2018 |  |  |  |  | 2018-09-14 |  |  |  |  | 2018-09-19 | Sep-18 |  | 15/08 - Materials ordered. LAAN requested, contact details requested, site visit required 28/08- Internals complete | 2018-09-20 |  |  |  |  | 2018-09-21 | Sep-18
AYCA-59CA2X | 13 Stafford St, Kingswood, NSW- 2747 | SDU | FTTP - Type 2 | 2PTH-02 | Mark Leal | #N/A | #N/A | Dane | Completed | [10 empty] | 27/09/2018 | X |  |  |  | 2018-09-27 | Sep-18 |  | 24/07 - CRQ Required to be raised and scheduled for MPT swap 26/07- Waiting to hear back from Mark Leal regarding haul 26/07- CRQ request sent 27/07- LAANs received 03/08 - CRQ booked in for 27/08 14/08- Pending site visit and MPT swap 28/08- Splicer discovered bad splice in AJL, rescheduled for completion 29/08 29/08- Fault was between AJL and MPT, requires rehaul. Blockages found on first attempt 07/09 - Reraise CRQ, 25-27 September, blockage on run, require RRP and Civils | 2018-10-04 |  | X |  |  | 2018-10-10 | Oct-18
AYCA-59DV6W | 41 Nelson St, Fairfield-NSW | MDU Externals | FTTP – Type 2 | 2CRR-72 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | TBC |  |  |  |  | 2018-07-30 | Jul-18 | 30/07/2018 | 06/07 - Issues with tracing connection from exchange to MPT, could be faulty MPT. Not proceeding to swap yet, need further investigation 12/07 - Further investigation booked in 13/07 25/07 - Fibre cut, solution proposed to NBN, waiting on NBN response - follow up with Ertan 26/07 - Email received from Ertan. waiting for approval from design and FS. estimated 2 days left of construction | 2018-08-03 |  |  |  |  | 2018-08-03 | Aug-18
AYCA-5A2Y34 | 100 George Street, East Maitland | MDU Externals | FTTP – Type 2 | 2MAI-03 | Ertan Cicek | 2019-02-15 | Feb-19 | Dane | Completed | Keith 0409 078 073 | TBC | TBC | TBC | [6 empty] | TBC | X | [5 empty] | 2019-01-07 | 06/07 - Ordered materials 06/06, require site visit 26/07: Proposed site visit by the 3rd of August 03/08 - Site in early stages of construction 27/09- Still waiting for first level to be built. Developer advises atleast a month 19/10- Developer advises another three weeks 11/01- LIC ready, sheeting walls of comms room | TBC |  |  |  |  | 19/03/2019
AYCA-5ALZB0 | 6 Woods Close, Huntingwood | MDU Externals | FTTP - Type 2 | 2BLK-07 | Ertan Cicek | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-07-06 |  |  |  |  | 2018-07-06 | Jul-18 |  |  | 2018-07-06 |  |  |  |  | 2018-07-06 | Jul-18
AYCA-5ALZB0 | 6 Woods Close, Huntingwood | MDU Internals | FTTP - Type 2 | 2BLK-07 | Nabeel Jaimon | #N/A |  |  | Completed |  | X | X | X | [6 empty] | 2018-07-06 |  |  |  |  | 2018-07-06 | Jul-18 |  |  | 2018-07-06 |  |  |  |  | 2018-07-06 | Jul-18
AYCA-5AVN4W | 23-25 Forest Grove, Epping | MDU Externals | FTTP - Type 2 | 2EPP-62 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 22/08/2018 |  |  |  |  | 2018-08-23 | Aug-18 |  | 06/07 - Scheduled crew civils RRP + Civils 12/07 - site also still early 12/07 - Need to send alternate route plan road crossing to Ertan, require revised LAANs 25/07 - Advised design on new MPT location, waiting for revised LAANs. 26/07 - LAAN waiver received. civils scheduled for week starting 30/07 01/08 - multiple blockages. at least 3 blockages. 09/08- Road crossing does not exist, one blockage will require a new build, MPT needs to be oved to 8 pit on corner of Maida and Forest Grove to avoid joining tethers 09/08- Need to prove alternate route before sending proposal 15/08- Proposal sent and approved, civils and haul feild completion 17/08 | 23/08/2018 |  |  |  |  | 23/08/2018 | Aug-18
AYCA-5AXHNZ | 4 Murray Rose Ave, Sydney Olympic Park, NSW, 2127 | MDU Externals | FTTP - Type 3 (MT-LFN) | 2SIL-02 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X |  | 18/07/2018 |  |  |  |  | 2018-10-08 |  |  |  |  | 2018-10-08 |  |  | 09/07 - Materials ordered, Site visit required 26/07: Site visit organised for 27/07 03/08 - awaiting for design response 09/08- Design approved, waiting for new job pack and CTL installation dates from Ertan 22/08 - Pending SOPA Permit, submitted on 27/08 20/09 - Delay on SOPA, require follow up 04/10 - Site access issues regarding boom lift, require another boom lift that can be utilised on the ramp to cable tie haul cable. Success to get access with hours behind, potential PC submit now 05/10 05/10 - Change of design, cable damaged, build pushed out till 08/10 | 2018-10-09 |  |  |  |  | 2018-10-10 | Oct-18
AYCA-5BOGUB | 11B Lachlan St, Waterloo, NSW 2017- Externals | MDU | FTTP- Type 2 | 2RED-01 | Ertan Cicek | 2019-02-22 |  | Dane | Completed | James 0417 430 622 |  |  |  |  | 2018-12-12 | [12 empty] | 22/01- public domain works due in fortnight 11/02- New design underway, LAANs ciommence 26th Feb, need to do work inside site before this and tie in with public domian works 15/02- LAANs commence 26/02, scheduled to start on 25/2 internally | [5 empty] | 18/04/2019
AYCA-4L1IJG | 19 Gregory St South West Rocks, NSW 2431 | MDU | FTTP- Type 2 | 2SWR-20 | Ertan Cicek | 2019-03-08 |  | Dane | In Construction | [5 empty] | 20/11/2018 | [12 empty] | 23/11- Materials sent to contractor, site visit to come 14/12- Multiple blockages identified, new route confirmed but requires 60m new build 11/01- New proposal sent through 14/03- Hauling route exceeds 500m, new design proposal sent through 22/03- new design approved, no CWP 11/04- Cable hauled, waiting for lead in to be brought out to do civils
AYCA-5BX3DW | 7-9 Hutchinson St, St Peters | MDU Externals | FTTP - Type 3 (MT-LFN) | 2NEW-23 | Ertan Cicek | #N/A | #N/A |  | Completed | 0416132133 | X | X | X | [6 empty] | 2018-08-31 |  |  |  |  | 2018-08-31 | Aug-18 |  | 06/07 - Potentially October A END will be available. NBN to find alternative A END 12/07 - Ertan to follow up 25/07 - Alternative route, waiting on parent site (MPT): (AYCA-3RKWY1) - scheduled to complete October. DT to remove FSD cable 02/08 - Advised MPT will be installed 17/08 09/08- MPT location changed, awiting PON Patching 16/08 - VPL installing end of week. Possible commencement week commencing 20/08 21/08 - Hauling completed but BMPT from VPL not installed. Advised NBN. 24/08 - Advised MPT install should be done on weekend, schedule 27/08 week starting | 2018-08-31 |  |  |  |  | 2018-08-31 | Aug-18
AYCA-4ULUDH | 5-7 Higherdale Ave., Miranda | MDU | FTTP- Type 2 | 2MIR-26 | Ertan Cicek | 30/07/2019 |  | Dane | Site Visit | Nicholas 0421 470 884 Sharbel 0411 080 672 | [17 empty] | 18/01- Site very early stages, due end of Feb 01/03- R%ough in no yet started, site approx 4-5 months away from handover
AYCA-5CMO2F | 6 Parish Dr, Beresfield, NSW- 2322 | MDU Externals |  | 2TAR-01 | Ertan Cicek | 2019-02-22 | Feb-19 | Dane | Completed | Bruce 0416 282 166 | TBC | TBC | TBC |  | 24/08/2018 |  |  |  |  | TBC | [7 empty] | 13/08 - Ordered materials, requires site visit, requested for LAANs 06/01- Development nearly ready, sheduiled for scope week starting 07/01 11/01- Unable to contact, child site hanging off AJLwith EFSCD 01/02/2019 01/03- internalsd scheduled ws 08/03 07/03- Scheduled WS 11/03 | TBC |  |  |  |  | 19/03/2019
AYCA-43APKG | 6-14 Cosgrove Road, Strathfield, NSW 2136 | MDU | FTTP - Type 3 (MT-LFN) | 2HOM-20 | Ertan Cicek | 2019-03-01 |  | Dane | Site Visit | Frank Giammarco 0413 973 971 |  |  |  |  | 25/02/2019 | [11 empty] | 2019-11-01 | 23/11- still awaiting councilo LAANs, only receieved RMS 19/12- Concrete structure, no framing, suspect lead in already completed by developer 22/03- Link up done by developer, haul and splice outstanding. waiting for A end, due 26/04. materials ordered 04/04- Jemena booked for 06/05
AYCA-5CSK69 | 94 Flowerdale Road, Liverpool | MDU Externals | FTTP - Type 2 | 2LIV-03 | Ertan Cicek | #N/A | #N/A |  | Completed |  | X | X | X | [6 empty] | 2018-07-02 |  |  |  |  | 2018-07-02 | Jul-18 |  |  | 2018-07-05 |  |  |  |  | 2018-05-07 | May-18
AYCA-5CYZU8 | 12 Highgate Circuit, Kellyville, NSW 2155 | Tech Choice Type 3 | FTTP - Type 3 | 2ROU-02 | Mark Leal | #N/A |  | Dane | Completed | Requested |  |  |  |  | Requested |  |  |  |  | 2018-09-17 |  | X |  |  | 17/09/2018 | Sep-18 |  | 20/08 - Quote submitted 24/08 - Re-signed MWI 29/08 - Project received, Requested LAAN, PON Patching SOW, Contact Details | 2018-09-21 |  |  |  |  | 2018-09-21 | Sep-18
AYCA-5D2DU0 | Lot 65 Shorebreak Crescent Lake Cathie, NSW 2445 | SDU | FTTP- Type 2 | 2LCT-01 | Mark Leal | 2019-02-08 |  | Dane | Completed | [5 empty] | 20/11/2018 |  |  |  |  | 14/12/2018 |  |  |  |  | 14/12/2018 |  |  | 16/11- Materials ordered, sent to contractor 23/11- Civils and haul scheduled week starting 26/11, splicing scheduled week starting 03/12 01/12- Haul completed, splicing pushed out to week starting 10/12 14/12- Splice completed | 31/01 |  |  |  |  | 31/01/2019
AYCA-5D4EG4 | 8 Totness Court, Castle Hill NSW 2154 | Tech Choice Type 3 | FTTP - Type 3 | 2CAS-23 | Mark Leal | #N/A |  | Dane | Completed | [5 empty] | 2018-10-09 |  |  |  |  | 2018-09-17 |  | X |  |  | 17/09/2018 | Sep-18 |  | 24/08 - Received project 26/08 - Requested LAANs and docs. Materials ordered 11/09 - Hauled completed, roped lead-in to side of house | 2018-09-21 |  |  |  |  | 2018-09-21 | Sep-18
AYCA-5DL8UH | Boland Drive, Moree | NSB |  |  |  | 2018-05-10 |  | Dane | Completed | [10 empty] | 2019-08-02 | X | [6 empty] | 11/09 - Survey scheduled 13/09 18/09 - Survey was delayed, now commenced today 25/09 - Submitted FIR on 21/09 23/10- Awaiting response, Shankar to speak to Mark Leal by Friday if nothing heard 11/01- Scheduled for week starting 14/01 18/01- Scheduled for week strating 21/01 01/02- Civils and haul complete, splicing scheduled week starting 04/02 | 13/02/2019 |  |  |  |  | 26/02/2019 | Feb-19
AYCA-5DPOWN | 13 Technology Drive, Appin - EXTERNAL | MDU Internals | FTTP - Type 3 (MT-LFN) | 2APN-01 | Ertan Cicek | #N/A | #N/A | Dane | Completed |  | X | X | X | [6 empty] | 18/07/2018 |  |  |  |  | 2018-07-18 | Jul-18 |  | 06/07 - Waiting on 1000M cable, once receive, schedule haul and splice 12/07 - Material arrived. Scheduled week commencing 16/07 17/07- to be completed by end of the week | 2018-07-23 |  |  |  |  | 2018-07-23 | Jul-18
AYCA-5DPOWN | 13 Technology Drive, Appin - INTERNAL | MDU Externals | FTTP - Type 3 (MT-LFN) | 2APN-01 | Nabeel Jaimon | #N/A | #N/A | Dane | Completed | [10 empty] | 18/07/2018 |  |  |  |  | 2018-07-18 | Jul-18 |  |  | 2018-07-23 |  |  |  |  | 2018-07-23 | Jul-18
AYCA-5DVB9M | 4 Magdalene Terrace, Wolli Creek, NSW 2205 | MDU | FTTP- Type 2 | 2ROC-02 | Ertan Cicek | 2018-12-21 |  | Dane | Completed | George 04154645 Steven 0405 462 403 |  |  |  |  | Waived |  |  |  |  | 2018-05-12 | X | [6 empty] | 25/10- Internals complete 08/11- Conduit located, need to dig down and see if we can extend to boundary 13/11 - Dig down performed last week, could not find duct, identified concrete potential footing. Confirmed from dev it was not. Site visit on 13/11 with NBN FS indicate to dig down back to A end but widen the dig down to locate comms 01/12- Waiting on electrician to install cable tray | 2018-10-12 |  |  |  |  | 2018-05-12
AYCA-48OYT0 | 240 New South Head Road Edgecliff NSW 2027 | MDU Externals | FTTP – Type 2 | 2EDG-65 | Ertan Cicek | 2019-02-28 | Feb-19 | Dane | Completed |  | X | TBC | X | [6 empty] | TBC | [7 empty] | 06/07 - LIC ready, comms room ready, issues with design, hopefully have something sorted 09/07 09/07- Unable to contact 10/07- Unable to contact 17/07- Still working with NBN regarding termination point, waiting for approval for a comms rack. 25/07- Installing a comms cabinet, electrician to let us know when it is on site 03/08 - No change 03/08- Comms cabinet and pathway ready 15/08- Requires another site visit to confirm civil requirements 31/08 - Waiting on ROL should be ready by WS 03/09 21/09 - Comms cabinet actually not ready as per dev. 07/03- Internals complete 14/03- Blockage identified on route in new footpath, waiting for ROL to try and flush 02/05- Blockage is actually buried pit filled with concrete. need to do 8m trench through new footpath to link. | TBC |  |  |  |  | 17/05/2019
AYCA-2LCFXK | Skyview - 1 - 248-252 Liverpool Road, Enfield | MDU Externals | FTTP - Type 2 | 2BUR-65 | Ertan Cicek | 2019-02-22 |  | Dane | Completed | 9758 8234 |  |  |  |  | 2018-09-26 | [12 empty] | 07/09 - Ordered materials. Awaiting for LAANs. Require site visit 16/11- Multiple blockages identified, will possibly require new build 18/01- Awaiting ROL, applied for 14/01 11/02- Requires extensive new build 22/03- Waiting for renewed ROLs 28/03- Vac unit scheduled for 01/04 04/04- Waiting for ROL 11/04- Still waiting on ROLs 18/04- Sceduled to commence new build on 29/04 02/05- Civils 50% complete, Splicing to commence WS 13/05
AYCA-5ENHJH | Browning and Colenso Cct Edmondson Park | SDU | FTTP - Type 2 | 2MIL-01 | Andrew Mahasay | #N/A |  |  | Completed | [10 empty] | 2018-06-14 |  |  |  |  | 2018-06-14 | Jun-18 |  |  | 2018-06-15 |  |  |  |  | 2018-06-15 | Jun-18
AYCA-5ETO6E | 4 Jack Smyth Drive, Hillvue | Tech Choice Type 3 | FTTP - Type 3 (MT-LFN) | 2TAM-07 | Mark Leal | #N/A |  | Dane | Completed | Daniel Murphy 0420 366 405 |  |  |  |  | 2018-04-10 |  |  |  |  | 14/12/2018 | [7 empty] | 06/11 - Waiting on CLAANs for V2 of build which encompasses a second build 06/11 - RRP the whole routes, 09/11- Waiver received 23/11- Hauling completed, scheduled for splicing week starting 03/12 30/11- Pushed out to week starting 10/12 06/01- PC pending new Workbook | 19/12/2018
AYCA-5F0TZX | 6 Bangalley Way, Avalon Beach, NSW- 2107 | MDU Externals | FTTN | 2AVA-01 | Ertan Cicek | #N/A |  | Dane | Completed | Tom 0404474075 | X | X | X |  | 24/08/2018 |  |  |  |  | 24/08/2018 |  |  |  |  | 2018-08-24 | Aug-18 |  | 08/08 - Quote provided to NBN 15/08 - Project issued to DT, LAANs commence 24/08 16/08- Commence work as soon as LAANs commence | 27/08/2018 |  |  |  |  | 2018-08-24 | Aug-18
AYCA-5FA5OM | 4-6 Crammond Boulevard, Caringbah , NSW- 2229 | MDU Internals | FTTP - Type 3 | 2MIR-24 | Ertan Cicek | 2018-06-01 | Jun-18 |  | Completed | Mohammed 0403301183 Michael unit 1 0448 350 750 Andrew Berry unit 6 0415208491 | X | X | X |  | 2018-10-09 |  |  |  |  | 2018-10-08 | X |  |  |  | 2018-10-08 | Oct-18 |  | 07/09 - Waiting for Externals to complete 28/09- Awaiting certified pathway approval 02/10- Notify developer before coming for internals as units are now occupied 09/02- Waiting for residents to contact to complete installation in units 1 and 2 | 2018-10-10 |  | X |  |  | 22/02/2019 | Feb-19
AYCA-5FA5OM | 4-6 Crammond Boulevard, Caringbah | MDU Externals | FTTP - Type 3 | 2MIR-24 | Ertan Cicek | 2018-06-01 | Jun-18 |  | Completed | Mohammed 0403301183 | X | X | X |  | 2018-10-09 |  |  |  |  | 2018-10-08 |  | X |  |  | 2018-08-10 |  |  | 28/08 - Materials ordered, CLAAN requested, Contact details requested, PON Patching SOW received 31/08 - Dev already installed lead-in, waiting on NBN response regarding slight change in design 07/09 - NBN picked up council/dev issue, require site meeting before civil commencement - TBC on site meeting 12/09 - Confirm pits link and route 13/09- Organise site meeting with Council and NBN - Confirm dev final street levels, confirm 20/09 - Scheduled for complete 28/09 04/10 - Field completion today, PC today | 2018-10-10 |  | X |  |  | 2018-11-10 | Nov-18
AYCA-5FCHOB | 23 Grahams Hill Road, Narellan | Tech Choice | FTTP - Type 3 (MT-LFN) | 2NRN-05 | Mark Leal | #N/A |  | Dane | Completed | [10 empty] | 2019-08-02 | [7 empty] | 29/01- Multiple blockages identified 09/02- pits located, blockages remaining 11/02- Blockages cleared 19/02- Kinked cables whuilst hauling, waiting for new cables to arrive 02/03- Change to design, need to re-route already hauled cables 07/03- Reverted back to original design, hauling to recommence over the weekend | 14/02/2019 |  |  |  |  | 2019-05-04
AYCA-5FCMYJ | 117 Rookwood Road, Yagoona | Tech Choice | FTTP - Type 3 (MT-LFN) | 2BAN-60 | Mark Leal |  |  | Dane | Completed | [18 empty] | 18/01- Waiting for LAANs 18/01- Confirm lead in capacity | [5 empty] | 2019-06-03
AYCA-5FE5LS | 50 Hoxton Park Road, Liverpool, NSW- 2170 | MDU Externals | FTTP - Type 2 | 2LIV-03 | Ertan Cicek | 2018-12-20 | Dec-18 | Dane | Completed | Buddy 0415930457 | X | X | X |  | 28/08/2018 |  |  |  |  | 14/12/2018 | X |  |  |  | 2019-08-01 |  |  | 15/08 - Materials ordered. LAAN requested, contact details requested, site visit required, PON Patching requested 18/10 - Issues with obtaining TCP. Received 17/10. Ready to commence 19/10 - also CTL not installed, will check if can test and coil and request NBN 25/10- Advised we cannot test and coil as CTL location has not been confirmed. Civils and 2x MSS hauls completed. Remob required for 3rd MSS haul 09/11- Waiting on NBN confirmation to CTL location 30/11- Haul completed, splicing outstanding 06/01- Sheduled to re-commence 07/01/2019 | 16/01/2019 |  |  |  |  | 116/01/2019
AYCA-5FJLCJ | 476 Macleay Valley Way, South Kempsey, NSW, 2440 | Tech Choice | FTTP - Type 3 (MT-LFN) | 2KMS-20 | Mark Leal |  |  | Dane | Completed | [5 empty] | Requested | [12 empty] | 09/02- Hauling scheduled week startiong 11/02 19/02- Hauling commencing this week 08/03- Splicing to commence WS 18/03 | [5 empty] | 22/03/2019
AYCA-5BOGUB | 11B Lachlan St Waterloo NSW 2017 - Internals | MDU Internals | FTTP- Type 2 | 2RED-01 | ? | 2019-02-22 |  | Dane | Completed | [19 empty] | 2019-03-05 |  |  |  |  | 2019-10-05
AYCA-5GPSWE | 100A- 100B Northcote Street, Canterbury | MDU | FTTN | 2CAM-20 | Ertan Cicek | #N/A | #N/A | Dane | Completed | Simon 0414282065 | X | X | X | [6 empty] | 2018-08-21 |  |  |  |  | 2018-08-21 | Aug-18 |  | 13/08 - LAAN start 28/08, late application, requested NBN for waiver to start asap 16/08- Waiver approved, ise visit confirmed breakout of new footpath required, awaiting developer contact to confirm LIC location. 17/08 - Schedule for civils 20/08, Copper term 21/08 | 2018-08-23 |  |  |  |  | 23/08/2018 | Aug-18
AYCA-5GWBTB | 4 Davies Place, Picton | Tech Choice Type 3 | FTTP - Type 3 (MT-LFN) | 2TAH-01 | Mark Leal | #N/A |  | Dane | Completed | [5 empty] | 23/10/2018 |  |  |  |  | 2018-02-11 |  |  |  |  | 30/10/2018 |  |  | 16/10 - Require to order materials, can commence after 23/10 23/10- Scheduled for RRP later in week | 2018-07-11 |  |  |  |  | 2018-08-11
AYCA-5HY3IQ | 1 Stratheden Street, Kyogle | Tech Choice | FTTP - Type 3 (MT-LFN) | 2KYO-20 | Mark Leal |  |  | Dane | Completed | [18 empty] | 18/01- Waiting for LAANs 19/02- Hauling to commence WS 25/02 08/03- Splicing to commmence WS 18/03 | [5 empty] | 2019-10-04
AYCA-5K2YBV | 65 Victoria Street Coffs Harbour, NSW 2450, Victoria Terrace | MDU | FTTP - Type 2 | 2CFS-03 | Ertan Cicek | 2019-06-21 |  | Dane | In Construction | [5 empty] | 15/10/2018 | [12 empty] | 09/11- LAANs and contact requested, materials ordered 23/11- Deatails given to contractor, will schedule site visit shortly 14/12- Developer not ready until March 12/04- Drill shot complete
AYCA-5IWI3A | 26 Queen Street, Stockton | Tech Choice Type 3 | FTTP - Type 3 (MT-LFN) | 2WLL-20 | Mark Leal | #N/A | N/A | Dane | Completed | [5 empty] | 29/10/2018 |  |  |  |  | 2018-02-11 |  |  |  |  | 2018-02-11 |  |  | 26/09 - Ordered materials, requested LAANs 28/09- Still waiting on LAANs 05/10 - Issues with Queen St route, new build 150m 09/10 - New build approved by Michael P. need revised LAANS Civils to commence WS 15/10, splicing WS 22/10 23/10- Scheduled to start 29/10 | 2018-08-11
AYCA-397TA7 | 6-8 Painters Lane, Terrigal | SDU | FTTP - Type 2 | 2TGL-02 | Ertan Cicek | 2019-02-08 | Feb-19 | Dane | Completed | Brett 0488059648 |  |  |  |  | 2018-09-07 |  |  |  |  | TBC | [7 empty] | 06/07 - Road works delay, site no where near ready, 06/07 26/07: Follow up on the 13th of August 03/08 - No change 16/08 - There is relocation works of all assets in the area which is why lead-in conduit from dev not completed yet. They are still waiting for Jemena site assessment. At this stage they will not commence work till end of August. 07/09 - End of September. 11/10- No relocation works strarted yet, council still to approve. atleast another month 09/11- Gas has been rellocated but still waiting on EL and Telstra. advised 3 weeks 22/1- Ertan advises needs to be done this year 14/12- Still with Ertan and NBN, no change 06/01- Still waiting on developers pit and pipe 18/01- No change 07/03- Relocation works complete 12/03- Aerial relocation work did not get completed all the way down the street 22/03- Proposal sent through 28/03- RRP fro alternate route due today 04/04- Awaiting Council response regarding waiver. 18/04- Scheduled to commence 29/04 02/05- Civils underway, expected to be finished early next week | TBC |  |  |  |  | 17/05/2019
AYCA-5JYO3A | 1B Maddox Street, Alexandria NSW 2015 | MDU | FTTN | 2KNS-03 | Ertan Cicek | #N/A |  | Dane | Completed | Luke 0404 837 327 |  |  |  |  | 22/10/2018 |  |  |  |  | 16/11/2018 | [7 empty] | 02/11- Tesltra new build confirmed. Ok to schedule for next week 08/11- Hauled, just needs to be jointed | 21/11/2018 |  |  |  |  | 21/11/2018
AYCA-4H8EZO | 117-123 Victoria Rd, Gladesville, NSW, 2111 | MDU Externals | FTTP - Type 2 | 2HUH-22 | Ertan Cicek | 2019-02-07 |  | Dane | Site Visit | [5 empty] | 2019-08-02
AYCA-5KDIAQ | 67 Newleaf Parade, Bonnyrigg NSW 2177 | MDU | FTTP - Type 3 (MT-LFN) | 2ERP-60 | Ertan Cicek | 2019-02-02 |  | Dane | Completed | Anthony electrician 0416 170 077 Anthony foreman 0414974622 |  |  |  |  | 20/11/2018 |  |  |  |  | 2019-05-02 | X | [6 empty] | 14/11- materials ordered, waiting on LAANs 15/11- Action on Ertan to advise on parent site completion 22/11- Parent site complete, advised by Ertan in meeting, Ertan wants it in this year 23/11- Unable to contact 01/12- Questions regarding design sent to Ertan 14/12- Haul complete, splicing outstanding | 2019-06-02 |  |  |  |  | 22/02/2019
AYCA-5KPEKH | Olive Hill Drvie Cobbitty NSW 2570 | SDU | be | 2NRN-06 | Mark Leal | 2019-03-29 |  | Dane | Completed | [18 empty] | 23/11- Request put in for CRQ 27/11- CRQ pending for 17/12 01/03- CRQ booked for 11th March | [5 empty] | 14/03/2019
AYCA-5L49UP | 4 Water Street, Wentworthville NSW 2145 | MDU | FTTP - Type 3 (MT-LFN) | 2PEN-64 | Ertan Cicek | 2018-09-10 |  | Dane | Completed | Joseph 0421 777 454 Ray 0415 553 732 | X | X | X |  | 19/10/2018 | [6 empty] | 29/10/2018 | [5 empty] | 18/10 - Ertan chased up on site visit 25/10- Hauling completed, link up complete, splicing outstanding | 2018-02-11
AYCA-4VH4MG | 36 Barber Ave, Penrith, NSW- 2750 | MDU Externals | FTTP - Type 2 | 2PTH-02 | Ertan Cicek | 2019-02-04 | Feb-19 | Dane | Completed | George 0411 199 884 sparky 0438 870 766 Thomas | TBC | TBC | TBC |  | 27/07/2018 |  |  |  |  | TBC | [6 empty] | 13/12/2018 | 20/07 - Materials ordered, pending site visit 24/07- No comms room or LIC. Developers electrician thinks there is no comms room. need to clarify. Electrician George 0411199884. Needs another site visit to confirm A end. Scaff not due to come down for a few months. 03/08 - no change 25/10- Scaff not due to come down until Feb 2019. 01/02- Scaff due down in three weeks 15/02- Scaff down in two weeks and LIC to be brought out 07/03- Unable to contact electrician 14/03- Scaff down, LIC to be built next week. footpath not due for a while 02/05- Link up complete, 2 pairs confirmed to have been inactive, now room in P20 conduit to haul our cabes | [5 empty] | 2019-05-25
AYCA-5M4R4N | 76 Irwin Street, Werrington NSW 2747 | MDU | FTTP - Type 3 (MT-LFN) | 2SHA-64 | Ertan Cicek | 2019-01-03 |  | Dane | Completed | Patrick 0415 131 106 |  |  |  |  | 2018-06-11 |  |  |  |  | 2019-08-03 | X | [5 empty] | 2019-01-07 | 16/11- LIC brought out, waiting for comms room to be built, advised this would be ready on the 26th 23/11- Pushed out another week 01/12- Pushed out again, advised will call on Tuesday or Wednesday for an update 14/12- No change 11/01- Waiting for meter box to be installed 18/01- Civils complete 15/02- 4 blockages identified, scheduled in to clear week starting 18/02 | 13/03/2019 |  |  |  |  | 19/03/2019
AYCA-5M84RG | 72 Boultwood Street, Coffs Harbour, NSW 2450 | MDU Externals | FTTP - Type 2 | 2CFS-02 | Ertan Cicek |  |  | Dane | Completed | [24 empty] | 2019-05-04
AYCA-5MG99P | 593 Old Illawarra Road, Menai NSW 2234 | MDU | FTTP - Type 3 (MT-LFN) | 2MEN-62 | Ertan Cicek | 2019-01-28 |  | Dane | Completed | Joseph 0438 324 803 George 0418 6000 48 |  |  |  |  | 2018-12-18 | [5 empty] | X | [6 empty] | 23/11- Waiting on LAANs, project is urgent 11/01- Scheduled week starting 21/01 | [5 empty] | 14/02/2019
AYCA-5MG99P | 593 Old Illawarra Road Menai NSW 2234 | MDU Internals | FTTP - Type 3 (MT-LFN) | 2MEN-62 | Nabeel Jaimon | 2019-01-28 |  | Dane | Completed | [18 empty] | 11/12- Advised site is ready for internals and externals | [5 empty] | 14/02/2019
AYCA-5MGOY8 | 589 Old Illawarra Road, Menai NSW 2234 | MDU | FTTP - Type 3 (MT-LFN) | 2MEN-62 | Ertan Cicek | 2019-01-28 |  | Dane | Completed | Johhny 0452 395 593 |  |  |  |  | 2019-12-18 | [5 empty] | X | [6 empty] | 11/01- Scheduled week starting 21/01 | [5 empty] | 14/02/2019
AYCA-5MGOY8 | 589 Old Illawarra Road Menai NSW 2234 | MDU Internals | FTTP - Type 3 (MT-LFN) | 2MEN-62 | Nabeel Jaimon | 2019-01-28 |  | Dane | Completed | [24 empty] | 14/02/2019
AYCA-5MHAO7 | Site 18, Dawn Fraser Avenue Sydney Olympic Park, NSW 2127 | MDU | FTTP - Type 3 (MT-LFN) | 2SIL-02 | Ertan Cicek | 2019-01-14 |  | Dane | Completed | Aaron 04 22 101 591 |  |  |  |  | 26/11/2018 |  |  |  |  | 15/02/2019 | X | [6 empty] | 16/11- Materials ordered 23/11- Hauling complete 01/12- Developer advises that Telstra is to build new network to development, and will leave NBN a conduit 11/01- No NBN conduit was left, requires 2m link up between Telstra pit and internal pit for new NBN duct. 18/01- Waiting response from developer to see if he can install new lead in 01/02- Civils and haul scheduled week starting 04/02 09/02- Splicing to be complete on Monday | 20/02/2019 |  |  |  |  | 18/02/2019
AYCA-5ML96W | 24 Blackwood Avenue Casula NSW 2170 | MDU Internals | FTTP - Type 3 (MT-LFN) | 2LIV-61 | Nabeel Jaimon | #N/A |  | Dane | Completed | [5 empty] | 22/10/2018 |  |  |  |  | 19/11/2018 | [7 empty] | 04/10 - Pending to request LAANs 12/10- Materials ordered | 23/11/2018 |  |  |  |  | 2018-03-12
AYCA-5ML96W | 24 Blackwood Avenue Casula NSW 2170 | MDU Externals | FTTP - Type 3 (MT-LFN) | 2LIV-61 | Ertan Cicek | #N/A |  | Dane | Completed | [5 empty] | 22/10/2018 |  |  |  |  | 16/11/2018 | X | [6 empty] | 04/10 - Pending to request LAAN 12/10- Still awaiting to receieve MW pack 18/10 - Ertan advised possibly occupied in next 2 weeks 19/10- Still waiting for a response from NBN regarding external MW pack 25/10- No change 01/11- Docs received shedule in for next week RRP 08/11- Scheduled in for week starting 12/11 | 21/11/2018 |  |  |  |  | 21/11/2018
AYCA-5MNUDQ | 221 Queen Street Beaconsfield NSW 2015 | NSB | FTTP - Type 2 | 2KNS-03 | Mark Leal | 2018-08-18 | Aug-18 | Dane | Completed | [5 empty] | 2018-06-09 |  |  |  |  | 2018-07-12 |  |  |  |  | 2018-07-12 |  |  | 23/08 - Requested if dependent site built 28/08 - Survey laan sent, 5/09 will be the survey 11/09 - Attended issues access to comms room, left card 07/09 23/10- 2 end users adequately served ie scotch locked to internal cat 6 cable 23-10- PC NEEDS SUBMISSION BY 21/11/2018 AT LATEST 16/11- Blockages identified on route 30/11- Attempting to push spare pairs to development side of blockage 06/01- In consultation with NBN regarding potential defects for PCD location 11/01- Waiting for a response from FS 18/01- Requires site visit | 14/12/2018 |  |  |  |  | 25/01/2019
AYCA-5MWJQ4 | 222 Wallace St Macksville | SDU | FTTP - Type 3 (MT-LFN) | 2MAC-22 | Mark Leal | 2018-10-31 |  | Dane | Completed | [5 empty] | 20/11/2018 |  |  |  |  | 25/01/2019 | X | [6 empty] | 14/11- Dependant projcet in service, materials ordered, waiting on LAANs 16/11- LAANs pending with LASE 27/11- LAANs receieved 01/12- Haul complete | 31/01/2019 |  |  |  |  | 31/01/2019
AYCA-5N0IF2 | 30 Park Ave Coffs Harbour NSW 2450 | NSB |  |  | Mark Leal | 2018-08-22 | Aug-18 | Dane | Completed | Daniel Quinn 0409 488 534 | [17 empty] | 30/08 - Under Design, Survey to be done 05/09 11/09 - Survey done 06/09, FIR submitted 25/09 - No feedback yet on FIR 16/10 - Shankar responded on FIR feedback 30/11- No change 11/01-Hauling scheduled week starting 14/01 18/01- Haul complete, requires splicing | [5 empty] | 14/02/2019 | Feb-19
AYCA-5NB7OP | 83 Redhead Road, Redhead, NSW, 2290 | Tech Choice | FTTP - Type 3 (MT-LFN) | 2CHL-08 | Mark Leal |  |  | Dane | Completed | [5 empty] | 22/02/2019 | [12 empty] | Haul scheduled WS 04/03 | [5 empty] | 2019-10-04
AYCA-5NM0LP | 118 Burwood Road, Croydon Park NSW 2133 | MDU | FTTP - Type 3 (MT-LFN) | 2BUR-65 | Ertan Cicek | 2019-01-25 |  | Dane | Completed | Chemel Faker M: 0415 351 745 |  |  |  |  | 30/10/2018 |  |  |  |  | 2018-07-12 | X | [6 empty] | 12/11 - Requested ROL due to Burwood Rd. From photos, looks link concrete cut, 7-10m concrete cut P50 link up to TLS 5 Pit. Advised footpath works pending 12/11 - Karsten attended site: confirmed best is to drop 5 Pit over existing P50. Confirmed with developer appropriate area to drop, better than breaking out concrete 7m. Proving up the street to road crossing 2pit and 2 pit 12/11 - Confirming with Chemel if able to bring back fencing so make room for pedestrians while crew installs pit 13/11 - Chemel confirmed can pull back fence line for pedestrians. No Third party TC required. Confirm with Chemel one day prior to arriving onsite 16/11- Awaiting ROL 14/12- Haul complete, splicing commenced 06/01- PC pending new Workbook | 2018-12-12 |  |  |  |  | 15/01/2019
AYCA-3E5O97 | Hancy - 85-89 Samantha Riley Drive | MDU Externals | FTTP – Type 2 | 2ROU-03 | Ertan Cicek | 2019-01-06 | Jan-19 | Dane | In Construction | PM: Paul 0481227123 Charlie Sparky 0414546729 Geroge HCM | TBC | X | TBC | [6 empty] | TBC | [7 empty] | 06/07 - Site back up and running, contact in a month from 02/07 for update. contact harry 0420480303 03/08- Call in another 3 weeks 23/08- Comms room ready, conduit not yet brought to boundary, advised to call in one week and project manager will have a date organised with electrician 05/09- Follow up with electrician on 12/09 14/09- Follow up 17/09 21/09 - No framing up. Early stages. 1 month follow up 07/03- LIC to be brought out to boundary ws 11/03 04/04- New build reqiured, need Jemena stand by to locate gas main 09/05- No change | TBC
AYCA-5PBMZD | 14 SALISBURY ST URALLA NSW 2358 | MDU | FTTN | 2URL-20 | Mark Leal | 2018-09-18 |  | Dane | Completed | [5 empty] | 21/11/2018 | [7 empty] | X |  |  |  |  | 11/01- Materials delivered, scheduled tentativelly for week starting 28/01/2019 18/01- Pushed out to week starting 04/02 22/01- Pushed out to week starting 18/02 to make way for Mudgee | 27/02/2019 |  |  |  |  | 2019-04-03
AYCA-5PIMJX | 36A Park Road, Naremburn, NSW 2065 | MDU | FTTP - Type 3 (MT-LFN) | 2STL-66 | Ertan Cicek | 2018-10-22 |  | Dane | Completed | [5 empty] | 20/11/2018 |  |  |  |  | 2019-08-03 | X | [6 empty] | 16/11- Dependent DFN nbuild not yet approved by NBN. Tentative DFN build completion date is end of Januray 22/11- PC mid February depending on DFN 13/12- Internals due mid Jan 09/02- Civils completed, blockage outstanding pending with Council 07/03- Waiting for response from NBN regarding pathways | 13/03/2019 |  |  |  |  | 29/03/2019
AYCA-5BXBTE | 41 Langer Ave, Caringbah | MDU Externals | FTTP - Type 3 (MT-LFN) | 2MIR-27 | Ertan Cicek | 2018-06-04 | Jun-18 | Dane | Completed |  | X | X | X |  | 2018-06-08 |  |  |  |  | 2019-01-02 | X | [6 empty] | 26/07 - Material order request sent, site visit required. Request for PON Patching details and LAAN. 6th of August start of the LAAN 02/08 - Waiting FJL to be installed, ETA Nov 2018. 2 Blockages on the route. 09/08- Linked developer pipe, installed SDS from MPT to premise. 2x Blockages outstanding 17/08 - Waiting on Ertan to confirm Parent Site build completion - ETA Dec 2018 11/10- DJL's built, waiting on FJL, advised this will be soon 18/10 - Early november FJL installation 01/11- Ertan to follow up 15/11- DP not running on schedule. possible that we need to build it 29/11- On hold 06/12- Due March 13/12- No change 06/01- No change 18/01- A end ready, schedule for week starting 21/01 09/02- Issues with HDODF rack, waiting for answers from NBN 15/02- No change | 2019-06-02
AYCA-4F75OS | 66-68 Cambridge St, Blacktown, Blacktown 2148 | MDU Externals | FTTP - Type 2 | 2BLK-12 | Ertan Cicek | 17/08/2019 |  | Dane | In Design | [5 empty] | 16/04/2019 | [12 empty] | 28/03- NDD submitted 11/03 04/04- DDD submitted 02/04 16/04- Awaiting NBN DDD approval 07/05- No change
AYCA-4QNRBL | 822 Windsor Road Rouse Hill, NSW 2155 | MDU Externals | FTTP - Type 2 | 2KEL-03 | Ertan Cicek |  |  | Dane | Completed | [5 empty] | 15/04/2019 | [12 empty] | 28/03- NDD submitted 11/03 04/04- DDD submitted 02/04 12/04- Materials ordered 639917 15/04- Scoped, A end manhole seems to be buried, ROL applied for incase we have to escavate 15/04- DDD approved 18/04- Civils and haul scheduled 18/04 | [5 empty] | 2019-09-05
AYCA-4RS6QG | 31 William Street Alexandria, NSW 2015 | MDU Externals | FTTP - Type 2 | 2KNS-03 | Ertan Cicek | 23/11/2019 |  | Dane | In Design | [18 empty] | 28/03- NDD submitted 08/03 15/04- DDD Submitted 11/04, awaiting response 02/05- Heritage exemption submitted today 31/05- Exemption approved
AYCA-EV5EP | Smiths Lane Wongawilli NSW 2530 | SDU | FTTP- Type 2 | 2DAP-01 | Mark Leal | 2019-05-31 |  | Dane | Completed | [18 empty] | 01/12- Still awaiting LAANs 06/02- LAANs commence 19/02 | [5 empty] | 21/02/2019
AYCA-4W57Z3 | 11-17 Cross St Bankstown, NSW 2200 | Transformation | FTTP - Type 2 | 2 BAN-64 | Ertan Cicek | 23/11/2019 |  | Dane | In Design | [18 empty] | 16/04- Awaiting DDD 07/05- DDD submitted 03/05 31/05- Site 4-5 months away
AYCA-2L9FVY | 117-119 Pacific Highway | New Devs - MDU | FTTP - Type 2 | 2HOR-02 | Ertan Cicek | #REF! | #REF! | Mickey | Completed | Brett site manager 0422 871 281 Matt Elec 0431540094 |  |  |  |  | Start: 01/11/2018 End: 04/05/2018 | [12 empty] | 19/12- lead in pit to boundary will be crossing multiple services and not to depth, potentially better option to drop new pit middle of development, cable tray to comms room. End of Jan footpath to be poured. Needs ROL and night work 11/01- ROL applied for 15/02 - Followed up with ROL/TCP. Possible night works. Followed up on CLAAN 27/02 - ROL received, lead-in ready, comms ready, PDH not installed, Matt (Elec) having meeting with Steve Austin, will mention about PDH install for External to haul splice; Ertan advised 05/03 - Pending PDH install and partial comms pathways Tentative start night works 25/03. Developer OK with access, confirm closer to date 15/03 - Brett will advise if PDH installed and internal tray ready Monday 30/03 - lead-in connected, required 2 nights due to lots of services in area, services shallow, require concrete encase, pavers, required to install pit to reduce trench due to pavers and services 02/04 - External hauling to commence today 23/04 - booked splicing 06/05 06/05 - Rack RU30 is not ready, no cables coming out of it. 21/05 - Cable to be hauled approx 170m to DJL, designer to send spatial map of Hornsby # to DJL route 23/05 - Haul 30/05, splice 31/05, PC 05/06 01/06 - Confirming pit location OK within 8m of substation
AYCA-2PNFXD | HFC DFN 2ROS-66 | HFC DFN | DFN | 2ROS-66 | Mark Leal |  |  | Mickey | Completed | NA |  |  |  |  | 2019-02-08 |  |  |  |  | 2019-03-15 | [7 empty] | 29/01 - Ordering materials, commencement 12/02/2019 19/02 - Civil works commence yesterday, waiting on ROLs for road cuts, hopefully by 22/02. Need to notify council 28/02 - Civils 40% complete, pending 2 road crossings ROL for council notification approval Relocate 2 DJL-205 and DJL-209 05/03 - Pending ROL 12/03 - Pending ROL, relocating DJL, confirming route. On Track 12/03 - Request on commencement of hauling 16/03 - 40% hauled 30/03 - scheduled road crossing works 03/04, other road crossing complete, | 2019-04-15
AYCA-33L9HP | HFC DFN 2BAN-64 | HFC DFN | DFN | 2BAN-64 | Mark Leal | #REF! | #REF! | Mickey | Completed | NA |  |  |  |  | 2018-05-10 |  |  |  |  | 30/11/2018 |  |  |  |  | 30/11/2018 | Nov-18 |  | 22/08 - Currently in Design Stage - Survey started 22/08 23/10 - CBD blockages fixed, hauled DSS 53,54,56,58. Waiting on Telstra response regarding rack allocations . ETA mid november Ordered cable drum, no confirmation on ETA, this is for 1650m length. Tunnel access waiting for approval Telstra 30/10 - All blockages completed, all hauling completed except for DSS-57 (waiting on 2k drum) and DSS-51 (rack allocation), tunnel access approved. 06/11 - Waiting on Telstra rack allocation / Tunnel access approve / Civils complete / Blockages complete / Hauling complete except for the cable coming from Exchange 13/11 - Confirmed rack allocation for 1 x 72F, we will be hauling this and to commence the splicing next week. 20/11 - Ontrack 27/11 - Ontrack for PC 30/11/2018 | [5 empty] | 2018-12-03 | Dec-18
AYCA-40TCKL | 221 Miller St, North Sydney, NSW 2060 | New Devs - MDU | FTTP- Type 2 | 2NSY-02 | Ertan Cicek | #REF! | #REF! | Mickey | In Construction | Andrew 0419285335 Stephen Brennan 0414695849 Victor PM 0411064032 Jack PE 0403535871 |  |  |  |  | Start: 18/12/2018 End: 18/06/2019 | [12 empty] | 16/02 - Materials ordered, LAAN received, Dependency In Service. Requires site visit. 04/03 - Site visit update: - P100 starters in place - construction material all over the front require removing before commence - building fence line is in front of the manhole and pits - Internal pathway not ready - Comms room not ready 30/03 - Met with Jack onsite, require replace ACM pit and link 2 x P100 from dev, dev will move construction material around WS 08/04, will need to double check before deploying crew 02/04 - No change 05/04 Tentative booked for later next week, pending on Jack to have area ready 23/04 - Conduit installlation complete, acm pit removal tentative 05/06 01/05 - Booked in for ACM Pit removal and upgrade plus link up on 06/05/2019 07/05 - Pit upgrade in progress 11/05 - Blockages in route, mainly construction material in manholes and ducts, require vac unit to clean through. Using ROL of Richard Crookes in the first instance 21/05 - Vac unit proved 90% of route, from DJL to 6 PIT difficult, another attempt 22/05 01/06 - ROL confirmed and dig down WS 03/06
AYCA-41FBT3 | 231 Miller St, North Sydney, NSW 2060 | New Devs - MDU | FTTP- Type 2 | 2NSY-02 | Ertan Cicek | #REF! | #REF! | Mickey | In Construction | Joshua public domain 0447 875 016 |  |  |  |  | Start: 13/11/2018 End: 14/05/2019 | [12 empty] | 21/02 - Joshua advised approx 23/03 ready to go (to have lead-in ready where Karsten advised, comms room ready), saved MT number 22/03 - Scheduled night works 25/03/2019 02/04 - Site not ready 23/04 - Design change occurred confirmed by josh, ripped out lead-in and rebuild the front. Will need site visit to confirm changes. Tentative civil schedule WS 06/05 02/05 - Touched base with Joshua, advised will be ready by Tuesday 07/05, will perform site visit before civil works, doesnt need to be night works 11/05 - Blockages in route, mainly construction material in manholes and ducts, require vac unit to clean through. Using ROL of Richard Crookes in the first instance 14/05 - Tentative vac unit scheduled 21/05 - Vac unit proved 90% of route, from DJL to 6 PIT difficult, another attempt 22/05 01/06 - ROL confirmed and dig down WS 03/06
AYCA-4A46K7 | HFC DFN 2PAR-63 | HFC DFN | DFN | 2PAR-63 | Mark Leal |  |  | Mickey | Completed | Joe 0418673227 |  |  |  |  | 25/07/2018 |  |  |  |  | TBC |  |  |  |  | 2018-10-10 | Oct-18 |  | 25/07 - Materials received 23/08 - RRP completed 18/07 23/08 - Blockages and civil road crossing to be rectified, blockages also rectification works 29/08 04/09 - Commenced hauling on sections: DSS-053,DSS-055,DSS-057,DSS-059 = approx 1753m, Splicing will be able to commence early next week - On track 11/09 - Need to find out if we can bring the lead-in to property boundary, work with electrician to find suitable location so we can bring this one in end of Sept 25/09 - Confirmed civils pit upgrade 26/09, remaining hauling to be completed by 27/09 05/10 - Currently splicing remaining joints 10/10- Developer doing driveways, lead in conduits not yet complete 19/10- Unable to contact 26/10- Scheduled week starting 29/10 | [5 empty] | 2018-10-19 | Oct-18
AYCA-4DW3WX | 18-22 Lords Ave + 421-425 Pacific Hwy, Asquith, NSW 2077 | New Devs - MDU | FTTP - Type 2 | 2HOR-62 | Ertan Cicek | #REF! | #REF! | Mickey | Completed | Terek-builder - 0405166899 Delor PM - 0401040463 Justin - 0430533573 |  | X | X |  | Start: 11/01/2018 End: 11/05/2019 | [12 empty] | 09/11- LAANs and contact requested 19/02 - Additional materials ordered patch cords and Vasko Require site visit 26/02 - Site visit by scoper identified developer brought lead-in to Lords Ave, no network present there, Steve Austin advised 4 times to bring it out there. Developers words only. We have advised to bring out to Pacific Hwy, they will advise when available. 03/03 - Advised NBN, will follow up with developer to see when available 05/03 - Back onto developer, follow up required when corehole ready 11/03 - Civils complete and hauled up to the new 5 Pit installed lead-in pit. Waiting on developer to install new cable trays | 2019-03-25 |  |  |  |  | 2019-03-25
AYCA-4HTS7R | 875 Richmond Road, Marsden Park | SDU |  |  | Andrew Mahasay | 2018-12-14 | 2018-12-01 | Mickey | Completed | [18 empty] | "06/07 - Revising LAANs for bore shot across Richmond Road 03/08 - No change 14/08- Still awaiting response from NBN, follow up on Friday 09/11- Quote to be finalised 13/11 for drill shot 16/11- Still waiting to receiev quote 18/01- Driller pushed out until mid Feb" 08/03 - P&P certificate complete - Require to scope, site now 01/04 - Booked in Gas Standby Day works 18/04/2019 08:00AM, booked driller on the day. Also transmission will need to be advised 4 days prior to drill works 01/05 - Drill shot completed, require pit install and link up to site, booked in 08/05 07/05 - ROL in, require book night crew start next week to link bore pipe) 11/05 - Scheduled 13/05 night work | 2019-05-17
AYCA-4IIZWC | 22-28 Albany Street, St Leonards | New Devs - MDU | FTTP - Type 3 (MT-LFN) | 2STL-60 | Ertan Cicek | 2019-06-07 | Jun-19 | Mickey | Completed | Anthony PM 0417423463 Johnny Calabro 0405123334 |  |  |  |  | Start: 13/02/2019 End: 31/07/2019 | [12 empty] | 06/07 - Attended site, obtained contact details, site manager advised still at least 6 months out from 29/06. Starting to put staffolding around site. Only started base. 26/07: No Change 03/08 - no change 15/03 - Developer advised lead-in conduit ready for 20/03, Vasko to arrive after to check site readiness 30/03 - developer said will move a section of scaffold for us, will advise when done 01/05 - Developer contacted advising scaffold section remove by thursday. booked in tentative 07/05, advised council and letterbox drop for night works already 11/05 - Link up completed, route not ready, tentatively scheduled WS 20/05 21/05 - No call back from developer, probably not ready 23/05 - Confirmed by developer, all set, haul and splice WS 27/05 | 2019-05-31
AYCA-4IIZWC | HFC DFN 2STL-66 | HFC DFN | DFN | 2STL-66 | Mark Leal | #REF! | #REF! | Mickey | Completed | NA |  |  |  |  | 28/11/2018 |  |  |  |  | 2019-01-31 | [7 empty] | 23/10 - Design 60% 06/11 - Design handed in 02/11, waiting for feedback 20/11 - Ordered materials 16/11, ROL requested, Blockage dig down commence 28/11 27/11 - No change, blockage dig down commence 28/11 04/12 - Blockage commenced, civils commenced, require to locate DJL location on leg DSS-057 due to services and trees, only 38m back. Reflect as builts. New builds also may be required due to coming across thick tree roots covering ducts. Crews unable to access dig down block location due to tree roots covering area. New build may be required, will advise 05/12 - 2 more blockages to go. 06/12 - Civil build solution complete on Park Rd Naremburn 11/12 - 2 more blockages to go which were done at night due to CBD location of St Leonards. Waiting feedback if successful. Hauling is commencing tomorrow. 17/12 - Civil build performed on Northcote St, Naremburn through blockages blockage in middle of road at road-about, busy cbd area, likely broken conduit due to water works, engage with council to notify, likely works to commence mid next year (also ROL road, has been applied) 20/12 - More civil build required on 78-82 Northcote St, Naremburn (blockage under footpath drain) 08/01 - Schedule crew onto night works to perform dig down into road blockage Christie st/Chandos st - likely late this week 15/01 - Civils complete with blockage rectification in Chandos St rectified. Conduit looked to be damaged by the works carried out by Water. Asphalt | 2019-02-01
AYCA-4PEEEK | HFC DFN 2RYD-63 | HFC DFN | DFN | 2RYD-63 | Mark Leal | #REF! | #REF! | Mickey | Completed | Rob 0418 969 253 |  |  |  |  | 2019-01-14 |  |  |  |  | 2019-02-27 | [7 empty] | 27/11 - DDD 30% complete by design 08/01 - Ordering materials today 18/01 - Civil commenced 17/01, Bowden St P100 success, checking DJL locations to be relocated 19/02 - Blockage in the middle of road, require TC night works, hauling to be completed after blockage 07/03 - Blockage rectified tonight, 2 DJL relocation, 1 pit install Monday 11/03, rehaul after 12/03 - Splicing commenced and ODF termination complete, relocating 3 DJLs, blockage second section in road thursday, pushed PC 16/03 - Blockage has been postpone due to weather, major safety concern even with light rain, shift to 20/03 opening of no rain. 2 more pit installs for DJL relocation 25/03 - Blockage rectified late last week, hauling this week with splicing to follow, revised 30/03 - Splicing remaining | 2019-04-05
AYCA-4QDZCA | 31-33 Albany St, Crows Nest, NSW- 2065 | New Devs - MDU | FTTP - Type 2 | 2STL-61 | Ertan Cicek | 2019-08-30 | Aug-19 | Mickey | Developer Delay | Chris site manager 0466901510 |  |  |  |  | 27/07/2018 | [11 empty] | 2019-01-07 | 15/06 - Pending material order and Site Visit 17/07- Materials ordered, needs site visit 20/07 - Site boarded up, only base of structure complete, very early stages, A end DJL exist, route not proven but looks straight forward, lead-in will be corehole into lead-in M/H. Contact obtained - Chris 0466901510 26/07: No Change 03/08 - no change 12/10- Developer advises they wont be ready until next year, follow up in December 23/04 - Site visit performed, P50 currently being used to run temp power for site. Comms room not ready. Builder confirmed ready approx July/August
AYCA-4WB37J | HFC DFN 2FRE-61 | HFC DFN | DFN | 2FRE-61 | Mark Leal |  | Jan-00 | Mickey | Completed | NA |  |  |  |  | 31/10/2018 |  |  |  |  | 2019-02-20 | [7 empty] | 23/10 - RRP 50% 31/10 - Sent through high level design to request ROL to speed things up 06/11 - 90% design completion. Issuing construction LAANs with 13/11 - Performing a walkout with NBN FS Tony, Damien, Shankar, for new builds / blockages 20/11 - Requested for TCP from Traffic Management 27/11 - Blockage dig down commenced on Fitzpatrick Ave and Bantry Bay Rd. This weekend performing dig down on Oxford Falls Rd and TC 04/12 - Dig downs continuing on blockages, working through 23 dig downs, completed 30%, new build required DSS-060 leg 11/12 - New build required on DSS-060, waiting confirmation from council to commence, sensitive council flagged. Will wait for outcome before commencing 17/12 - continuing with blockages, once completed, new civil build requirements provided onto one CLAAN to council 08/01 - Revised CLAAN sent for 3 construction areas required, can re-commencement 22/01 19/02 - Church OK for driveway cut, performed today, hauling finalising next week 12/03 - Splicing to be completed 14/03, PC on track. 16/03 - Delayed due to LL portion not hauled/spliced 19/03 - Mark will advise on progress 02/04 - No change 09/04 - Confirm other DJL to Mark and advise to give date | 2019-05-11
AYCA-4WGB20 | 64-66 Chandos St, St Leonards, NSW 2065 | New Devs - MDU | FTTP- Type 2 | 2STL-60 | Ertan Cicek |  |  | Mickey | Developer Delay | Dominic - 0427 102 429 |  |  |  |  | Start: 18/12/2018 End: 18/06/2019 | [12 empty] | 17/02 - Materials ordered, LAAN received. Dependency following up. Site visit performed 04/12. Site visit identified ground still being excavated and form work
AYCA-4XIVYZ | HFC DFN 2UND-62 | HFC DFN | DFN | 2UND-62 | Mark Leal |  |  | Mickey | Completed | NA |  |  |  |  | 2019-02-13 |  |  |  |  | 2019-03-08 | [7 empty] | 29/01 - Ordering materials, commencement 12/02/2019 19/02 - Need to potentially relocate DJL on Illawarra Rd, Marrickville CBD, no stop lane, main road, not a good location. Pit replacement requires gas standby, booking gas. 12/03 - ROL received, commence hauling on this week 16/03 - Gas standby booked 04/04, DJL shifted to Calvert St, Haul 50% 26/03 - Forecast to complete 18/04 before Anzac day 01/05 - Mark asking Planning Team regarding RU32, followed up | 2019-05-08
AYCA-4ZNBL1 | HFC DFN 2EPP-60 | HFC DFN | DFN | 2EPP-60 | Mark Leal |  |  | Mickey | Completed | NA |  |  |  |  | 2019-11-02 |  |  |  |  | 2019-01-25 | [7 empty] | 23/10 - Materials ordered, ROLs requested. Tunnel access issue underneath M2 30/10 - Heritage impact on 7 blockage dig downs (2 x dss runs = 1700m). Some in driveways, footpaths and one next to a Devlins creek. Heritage exemption has been checked with NBN LASA and now have engaged with council heritage point of contact. Works that can progress: - 8 blockage dig downs - 8 DSS cable runs - road crossing - 8 pit install for relocation of DJL-056 06/11 - Civil works commencing this week with blockages, heritage exemption request sent through to council. Rack allocation is also completed. Council approval end of this week. 13/11 - Identified civil works on Norfolk Rd, approx 70m of build. Express duct is the terracotta pipe which has no cables, blockages identified crushed pipe, alternative is all congested with copper cable - Impact is DSS-053 and DSS-054. Slight delay with council still waiting on heritage exemption. 20/11 - Civils 90% complete, Hauling commenced today on Beecroft Rd 27/11 - Malton Rd 1 alternative route continue provinf today: 50% success so far, civils on Malton Rd 2 complete, not required to breakout driveway, P100 grundy complete and install 8 Pit for joint 04/12 - Canal blockage following up today, road crossing malton road commencing this week, looking at splicing to commence by end of this week 11/12 - 67m of new build required in conservation area of Cheltenham, advised council waiting on response for approval. This may push out field completion. 17/12 - New build in heritage: Datateks to provide arborist report and get back to council working with nbn lasa team Canal blockage rectified on Friday, require to haul splice the rest bar DSS/DJL-062, likely to have that splice by mid next year 07/01 - DSS-059 scheduled to be hauled later in the week to align with night works haul with 2FRE-61. Conservation heritage area Cheltenham, council advised no DA application required and ROP with Arborist report required. Sent this off today. Finish off the splicing next week except for heritage area. 07/03 - Commenced prep for heritage works. Vac truck booked for non destructive, hand dig by civil crew, TCP required for location stop/go | 2019-03-29
AYCA-512UVL | Marineres Centre of Excellence Tuggerah | D&B NSB | FTTB | 2WYO-03 | Mark Leal |  |  | Mickey | Completed | Daniel Campbell (Building Manager) 0490040742 |  |  |  |  | 2018-11-28 |  |  | 2019-01-07 | 2019-01-07 | 2019-02-08 | [7 empty] | 10/12 - Ordered materials. Could not complete order, requesting order access from NBN supply. Onsite meeting TBC 12/12 - Ordered all materials with the MX6 confirmed bundle 08/01 - Crew attended but cannot drill through corehole to electrical switch room, as the core will be in the above room. New revised plan to be sent and checked with building manager (advised building manager) 18/01 - Approved redesign, building pathway 19/01 25/01 - Pathway built, splicing commitment WS 04/02 28/02 - Integration booked 08/03 16/03 - Integration complete, cut over booked 03/04 01/05 - Complete | 2019-04-08
AYCA-52924C | 38 French Rd , Wangi Wangi | Transformation Project | FTTP - Type 3 (MT-LFN) |  | Ertan Cicek | 2019-12-11 | Dec-19 | Mickey | Developer Delay | 03/04 - Requested |  |  |  |  | Start: 20/03/2019 | [12 empty] | 01/05 - Site visit indicated that it is no where near ready for construction. EFSCD change to Dec-19
AYCA-578FAA | 229 MILLER STREET, NORTH SYDNEY NSW 2060 | New Devs - MDU | FTTP- Type 2 | 2NSY-02 | Ertan Cicek | #REF! | #REF! | Mickey | In Construction | [5 empty] | Start: 04/12/2018 End: 03/06/2019 | [12 empty] | 17/02 - Materials ordered and received, LAAN received, Dependency is 231 Miller St, another DTKS project 23/04 - Site visit confirmed that site is approx 6 months behind schedule. Site not ready to perform scoping
AYCA-59DV6W | HFC DFN 2CRR-72 | HFC DFN | DFN | 2CRR-72 | Mark Leal |  |  | Mickey | Completed | NA |  |  |  |  | 2018-04-09 |  |  |  |  | 2018-09-20 |  |  |  |  | 2018-09-20 | Sep-18 |  | 21/08 - Materials ordered. 31/08 - 04/09 - Dig down and repairs will commence, hauling 06/09 04/09 - Hauling to commence 04/09 14/09 - Splicing started 11/09 18/09 - 5/6 DJL's completed, last DJL proposed relocation, NBN field services approved | [5 empty] | 2018-10-05 | Oct-18
AYCA-5E7TWE | HFC DFN 2MEN-60 | HFC DFN | DFN | 2MEN-60 | Mark Leal |  |  | Mickey | Completed | NA |  |  |  |  | 2019-02-06 |  |  |  |  | 2019-03-15 | [7 empty] | 20/01 - Ordering materials, commencement 06/02/2019 29/01 - confirmed 8 sections of long duct runs which require vacing out the water and blowing the duct to get rope through. Final solution to dig down midpoint 19/02 - Dig downs 2 completed so far 12/03 - status: 40% hauling complete (144F cables) 2 more blockages, 1 dig down long run 26/03 - 80% hauling, on track splicing and PC comp 02/04 - remaining 20% hauling on menai rd to be completed this week, splicing ready 08/04 05/04 - Scheduled night haul 8-9/04 09/04 - Night haul | 2019-04-25
AYCA-5FEXSP | HFC DFN 2PEN-61 | HFC DFN | DFN | 2PEN-61 | Mark Leal |  |  | Mickey | Completed | NA |  |  |  |  | 2019-01-07 |  |  | 2019-01-14 |  | 2019-02-25 | [7 empty] | 23/10 - RRP to be completed today, Design 40% 06/11 - 80% completion on design 27/11 - Tomorrow possible submission, 95% complete 17/12 - Ordered materials, ready to start 07/01/2019, will request ROL's start of next year 20/12 - 80% of the hauling can commence immediately, Gas standby on 3 blockages requesting next year 08/01 - Commenced hauling of 576F - 11 DSS runs are ready to be hauled, Show stoppers: HP gas standby required on 3 blockage locations, crew today will have another attempt before requesting for HP gas standby 19/02 - Cable chamber access, approx 1 month to get it. Only thing pending left, splicing can commence 05/03 - Relocation of 3 joints required. New pit installs and impacting 3 rehauls: • 535m of 576F Rehaul on DSS-054 • 300m of 576F Rehaul on DSS-057 • 500m of 576F Rehaul on DSS-061 • 400m of 72F Rehaul on DSS-062 07/03 - Pit installs completed by 11/03 26/03 - On track to PC 29/03/2019 | 2019-03-29
AYCA-5FHXRP | 75 Park Road, Hunters Hill | Tech Choice | FTTP - Type 3 (MT-LFN) | 2HUH_22 | Mark Leal |  |  | Mickey | Completed | Paul O'Farrell |  |  |  |  | Waiting to receive |  |  |  |  | 2019-08-02 |  |  |  |  | 2019-02-22 |  |  | 15/10- Materials ordered 23/10- Blockages and possible new build required. Dates will need to be revised 05/11- New build proposal approved, awaiting new LAANs 23/11- No change 30/11- Booked in tentatively for Thursday, pending council waiver 14/12- NBN put hold on due to council concerns about construction standards 06/01- Awaiting response from council 08/11- Conntaced Bruce from Council who will look at site tomorrow and get back to us with aqpproval 11/01- No contact from council, unable to reach Bruce on phone 09/02- Road crossing complete, blockage in EUs front yard outstanding | [5 empty] | 2019-02-27
AYCA-5KAX1D | 20 Burrundulla Ave Mudgee | D&B NSB | FTTN | 2MDG-01 | Mark Leal |  |  | Mickey | Completed | [18 empty] | 25/02 - Site meeting with council and resident Obtained the OK from housing for 35 Burrundulla Obtained the OK from council, will need provide access to empty land Taken dilap photos of area, broken footpath prior to our works NBN FS questioning about Comms pits/duct being used, will get back to us. Cannot commence until field advises 28/02 - New drill shot build, need amend design, CLAAN revise sent | 2019-03-29
AYCA-5KDV96 | 43,45,47,49 Eastern Valley Way, Tallwood | Non Standard | FTTN | 2NAB-20 | Mark Leal |  |  | Mickey | Completed | [5 empty] | Start: 04/04/2019 | [12 empty] | 28/02 - Pending material order as we require Project Number Contractor advised they have all the materials ready to build, 09/03 - Pending CLAAN, followed up with Mary and Mark 12/03 - Followed up on 19/03 - Attending 04/04/2019, PC 06/04/2019 14/05 - CRS | 2019-05-08
AYCA-5LC14Q | 100 Mount street, North sydney, NSW 2060 | New Devs - MDU | FTTP- Type 2 | 2NSY-21 | Ertan Cicek | #REF! | #REF! | Mickey | Completed | Mark Hansen 0411660160 Ben 0484557 660 |  |  |  |  | Start: 31/10/2018 End: 30/04/2019 | [12 empty] | 19/10- Waiting for LAANs 15/02 - CLAAN received 25/10 19/02 - Require site visit, scheduled for Vasko 4th on list 27/02 - Organising with Ben with our crews to have inducted, need to discuss if we can find alternative day next week due to scheduled works on Monday. Hoarding in approx 7m to the link up inside the development, liaising with developer 23/04 - Require to rectify defect of cable tie. Developer to arrange scissor lift that works on ramp, developer to advise when it is available 14/05 - Scissor lift available to confirm for Thursday 16/05 | 2019-04-26
AYCA-5MQHDT | 32 Ruskin Rowe, Avalon Beach | Tech Choice | FTTP - Type 3 (MT-LFN) | 2AVA-02 | Mark Leal |  |  | Mickey | Completed | Sarah Parry-Okeden sarahparryokeden@gmail.com |  |  |  |  | Start: 03/01/2019 End: 20/06/2019 | [12 empty] | 18/01- Haul scheduled week starting 21/01 24/01- Mulitple blockages and missing network 09/02- Majority of network found, two pits remaining, required locator 19/02 - Still missing 1 pit, due back 20/02 to go out and find pit and haul
AYCA-5OZYD0 | 204-214 Chandos St Horsley Park | Business Segment | FTTP - Type 3 (MT-LFN) | 2ERP-20 | David Yeomans |  |  | Mickey | Completed | Simon Duane 0408 574 046 (Ian no longer works for business) |  |  |  |  | 22/11/2018 | 2018-12-11 | 2018-12-11 | 2019-03-20 | 2019-04-15 | 2019-04-26 | [7 empty] | 30/11 - Waiting for confirmation of Gas Standby to perform civils. 04/12 - Confirming with Jemena when Site Contact/Standby available to commence with civils 10/12 - Ian advised this will be pushed out till next year. Unable to confirm when 13/12 - No Change 18/01 - Simon advised good to schedule 20/03. 12/03 - Confirmed with Simon to commence 4th and 5th april for 7am start 01/05 - Jemena advised 14/05 07:00AM available 11/05 - Reattending to finish off haul/splice 14/05 | TBC
AYCA-5OZYGU | 194-204 Chandos St Horsley Park | Business Segment | FTTP - Type 3 (MT-LFN) | 2ERP-20 | David Yeomans |  |  | Mickey | Completed | Adam Christen 0402059783 |  |  |  |  | 30/11/2018 | 31/10/2018 | 31/10/2018 | 2018-12-04 | 2018-12-04 | 2019-01-11 |  |  |  |  | 2019-01-07 | Jan-19 |  | 30/11 - Waiting for confirmation of Gas Standby to perform civils. 04/12 - Commenced with civils today, approx 2-3 days to finish 10/12 - Civils and haul completed, require return to perform termination. Only available after 18/12. 12/12 - Access provided to splice on 19/12 20/12 - Pushed out till second week of January due to tech unavailability 08/01 - Successful vis test performed 07/01 - pending perm resto of concrete slab | 2019-01-15 |  |  |  |  | 2019-01-10 | Jan-19
AYCA-5PYJJF | Sailfish Way & Seaside Drive Kingscliff | D&B NSB | FTTP – Type 2 | 2KCL-02 | Mark Leal |  |  | Mickey | Completed | [5 empty] | Start: 07/02/2019 End: 27/06/2019 | [12 empty] | 19/02 - Cable sent up, should receive today or tomorrow 28/02 - Cable hauled, civils link and pit install complete, end up 8 pit with riser. Ready for splicing 05/03 - Splicing 25-29th to attend
AYCA-5QTMEE | 68-82 Fairway Drive Kellyville | D&B NSB |  | 2KEL-07 | Mark Leal |  |  | Mickey | Completed | [5 empty] | Start: 25/01/2019 End: 14/06/2019 | [12 empty] | 18/02 - CRQ approved for 21/02 to 23/02 to perform MPT swap 26/02 - PON Patching request due to dead SPL. Require 8 patches, only done 3 28/02 - Need to liven up splitter | 2019-03-13
AYCA-5RHH4X | 68 Beecroft Road, Beecroft NSW 2119 | New Devs - MDU | FTTP - Type 3 (MT-LFN) | 2PNN-68 | Ertan Cicek | 2019-09-25 | Sep-19 | Mickey | In Construction | Sam (Elec) - 0415151000 Nick 0415441001 | X |  | X |  | Start: 05/01/2019 End: 15/06/2019 | [12 empty] | 11/01- ROL applied for. night works 17/02 - Materials ordered additional, followed up on ROL/TCP, Dependency in service. Requires site visit 04/03 - Site visit indicated: - Comms Room not ready - Lead-in ready - Pathway to comms ready 16/03 - Booked 27/03 night works 30/03 - Developer advised not ready, they have requested WS 01/04, but will need to be revised for next available 01/05 - issues onsite regards to pit upgrade and picking up existing. Solution is to drop larger pit, require full night - rescheduled after ROL renew for May 11/05 - Reattend site to install pit and link 15/05 23/05 - 12/06 can reattend due to metro project
AYCA-5ST32Q | 42-44 Enterprise Cres, McDouglass Hill | Business Segment | FTTP - Type 3 (MT-LFN) | 2SIN-22 | David Yeomans |  |  | Mickey | Completed | Samantha Dunne 6575 9920 |  |  |  |  | 2018-12-27 | 2018-12-13 | 2018-12-13 | 2018-01-07 | 2019-01-14 | 2019-02-06 |  |  |  |  | 2019-02-11 | Feb-19 |  | 12/12 - Customer advised not aware of build approved. 13/12 - Confirmed driller can commence WS 07/01/2019, Ordered materials 08/01 - Driller commenced but found rock plus storm water. Unable to drill using current drill, need to return with appropriate rock drill on Thursday/Friday. Will need to go down 3m deep to avoid storm water. 09/01 - Approved for drill shot into rock, pushed out now 2 weeks time. Driller to provide update of availability 18/01 - Drill complete, civil and haul works 18/01, splicing 25/01 - Require to reattend to blockage 26/01, planned splicing WS 30/01 29/01 - Postponed splicer, aiming to attend WS 04/02 | 2019-02-13 |  |  |  |  | 2019-02-18 | Feb-19
AYCA-5ST336 | 78-82 RIVERSIDE RD, CHIPPING NORTON NSW 2170 | Business Segment | FTTP - Type 3 (MT-LFN) | 2LIV-68 | David Yeomans |  |  | Mickey | Completed | [5 empty] | 2019-01-11 | 2018-12-19 | 2018-12-19 | 2019-01-21 |  | 2019-02-11 |  |  |  |  | 2019-02-01 | Feb-19 |  | 12/12 - Ordered materials, unable to commence construction, CLAAN not issued due to design not approved 20/12 - CLAAN raised, start date 11/01/2019 08/01 - Ordered materials 624997 and commencing haul next week 18/01 - blockage and hauling commenced 18/01 | 2019-01-31 |  |  |  |  | 2019-02-05 | Feb-19
AYCA-5T4J9J | 41 Production Ave Wauchope | D&B NSB | FTTN | 2WAU-21 | Mark Leal |  |  | Mickey | Completed | [5 empty] | Start: 01/03/2019 | [12 empty] | 18/02 - Draft design received, CLAAN issued will commence 01/03 19/02 - Ordered materials, shipped to Kev, will commence after 01/03 28/02 - Pending 10pr copper, no ETA 16/03 - Require to try fix lead-in on 18/03 | 2019-03-22
AYCA-5UQX4I | 29 Moorefield Avenue, Hunters Hill NSW 2110 | New Devs - MDU | FTTN | 2HUH-20 | Ertan Cicek | #REF! | #REF! | Mickey | Completed | Peter Falzon - 0419251215 Paul site manager | [17 empty] | 16/02 - Materials ordered, LAAN not on priority list, not received. Depending on the option of dependency will depend on the PON Patching. Site not visited 21/02 - Advised change of tech from FTTP to FTTN, received docs 21/02 - Established contact with Peter, apparently 2 pr already servicing a house but not enough to service all prems. Site is already 95% complete and telstra already performed link up. Site visit this afternoon
AYCA-5V8GAT | 1A DARTFORD RD, THORNLEIGH NSW 2120 - Thornleigh Sports Centre | Business Segment | FTTP - Type 3 (MT-LFN) | 2PNN-60 | David Yeomans |  |  | Mickey | Completed | [5 empty] | CLAAN: 09/04/2019 |  |  |  | 2019-04-09 | 2019-05-24 | [7 empty] | 01/03 - Rod and rope commenced, SLAAN 1603 - Survey 90% 16/03 - Design delivery 21/03 30/03 - Ordered materials 11/05 - Remaining civils commencing 13/05 28/05 - Civils complete on reroute using existing lead-in and breaking out for new building lead-in. Splicing 29/05 01/06 - Field completed 31/06, PC Pack 05/06
AYCA-5V8GEZ | 31-33 SEFTON RD, THORNLEIGH NSW 2120 - Thornleigh Depot | Business Segment | FTTP - Type 3 (MT-LFN) | 2PNN-60 | David Yeomans |  |  | Mickey | In Construction | [5 empty] | CLAAN: 04/04/2019 |  |  |  | 2019-04-08 | 2019-05-30 | [7 empty] | 01/03 - Rod and rope commenced, SLAAN 16/03 - Design delivery 19/03 11/05 - Road crossing planned for WS 20/05 01/06 - Road crossing completed 30/06/2019, hauling completed 31/06, Splicing 05/06/2019
AYCA-5V8GGB | 70 YARRARA RD, PENNANT HILLS NSW 2120 - Pennant Hills Library | Business Segment | FTTP - Type 3 (MT-LFN) | 2PNN-62 | David Yeomans |  |  | Mickey | Completed | [5 empty] | SLAAN: 22/02/2019 CLAAN: 25/03/2019 |  |  |  | 2019-04-01 | 2019-04-05 | [7 empty] | 01/03 - Rod and rope commenced, SLAAN 13/03 - Tentative start date 25/03/2019 and Con-comp 29/03/2019 | 2019-03-29
AYCA-53VL4I | HFC DFN 2PNN-68 | HFC DFN | DFN | 2PNN-68 | Mark Leal |  |  | Mickey | Completed | [5 empty] | 2019-03-11 | [12 empty] | 12/03 - Civils to commence 18/03. ROL requested for our civil works on Castle Hill Rd, pending 16/03 - Blockages commenced 26/03 - 50% of blockages completed 02/04 - 90% blockages completed, 20% hauling ROL received, Castle Hill Rd window is only 2 nights with 7 hr intervals 2 Blockages 09/04 and 10/04 02/04 - worse case, requested ROL for next month 09/04 - Crews booked tonight to utilise existing first, dig downs and pull rope through, rather new build on Castle Hill Rd | 2019-05-10
AYCA-5QBJSS | HFC DFN 2PRA-62 | HFC DFN | DFN | 2PRA-62 | Mark Leal |  |  | Mickey | Completed | NA |  |  |  |  | 2019-03-08 | [12 empty] | 12/03 - Civils commenced, 10% completed 2 pits required 2 blockage section 1 trench section 5m 26/03 - 80% civils, gas standover 18/04 for pit install | 2019-05-03
AYCA-5KIM5I | 19 Clarence Street, Lake Munmorah-Estate+TTFN | SDU | FTTN | 2BUP-05 | Mark Leal |  |  | Mickey | Completed | Peter Roome 0412606280 bill 0411243377 |  |  |  |  | Requested 13/03/2019 | [12 empty] | 13/03 - Requested dev details and CLAAN 16/03 - Booked in copper aerial jointer 01/04 16/04 - Waiting on direction regarding the developer lead-ins from underground to aerial 01/05 - Requested Michael P/Dave for recommendation before returning 06/05 - Reattending this week to fix lead-ins and perform transitions 14/05 - Prem count updated from 3 to 2 | 2019-05-17
AYCA-5OJCT8 | Lot 51,155 Woy Woy Road Kariong NSW-Estate+TTFN | Tech Choice | FTTP - Type 3 (MT-LFN) | 2GOS-20 | Mark Leal |  |  | Mickey | Completed | Gary 0408757475 |  |  |  |  | SLAAN Only Pending: National Park | [12 empty] | 14/03 - Spoke to customer, heads up, tentative mobilisation to prove LIC first, WS 18/03/2019 26/03 - Lead-in proven, there's actual 6 pit in between.. 220m + 20m 02/04 - Hauling and roping the lead-in week starting 08/04. Forecast PC 12/04 - Missing pits along route, require vac truck and locator, ducts are blockage by mud - area should not be national park area - if all goes well with vac truck, can tentative PC 03/05 | 2019-05-03
AYCA-5PAIM1 | 3 Jarrod Close, Charlestown NSW | Tech Choice | FTTP - Type 3 (MT-LFN) | 2CHL-07 | Mark Leal |  |  | Mickey | Completed | Andrew Frith- andrew@frithfamily.com.au- 0412 747 500 |  |  |  |  | Start: 20/03/2019 |  |  | 2019-04-11 |  | 2019-05-01 | [7 empty] | 19/03 - Ordered materials 19/03 - Attending RRP and haull on Week Start 01/04 02/04 - Starting onsite pushed out to next week, due to project up north held up 05/04 - Onsite start 11/04 12/04 - Pushed out to 29/04 due to crew availability. This has been hauled ready for termination and activation on WS 29/04 13/04 - Revise splicing date as customer going on leave. Confirming with customer availability after coming back from leave and hopefully 01/05 - Confirmed with customer WS 06/05. Proposed PC 10/05 | 2019-05-10
AYCA-2WNBI8 | HFC DFN 2PEN-64 | HFC DFN | DFN | 2PEN-64 | Mark Leal |  |  | Mickey | Completed | [5 empty] | Start: 19/03/2019 | [12 empty] | 20/03 - Civil kick off 25/03 25/03 - Cable materials ordered and Hauling has commenced 26/03 - Commenced on blockages and prep haul 09/04 - Follow up on ROL 01/05 - two blockages and two cable hauls remaining. On track for completion 10/05 11/05 - Railway corridor, can commence after 23/05, pushed out completion 31/05 01/06 - Completed 31/06 | 31/06/2019
AYCA-5JQV6N | HFC DFN 2BAN-62 | HFC DFN | DFN | 2BAN-62 | Mark Leal |  |  | Mickey | In Construction | [5 empty] | Start: 04/04/2019 | [12 empty] | 09/04 - Hauled 10%, blockages working through - ROL Requested 01/04 16/04 - Should be receiving ROL tomorrow, follow up. Blockages rectification 30%, Blockage on Hume highway still pending and 2 sections not R&R due to m/h in middle of Hume highway 01/05 - Hauled 30%, 2 major civils pending, ROL should receive by today/tomorrow advised by TMC 07/05 - ROL to come, pending 1 drill, 1 blockage, 1 haul through hume hwy | 17/05/2019 (31/05/2019)
AYCA-5SPCV6 | HFC DFN 2BOT-61 | HFC DFN | DFN | 2BOT-61 | Mark Leal |  |  | Mickey | In Construction | [5 empty] | Start: 20/05/2019 | [12 empty] | 11/05 - Commencement of ordering materials and requesting ROL
AYCA-5MELWX | HFC DFN 2BOT-62 | HFC DFN | DFN | 2BOT-62 | Mark Leal |  |  | Mickey | In Construction | [5 empty] | Start: 12/04/2019 | [12 empty] | 01/05 - Materials ordered, commenced with blockages, progressing. ROL requesting commenced, 50m civil build main road, 50m civil build road crossing - confirming with driller 11/05 - 20% blockages completed | 2019-06-14
AYCA-5E2I7I | HFC DFN 2KNS-62 | HFC DFN | DFN | 2KNS-62 | Mark Leal |  |  | Mickey | Completed | [5 empty] | Start: 29/04/2019 | [12 empty] | 01/05 - Ordered materials, no major stoppers, can deliver by end of May ROL requested 11/05 - Waiting on Todman Ave ROL 01/06 - Completed 31/05 | 2019-05-31
AYCA-52ZW78 | HFC DFN 2STL-60 | HFC DFN | DFN | 2STL-60 | Mark Leal |  |  | Mickey | Completed | [5 empty] | Start: 01/04/2019 | [12 empty] | 25/03 - Ordered materials, schedule start date 30/03 - WS 01/04 will start hauling, PC on track 09/04 - Pedestrian restriction | 2019-04-10
AYCA-45502V | 127 Prince St Clarence Town NSW 2321 | SDU | FTTN | 2CTW-20 | Mark Leal |  |  | Mickey | Completed | [5 empty] | Start:08/04/2019 (Heritage Exemption) | [12 empty] | 25/03 - Requested site contact, CLAAN and proj number 30/03 - Followed up 09/04 - wait for exemptions 01/05 - Received exemption signed by council. Notifying as long as we do not disturb the trees. Field completion 20/05 11/05 - 2 out of 3 lots found pairs, middle lot is existing house heritage already connected Prem count change from 3 to 2 | 2019-05-22
AYCA-5JCP5O | 32 Azalea Street, Mullumbimby NSW 2482 | SDU | FTTN | 2MUL-01 | Mark Leal |  |  | Mickey | Completed | [5 empty] | DTKS creating 04/04 |  |  |  |  | 2019-05-03 | [7 empty] | 30/03 - Requested site contact, CLAAN and proj number 03/04 - No CLAAN, DTKS to raise/request on 04/04 09/04 - CLAAN issued by DTKS 16/04 - Confirming attendance date 18/04 - Development not ready, but will have the copper lead-ins at the lead-in pits 01/05 - Site not ready but due to copper, finding available pairs. Only able to find 1 pair out of 4. Require revisit | 2019-05-21
AYCA-5HZXRM | HFC DFN 2SHA-64 | HFC DFN | DFN | 2SHA-64 | Mark Leal |  |  | Mickey | In Construction | [5 empty] | Start: 08/04/2019 | [12 empty] | 09/04 - Ordered materials, requested ROL, and started pit cleanouts and blockages 10% , 03/04 requested ROL 01/05 -
WOR100129896564 | DFN NODE SPLIT 2UND-60 | NODE SPLIT | DFN | 2UND-60 | Greg Moeller |  |  | Mickey | [6 empty] | Start: 19/04/2019 | [12 empty] | 01/05 - Hauling complete, ready for splicing by end of week. PC 08/05
AYCA-4Y3W7O | HFC DFN 2PYM-60 | HFC DFN | DFN | 2PYM-60 | Mark Leal |  |  | Mickey | In Construction | [5 empty] | Start: 24/04/2019 | [12 empty] | 17/04 - materials ordered, Pending ROL's to come back
AYCA-4LKVQJ | HFC DFN 2ROC-61 | HFC DFN | DFN | 2ROC-61 | Mark Leal |  |  | Mickey | In Construction | [5 empty] | Start:15/05/2019 | [12 empty] | 01/05 - materials ordered, ROL requests commenced
AYCA-49ZOSX | HFC DFN 2ROC-60 | HFC DFN | DFN | 2ROC-60 | Mark Leal |  |  | Mickey | In Construction | [5 empty] | Start: 10/05/2019
AYCA-31DCKF | HFC DFN 2EAS-62 | HFC DFN | DFN | 2EAS-62 | Mark Leal |  |  | Mickey | In Construction | [5 empty] | Start: 01/05/2019 | [12 empty] | 01/05 - materials ordered, ROL requests commenced
AYCA-4HLUIU | HFC DFN 2PYM-62 | HFC DFN | DFN | 2PYM-62 | Mark Leal |  |  | Mickey | In Construction | [5 empty] | Start: 22/05/2019 | [12 empty] | 21/05 - Drill shot and civil works required.
WOR100132471129 | DFN NODE SPLIT 2BAL-61 | NODE SPLIT | DFN | 2UND-60 | Greg Moeller |  |  | Mickey | In Construction | [5 empty] | Start: 16/05/2019 | [12 empty] | 20/05 - materials ordered, ROL requests commenced
WOR100130218736 | HFC DFN 2SEF-61 | HFC DFN | DFN | 2SEF-61 | Mark Leal |  |  | Mickey | Pre-Construction | [5 empty] | Start: 05/06/2019
AYCA-4WLRNG | 51-53 Foxall road,Kellyville NSW 2155 | SDU | FTTP - Type 2 | 2ROU-03 | Mark Leal |  |  | Dane | Completed | [18 empty] | 02/05- Route roped and proven | [5 empty] | 2019-05-25
AYCA-5E4D09 | 2-6 Dolerite Way Pemulwuy NSW 2145 | MDU Internals | FTTP - Type 3 (MT-LFN) | 2PEN-01 | Sundeep Chokshi |  |  | Dane | PC | [18 empty] | 16/02- Ready to commence 02/03- Scheduled WS 04/03 02/05- Internals commenced, issues with DSS cable on route
AYCA-5EJRTN | 31-31A Perry St, Campsie | Transformation | FTTP - Type 2 | 2CAM-02 | Ertan Cicek | 2019-01-10 |  | Dane | In Design | [5 empty] | 18/04/2019 | [12 empty] | 28/03- DDD submitted 26/03 16/04- CRQ raised for 02/05 18/04- LIC brought out directly to side of pit, cable tray not yet installed 02/05- MPT upgrade complete, need new FDH patching allocation
AYCA-5G1AHP | 2-14 Amelia Street, Waterloo - | MDU Externals | FTTP - Type 2 | 2RED-01 | Ertan Cicek | 30/06/2019 |  | Dane | In Design | Maroun |  |  |  |  | 15/04/2019 | [12 empty] | 28/03- DDD submitted 28/03 16/04- DDD approved 18/04- Developer to bring LIC to boundary after Easter break 09/05- LIC to be brought out next week when scaff is down 22/05- Scaff down this week, plan to install LIC Monday 27/05 31/05- Scaff down in another 2 weeks
AYCA-5IOF6P | 120 Hume Highway, Chullora | Transformation | FTTP - Type 2 | 2BAN-60 | Ertan Cicek | 26/06/2019 |  | Dane | In Design | Daniel Tully 0407 253 722 |  |  |  |  | 16/04/2019 | [12 empty] | 28/03- NDD submitted 07/03 29/03- DDD submitted 29/03 16/04- DDD approved 18/04- Check on LIC progress mid may as advised by developer
AYCA-5JO5XA | 5-9 White Avenue, Bankstown | Transformation | FTTP - Type 2 | 2BAN-70 | Ertan Cicek | 28/06/2019 |  | Dane | In Design | [5 empty] | 21/05/2019 | [12 empty] | 02/05- DDD submitted 01/05/2019 07/05- Awaiting response 08/05- Materials ordered 31/05- Site is 2 months away
AYCA-5LZJ26 | 72 Canterbury Road, Bankstown , NSW2200 | Transformation | FTTP - Type 2 | 2BAN-70 | Ertan Cicek | 2019-06-04 |  | Dane | PC | [5 empty] | 2019-03-05 | [12 empty] | 28/03- NDD submitted 15/03 02/04- Advised internals is complete 02/05- DDD Approved 02/05- Materials ordered 642086 02/05- Scoped 03/05 08/05- Scheduled WS 20/05, or when we recieve ROL
AYCA-5QX4TH | 164 Cathedral Street, Woolloomooloo, NSW 2011 | MDU External | FTTP - Type 3 (MT-LFN) | 2EAS-60 | Ertan Cicek | 2019-04-05 |  | Dane | In Design | [5 empty] | 2019-06-12 | [12 empty] | 02/05- DDD Due 03/05 09/05- DDD submitted, awaiting response, materials ordered 24/05- LAANs to be issued today
AYCA-5T1531 | 293 Princes Highway, Saint Peters, NSW 2044 | MDU External | FTTP - Type 3 (MT-LFN) | 2NEW-60 | Ertan Cicek |  |  | Dane | In Design | [5 empty] | 2019-11-04 | [12 empty] | 16/04- Applied for an ROL 08/04, lead in pit not linked to network, possibly upgrade pit and try and pick up duct, or tench 10m back to 5 pit 31/05- LIC to be brought out Monday
AYCA-5WOZHL | 18 Rawson Road, South Wentworthville, NSW 2145 | MDU Externals | FTTP- Type 2 | 2PEN-66 | Ertan Cicek |  |  | Dane | Site Visit | [5 empty] | 20/03/2019 | [12 empty] | 02/03- Ready to go 08/03- Lead in 6 pit needs to be replaced and upgraded, developer looking into it with Telstra 04/04- ready to go
AYCA-60KQLM | 44A Foveaux Street, Surry Hills NSW | Transformation | FTTP - Type 3 (MT-LFN) | 2HMK-20 | Ertan Cicek | 2019-10-05 |  | Dane | In Design | [18 empty] | 16/04- NDD submitted 04/002/05- DDD submitted 26/04 07/05- Heritage exemtion submitted 02/05 08/05- Waiting for heritage
AYCA-5E4D09 | 2-6 Dolerite Way, Pemulwuy NSW 2145 | MDU | FTTP - Type 3 (MT-LFN) | 2PEN-01 | Ertan Cicek |  |  | Dane | PC | [18 empty] | 04/04- Waiting for new CPLAN 02/05- Issue with existing DSS cable, need to try and alleviate bend radius, or haul new cable 08/05- Need to redesign new haul
AYCA-5T1531 | 293 Princes Highway, Saint Peters, NSW 2044 | MDU Internals | FTTP - Type 3 (MT-LFN) | 2NEW-60 |  |  |  | Dane | Site Visit | [18 empty] | 02/05- Pending externals
AYCA-5218CU | 1- Springbrook Boulevarde | SDU | FTTP - Type 2 | 2ROU-02 | Mark Leal |  |  | Dane | Site Visit | [5 empty] | 2019-02-05 | [12 empty] | Dependent on a project not yet issued top Datateks
AYCA-3T5IJK | 58 George Street, Box Hill | SDU | FTTP - Type 3 (MT-LFN) | 2ROU-01 | Mark Leal |  |  | Dane | Completed | [5 empty] | Waiver | [18 empty] | 2019-05-23
AYCA-5TDQG3 | 20-22 Craig Street, Punchbowl | MDU Externals | FTTP - Type 3 (MT-LFN) | 2ROU-01 | Ertan Cicek |  |  | Dane | PC | [18 empty] | 29/04- DDD approved 08/05- Scheduled for internal access 16th and 17th may
AYCA-53IJ1X | 21 Hall St Pitt Town NSW 2756 | AYCA-4S2PFJ | FTTP - Type 2 | 2PIT-01 | Mark Leal |  |  | Dane | Completed | [18 empty] | 02/05- Aborginal heritage approved | [5 empty] | 2019-05-27
AYCA-63GR5P | 125-127 Victoria Street , Werrington | MDU Internals | FTTP - Type 3 (MT-LFN) | 2SHA-64 |  |  |  | Dane | In Design | [5 empty] | 2019-06-12
AYCA-5XSYES | 263-265 Maroubra Road , Maroubra | MDU Externals | FTTP - Type 2 | 2BOT-01 | Ertan Cicek |  |  | Dane | In Design | [5 empty] | 2019-06-03
AYCA-3KSP3J | 180-192 Carline Chisholm Drive Winston Hills, NSW 2153 | MDU Externals | FTTP - Type 2 | 2SEV-61 | Ertan Cicek |  |  | Dane | Site Visit | [5 empty] | 22/05/2019 | [12 empty] | 08/05- Waiting for scoping document
AYCA-5TDQG3 | 20-22 Craig Street, Punchbowl | MDU Internals | FTTP - Type 3 (MT-LFN) | 2ROU-01 |  |  |  | Dane | PC
AYCA-60KQLM | 44A Foveaux Street, Surry Hills NSW | MDU Internals | FTTP - Type 3 (MT-LFN) | 2HMK-20 |  |  |  | Dane | Site Visit | [18 empty] | 10/05- Materials ordered
AYCA-58DDCW | 46 Linden Street Sutherland, NSW 2232 | MDU Externals | FTTP - Type 3 (MT-LFN) | 2CMO-23 | Mark Leal |  |  | Dane | PC
AYCA-603NCA | Lot 39 Patricia St, Blacktown | MDU Externals | FTTP - Type 2 | 2BLK-07 |  |  |  | Dane | In Design | [18 empty] | 28/05- DDD due 29/05
AYCA-63BVQ4 | 152 Military Road, Neutral Bay NSW 2089\ | MDU Externals | FTTP - Type 3 (MT-LFN) | 2CRM-66 | Ertan Cicek |  |  | Dane | In Design
AYCA-4PPE86 | 2 Mile End Rd, Rouse Hill | MDU Externals | FTTP - Type 2 | 2ROU-02 | Ertan Cicek |  |  | Dane | Site Visit | [18 empty] | 30/05- Materials ordered 645941
AYCA-4KF6NC | Bldg-B Parkland Estate, Rouse Hill | MDU Externals | FTTP - Type 3 (MT-LFN) | 2RIV-08 | Ertan Cicek |  |  | Dane | Site Visit | [18 empty] | 30/05- Materials ordered 645942
AYCA-67X5N1 | 3 Raymond Rd Neutr-Estate | NSB |  |  | Mark Leal |  |  | Dane | In Design
AYCA-4IUR8S | 3 WENTWORTH STREET, GLEBE | [6 empty] | Dane | In Design
AYCA-38Z3VZ | Greenbank Dr Blacktown, NSW 2148 | MDU Externals | FTTP - Type 2 | 2BLK-11 | Ertan Cicek |  |  | Dane | Site Visit | [18 empty] | 31/05- Materials ordered
AYCA-5667HJ | 12-16 Beetson Street, Boorooma | MDU Externals | FTTP - Type 2 | 2WAG-01 | Sogand Mohtat | 2018-02-22 | Feb-18 | Marshell | Completed | [5 empty] | 2018-05-18 |  |  | 2018-06-20 | 2018-06-20 | 2018-06-25 |  |  |  |  | 2018-06-21 | Jun-18 |  | 0 | 2018-06-21 |  |  |  |  | 2018-06-21 | Jun-18
AYCA-4KXY8F | 1 Wark Parade, Windradyne | MDU Externals | FTTP - Type 3 (MT-LFN) | 2BTH-02 | Ertan Cicek | 2018-04-01 | Apr-18 | Marshell | Completed | [5 empty] | 2018-02-27 |  |  | 2018-06-12 | 2018-06-12 | 2018-06-22 |  |  |  |  | 2018-06-21 | Jun-18 |  | 0 | 2018-06-27 |  |  |  |  | 2018-06-27 | Jun-18
AYCA-593AE3 | 12 Uriarra Road, Queanbeyan | MDU Internals | FTTP - Type 2 | 9QBN-03 | Mark Leal | 2018-05-01 | May-18 | Marshell | Completed | [5 empty] | 2018-08-09 |  |  | 2018-08-30 | 2018-08-17 | 2018-09-07 |  |  |  |  | 2018-09-07 | Sep-18 |  | 24/07: Job awarded. Asked for LAAN and LIFD, now that the property is occupied 09/08: LIFD Requested 15/08: LIFD sent. 16/08: Early waiver is signed by the property owner. DT to liaise with property manager for access to each unit 24/08: SDS and PCD installed. Scheduled in to install NTDs on the 31st of August 31/08: 9 units will have NTD installed today. 1 unit will be installed on the 07/09 06/09: On track for completion by Friday 14/09: PC submitted 07/09 | 2018-09-07 |  |  |  |  | 2018-09-07 | Sep-18
AYCA-4YPT3F | 145 Hammond Ave, East Wagga | MDU Externals | FTTN | 2WAG-05 | Ertan Cicek | 2018-05-04 | May-18 | Marshell | Completed | [8 empty] | 2018-06-15 | 2018-06-15 | 2018-06-15 |  |  |  |  | 2018-06-15 | Jun-18 |  | 0 | 2018-06-18 |  |  |  |  | 2018-06-18 | Jun-18
AYCA-48LNJ7 | Cedar St, Orange | SDU | FTTN | 2ORG-02 | Mark Leal | 2018-05-10 | May-18 | Marshell | Completed | [8 empty] | 2018-06-06 | 2018-06-06 | [5 empty] | 2018-06-10 | Jun-18 |  | 0 | 2018-06-14 |  |  |  |  | 2018-06-14 | Jun-18
AYCA-5A3CT0 | 1 Beaconsfield St, Fyshwick | MDU Externals | FTTP - Type 3 (MT-LFN) | 9MNK-01 | Ertan Cicek | 2018-06-01 | Jun-18 | Marshell | NBN Delay | [5 empty] | 2018-08-27 |  |  | 2018-08-27 | 2018-08-28 | 2019-06-30 | [7 empty] | 10/08: job awarded 17/08: Planned to start construction on the 27th of August. LAAN started on the 27th of August 24/08: Additional internal work needs to be completed by the developer. TBA 31/08: civil works completed. Awaiting for the DJL to be installed and internal work 06/09: No update on the A end. Internal work being completed today, as advised by the developer. Internal hauling commencing tomorrow 14/09 - Still waiting for A END DJL - SDS cables hauled 21/09 - no change 28/09 - no change. still awaiting for A End. DJL proposed location is within EPR zone 12/10 - no change 19/10 - no change 25/10 - no change 01/11 - no change 09/11 - no change 16/11 - no change 23/11 - no change. possible push out until 2019 30/11 - no change. no further update will be given until further notice by nbn .
AYCA-5DBDK2 | 8 Werrang St, Albion Park Rail | SDU | FTTN | 2ABN-03 | Ertan Cicek | 2018-06-01 | Jun-18 | Marshell | Completed | [15 empty] | 2018-07-03 | Jul-18 |  | 0 | 2018-07-03 |  |  |  |  | 2018-07-05 | Jul-18
AYCA-4V3JM3 | 69 High Street, Thirroul | SDU | FTTP - Type 3 (MT-LFN) | 2COR-01 | David Yeomans | 2018-06-29 | Jun-18 | Marshell | Completed | [8 empty] | 2018-06-25 | 2018-06-25 | 2018-06-29 |  |  |  |  | 2018-07-05 | Jul-18 |  | 0 | 2018-07-05 |  |  |  |  | 2018-07-05 | Jul-18
AYCA-4M2GZ2 | 2 Pine Street, Albion Park Rail | SDU | FTTP - Type 3 (MT-LFN) | 2ABN-01 | David Yeomans | 2018-06-29 | Jun-18 | Marshell | Completed | [5 empty] | 2018-06-20 |  |  | 2018-07-03 | 2018-07-03 | 2018-07-06 |  |  |  |  | 2018-07-10 | Jul-18 |  | 06/07 - Blockages on route, dig down repairs required, customer internal route issues. 13/07 - Completed 11/07 | 2018-07-11 |  |  |  |  | 2018-07-11 | Jul-18
AYCA-5K7QBN | 74 Uriarra Road , Queanbeyan | NSB | Type 2 | 9QBN-03 | Mark Leal | 2018-07-01 | Jul-18 | Marshell | Completed | [8 empty] | 2018-08-14 | 2018-08-15 | 2018-09-28 |  |  |  |  | 2018-09-27 | Sep-18 |  | 17/08 - design and survey completed. Submitted to nbn for review 24/08 - awaiting for LAAN and LIFD construction 31/08: Scheduled in for WS 17/09 06/09: No change 14/09: no change 21/09: design submitted 17/09. awaiting for nbn response 28/09: design approved 26/09. PC submitted 27/09 | 2018-09-27 |  |  |  |  | 2018-09-27 | Sep-18
AYCA-52381N | 284, River Rd, Sussex Inlet | MDU Externals | FTTN | 2SUX-01 | Ertan Cicek | 2018-07-04 | Jul-18 | Marshell | Completed | [5 empty] | 2018-06-15 |  |  | 2018-06-25 | 2018-06-28 | 2018-06-29 |  |  |  |  | 2018-06-29 | Jun-18 |  | 0 | 2018-07-04 |  |  |  |  | 2018-07-04 | Jul-18
AYCA-4VAQ8P | 11 Prevost Pl, MacGregor | MDU Externals | FTTN | 9SCU-07 | Andrew Mahasay | 2018-07-04 | Jul-18 | Marshell | Completed | [5 empty] | 2018-06-26 |  |  | 2018-07-04 | 2018-06-29 | 2018-07-11 |  |  |  |  | 2018-07-11 | Jul-18 |  | 06/07 - Scheduled copper works week commencing 09/07 13/07 - Completed 11/07 | 2018-07-16 |  |  |  |  | 2018-07-16 | Jul-18
AYCA-3MEHNA | Nevertire St, Lawson | MDU Externals | FTTP - Type 2 | 9BLC-04 | Ertan Cicek | 2018-07-14 | Jul-18 | Marshell | Completed | [5 empty] | 2018-07-09 |  |  | 2018-07-16 | 2018-07-16 | 2018-07-20 |  |  |  |  | 2018-07-18 | Jul-18 |  | 06/07 - Forecast start date 16/07 13/07 - Identified CTL not installed by Internal NBN Contractors. Will perform coil option | 2018-07-23 |  |  |  |  | 2018-07-23 | Jul-18
AYCA-54NU37 | 177 Newman-Morris Circuit, Oxley | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 9KBA-20 | Mark Leal | 2018-07-31 | Jul-18 | Marshell | Completed | [5 empty] | 2018-07-05 |  |  | 2018-08-20 | 2018-08-20 | [5 empty] | 2018-09-17 | Sep-18 |  | 06/07 - Quote submitted 20/06 27/07 - no change 03/08 - TTM approved by TCCS ACT . Proposed start date on the 20/08 10/08: NO change 17/08: Planned to start on Tuesday, 21/08/2018 24/08: Drill is completed. R&R, Haul, and ACM pit upgrade to be completed next week 31/08: Awaiting for the revised LAAN to be submitted 06/09: ACM pit removal planned for next week. This will then decide whether additional new build is required 14/09: civil and cable hauling completed. Aim for completion next week 21/09: PC Submitted 18/09 | 2018-09-18 |  |  |  |  | 2018-09-18 | Sep-18
AYCA-547JTQ | 1D Rawson St, Dubbo | MDU Externals | FTTP - Type 2 | 2DBB-04 | Andrew Mahasay | 2018-08-01 | Aug-18 | Marshell | Completed | [5 empty] | 2018-06-12 |  |  | 2018-07-26 | 2018-07-27 | 2018-07-27 |  |  |  |  | 2018-07-27 | Jul-18 |  | 0 | 2018-07-30 |  |  |  |  | 2018-07-30 | Jul-18
AYCA-5AZ97T | 1 Wark Parade (second stage), Windradyne | MDU Externals | FTTP - Type 3 (MT-LFN) | 2BTH-02 | Ertan Cicek | 2018-08-30 | Aug-18 | Marshell | Completed | [5 empty] | 2018-07-04 |  |  | 2018-07-23 | 2018-07-23 | 2018-07-27 |  |  |  |  | 2018-07-26 | Jul-18 |  | 06/07 - Forecast start date 23/07 13/07 - No change 20/07 - No change 27/07 - construction completed on the 26h of July | 2018-07-31 |  |  |  |  | 2018-07-31 | Jul-18
AYCA-4VRIOS | 37 High Street (Holy Family Primary School), Parkes | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2PKS-20 | Mark Leal | 2018-08-31 | Aug-18 | Marshell | Completed | [5 empty] | 2018-07-25 |  |  | 2018-08-20 | 2018-08-20 | 2018-08-24 |  |  |  |  | 2018-08-24 | Aug-18 |  | 06/07 - Quote submitted 05/07 20/07 - Forecast start 13/08 27/07 - no change 03/08 - awaiting for 500m double ended tehter to schedule. Advised by Mark that material will be available to NBN warehouse on the 6th of August 10/08 - no change 17/08 - planned to start construction on 20/08 24/08 - construction completed | 2018-08-27 |  |  |  |  | 2018-08-27 | Aug-18
AYCA-59JUMX | 83 Trail Street, Wagga Wagga | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2WAG-02 | Mark Leal | 2018-09-06 | Sep-18 | Marshell | Completed | [5 empty] | 2018-06-25 |  |  | 2018-08-13 | 2018-08-13 | 2018-08-24 |  |  |  |  | 2018-08-24 | Aug-18 |  | 06/07 - Quote submitted on 31/05 20/07 - Forecast start 13/08 27/07 - no change 03/08 - no change 10/08 - no change 17/08 - field completion today | 2018-08-24 |  |  |  |  | 2018-08-24 | Aug-18
AYCA-3V2064 | 29 Gibson Street, Boorooma | MDU Externals | FTTP - Type 2 | 2WAG-01 | Sogand Mohtat | 2018-09-07 | Sep-18 | Marshell | Completed | [5 empty] | 2018-05-29 |  |  | 2018-07-23 | 2018-07-30 | 2018-07-27 |  |  |  |  | 2018-08-07 | Aug-18 |  | 06/07 - Forecast start date 23/07 13/07 - No change 20/07 - No change 27/07 - construction completed on the 27th of July 03/08 - splicing and testing remain to be completed 10/08 - PC submitted 08/08/2018 | 2018-08-08 |  |  |  |  | 2018-08-08 | Aug-18
AYCA-5A2PE8 | 35 Pademelon St, Throsby | MDU Externals | FTTP - Type 2 | 9CRC-06 | Ertan Cicek | 2018-09-10 | Sep-18 | Marshell | Completed | [10 empty] | 2018-09-21 |  |  |  |  | 2018-09-17 | Sep-18 |  | 21/09 - PC submitted 18/09 | 2018-09-18 |  |  |  |  | 2018-09-18 | Sep-18
AYCA-5FHVE5 | 71 Bletchington Street - EXT, Orange | MDU Externals | FTTP - Type 3 (MT-LFN) | 2ORG-06 | Ertan Cicek | 2018-09-14 | Sep-18 | Marshell | Completed | [5 empty] | 2018-08-10 |  |  | 2018-09-10 | 2018-09-12 | 2018-09-14 |  |  |  |  | 2018-09-14 | Sep-18 |  | 31/08: planned to start WS 10/09 06/09: awaiting for LAAN. Planned to prove the external run WS 10/09. complete the installation, both external and internal at the same time. ETA on the internal MWI is unknown 14/09 - Field completed today. 21/09 - PC submitted 17/09 | 2018-09-17 |  |  |  |  | 2018-09-17 | Sep-18
AYCA-5FHVE5 | 71 Bletchington Street - INT, Orange | MDU Internals | FTTP - Type 3 (MT-LFN) | 2ORG-06 | Richard Huffadine | 2018-09-14 | Sep-18 | Marshell | Completed | [5 empty] | N/A |  |  | 2018-09-12 | 2018-09-12 | 2018-09-14 |  |  |  |  | 2018-09-14 | Sep-18 |  | 31/08: planned to start WS 10/09 06/09: awaiting for LAAN. Planned to prove the external run WS 10/09. complete the installation, both external and internal at the same time. ETA on the internal MWI is unknown 14/09 - Field completed today. 21/09 - PC submitted 17/09 | 2018-09-17 |  |  |  |  | 2018-09-17 | Sep-18
AYCA-4YZZ1I | 149 The Boulevarde, Oak Flats | MDU Externals | FTTN | 2ABN-03 | Mark Leal | 2018-09-17 | Sep-18 | Marshell | Completed | [5 empty] | Heritage Waived |  |  | 2019-01-14 | 2019-01-12 | 2019-01-18 |  |  |  |  | 2019-01-31 | Jan-19 |  | 06/07 - Waiting for Heritage Exemption 13/07 - No change 20/07 - No change 27/07 - no change 03/08 - no change 10/08 - no change 17/08 - No change 24/08 - No change 31/08: No change 06/09 - no change 14/09 - no change 21/09 - no change 28/09 - no change. Still awaiting for heritage exemption 12/10 - no change 19/10 - no change 26/10 - no change 01/11 - no change 09/11 - no change 16/11 - no change 23/11 - no change 30/11 - no change. No further update will be given until heritage exemption is approved 07/12 - heritage exemption was given this week 14/12 - scheduled in for Jan 2019 21/12 - no change 11/01 - civil is to commence early next week. planned for field completion 18/01/2019 18/01 - no change 23/01 - PCDs needs to be replaced. Awaiting for stock to come through. 1 lead-in (unit 4) cannot be completed due to a what to be a seperated riser pipe with the UG pipe. Suspect the developer joined the conduit using coreflex in UG rather than a P20 bends . | 2019-01-23 |  |  |  |  | 2019-02-01 | Feb-19
AYCA-58DKIW | 43 Jondaryan Avenue, Griffith | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2GFT-20 | Mark Leal | 2018-09-21 | Sep-18 | Marshell | Completed | [5 empty] | 2018-10-08 |  |  | 2018-08-27 | 2018-08-20 | 2018-11-02 |  |  |  |  | 2018-11-01 | Nov-18 |  | 06/07 - Quote submitted 03/07 20/07 - Forecast start 13/08 27/07 - no change 03/08 - awaiting for 500m double ended tehter to schedule. Advised by Mark that material will be available to NBN warehouse on the 6th of August 10/08 - no change 17/08 - planned to start construction 27/08 24/08 - quote submitted to nbn for the new lead-in on the 22nd of August 31/08: No change. awaiting for approval for the lead-in quote 06/09: no change 14/09 - Lead-in approved. MA to provide forecast start date next week 21/09 - drill booked in 22/10 28/09 - no change 12/10 - Aiming to hold the proposed start date. council work permit application submitted 11/10. 19/10 - council approval obtained on the 15th of October. Start next week 26/10 - Civil is completed. internal haul to commence on Monday 29/10 01/11 - our FSD cable was kinked, highly suspected due to Telstra new fibre. Rehaul completed today, aiming for field completion this week | 2018-11-07 |  |  |  |  | 2018-11-06 | Nov-18
AYCA-56GE93 | 10 Dandaloo St, Narromine | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2NMN-20 | Mark Leal | 2018-09-24 | Sep-18 | Marshell | Completed | [5 empty] | 2018-09-03 |  |  | 2018-09-10 | 2018-09-10 | [5 empty] | 2018-11-09 | Nov-18 |  | 06/09: Planned to start WS 10/09 14/09 - haul and splice completed. PON Patching delay 21/09 - no change 28/09 - no change. Still awaiting for confirmation of the PON Patching readiness 12/10 - no change 19/10 - no change. Still awaiting confirmation of the PON Patching 26/10 - no change 01/11 - Confirmed by Vipin OLT is installed. scheduled in for next week 09/11 - job is completed this week. PC Pack next week | 2018-11-12 |  |  |  |  | 2018-11-12 | Nov-18
AYCA-50T2L6 | 76 Capper St, Tumut | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2TUM-20 | Mark Leal | 2018-09-24 | Sep-18 | Marshell | Completed | [5 empty] | Waive - As long as no civil works |  |  | 2018-10-08 |  | 2018-10-12 |  |  |  |  | 2018-10-12 | Oct-18 |  | 26/08 - Quote sent 06/09 - awaiting for LAAN 14/09 - pon patching delay 21/09 - no change 28/09 - proposed to start on 08/10, assuming PON Patching is ready by today 12/10 - field work completed. PC on 17th of October 19/10 - PC submitted on Monday, 15/10 | 2018-10-17 |  |  |  |  | 2018-10-16 | Oct-18
AYCA-54E9AY | 107-113 Main St - Woolworths, Merimbula | MDU Externals | FTTP - Type 3 (MT-LFN) | 2MER-21 | Ertan Cicek | 2018-09-26 | Sep-18 | Marshell | Completed | [5 empty] | 2018-10-26 |  |  | 2018-10-18 |  | 2018-10-19 |  |  |  |  | 2018-10-19 | Oct-18 |  | 12/10 - Civil lead-in link up is completed. DJL (A End) is installed. FJL location will need to be moved. 19/10 - Job is completed. PC Pack next week | 2018-10-24 |  |  |  |  | 2018-10-23 | Oct-18
AYCA-5866DJ | 2 Cecile Street, Parkes | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2PKS-21 | Mark Leal | 2018-09-27 | Sep-18 | Marshell | Completed | [5 empty] | 2018-08-01 |  |  | 2018-08-20 | 2018-08-22 | 2018-08-24 |  |  |  |  | 2018-08-24 | Aug-18 |  | 06/07 - Quote submitted 06/07, awarded. 13/07 - Forecast start date 13/08 20/07 - No change 27/07 - no change 03/08 - No change 10/08 - forecast start with 37 High St, Parkes 17/08 - planned to start construction on 20/08 24/08 - construction completed | 2018-08-27 |  |  |  |  | 2018-08-27 | Aug-18
AYCA-5BRJ2L | 93-97 Broughton St, Campbelltown | MDU Externals | FTTP - Type 2 | 2CBT-01 | Mark Leal | 2018-10-05 | Oct-18 | Marshell | nbn delay | [5 empty] | 2018-10-30 | [12 empty] | "28/08 - Materials ordered, CLAAN requested, contact details requested, PON Patching SOW requested 29/08 - Received Contact, PON Patching details 31/08 - Waiting on LAANs 05/09- Still waiting on LAANs, site visit scheduled 06/09/2018 07/09 - Scoped, site already completed, require to send through photos/details to Ertan, require potential redesign due to lead-in not going to comms room 21/09 - Advised NBN redesign of external/internal 12/10- New design received, waiting for waiver from council to commence work before the 30th 09/11- Waiting on NBN to contact Strata to get access to occupied apartments " 22/02 - awaiting from Mark regarding the smaller PCD. items are not in our istore catalogue (11015307) 08/03 - no change 05/04 - no change. No further update will be given until advised by nbn
AYCA-5A18P2 | 249 Shellharbour Road, Warrawong | MDU Externals | FTTP - Type 3 (MT-LFN) | 2PKE-04 | Ertan Cicek | 2018-10-13 | Oct-18 | Marshell | Completed | [5 empty] | 2018-08-15 |  |  | 2018-09-17 | 2018-09-04 | 2018-10-12 |  |  |  |  | 2018-10-11 | Oct-18 |  | 24/08 - site visit and internal planning next week, 27/08 31/08 - construction planned to start WS 10/09 06/09 - rod and rope completed. Hauling pending site access, ETA on 17/09 - on track 14/09 - on track to complete next week 21/09 - developer delay. site induction 28/09 28/09 - still as per plan 12/10 - awaiting confirmation from Ertan regarding extra services 15/10 - confirmed by Ertan the extra services will not impact our external work. PC submitted 15/10 | 2018-10-17 |  |  |  |  | 2018-10-15 | Oct-18
AYCA-5JRURV | 37 Belconnen Way, Weetangera | MDU Externals | FTTP - Type 3 (MT-LFN) | 9BLC-20 | Ertan Cicek | 2018-10-15 | Oct-18 | Marshell | Completed | [5 empty] | 2018-10-15 |  |  | 2018-10-15 |  | 2018-10-19 |  |  |  |  | 2018-10-17 | Oct-18 |  | 12/10 - planned to start next week 19/10 - job is completed. PC Pack next week | 2018-10-24 |  |  |  |  | 2018-10-22 | Oct-18
AYCA-5SMBZ7 | 54 Arndell Street, Macquarie | NSB | FTTN | 9BLC-20 | Mark Leal | 2018-10-23 | Oct-18 | Marshell | Completed | [5 empty] | 2019-02-14 |  |  |  | 2019-02-25 | [5 empty] | 2019-03-08 | Mar-19 |  | 07/12 - survey was completed this week. Design to be finalised by mid next week 14/12 - awaiting for nbn response on whether we need to submit the design. Awaiting for CSPO 21/12 - no change 11/01 - design is commencing soon. Still awaiting for CSPO 18/01 - CSPO received. Design to be submitted 31/01 23/01 - no change 22/02 - design approved by nbn on 12/02. Construction has commenced 01/03 - civil and external haul is completed 08/03 - Field completed today. PC next week | 2019-03-13 |  |  |  |  | 2019-03-11 | Mar-19
AYCA-5I9AIZ | 11B Banna Ave, Griffith | Business Segment | FTTP - Type 3 (MT-LFN) | 2GFT-21 | David Yeomans | 2018-10-24 | Oct-18 | Marshell | Completed | [5 empty] | Waive |  | 2018-08-30 | 2018-10-22 | 2018-10-22 | 2018-10-26 |  |  |  |  | 2018-10-26 | Oct-18 |  | 21/09 - awaiting for Telstra reservation duct 28/09 - no change. 12/10 - Plan to start 22/10. Telstra reservation duct approved 11/10 19/10 - council approval obtained on the 15th of October. Start next week 26/10 - job is due to be completed today | 2018-10-29 |  |  |  |  | 2018-10-29 | Oct-18
AYCA-4WVWPI | 31 Molong Road, Orange | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2ORG-04 | Mark Leal | 2018-10-31 | Oct-18 | Marshell | Completed | [5 empty] | 2018-08-27 |  |  |  |  | 2018-11-16 |  |  |  |  | 2018-11-16 | Nov-18 |  | 06/09: Planned to start WS 10/09 14/09 - MA to advise Mark Leal regarding lead-in conduit. 21/09 - awaiting for nbn approval for new lead-in 28/09 - Lead-in quote submitted to Mark Leal on 27/09 12/10 - no change 19/10 - no change 26/10 - no change 01/11 - awaiting for confirmaiton of lead-in 09/11 - lead-in is completed by customer, scheduled in this month 16/11 - job is completed, PC Pack next week | 2018-11-21 |  |  |  |  | 2018-11-20 | Nov-18
AYCA-5N4YCV | 5 Watt Drive, Robin Hill | MDU Externals | FTTP - Type 3 (MT-LFN) | 2BTH-02 | Ertan Cicek | 2018-10-31 | Oct-18 | Marshell | Completed | [5 empty] | 2018-10-22 |  |  | 2018-11-05 |  | 2018-11-16 |  |  |  |  | 2018-11-16 | Nov-18 |  | 12/10 - job awarded 11/10. material ordered 19/10 - LAAN received. Crew tentatively booked for the 05/11/2018 25/10 - no change 01/11 - no change 09/11 - job is completed. PC Pack next week 16/11 - job was delayed last week due to insufficient time to complete the test. Job is completed this week. PC Pack next week | 2018-11-21 |  |  |  |  | 2018-11-20 | Nov-18
AYCA-5N4YCV | 5 Watt Drive, Robin Hill | MDU Internals | FTTP - Type 3 (MT-LFN) | 2BTH-02 | Sundeep Chokshi | 2018-10-31 | Oct-18 | Marshell | Completed | [8 empty] | 2018-11-05 |  | 2018-11-16 |  |  |  |  | 2018-11-16 | Nov-18 |  | 26/10 - Aim to completed this at the same week as the external 01/11 - no change 09/11 - job is completed, PC Pack next week 16/11 - job was delayed last week due to insufficient time to complete the test. Job is completed this week. PC Pack next week | 2018-11-21 |  |  |  |  | 2018-11-20 | Nov-18
AYCA-4E9HF0 | Beaumont - 11-15 Nero St, Mittagong | MDU Externals | FTTP - Type 3 (MT-LFN) | 2MTT-03 | Mark Leal | 2018-11-01 | Nov-18 | Marshell | Completed | [5 empty] | Waive |  |  | 2018-10-11 |  | 2018-10-12 |  |  |  |  | 2018-10-11 | Oct-18 |  | 06/08- Site visit required, materials order request sent 10/08 - no change 17/08 - No change 24/08 - no change 31/08 - consruction will start WS 10/09 06/09 - delayed until WS 17/09 due to parent site delay 14/09 - no change 21/09 - delayed parent site for another week 28/09 - parent site delayed, until 05/10 12/10 - job was completed by others. awaiting advise from nbn 15/10 - Vipin advises us to submit PC. PC submitted on Monday | 2018-10-17 |  |  |  |  | 2018-10-15 | Oct-18
AYCA-4LHC6F | 30 Ritz Place, Dubbo | MDU Externals | FTTP - Type 2 | 2DBB-01 | Mark Leal | 2018-11-01 | Nov-18 | Marshell | Completed | [5 empty] | 2018-07-12 |  |  | 2018-09-10 | 2018-09-10 | 2018-09-14 |  |  |  |  | 2018-09-10 | Sep-18 |  | 06/07 - Forecast start date 26/07 13/07 - No change 20/07 - No change 27/07 - no change 03/08 - No change 10/08 - delay start date until TBA 17/08 - no change 24/08 - no change 31/08 - construction will start WS 03/09 06/09 - construction delayed until WS 10/09 14/09 - field completed today 21/09 - PC submitted 17/09 | 2018-09-17 |  |  |  |  | 2018-09-17 | Sep-18
AYCA-4K6VYT | 30 Twynam St, Jindabyne | MDU Externals | FTTP - Type 3 (MT-LFN) | 2JNB-20 | Mark Leal | 2018-11-03 | Nov-18 | Marshell | Completed | [5 empty] | 2018-08-08 |  |  | 2018-09-07 |  | 2018-09-11 |  |  |  |  | 2018-09-07 | Sep-18 |  | 27/07 - Ordered materials, require site visit 03/08 - site visit done. No construction is required 10/08 - No change 17/08 - no change 24/08 - no change 31/08 - no change 06/09 - no change 14/09 - PC submitted 07/09 | 2018-09-07 |  |  |  |  | 2018-09-07 | Sep-18
AYCA-57Y170 | 17 Hitchcocks Lane, Berry | MDU Externals | FTTP - Type 2 | 2BRY-01 | Ertan Cicek | 2018-11-07 | Nov-18 | Marshell | Completed | [5 empty] | 2018-08-10 |  |  | 2018-09-17 | 2018-09-03 | 2018-10-05 |  |  |  |  | 2018-10-04 | Oct-18 |  | 22/07 - Material order request sent, site visit required 27/07 - no change 03/08 - No change 10/08 - no change 17/08 - plan to start construction 27/08 24/08 - no change 31/08 - construction will start WS 03/09 06/09 - external haul completed. Awaiting for instruction on internal distance 14/09 - Made contact with dev. Aim to complete WE 28/09/2018 21/09 - no change 24/09 - CTL enclosure (aluminium box) has not been installed yet. Due to be installed by the electrician this week. Planned to complete the job next week, 05/10/2018 12/10 - PC submitted this week | 2018-10-08 |  |  |  |  | 2018-10-08 | Oct-18
AYCA-5PIVSY | 11 Lombard Drive , Robin Hill | MDU Externals | FTTP - Type 3 (MT-LFN) | 2BTH-02 | Ertan Cicek | 2018-11-13 | Nov-18 | Marshell | Completed | [8 empty] | 2018-11-05 |  | 2018-11-09 |  |  |  |  | 2018-11-09 | Nov-18 |  | 01/11 - received the job 31/10 09/11 - planned to be completed this week. PC Pack planned for next week | 2018-11-14 |  |  |  |  | 2018-11-13 | Nov-18
AYCA-5PIVSY | 11 Lombard Drive , Robin Hill | MDU Internals | FTTP - Type 3 (MT-LFN) | 2BTH-02 | Sundeep Chokshi | 2018-11-13 | Nov-18 | Marshell | Completed | [8 empty] | 2018-11-05 |  | 2018-11-09 |  |  |  |  | 2018-11-09 | Nov-18 |  | 01/11 - received the job 31/10 09/11 - planned to be completed this week. PC Pack planned for next week | 2018-11-14 |  |  |  |  | 2018-11-13 | Nov-18
AYCA-5SZ0LP | 17 Thornhill St, Young | MDU Externals | FTTN | 2YON-01 | Mark Leal | 2018-11-15 | Nov-18 | Marshell | Completed | [5 empty] | 2019-05-09 |  |  | 2019-05-13 |  | 2019-05-17 |  |  |  |  | 2019-05-17 | May-19 |  | 02/05 - scope is completed. CLAAN starts 09/05. Plan to start on WS 13/05 10/05 - to start next week 18/05 - field completed this week | 2019-05-24 |  |  |  |  | 2019-05-24 | May-19
AYCA-52S52D | 18 Hobson Cl, Eglinton | MDU Externals | FTTP - Type 2 | 2BTH-01 | Mark Leal | 2018-11-19 | Nov-18 | Marshell | Completed | [5 empty] | 2018-06-25 |  |  |  | 2018-06-05 | [5 empty] | 2018-07-26 | Jul-18 |  | 06/07 - Forecast rehaul 24/07 13/07 - No change 20/07 - No change 27/07 - construction completed on the 26th of July | 2018-07-30 |  |  |  |  | 2018-07-30 | Jul-18
AYCA-50OJVS | 419 Kelly St, Deniliquin | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2DNQ-22 | Mark Leal | 2018-11-21 | Nov-18 | Marshell | Completed | [5 empty] | 2018-09-10 |  |  | 2018-10-15 | 2018-10-15 | 2018-12-07 |  |  |  |  | 2018-12-07 | Dec-18 |  | 21/09 - material ordered 28/09 - aim to start 15/10 12/10 - no change 19/10 - direct buried section was identified. Need an underbore team, tentatively booked in 12/11. ACM pit also required to be upgraded. 22/10 - awaiting for the updated LAAN 24/10 - council advised us that work cannot commenced until 30/11 01/11 - no change 09/11 - no change 16/11 - no change 23/11 - possible start next week 30/11 - civil is being done this week. aiming for field completion by the 7th of December 07/12 - field completed. PC submission mid next week | 2018-12-12 |  |  |  |  | 2018-12-10 | Dec-18
AYCA-5JF564 | 9 Braybrooke Street, Bruce | MDU Externals | FTTP - Type 2 | 9BLC-21 | Ertan Cicek | 2018-11-23 | Nov-18 | Marshell | Completed | [5 empty] | 2018-11-19 |  |  | 2018-11-19 | 2018-11-19 | 2018-12-12 |  |  |  |  | 2018-12-07 | Dec-18 |  | 09/11 - site visit next week 16/11 - new footpath has been poured. Developer asked us to delay civil until their footpath work is certified by council, which probably by end of this week 23/11 - civil works completed. External haul completed. Awaiting for internal design 30/11 - no change 07/12 - internal design sent to us 05/12 | 2018-12-17 |  |  |  |  | 2018-12-10 | Dec-18
AYCA-4P6YWU | 11 Kite Place - INT, Blackbutt | MDU Internals | FTTP - Type 2 | 2SHH-05 | Nabeel Jaimon | 2018-11-30 | Nov-18 | Marshell | Completed | [10 empty] | 2018-11-13 |  |  |  |  | 2018-11-15 | Nov-18 |  | 15/08 - Materials ordered, requires site visit, LAAN received 17/08 - no change 24/08 - no change 31/08 - civil and external haul is completed. Awaiting developer to be ready, in 4 weeks 06/09 - no change 14/09 - no change 21/09 - no change 28/09 - no change 12/10 - no change 19/10 - no change 25/10 - aiming for completion next week 01/11 - pushed out to WS 12/11/2018 09/11 - no change 16/11 - PC submitted today | 2018-11-16 |  |  |  |  | 2018-11-16 | Nov-18
AYCA-4P6YWU | 11 Kite Place - EXT, Blackbutt | MDU Externals | FTTP - Type 2 | 2SHH-05 | Ertan Cicek | 2018-11-30 | Nov-18 | Marshell | Completed | [5 empty] | 2018-08-15 |  |  | 2018-08-29 | 2018-08-29 | 2018-11-13 |  |  |  |  | 2018-11-15 | Nov-18 |  | 15/08 - Materials ordered, requires site visit, LAAN received 17/08 - no change 24/08 - no change 31/08 - civil and external haul is completed. Awaiting developer to be ready, in 4 weeks 06/09 - no change 14/09 - no change 21/09 - no change 28/09 - no change 12/10 - no change 19/10 - no change 25/10 - aiming for completion next week 01/11 - pushed out to WS 12/11/2018 09/11 - no change 16/11 - PC submitted today | 2018-11-20 |  |  |  |  | 2018-11-16 | Nov-18
AYCA-61L3QL | Casuarina & Sailfish Way, Seaside Drive, Nautilus Way , Kingscliff | NSB | 0 | 2KCL | Mark Leal | 2018-12-01 | Dec-18 | Marshell | Pre-Construction | [18 empty] | 02/05 - survey is in progress 18/05 - on hold for FDH relocation 24/05 - quote is approved. FDH location document to be created soon
AYCA-4QEPUO | 23 Rossi St, Yass | MDU Externals | FTTN | 2YAS-01 | Mark Leal | 2018-12-03 | Dec-18 | Marshell | Completed | [5 empty] | 2018-09-24 |  |  | 2018-09-24 |  | 2018-09-26 |  |  |  |  | 2018-09-26 | Sep-18 |  | 10/08 - Quote provided to NBN 14/08 - Project issued to DT 24/08 - planned on start construction 10/09 31/08 - awaiting LAAN response 06/09 - no change 14/09 - LAAN received. To commenced WS 24/09/2018 21/09 - no change 28/09 - PC submitted 27/09 | 2018-09-27 |  |  |  |  | 2018-09-27 | Sep-18
AYCA-21R8AP | 12-14 New Dapto Road, Wollongong | MDU Externals | FTTP - Type 2 | 2WLG-07 | Ertan Cicek | 2018-12-03 | Dec-18 | Marshell | Completed | [5 empty] | 2018-07-23 |  |  | 2018-10-17 |  | 2018-10-29 |  |  |  |  | 2018-10-26 | Oct-18 |  | 06/07 - Ordered materials, require site visit 13/07 - Forecast start date 03/09 20/07 - No change 27/07 - no change 03/08 - no change 10/08 - no change 17/08 - no change 24/08 - no change 31/08 - developer will be ready on the 17th of September 06/09 - no change 14/09 - no change 21/09 - no change 28/09 - no change 12/10 - planned to start next week 19/10 - civil is completed 25/10 - aiming for completion next week | 2018-10-31 |  |  |  |  | 2018-10-30 | Oct-18
AYCA-5SK61D | 39 Cumberland Avenue, South Nowra | SDU - External | FTTP - Type 2 | 2NWR-03 | Ertan Cicek | 2018-12-05 | Dec-18 | Marshell | Completed | [9 empty] | 2019-01-14 | 2019-01-18 |  |  |  |  | 2019-01-15 | Jan-19 |  | 11/01 - CSPO received this week. Site visit next week 18/01 - work order is completed. PC due next week | 2019-01-23 |  |  |  |  | 2019-01-21 | Jan-19
AYCA-5SK61D | 39 Cumberland Avenue, South Nowra | SDU - Internal | FTTP - Type 2 | 2NWR-03 | Sogand Mohtat | 2018-12-05 | Dec-18 | Marshell | Completed | [9 empty] | 2019-01-14 | 2019-01-18 |  |  |  |  | 2019-01-15 | Jan-19 |  | 11/01 - CSPO received this week. Site visit next week 18/01 - work order is completed. PC due next week | 2019-01-23 |  |  |  |  | 2019-01-21 | Jan-19
AYCA-5MT9Y3 | Bon Scott Crescent, Moncrieff | MDU Externals | FTTP - Type 2 | 9BON-03 | Ertan Cicek | 2018-12-10 | Dec-18 | Marshell | Completed | [5 empty] | 2018-10-29 |  |  | 2018-11-26 |  | 2018-12-07 |  |  |  |  | 2018-12-07 | Dec-18 |  | 19/10 - job awarded 17/10. Material ordered. LAAN received. Awaiting for LAAN start date 25/10 - LAAN start on the 29th of October 01/11 - Hauling has commenced 09/11 - no change 16/11 - splicing next week. Hauling completed 23/11 - awaiting for confirmation on the internal build 30/11 - internal build confirmed by the end of this week. aiming to finish external construction by the 7th of December 07/12 - field completed this week. PC submission mid next week | 2018-12-12 |  |  |  |  | 2018-12-08 | Dec-18
AYCA-4OJUJI | 20 Cathcart St , Goulburn | MDU Externals | FTTN | 2GLB-04 | Mark Leal | 2018-12-10 | Dec-18 | Marshell | Completed | [5 empty] | 2018-05-28 |  |  |  | 2018-07-12 | 2018-09-24 |  |  |  |  | 2018-09-24 | Sep-18 |  | 13/07 - Hauling commenced 12/07 27/07 - no change 03/08 - no change 10/08 - TBA on civil schedule 17/08 - no change 24/08 - no change 31/08 - civil scheduled in on WS 10/09 06/09 - no change 14/09 - field completed today 21/09 - aim for PC 25/09/2018 28/09 - PC submitted on 24/09 | 2018-09-24 |  |  |  |  | 2018-09-24 | Sep-18
AYCA-4LYVIU | 136 Peel St, Bathurst | MDU Externals | FTTN | 2BTH-01 | Mark Leal | 2018-12-17 | Dec-18 | Marshell | Completed | [8 empty] | 2018-11-05 | [6 empty] | 2018-11-15 | Nov-18 |  | 23/07 - No response from developer since 2017 03/08 - No change 24/08: no change 31/08: N0 change 06/09 - ETA start on mid october 14/09 - no change 21/09 - no change 28/09 - no change 12/10 - construction to start on the week 5th of November 19/10 - no change 26/10 - no change 01/11 - no change 09/11 - planned to be completed this week 16/11 - PC submitted today | 2018-11-16 |  |  |  |  | 2018-11-16 | Nov-18
AYCA-53Y6BS | The Park - 1, Moncrieff | MDU Externals | FTTP - Type 2 | 9BON-03 | Ertan Cicek | 2018-12-20 | Dec-18 | Marshell | Completed | [5 empty] | 2018-11-19 |  |  | 2018-12-03 |  | 2018-12-07 |  |  |  |  | 2018-12-07 | Dec-18 |  | 23/11 - civil works completed. External haul to commence next week 30/11 - aiming to field completion by the 7th of December 07/12 - field completed this week. PC submission by mid next week | 2018-12-12 |  |  |  |  | 2018-12-08 | Dec-18
AYCA-5JRURV | 37 Belconnen Way, Weetangera | MDU Internals | FTTP - Type 3 (MT-LFN) | 9BLC-20 | Nabeel Jaimon | 2018-12-21 | Dec-18 | Marshell | Completed | [8 empty] | 2018-12-03 | [6 empty] | 2018-12-05 | Dec-18 |  | 23/10 - job awarded 22/10. Material ordered 01/11 - awaiting developer to install power/electricity to site 09/11 - no change 16/11 - advised by the developer that the power will be installed end of November 23/11 - no change 30/11 - no change 07/12 - field completed this week. PC submission by mid next week | 2018-12-12 |  |  |  |  | 2018-12-07 | Dec-18
AYCA-5L1XWG | 365 Hume Highway, Liverpool | MDU Externals | FTTP - Type 3 (MT-LFN) | 2LIV-67 | Ertan Cicek | 2018-12-21 | Dec-18 | Marshell | In construction | [5 empty] | 2019-04-15 | 2019-03-27 | 2019-03-27 |  |  | 2019-06-07 |  |  |  |  | 2019-05-31 | May-19 |  | 27/02 - CSPO and intial scope received on 25/02. NDD to be submitted to nbn 28/02 01/03 - NDD submitted to nbn on 28/02 05/03 - nbn review of the NDD today -12/03 NDD feedback received -14/03 Revised NDD delivered 19/03 - NDD Approved 22/03 - DDD in progress 27/03 - DDD submitted. 05/04 - Queries sent to nbn regarding lead-in and who wil contact AHG head office 12/04 - tried to contact the contractor who build the communication line. no response. will try again next week 18/04 - Obtained the internal pathway from the contractor that build the AHG site. Will send someone out there early next week to rescope the run 26/04 - ROL applied on 24/04. Require detailed investigation to find the lead-in conduit 02/05 - awaiting for ROL 10/05 - ROL obtained. scheduled in next week to locate lead-in and possible link up 18/05 - civil and haul to be completed WE 24/05 24/05 - civil is completed. haul is to be completed next week due to access 31/05 - field completed this week. PC next week | 2019-06-07
AYCA-568KCW | 61 Belinda St (Mayflower), Gerrigong | MDU Externals | FTTP - Type 2 | 2GER-01 | Ertan Cicek | 2019-01-07 | Jan-19 | Marshell | Completed | [5 empty] | 2018-11-12 |  |  | 2018-11-26 | 2018-11-24 | 2018-11-30 |  |  |  |  | 2018-11-27 | Nov-18 |  | 01/11 - LAAN requested 09/11 - awaiting for LAAN 16/11 - site visit next week 23/11 - planned to be completed next 2 weeks 30/11 - field completed this week | 2018-12-05 |  |  |  |  | 2018-11-28 | Nov-18
AYCA-4DQVDO | 2 Branch Ave, Figtree | Estate | FTTN | 2PKE-01 | Mark Leal | 2019-01-09 | Jan-19 | Marshell | Completed | [5 empty] | 2019-04-12 | [12 empty] | 28/03 - clarification request sent to Mary 05/04 - Start when the CLAAN active 12/04 - job to be completed next week 18/04 - job completed | [5 empty] | 2019-04-15 | Apr-19
AYCA-4UFUW5 | 180 Clive Steele Ave, Monash | MDU Externals | FTTP - Type 3 (MT-LFN) | 9MNS-25 | Ertan Cicek | 2019-01-21 | Jan-19 | Marshell | Completed | [5 empty] | 2018-11-19 |  |  |  |  | 2019-06-30 |  |  |  |  | 2019-02-28 | Feb-19 |  | 09/11 - site visit next week 16/11 - ADA/SAM has not been constructed 23/11 - awaiting for ADA/SAM to be built, possibly 2019 30/11 - no change. No further update will be given until Feb 2019 21/12 - site is due for completion end of Feb 2019. 18/01 - civil to commence next week 23/01 - civil has commecned this week, aim to be completed by Friday. Non-standard install required and in consultation with Zlate 22/02 - external haul completed. Splicing will follow once internal is completed. Internal crew was working as of today 01/03 - job is completed. PC Pack next week | 2019-03-06 |  |  |  |  | 2019-03-05 | Mar-19
AYCA-48QOI8 | 155F Lodges Road, Elderslie | MDU Externals | FTTP - Type 2 | 2NRN-05 | Mark Leal | 2019-01-28 | Jan-19 | Marshell | Completed | [5 empty] | 2019-04-16 |  |  |  |  | 2019-04-26 |  |  |  |  | 2019-04-26 | Apr-19 |  | 20/08 - Quote submitted 22/08 - LAAN Received 07/09 - Site visit 04/07 identified that no internal pits ready. Require internal network to at least pull through copper 2 pr and coil up in lead-in pits 21/09 - No change 22/02- Waiting for response from Mark Leal regarding scope and which units to service 01/03 - no change 08/03 - link up needs to be completed. schedule in the next 2 weeks 15/03 - link up completed today. Need to address the issue between Pillar P5 and Pillar P6 22/03 - nbn planning team is looking into the issue between Pillar P5 and Pillar P6 29/03 - redesign received from nbn, change technology to fibre. CLAAN to be submitted early next week 05/04 - fibre construction will commence shortly 12/04 - no change 18/04 - hauling is completed. splicing is to commence shortly 26/04 - splicing to commence next week 01/05 - job is completed. PC this week | 2019-05-03 |  |  |  |  | 2019-05-09 | May-19
AYCA-57DG41 | 93 Stanley St - INT, Bathurst | MDU Internals | FTTP - Type 2 | 2BTH-01 | Richard Huffadine | 2019-01-28 | Jan-19 | Marshell | Completed | [8 empty] | 2018-11-05 |  | 2018-11-16 |  |  |  |  | 2018-11-16 | Nov-18 |  | 27/07 - Ordered materials, require site visit 03/08 - no change 10/08 - no change 17/08 - no change 24/08 - no change 31/08 - no change 06/09 - developer has not responded yet. Follow up next week 14/09 - no change 21/09 - no change 28/09 - Made contact with developer this week. aim to mobilise the crew 05/11 12/10 - no change 19/10 - no change 25/10 - no change 01/11 - no change 09/11 - planned to be completed this week. PC Next week 16/11 - PC next week | 2018-11-21 |  |  |  |  | 2018-11-20 | Nov-18
AYCA-57DG41 | 93 Stanley St - EXT, Bathurst | MDU Externals | FTTP - Type 2 | 2BTH-01 | Ertan Cicek | 2019-01-28 | Jan-19 | Marshell | Completed | [5 empty] | 2018-08-08 |  |  | 2018-11-05 |  | 2018-11-16 |  |  |  |  | 2018-11-16 | Nov-18 |  | 27/07 - Ordered materials, require site visit 03/08 - no change 10/08 - no change 17/08 - no change 24/08 - no change 31/08 - no change 06/09 - developer has not responded yet. Follow up next week 14/09 - no change 21/09 - no change 28/09 - Made contact with developer this week. aim to mobilise the crew 05/11 12/10 - no change 19/10 - no change 25/10 - no change 01/11 - no change 09/11 - planned to be completed this week. PC Next week 16/11 - PC next week | 2018-11-21 |  |  |  |  | 2018-11-20 | Nov-18
AYCA-5CXXCR | 30 Golf Links Dr, Batemans Bay | MDU Externals | FTTP - Type 2 | 2BTM-21 | Ertan Cicek | 2019-01-31 | Jan-19 | Marshell | Completed | [5 empty] | 2018-10-02 |  |  | 2018-10-15 | 2018-12-03 | 2018-01-18 |  |  |  |  | 2018-01-16 | Jan-18 |  | 21/09 - awaiting for LAAN and PON Patching 28/09 - no change 12/10 - civil works to commence next week 19/10 - civil works is completed. Awaiting for site to be ready 25/10 - no change 01/11 - no change 09/11 - no change 16/11 - no change 23/11 - no change 30/11 - site will be ready for external build in 2-3 weeks time 07/12 - no change 14/12 - developer is going to connect the lead-in conduit in few weeks time. aim to complete this before end of Jan 21/12 - no change 11/01 - still awaiting for developer to complete lead-in 18/01 - work order is completed. PC is due next week | 2018-01-23 |  |  |  |  | 2019-01-23 | Jan-19
AYCA-53Y8BE | 17 Nicholii Street, Montefiores | MDU Externals | FTTN | 2WEL-01 | Mark Leal | 2019-01-31 | Jan-19 | Marshell | Completed | [5 empty] | 2018-05-21 |  |  | 2018-09-11 | 2018-09-12 | 2018-09-14 |  |  |  |  | 2018-09-14 | Sep-18 |  | 20/07 - Materials ordered, pending start date 27/07 - no change 03/08 - no change 10/08 - no change 17/08 - no change 24/08 - no change 31/08 - no change 06/09 - no change 14/09 - PC submitted today | 2018-09-14 |  |  |  |  | 2018-09-14 | Sep-18
AYCA-5I62CV | 55 Sutherland Cr / 3 Bischoff St, Taylor | MDU Externals | FTTP - Type 2 | 9BON-03 | Ertan Cicek | 2019-01-31 | Jan-19 | Marshell | Completed | [10 empty] | 2019-01-25 |  |  |  |  | 2019-01-25 | Jan-19 |  | 11/01 - CSPO received this week. site was almost ready. Planned to have this completed on the 25/01 18/01 - no change 23/01 - aim for the completion on Friday. PC next week | 2019-01-30 |  |  |  |  | 2019-01-29 | Jan-19
AYCA-5TDBKQ | 44 Hopkins Street, Eden | SDU | FTTN | 2EDN-20 | Ertan Cicek | 2019-02-01 | Feb-19 | Marshell | Completed | [5 empty] | 2019-02-08 |  |  | 2019-02-04 | 2019-02-04 | 2019-02-08 |  |  |  |  | 2019-02-17 | Feb-19 |  | 18/01 - CSPO received this week. Awaiting LAAN 23/01 - LAAN applied by DT | 2019-02-13 |  |  |  |  | 2019-02-18 | Feb-19
AYCA-3R9RDG | 193 & 205 Wheeo Road, Goulburn | MDU Externals | FTTP - Type 3 (MT-LFN) | 2GLB-04 | Mark Leal | 2019-02-08 | Feb-19 | Marshell | Developer Delay | [5 empty] | 2019-03-20 | [12 empty] | 15/03 - schedule to start WS 25/03. Awaiting for CSPO 22/03 - issue with the existing network. Awaiting DT to submit quote to Mark Leal 29/03 - quote suibmitted to Mark Leal and also updated CWP 05/04 - awaiting response from Mark Leal 12/04 - no response 18/04 - no change 26/04 - no change 01/05 - no change 07/05 - no change 18/05 - advised by Mark Leal to go ahead. DT to organise drilling 24/05 - tentative start date 03/06 31/05 - drill is completed. haul and splice next week | 2019-06-07
AYCA-5M7EQR | 40 Basil Street, South Nowra | MDU Externals | FTTP - Type 2 | 2NWR-01 | Ertan Cicek | 2019-02-08 | Feb-19 | Marshell | Completed | [5 empty] | 2018-11-13 |  |  | 2018-12-10 | 2018-12-10 | 2019-01-18 |  |  |  |  | 2019-01-14 | Jan-19 |  | 09/11 job awarded this week 16/11 - site visit is next week 23/11 - CRQ booked in 14/12 30/11 - no change 07/12 - no change 14/12 - aim for field completed on the 14th of December 21/12 - MPT change out is completed last week. Cable was faulty. Awaiting for new cable to arrive 11/01 - planned to have this completed by next week 18/01 - work order is completed. PC due next week | 2018-01-23 |  |  |  |  | 2019-01-21 | Jan-19
AYCA-4W183C | 71 Auburn St, Wollongong | MDU Internals | FTTP - Type 2 | 2WLG-02 | Nabeel Jaimon | 2019-02-28 | Feb-19 | Marshell | Completed | [5 empty] | N/A | [9 empty] | 2019-04-09 | Apr-19 |  | 06/07 - Materials ordered, waiting for site ready 26/07: No change 03/08 - no change 15/08- Sent update request for external 15/08 - EFSCD moved 05/11 22/02- Developer advises ready in next two weeks 01/03 - aim for completion next week 08/03 - PC next week 15/03 - delayed for another week due to faulty cable | 2019-04-09 |  |  |  |  | 2019-04-09 | Apr-19
AYCA-LYHJJ | 10 Cardigan St, Mittagong | MDU Externals | FTTP - Type 2 | 2MTT-02 | Mark Leal | 2019-03-01 | Mar-19 | Marshell | Completed | [5 empty] | 2018-07-12 |  |  | 2018-09-03 |  | 2018-09-17 |  |  |  |  | 2018-09-10 | Sep-18 |  | 06/08- Site visit required, materials order request sent 10/08 - no change 17/08 - No change 24/08 - no change 31/08 - consruction will start WS 10/09 06/09 - delay for 1 week, to WS 17/09 14/09 - no change 17/09 - PC submitted 17/09 | 2018-09-17 |  |  |  |  | 2018-09-17 | Sep-18
AYCA-62WIE0 | 3 Actinotus Avenue, Caringbah South | MDU Externals | FTTP - Type 2 | 2MIR-25 | Ertan Cicek | 2019-03-06 | Mar-19 | Marshell | Pre-Construction | [5 empty] | 2019-06-05 | 2019-05-24 | 2019-05-20 | [10 empty] | 01/05 - Site is already occupied. DDD WIP 10/05 - DDD to be submitted next week 18/05 - DDD in progress 24/05 - DDD submitted 20/05. CLAAN applied 31/05 - to be completed with internal
AYCA-5B4OYT | Macquarie Drive, The Lakes - 9A, Burrill Lake | MDU Externals | FTTP - Type 2 | 2ULL-04 | Mark Leal | 2019-03-15 | Mar-19 | Marshell | Completed | [5 empty] | 2018-10-24 |  |  | 2018-11-23 | 2018-11-23 | 2018-11-30 |  |  |  |  | 2018-11-27 | Nov-18 |  | 12/10 - job awarded 11/10. material ordered. 19/10 - awaiting LAAN start date 25/10 - no change 09/11 - no change 16/11 - no change 23/11 - external haul completed this week 30/11 - splicing and testing completed this week. PC submitted this week | 2018-12-05 |  |  |  |  | 2018-11-30 | Nov-18
AYCA-5XRS1Z | 7-9 Princes Highway, Dapto | MDU Externals | FTTP - Type 2 | 2DAP-02 | Ertan Cicek | 2019-03-20 | Mar-19 | Marshell | Completed | [5 empty] | 2019-04-29 | 2019-04-08 | 2019-04-08 | 2019-05-13 |  | 2019-05-17 |  |  |  |  | 2019-05-17 | May-19 |  | 26/02 - Job accepted through maximo 06/03 - NDD submitted to nbn today 22/03 - still awaiting nbn response 29/03 - no change 05/04 - no change. DDD to be submitted 12/04 09/04 - DDD was submitted 08/04. CLAAN issued today 18/04 - survey is scheduled ealry next week 26/04 - survey is completed. Scheduled in WS 13/05. 02/05 - no change 10/05 - no change 18/05 - PC submitted this week. Issue with Maximo, raised with Solmaz | 2019-05-24 |  |  |  |  | 2019-05-17 | May-19
AYCA-65UPJG | Cnr Orphend & Ironbark Cr, Bellingen | NSB | 0 | 2BLG-20 | Mark Leal | 2019-03-25 | Mar-19 | Marshell | Survey | [18 empty] | 18/04 - survey to be done after Anzac day weekend 14/05 - FIR to be submitted end of this week 24/05 - FIR WIP
AYCA-5L8461 | 14 Holder Street, Turner | MDU Externals | FTTP - Type 3 (MT-LFN) | 9CVI-21 | Ertan Cicek | 2019-04-01 | Apr-19 | Marshell | Completed | [5 empty] | 2018-11-14 | [9 empty] | 2019-03-14 | Mar-19 |  | 09/11 - site visit next week 16/11 - no change 23/11 - site visit delayed until next week 30/11 - site is not ready until couple of weeks 07/12 - awaiting for nbn response to the new proposed construction plan 14/12 - no change 21/12 - no change 11/01 - no change 18/01 - no change 23/01 - no change 25/02 - advised by Ertan to go ahead with the proposed new plan. new CLAAN raised by DT 08/03 - aim for field completion next week | 2019-03-20 |  |  |  |  | 2019-03-15 | Mar-19
AYCA-5JIMDQ | 166 Brisbane Street, Dubbo | MDU Internals | FTTP - Type 2 | 2DBB-02 | Sundeep Chokshi | 2019-04-12 | Apr-19 | Marshell | Completed | [5 empty] | N/A | [9 empty] | 2019-03-22 | Mar-19 |  | 14/12 - CSPO received this week. 21/12 - Site is still few months away 11/01 - no change 18/01 - no change 23/01 - CRQ applied for end of Feb. Site is not ready yet. Developer suggested to folllow up mid Feb 22/02 - folow up next week 25/02 - Spoke to the electrican and he advised to follow up with him another month as the site won't have power ready up until then. 22/03 - field completed this week. PC next week | 2019-03-27 |  |  |  |  | 2019-03-25 | Mar-19
AYCA-53R6D6 | 14 Toorale Tce, Lawson | MDU Externals | FTTP - Type 2 | 9BLC-04 | Ertan Cicek | 2019-04-15 | Apr-19 | Marshell | Completed | [5 empty] | 2018-11-07 |  |  | 2018-12-03 | [6 empty] | 2019-04-17 | Apr-19 |  | 12/10 - awaiting confirmation from nbn regarding rejection material order 19/10 - no change 25/10 - new material order has been placed and rejected. Awaiting for advise from nbn 01/11 - material ordered approved. Scheduled in for this month 09/11 - no change 16/11 - civil works is completed 23/11 - awaiting for site to be ready 30/11 - no change 07/12 - no change 14/12 - no change 21/12 - site is still not ready. pile of dirt still on the way. No ETA yet on the inernal. best to wait for internal to avoid CTL vs MSS connection 11/01 - no change 18/01 - no change 23/01 - awaiting for internal to completed. 22/02 - internal pit and pipe has not been certified. awaiting for confirmation 26/02 - advised by Nabeel that internal pit and pipe is good 01/03 - pits are still not in a good condition. Ertan advised to hold on 08/03 - no change 15/03 - no change 22/03 - no change 29/03 - no change 05/04 - advised by nbn that the pits have been remediated. awating for photos confirmation 12/04 - cable hauled. splice and test next week 18/04 - Field completed this week. PC next week | 2019-04-24 |  |  |  |  | 2019-04-23 | Apr-19
AYCA-5V4B6P | 53 Russell Street, Balgownie | MDU Internals | FTTP - Type 3 (MT-LFN) | 2COR-09 | Andrew Partalis | 2019-04-15 | Apr-19 | Marshell | Completed | [9 empty] | 2019-03-09 | [5 empty] | 2019-03-15 | Mar-19 |  | 01/03 - awaiting for external (by DT) 08/03 - aim for field completion next week 15/03 - next week completion. | 2019-03-20 |  |  |  |  | 2019-03-18 | Mar-19
AYCA-5V4B6P | 53 Russell Street, Balgownie | MDU Externals | FTTP - Type 3 (MT-LFN) | 2COR-09 | Ertan Cicek | 2019-04-15 | Apr-19 | Marshell | Completed | [5 empty] | 2019-04-11 | 2019-03-22 | 2019-03-22 | [7 empty] | 2019-05-10 | May-19 |  | 01/03 - NDD submitted to nbn on 26/02 08/03 - Feedback received from nbn 06/03. resubmit to nbn next week 22/03 - DDD to be submitted today 27/03 - CLAAN applied. Awaiting for nbn response on DDD submisison. DDD submitted today 05/04 - awaiting nbn response on the DDD 18/04 - awaiting for DDD response 26/04 - no change 02/05 - no change 10/05 - no change | 2019-05-17 |  |  |  |  | 2019-05-17 | May-19
AYCA-3GG3CO | 1-13 Dianella St, Caringbah | MDU Externals | FTTP - Type 2 | 2MIR-31 | Ertan Cicek | 2019-04-20 | Apr-19 | Marshell | Completed | [5 empty] | 2018-12-19 |  |  |  | 2019-02-19 | 2019-03-29 |  |  |  |  | 2019-03-29 | Mar-19 |  | 07/12- Unable to contact 22/02 - civil and external haul are completed 19/03 - splicing will be scheduled in next week 29/03 - field completed this week, PC next week 05/04 - PC submitted. RFC and variation awaiting for council quote | 2019-04-03 |  |  |  |  | 2019-04-03 | Apr-19
AYCA-5LTSYB | 12 Shumack Street , Weetangera | MDU Internals | FTTP - Type 3 (MT-LFN) | 9BLC-20 | Nabeel Jaimon | 2019-04-26 | Apr-19 | Marshell | Completed | [5 empty] | N/A | [9 empty] | 2019-03-08 | Mar-19 |  | 22/02 - CSPO received 21/02. Site is still few months out 08/03. field completed this week | 2019-03-13 |  |  |  |  | 2019-03-08 | Mar-19
AYCA-5LTSYB | 12 Shumack Street, Weetangera | MDU Externals | FTTP - Type 3 (MT-LFN) | 9BLC-20 | Ertan Cicek | 2019-04-26 | Apr-19 | Marshell | Completed | [5 empty] | 2019-02-27 | [9 empty] | 2019-03-08 | Mar-19 |  | 11/01 - CSPO received this week. Site visit next week 18/01 - follow up mid Feb 22/02 - LAAN received. Civil to commence next week due to developer timeframe to pour the concrete footpath soon 01/03 - civil is completed 08/03 - field completed this week | 2019-03-13 |  |  |  |  | 2019-03-08 | Mar-19
AYCA-328OYF | 37-41 Chamberlain St, Campbelltown | MDU Externals | FTTP - Type 2 | 2CBT-05 | Ertan Cicek | 2019-04-27 | Apr-19 | Marshell | Completed | [5 empty] | 2019-03-08 |  |  |  |  | 2018-03-29 |  |  |  |  | 2019-03-29 | Mar-19 |  | 06/07 - Ordered materials, require site visit 17/07- site visited, waiting on details 24/07- Waiting for construction company to return call 26/07: Scheduled in week starting 30/07 03/08 - pushed out to next week, week starting 06/08 09/08- Pushed out again untill next week 13/08 09/08- Developer gave incorrect details for site next door, waiting for correct info regarding LPC 10/08- Advised site is a few months away 22/02 - civil work scheduled in next week, before the developer pour concrete footpath 27/02 - DT Apply CLAAN 01/03 - link up completed 08/03 - aim for field completion in the next 2 weeks 15/03 - multiple blockages encountered. push back another week 22/03 - splicing to commence next week. civil and cable are hauled 29/03 - Field completed this week. PC next week | 2019-04-03 |  |  |  |  | 2019-04-03 | Apr-19
AYCA-5VXRM8 | 2 Actinotus Avenue, Caringbah South | MDU Externals | FTTP - Type 3 (MT-LFN) | 2MIR-25 | Ertan Cicek | 2019-04-29 | Apr-19 | Marshell | Pre-Construction | [5 empty] | 2019-05-15 | 2019-04-26 | 2019-04-26 |  |  | 2019-06-07 | [7 empty] | 05/04 - RFI email sent to Atul 09/04 - DDD to be submitted 16/04 18/04 - DDD work in progress. Delayed due to a delay response from nbn 02/05 - DDD submitted 26/04 and approved 01/04 10/05 - survey and scope next week 18/05 - civil to commence next week 24/05 - civil and haul to be completed next week 31/05 - outstanding civil to be completed next week. Splicing the following week | 2019-06-14
AYCA-5VXRM8 | 2 Actinotus Avenue, Caringbah South | MDU Internals | FTTP - Type 3 (MT-LFN) | 2MIR-25 | 0 | 2019-04-29 | Apr-19 | Marshell | Pre-Construction | [18 empty] | 18/04 - awaiting external design 02/05 - no change 10/05 - no change 18/05 - will complete this along with the external 24/05 - no change 31/05 - no change
AYCA-5MVKQ1 | O'Keefe Avenue, Moncrieff | MDU Externals | FTTP - Type 2 | 9BON-03 | Ertan Cicek | 2019-04-29 | Apr-19 | Marshell | Completed | [5 empty] | 2019-02-08 |  |  | 2019-02-14 | 2019-02-14 | 2019-02-15 |  |  |  |  | 2019-02-15 | Feb-19 |  | 23/11 - site still few months away, at least until new year 30/11 - no change 07/12 - no change 14/12 - no change 21/12 - no change 11/01 - due for follow up next week 18/01 - no change 23/01 - LAAN applied by DT. Site is not ready yet . | 2019-02-20 |  |  |  |  | 2019-02-19 | Feb-19
AYCA-44HH3F | 31-49 Warrego Circuit, Kaleen | MDU Externals | FTTP - Type 2 | 9BLC-22 | Ertan Cicek | 2019-04-30 | Apr-19 | Marshell | Developer Delay | [5 empty] | 2019-03-14 | [12 empty] | 21/12 - CSPO received this week. Site is still at least 4 months away. Follow up end of March 2019 22/03 - potential issue with the lead-in. follow up with the electrician next week 29/03 - issue raised with nbn regarding lead-in conduit and additional services 05/04 - clarification email sent to nbn on 04/04 12/04 - awaiting for response from Frank and the build partnership 18/04 - no change 26/04 - no change 02/05 - no change 10/05 - no change 18/05 - re-design to commence, awaiting for instruction from Ertan 31/05 - no change
AYCA-44HH3F | 31-49 Warrego Circuit, Kaleen | MDU Internals | FTTP - Type 2 | 9BLC-22 | Sundeep Chokshi | 2019-04-30 | Apr-19 | Marshell | Developer Delay | [5 empty] | N/A | [12 empty] | 18/02: CSPO received end of Jan 2019. Site construction is still underway 22/03 - potential issue with the lead-in. follow up with the electrician next week 29/03 - issue raised with nbn regarding lead-in conduit and additional services 05/04 - clarification email sent to nbn on 04/04 12/04 - awaiting for response from Frank and the build partnership 18/04 - no change 26/04 - no change 02/05 - no change 10/05 - no change 18/05 - awaiting for internal re-design 31/05 - no change
AYCA-4UF84M | 52 Copeland Street, Liverpool | MDU Externals | FTTP - Type 2 | 2LIV-04 | Ertan Cicek | 2019-04-30 | Apr-19 | Marshell | Completed | [5 empty] | 2018-11-08 |  |  |  |  | 2019-03-22 |  |  |  |  | 2019-03-20 | Mar-19 |  | 16/11- Advised site wont be ready until January. Pit may be relocated, TC required if we are upgrding 22/02- Internals ready 25/02 - ROL and TCP required as it is a main road. Applied today. Spoke to Damien and will need to let him know when we can mobilise the civil crew so he can remove the metal plate covering the lead-in pit 01/03 - TCP recevied. awaiting for ROL 08/03 - ROL obtained. scheduled civil next week, haul and splice the following week 15/03 - civil is completed. haul and splice next week | 2019-03-27 |  |  |  |  | 2019-03-22 | Mar-19
AYCA-5JGC8A | 2 Higgins Place, Higgins | MDU Externals | FTTP - Type 3 (MT-LFN) | 9SCU-23 | Ertan Cicek | 2019-05-01 | May-19 | Marshell | Design | [18 empty] | 05/04 - in design 18/04 - DDD in progress 26/04 - DDD is still work in progress 02/05 - no change 10/05 - no change 18/05 - no change 24/05 - still awaiting for RFI 31/05 - back in design
AYCA-5M7O7M | Shugg St, Taylor | MDU Externals | FTTP - Type 3 (MT-LFN) | 9BON-03 | Ertan Cicek | 2019-05-03 | May-19 | Marshell | Completed | [5 empty] | 2019-03-06 | [9 empty] | 2019-03-22 | Mar-19 |  | 14/12 - job is awarded this week. 21/12 - Site is still at least 2 months away. Follow up Mid Feb 22/02 - awaiting for LAAN 01/03 - developer not ready yet 08/03 - pit and pipe has not been certified yet 15/03 - external cable haul 22/03 - change of scope, confirmed by Ertan. Field completed this week. PC next week | 2019-03-27 |  |  |  |  | 2019-03-25 | Mar-19
AYCA-5NKJJY | 25 Judd Street, Cronulla | MDU Externals | FTTP - Type 3 (MT-LFN) | 2CRO-24 | Ertan Cicek | 2019-05-03 | May-19 | Marshell | Completed | [5 empty] | 2019-04-23 | 2019-04-04 | 2019-04-04 |  |  | 2019-05-17 |  |  |  |  | 2019-05-13 | May-19 |  | 01/03 - NDD submitted to nbn on 26/02 08/03 - Feedback received from nbn 06/03. resubmit 07/03 15/03 - awaiting nbn response 22/03 - no change 29/03 - DDD work in progress 05/04 - DDD submitted 04/04 10/04 - DDD approved 18/04 - CLAAN start on the 23rd of April. Will schedule this one in around Mid May 26/04 - no change 02/05 - DSS cable haul is completed. aim to complete the civil link up and haul next week and splicing to follow the week after 10/05 - splicing to commence next week 18/05 - field completed this week. PC next week | 2019-05-22 |  |  |  |  | 2019-05-20 | May-19
AYCA-5ALAXU | 104 Lysterfield Rd, Orange | MDU Externals | FTTP - Type 3 (MT-LFN) | 2ORG-02 | Mark Leal | 2019-05-05 | May-19 | Marshell | NBN Delay | [5 empty] | 2018-12-19 |  |  | 2019-05-15 |  | 2019-05-17 | [7 empty] | 14/12 - job awarded 10/12. LAAN starts 19/12. Parent site EFSCD 09/01/2019 21/12 - no change 11/01 - civil works are no longer required, done by others. Cable and nbn equipment have not been installed yet for the parent site 18/01 - awaiting confirmation from Mark Leal whether we need to test SMP installed by others 23/01 - no change 22/02 - no change. still awaiting confirmation from Mark Leal. 01/03 - aim to complete WS 18/03 15/03 - no change 19/03 - parent site not going to be built 15/04 12/04 - no change 18/04 - no change 26/04 - no change 02/05 - no change 07/05 - parent site is now ready, as advised by nbn 18/05 - Site visit this week. Parent site is not ready 24/05 - no change 31/05 no change | 2019-05-24
AYCA-5JIMDQ | 166 Brisbane Street, Dubbo | MDU Externals | FTTP - Type 2 | 2DBB-02 | Ertan Cicek | 2019-05-06 | May-19 | Marshell | Completed | [5 empty] | 2018-12-21 |  |  |  | 2019-03-19 | 2019-03-22 |  |  |  |  | 2019-03-22 | Mar-19 |  | 14/12 - CSPO received this week. 21/12 - Site is still few months away 11/01 - no change 18/01 - no change 23/01 - CRQ applied for end of Feb. Site is not ready yet. Developer suggested to folllow up mid Feb 22/02 - folow up next week 25/02 - Spoke to the electrican and he advised to follow up with him another month as the site won't have power ready up until then. 22/03 - field completed this week. PC next week | 2019-03-27 |  |  |  |  | 2019-03-25 | Mar-19
AYCA-5DHKDD | 36 Rawson Parade, Caringbah South | MDU Externals | FTTP - Type 3 (MT-LFN) | 2CRO-22 | Ertan Cicek | 2019-05-10 | May-19 | Marshell | Completed | [5 empty] | 2018-12-07 | [9 empty] | 2019-05-10 | May-19 |  | 07/12- Site ready, LIC brought out 08/03 - scope is scheduled next week 12/03 - site is almost ready. Need to confirm with the developer end of this week 15/03 - civil is scheduled in next week 22/03 - civil is 90% completed 02/04 - waiting for A end 18/04 - will send a rod and rope team early next week. will confirm that status of A End 26/04 - delayed to early next week 02/05 - civil and haul is completed. splice next week 10/05 - splicing is completed. to be submitted next week | 2019-05-17 |  |  |  |  | 2019-05-18 | May-19
AYCA-609IUY | 1 Gibbes Place, Weetangera | MDU Externals | FTTP - Type 3 (MT-LFN) | 9BLC-20 | Ertan Cicek | 2019-05-15 | May-19 | Marshell | Completed | [5 empty] | 2019-05-02 | 2019-04-11 | 2019-04-11 |  |  | 2019-05-24 | [7 empty] | 05/04 - in design 12/04 - DDD sumitted 11/04 18/04 - scope and survey next week 26/04 - awaiting for DDD approval 02/05 - scheduled to commence WS 20/05 10/05 - no change 18/05 - to commence next week 24/05 - on track | 2019-05-31
AYCA-609IUY | 1 Gibbes Place, Weetangera | MDU Internals | FTTP - Type 3 (MT-LFN) | 9BLC-20 | 0 | 2019-05-15 | May-19 | Marshell | Completed | [18 empty] | 18/04 - awaiting external design 26/04 no change 02/05 - same as externals 10/05 - no change 18/05 - to commence next week 24/05 - same as external
AYCA-4VAW65 | Lot 3,4 & 5 Denison St, Banksmeadow | MDU Externals | FTTP - Type 3 (MT-LFN) | 2BOT-22 | Ertan Cicek | 2019-05-15 | May-19 | Marshell | In construction | [5 empty] | 2019-05-16 | 2019-04-26 | 2019-04-26 |  |  | 2019-06-14 | [7 empty] | 22/03 - Design to commence shortly 05/04 - RFI email sent to Atul 30/04 - DDD submitted 26/04 18/05 - DDD to be revised next week 24/05 - civil to start next week 31/05 - civil is completed last week. Haul this week and splicing the week after | 2019-06-21
AYCA-4KZ9TH | 457-459 Pacific Highway, Asquith | MDU Externals | FTTP - Type 2 | 2HOR-62 | Ertan Cicek | 2019-05-17 | May-19 | Marshell | In construction | [5 empty] | 2019-05-01 | 2019-04-09 | 2019-04-09 |  |  | 2019-06-14 | [7 empty] | 26/02 - Transformation Project in Design, will be delivered to NBN tomorrow 30/03 - NDD submitted 26/03, waiting response 18/04 - DDD submitted 09/04 02/05 - survey is completed. ROL is applied on 01/05 10/05 - schedule to start in WS 20/05 18/05 - on track 24/05 - delayed until next 2 weeks 31/05 - civil is completed. haul and splice next week | 2019-06-21
AYCA-4YTCRX | 3-5A Citrus Ave, Hornsby | MDU Externals | FTTP - Type 2 | 2HOR-24 | Ertan Cicek | 2019-05-22 | May-19 | Marshell | In construction | [5 empty] | 2019-05-08 | [12 empty] | 26/04 - scope is completed. Awaiting for DDD approval and CLAAN to start 02/05 - new CLAAN to be submitted due to the change in civil works 10/05 - DDD approved 03/05 18/05 - new DDD approved 17/05. CLAAN to start 2 weeks from next week 24/05 - ROL required. have been applied 31/05 - drill to commence next week
AYCA-5W2PN2 | 55 Sutherland Crescent, Taylor | MDU Externals | FTTP - Type 3 (MT-LFN) | 9BON-03 | Ertan Cicek | 2019-05-29 | May-19 | Marshell | In construction | [5 empty] | 2019-05-01 | 2019-04-11 | 2019-04-11 |  |  | 2019-06-07 | [7 empty] | 05/04 - NDD submitted 02/04 18/04 - DDD submitted 10/04 26/04 - awaiting for DDD approval and CLAAN to start 02/05 - no change 10/05 - no change 18/05 - no change 24/05 - no change 31/05 - awaiting for PON Patching | 2019-06-14
ND000014434 | 28A Dixon Road, MOUNT RIVERVIEW | Network Extension | FTTP - Type 3 (MT-LFN) | 2SPW-22 | Jason Morley | 2019-05-29 | May-19 | Marshell | Completed | [5 empty] | 2019-05-02 | [12 empty] | 0
AYCA-4OCM1V | 260-264 Wardell Rd, Marrickville | MDU Externals | FTTP - Type 2 | 2UND-60 | Ertan Cicek | 2019-05-30 | May-19 | Marshell | Completed | [5 empty] | 2019-03-12 | [9 empty] | 2019-05-10 | May-19 |  | 20/07 - Site very early stages, not expecting hoarding down untill November. Call back 2 months from 20/07 26/07: No change 03/08 - no change 19/10- Hoarding not due to come down until after Christmas 22/02 - early March hoarding come down (04/03). Call back on the 4th to confirm 27/02 - DT Apply CLAAN 15/03 - civil is scheduled in next week. Developer is planning to pour concrete footpath late next week 22/03 - civil is awaiting for ROL 05/04 - no change 26/04 - civil is completed. Developper needs to connect to our starter pipe. Couldn't find the lead-in during construction 02/05 - haul to be completed end of next week. splicing to follow the week after 10/05 - no change | 2019-05-17 |  |  |  |  | 2019-05-18 | May-19
AYCA-5ZUB5A | 137 Victoria St, Ashfield | MDU externals | FTTP - Type 2 | 2ASH-62 | Ertan Cicek | 2019-05-31 | May-19 | Marshell | In construction | [5 empty] | 2019-05-08 | 2019-03-29 | 2019-03-29 | [10 empty] | 05/04 - NDD submitted 29/03. Internal design submitted 01/04. DDD to be submitted 11/04 18/04 - External DDD submitted 16/04 26/04 - scope to be done early next week 02/05 - MA to seek alternative build via directional drilling, meeting with subcontractor in WS 13/05. 10/05 - no change 18/05 - altenative route rejected by nbn. DT to organise with council 24/05 - council approval obtained. to start next week 31/05 - civil is underway. expecting completion next week. hauling to follow straight after
AYCA-5F1MOI | 1 Martha Street, Bowral | MDU Externals | FTTP - Type 3 (MT-LFN) | 2MSV-03 | Ertan Cicek | 2019-05-31 | May-19 | Marshell | Developer Delay | [5 empty] | 2018-11-20 | [12 empty] | 16/11 - job was awarded this week 23/11 - EFSCD still in feb 2019 30/11 - no change 07/12 - no change 14/12 - site visit is next week 21/12 - site is around 2-3 months away 11/01 - no change 18/01 - civil booked in early Feb 23/01 - no change. Drill is to commence early Feb 22/02 - civil works completed early Feb. Awaiting for developer to brought the lead-in conduit to as per the accepted pathway. Developer refused to do so. Reported this to Ertan. 08/03 - awaiting for response for the lead-in 15/03 - no change 22/03 - no change 29/03 - no change 05/04 - no change 26/04 - no change 02/05 - no change 10/05 - no change 18/05 - no change 24/05 - no change
ND000008778 | 1A / 61 Govetts St, The Ponds | Network Extension | FTTP - Type 3 (MT-LFN) | 2KEL-01 | Jason Morley | 2019-05-31 | May-19 | Marshell | Completed | [5 empty] | 2019-05-06 | [9 empty] | 2019-05-17 | May-19 |  | 0 | 2019-05-23 |  |  |  |  | 2019-05-23 | May-19
AYCA-65BVFE | 11 Lower Coast Rd, Stanwell Park | Network Extension | FTTP - Type 3 (MT-LFN) | 2APP-20 | Jason Morley | 2019-05-31 | May-19 | Marshell | Pre-Construction | [5 empty] | 2019-05-06 | [12 empty] | 0
AYCA-5072G6 | 123 CASTLEREAGH STREET, Liverpool | MDU Externals | FTTP - Type 2 | 2LIV-02 | Ertan Cicek | 2019-06-01 | Jun-19 | Marshell | Pre-Construction | [5 empty] | 2019-03-18 |  |  |  |  | 2019-06-07 | [7 empty] | 22/02 - awaiting for LAAN 01/04 - follow up this week regarding the scaffold 26/04 - will follow up next week 02/05 - no change 10/05 - scaffold has been removed. Awaiting for confirmation from the electrician regarding the lead-in conduit 18/05 - civil to commence next week 24/05 - civil is completed 31/05 - awaiting for developer to fix the internal pathway | 2019-06-14
AYCA-4Z5838 | 10 & 20 Seventeenth Ave, Austral | MDU Externals | FTTP - Type 3 (MT-LFN) | 2BRG-01 | Mark Leal | 2019-06-01 | Jun-19 | Marshell | Completed | [5 empty] | 2019-04-18 | 2019-03-29 | 2019-03-29 | [7 empty] | 2019-05-08 | May-19 |  | 15/03 - NDD submitted today 22/03 - awaiting nbn response 05/04 - DDD submitted 29/03. Awaiting for nbn response 18/04 - houses have not been built yet. pushed out 26/04 - no change 01/05 - no change 07/05 - Advised by nbn to confirm PON reading at the SMP and submit PC | 2019-05-17 |  |  |  |  | 2019-05-08 | May-19
AYCA-5FILA6 | 12 Marsden Street, Boorowa | MDU Externals | FTTN | 2BOW-20 | Ertan Cicek | 2019-06-03 | Jun-19 | Marshell | Developer Delay | [5 empty] | 2018-11-16 | [12 empty] | 23/11 - aim to start on the week starting 03/12 30/11 - site is not in construction yet. Possible start end of Feb or early March 2019. No further update will be given until Feb 2019 22/02 - EFSCD has been pushed out to June. Follow up early April 26/04 - follow up next week.
AYCA-5FWMQ5 | 14-18 Neringah Avenue South, Wahroonga | MDU Externals | FTTP - Type 2 | 2WRO-63 | Ertan Cicek | 2019-06-03 | Jun-19 | Marshell | Pre-Construction | [5 empty] | 13/02 - Requested | [12 empty] | 13/02 - Materials ordered, requested for LAANs, contact details, status on dependency, PON Patching 18/04 - survey to be done in the next coming weeks 26/04 - no change
AYCA-54A0VP | 7 Cherry St, Warrawee | MDU Externals | FTTP - Type 2 | 2PYM-62 | Ertan Cicek | 2019-06-05 | Jun-19 | Marshell | Developer Delay | [5 empty] | 2018-11-29 | [12 empty] | "23/11- LAANs commence 29/11, will schedule RRP after this date 19/12- Spoil over pits and temp fencing in way. advised completion is midFeb- early March. construction 70% complete. Lead in not done, footpath not due to be done until atleast late Feb" 01/03 - due to survey next week 08/03 - corehole and lead-in has not been completed by developer. will be done in the next 4 weeks 22/03 - suggest to follow up in a month time. possible funding issue 26/04 - follow up next week 18/05 - civil to commence next week. developer pouring concrete footpath next week 24/05 - civil completed
AYCA-5N4NUW | 36 Wyndora Avenue, Freshwater | MDU Externals | FTTP - Type 2 | 2HBD-23 | Ertan Cicek | 2019-06-05 | Jun-19 | Marshell | Site Visit | [5 empty] | 2018-12-07 | [12 empty] | 18/01- Hauling scheduled for next week 21/01 17/02 - Attended site, R&R 90% of the route, 2 blockages could not get through require dig down. 18/04 - scope and survey to be done in the next coming weeks 26/04 - issue with the DJL A end. Will send an email out next week
AYCA-5KIP6Y | 45 Rosemont Street, West Wollongong | MDU Internals | FTTP - Type 2 | 2WLG-07 | Ahmed Dalati | 2019-06-07 | Jun-19 | Marshell | Developer Delay | [5 empty] | N/A | [12 empty] | 12/10 - job awarded 10/10. Site still months away from completion 19/10 - no change 25/10 - no change 01/11 - no change 09/11 - no change 16/11 - no change 23/11 - no change 30/11 - no change 07/12 - no change 14/12 - no change 21/12 - no change 11/01 - no change 18/01 - no change 23/01 - follow up end of Feb 31/05 - advised by nbn the site is ready to go.
AYCA-5KIP6Y | 45 Rosemont Street, West Wollongong | MDU Externals | FTTP - Type 2 | 2WLG-07 | Ertan Cicek | 2019-06-07 | Jun-19 | Marshell | Developer Delay | [5 empty] | 2018-12-05 | [12 empty] | 16/11 - site still few months away 23/11 - no change 30/11 - no change 07/12 - no change 14/02 - no change 21/12 - no change 11/01 - no change 18/01 - no change 23/01 - follow up end of Feb 31/05 - advised by nbn the site is ready to go.
AYCA-5WHZHM | Jacobs Drive, Sussex Inlet | NSB | 0 | 2SUX-01 | Mark Leal | 2019-06-14 | Jun-19 | Marshell | Pre-Construction | [5 empty] | 2019-06-12 | 2019-05-23 | 2019-05-23 | [10 empty] | 19/03 - survey scheduled 21/03 29/03 - survey completed. FIR in progress 12/04 - FIR sent to nbn 27/05 - design submitted 23/05
AYCA-5ECAGW | 79 Sawmill CCT, Hume | MDU Externals | FTTP - Type 3 (MT-LFN) | 9QBN-09 | Ertan Cicek | 2019-06-14 | Jun-19 | Marshell | Developer Delay | [5 empty] | 2018-08-13 | [12 empty] | 27/07 - Ordered materials, require site visit 03/08 - no change 10/08 - site visit planned for WS 13/08 17/08 - site visit delayed, WS 20/08 24/08 - possible start in 2months time. Construction of site has not started yet 31/08 - no change 06/09 - no change 14/09 - no change 21/09 - no change 28/09 - no change 12/10 - no change 19/10 - no change 25/10 - no change 01/11 - no change 09/11 - no change 16/11 - no change 23/11 - no change 30/11 - no change 07/12 - no change 14/12 - no change 21/12 - no change 11/01 - no change 18/01 - no change. Follow up late Feb 31/05 - lead-in has not been brought out yet. incorrect pipe was used
AYCA-523PM8 | 8 Beaconsfield St, Fyshwick | MDU Externals | FTTP - Type 3 (MT-LFN) | 9MNK-01 | Ertan Cicek | 2019-06-14 | Jun-19 | Marshell | NBN Delay | [5 empty] | 2018-06-27 | [12 empty] | 06/07 - Forecast start date 27/08 13/07 - No change 20/07 - No change 27/07 - no change 03/08 - No change 10/08 - no change 17/09 - plan to start on 03/09 24/08 - possible delay. Developer not ready for us yet 31/08 - no change 06/09 - no change 14/09 - no change 21/09 - no change 28/09 - no change 12/10 - no change 19/10 - no change 25/10 - no change 01/11 - no change 09/11 - no change 16/11 - no change 23/11 - no change. possible push out until 2019 30/11 - no change. no further update will be given until further notice by nbn .
AYCA-5RXMK0 | 96 Bayldon Road, Queanbeyan West | MDU Externals | FTTP - Type 2 | 9QBN-08 | Ertan Cicek | 2019-06-14 | Jun-19 | Marshell | Pre-Construction | [5 empty] | 2018-12-12 | [12 empty] | 30/11 - job awarded 27/11 07/12 - site wont be ready for at least 2 months 14/12 - no change 21/12 - no change 11/01 - no one was working this week. There was not much progress since the last time we were there 18/01 - no change 23/01 - no change 22/02 - possible long delay. site has not progressing for the past 2 months. follow up end of March. .
AYCA-2GRL7A | Tatton 12B-Estate, | Estate | FTTP - Type 2 | 2KRG-03 | Mark Leal | 2019-06-18 | Jun-19 | Marshell | In construction | [5 empty] | 2019-03-25 | [9 empty] | 2019-05-17 | May-19 |  | 01/03 - job accepted through maximo this week 08/03 - awaiting for CLAAN from nbn 15/03 - CLAAN obtained. Start date on the 25th of March 22/03 - no change 29/03 - awaiting for confirmation from Mark, whether we can stop from at the MPT 05/04 - no change 12/04 - no change 26/04 - no change 02/05 - no change 10/05 - Mark advised us to fix the network blockages and not continue with the SDS haul 18/05 - blockage work underway | 2019-05-24 |  |  |  |  | 2019-05-22 | May-19
AYCA-4H9191 | 208-210 Princes Hwy, Bulli | MDU Externals | FTTP - Type 2 | 2COR-03 | Ertan Cicek | 2019-06-21 | Jun-19 | Marshell | Completed | [5 empty] | Heritage Waived | [9 empty] | 2019-05-24 | May-19 |  | 13/08: Job awarded. Material ordered. CRQ required to upgrade MPT 14/08: job delayed due to heritage 17/08 : DT to rod and rope for nbn to submit heritage exemption 24/08: rod and rope and survey completed to be submitted to nbn on Monday, 27/08 31/08: awaiting for nbn response 06/09 - no change 14/09 - no change 21/09 - no change 28/09 - no change. awaiting for heritage exemption 12/10 - no change 19/10 - New heritage exemption was submitted 16/10 26/10 - Heritage exemption was approved. Awaiting for LAAN 01/11 - no change 09/11 - no change 16/11 - no change 23/11 - no change 30/11 - advised by nbn that we can progress with this site. Civil is tentatively booked in for next week, dependant on Gas standby. CRQ to be booked for 14/12-17/12 07/12 - no change 14/12 - no gas standby available until after new year 21/12 - MPT upgrade is completed last week 11/01 - no change 18/01 - no change 23/01 - no change 15/03 - awaiting for response from nbn regarding vac unit. 29/03 - awaiting for ROL 05/04 - no change 18/04 - Gas standby booked in 13/05. ROL received 26/04 - no change 02/05 - no change 10/05 - ready to go next week 18/05 - field completed this week. PC next week 24/05 - PC delayed until next week | 2019-05-31 |  |  |  |  | 2019-05-31 | May-19
AYCA-4H9191 | 208-210 Princes Hwy, Bulli | MDU Internals | FTTP - Type 2 | 2COR-03 | Nabeel Jaimon | 2019-06-21 | Jun-19 | Marshell | Completed | [15 empty] | 2019-05-24 | May-19 |  | 18/04 - to be done at the same with external 26/04 - no change 02/05 - no change 18/05 - same as external 24/05 - no change | 2019-05-31 |  |  |  |  | 2019-05-31 | May-19
AYCA-3L3HR8 | 32 Mort Street, Braddon | MDU Externals | FTTP - Type 2 | 9CVI-01 | Ertan Cicek | 2019-06-22 | Jun-19 | Marshell | Pre-Construction | [5 empty] | 2019-04-01 | [12 empty] | 22/02 - CSPO received end of Jan. EFSCD in June. Site visit scheduled mid March
AYCA-4L3R6E | 4-6 Ventura Ave, Miranda | MDU Externals | FTTP - Type 3 (MT-LFN) | 2MIR-26 | Ertan Cicek | 2019-06-28 | Jun-19 | Marshell | Developer Delay | [5 empty] | 2019-03-11 | [12 empty] | 06/07 - foreman advises atleast 2 months from 29/06 before LPC ready, call back on 20/08 for follow up 26/07: No change 03/08 - no change 23/08- Have not been able to contact 30/08- Advised this wont be ready until the end of the year 13/12- Advised this wont be ready until January 18/01- Advised ready end of Feb 22/02 - follow up next week 27/02 - DT apply CLAAN 08/03 - scope next week 12/03 - ACM pit replacement is required 05/04 - awaiting for developer to brought the lead-in conduit 26/04 - no change 01/05 - starter pipe will be installed by the end next week 31/05 - as of last week, still awaiting for starter pipe
AYCA-5O866G | 113 Dooring Street, Dickson | MDU Externals | FTTP - Type 3 (MT-LFN) | 9CVI-22 | Ertan Cicek | 2019-06-28 | Jun-19 | Marshell | Pre-Construction | [5 empty] | 2019-06-12 | 2019-05-24 | 2019-05-24 | [10 empty] | 22/03 - NDD is work in progress 05/04 - NDD to be submitted 08/04 31/05 - DDD submitted 24/05
AYCA-58PGFK | 25 Ascot Rd, Bowral | MDU Internals | FTTP - Type 3 (MT-LFN) | 2MSV-03 | Sogand Mohtat | 2019-06-28 | Jun-19 | Marshell | Pre-Construction | [5 empty] | N/A | [12 empty] | 21/12 - CSPO received this week 11/01 - no change 18/01 - no change 23/01 - follow up with developer end of Feb 22/03 - site is around 90% completed. Lead-in has not been brought out to the boundary yet
AYCA-58PGFK | 25 Ascot Rd, Bowral | MDU Externals | FTTP - Type 3 (MT-LFN) | 2MSV-03 | Ertan Cicek | 2019-06-28 | Jun-19 | Marshell | Pre-Construction | [5 empty] | 2019-03-12 | [12 empty] | 14/12 - job is awarded this week 21/12 - no change 11/01 - no change 18/01 - no change 23/01 - follow up with developer end of Feb 22/03 - site is around 90% completed. Lead-in has not been brought out to the boundary yet
AYCA-5OO3VM | 2 Victoria Street, Wollongong | MDU Internals | FTTP - Type 2 | 2WLG-01 | Nabeel Jaimon | 2019-06-28 | Jun-19 | Marshell | Developer Delay | [5 empty] | N/A | [12 empty] | 21/02 - Monique advised us that the site won't be ready for civil lead-in link up due to hoarding is up. Maybe for the next couple of weeks
AYCA-5OO3VM | 2 Victoria Street, Wollongong | MDU Externals | FTTP - Type 2 | 2WLG-01 | Ertan Cicek | 2019-06-28 | Jun-19 | Marshell | Developer Delay | [5 empty] | 2018-11-22 | [12 empty] | 22/11- Site visit booked for week starting 03/12/2018 01/12- Site not ready until next year, slab only just poured 21/02 - Monique advised us that the site won't be ready for civil lead-in link up due to hoarding is up. Maybe for the next couple of weeks
AYCA-5ANVTS | 293 Port Hacking Rd, Miranda | MDU Externals | FTTP - Type 3 (MT-LFN) | 2MIR-26 | Ertan Cicek | 2019-06-28 | Jun-19 | Marshell | Pre-Construction | [5 empty] | 2019-03-20 | [12 empty] | 22/02 - awaiting for LAAN 29/03 - LAAN received. Site visit required
AYCA-5HNMQ4 | 2 - 4 Marlo Road, Cronulla | MDU Externals | FTTP - Type 3 (MT-LFN) | 2CRO-26 | Ertan Cicek | 2019-06-28 | Jun-19 | Marshell | Pre-Construction | [5 empty] | 2019-03-13 | [12 empty] | 22/02 - awaiting for LAAN 29/03 - LAAN received. Site visit required
AYCA-57OBUB | 399-403 Princes Hwy, Carlton | MDU Externals | FTTP - Type 2 | 2RAM-63 | Ertan Cicek | 2019-06-28 | Jun-19 | Marshell | Pre-Construction | [18 empty] | 31/05 - survey was completed this week. Site is still at least 1 month away
AYCA-587UWZ | 7 Lowrie Street, Dickson | MDU Externals | FTTP - Type 3 (MT-LFN) | 9CVI-22 | Ertan Cicek | 2019-08-30 | Aug-19 | Marshell | NBN Delay | [5 empty] | 2018-10-15 | [12 empty] | 12/10 - Job awarded 28/09. Awaiting for the dependent site to be completed 19/10 - no change 25/10 - no change 01/11 - no change 09/11 - no change 16/11 - no change 23/11 - no change 30/11 - no change. No further update will be given until furher notice by nbn 31/05 - awaiting for update from nbn
AYCA-5U1ZX9 | 32 Seaview Street, Cronulla | MDU Externals | FTTP - Type 3 (MT-LFN) | 2CRO-26 | Ertan Cicek | 2019-07-01 | Jul-19 | Marshell | Pre-Construction | [5 empty] | 2019-03-13 | [12 empty] | 10/01- Dependent site FTTC project PC due 14/04/2019 22/02 - awaiting for LAAN 29/03 - LAAN received. Site visit required
AYCA-4XYTH1 | 9 Charnwood Court, Glen Alpine | SDU | FTTN | 2CBT-02 | Mark Leal | 2019-07-01 | Jul-19 | Marshell | Completed | [5 empty] | 2019-04-16 |  |  |  |  | 2019-05-10 |  |  |  |  | 2019-05-10 | May-19 |  | 05/04 - CLAAN start soon 02/05 - civil to be completed this week. Haul and copper jointing next week 10/05 - to be field completed this week | 2019-05-17 |  |  |  |  | 2019-05-17 | May-19
AYCA-49DBF5 | 33-39 Croydon St, Cronulla | MDU Externals | FTTP - Type 2 | 2CRO-21 | Ertan Cicek | 2019-07-03 | Jul-19 | Marshell | Developer Delay | [5 empty] | 2019-03-12 |  |  | 2019-04-01 |  | 2019-06-07 | [7 empty] | 20/07 - Very early stages, site shed on top of proposed lead-in area, follow up 2 months from 20/07 26/07: No change 03/08 - no change 18/10- Follow up in three weeks 02/11- Unable to contact 08/11- Comms room has been moved to other side of building 09/11- Awaiting new schedule 16/11- Still waiting for new shedule 30/11- No change 06/01- Site ready, scheduled in for scoping week stag 07/01/2019 11/02- Scaff due down in 5 weeks, need to co-ordinate our work for when they rip up footpath 22/02 - advised by Daniel that they will be commencing their civil works on the first week of April. Follow up end of March 27/02 - DT apply CLAAN 22/03 - no change 29/03 - tentative start on civil, WS 15/04 05/04 - no change 12/04 - no change 18/04 - civil is 90% completed. awiating for the devleoper to remove the concrete footpath to finish the civil work 26/04 - no change 02/05 - civil to be completed end of this week 10/05 - civil is completed. haul next week, splicing the following week 31/05 - haul is completed. splice next week | 2019-06-14
AYCA-5BOGUQ | 2-6 Womerah St, Turramurra | MDU Externals | FTTP - Type 2 | 2PYM-61 | Ertan Cicek | 2019-07-03 | Jul-19 | Marshell | Developer Delay | [5 empty] | HEC Exemption | [12 empty] | 15/08 - Materials ordered. LAAN requested, contact details requested, site visit required, PON Patching requested 15/08 - Heritage delay, PON patching and contact received 09/11- Heritage exepmtion received, unable to contact developer 19/12- No core hole or LIC or cable tray, comms room complete, look at in new year, drop new pit closer to lead in to avoid tree roots
AYCA-587BWC | 218-222 Railway Parade, Kogarah | MDU Externals | FTTP - Type 2 | 2RAM-20 | Ertan Cicek | 2019-07-06 | Jul-19 | Marshell | Pre-Construction | [5 empty] | 2019-03-25 | [12 empty] | 22/02 - awaiting for LAAN 15/03 - ROL applied 26/04 - civil to commence WS 06/05 to line up with their footpath work 02/05 - no change 10/05 - civil is completed this week
AYCA-5I8I8D | 27-31 Thornleigh Street, Thornleigh | MDU Externals | FTTP - Type 2 | 2PNN-63 | Ertan Cicek | 2019-07-09 | Jul-19 | Marshell | Pre-Construction | [5 empty] | 2019-03-04 | [12 empty] | 11/01- Dependent site due 17/04/2019 but nbn propose Branch MPT-104 built earlier to accommodate us 17/02 - New CLAAN raised, requesting waiver to not wait till March 21/02 - Still waiting on LAANs, reminder of new proposal build 26/02 - Can start commencement 04/03 04/03 - John elec to provide update of lead-in conduit 05/03 05/03 - identified 35mm gal pipe on end of run, require pit upgrade to perform new trench works, possibly revise LAANs - Lead-in not ready, starter required to extend - A END is still not available, followed up 04/03 12/03 - Scope attended, require revise CLAAN, new build 50m, gal pipe only at full capacity
AYCA-5MELWX | Lot 6 Denison Street, Banksmeadow , Banksmeadow | MDU Externals | FTTP - Type 3 (MT-LFN) | 2BOT-22 | Ertan Cicek | 2019-07-17 | Jul-19 | Marshell | Pre-Construction | [5 empty] | 2019-05-16 | 2019-04-26 | 2019-04-26 | [10 empty] | 22/03 - Design to commence shortly 05/04 - RFI email sent to Atul 30/04 - DDD submitted 26/04. DDD approved 29/04
AYCA-52CPTI | 6-8 Cowan Rd, Mount Colah | MDU Externals | FTTP - Type 2 | 2HOR-63 | Ertan Cicek | 2019-07-17 | Jul-19 | Marshell | Design | [5 empty] | 2019-05-01 | 2019-04-11 | 2019-04-11 | [10 empty] | 26/02 - NDD completed, will be submitting today 01/03 - Require approval to commence pre-scope
AYCA-2QFUTJ | 37 Hilder Street, Elderslie | MDU Externals | FTTN | 2NRL-20 | Ertan Cicek | 2019-07-26 | Jul-19 | Marshell | Developer Delay | [18 empty] | 10/07 - Advised by developer still no progress on site. Will call once there is. 10/07 25/07 - Follow up required - developer not contacted for 2 weeks 26/07- site on hold, follow up in 6 weeks 03/08 - No change 07/09 - No answer 14/09 - Advised no change from developer 11/10- Advised by developer to call back in another month, still on hold 13/12- Ertan to follow up 22/02- No change
AYCA-5T6RSW | Clinton Street, Goulburn | MDU Externals | FTTP - Type 2 | 2GLB-04 | Ertan Cicek | 2019-07-26 | Jul-19 | Marshell | Pre-Construction | [5 empty] | Heritage issue | [12 empty] | 22/03 - issue with council regarding heritage 29/03 - no change
AYCA-3SB1HA | 40 Morgan St, Dubbo | Estate | FTTP - Type 2 | 2DBB-05 | Ertan Cicek | 2019-07-31 | Jul-19 | Marshell | Pre-Construction | [5 empty] | 2019-03-25 | [12 empty] | 22/03 - awaiting for new CWP from nbn for the new alternative solution, instead of new build via drilling
AYCA-472QK6 | 22 Albert St, Taylors Beach | MDU Externals | FTTN | 2NLB-06 | Mark Leal | 2019-07-31 | Jul-19 | Marshell | Completed | [5 empty] | 2019-05-02 |  |  |  |  | 2019-05-24 |  |  |  |  | 2019-05-24 | May-19 |  | 0 | 2019-05-31 |  |  |  |  | 2019-05-30 | May-19
AYCA-5KAIAA | Browns Lane, Moore Creek | MDU Externals | 0 | 2TAM-01 | Mark Leal | 2019-08-23 | Aug-19 | Marshell | Design | [6 empty] | 2019-05-14 | [11 empty] | 07/05 - No design required for this work order
AYCA-5NR7GA | 12 Berrima Road, Moss Vale | NSB | FTTN | 2MSV-02 | Mark Leal | 2019-08-30 | Aug-19 | Marshell | Design | [5 empty] | 2019-03-27 | [12 empty] | 29/03 - survey next week. FIR to be submitted next week 07/05 - FIR will be submitted this week. 18/05 - field completed this week. Issues with LT card
AYCA-4X1Z9M | 58/60 Karimbla Rd, Miranda | MDU Externals | FTTP - Type 3 (MT-LFN) | 2MIR-26 | Ertan Cicek | 2019-08-30 | Aug-19 | Marshell | Developer Delay | [5 empty] | 2019-03-11 | [12 empty] | 15/06 - Pending material order 17/07- site visited, waiting on details 19/07- Site just beginning escavation for ground works. 26/07: No Change 03/08 - no change 22/02- Due for follow up 27/02 - DT Apply CLAAN
AYCA-4Z8X0L | 34-44 Underwood St, Corrimal | MDU Externals | FTTP - Type 2 | 2COR-07 | Ertan Cicek | 2019-09-28 | Sep-19 | Marshell | Pre-Construction | [5 empty] | 2019-03-14 | [12 empty] | 22/02 - awaiting for the correct type of MW. Pre-Agreed instead of one-off
AYCA-4Q4RLG | MacArthur Road, Spring Farm | MDU Externals | FTTP - Type 3 (MT-LFN) | 2NRN-01 | Mark Leal | 2019-10-05 | Oct-19 | Marshell | Pre-Construction | [5 empty] | 2019-03-14 | [12 empty] | 25/02 - civil works only. DT to scope/survey prior to submit the CLAAN 27/02 - site is still in early stage. SMP has not been installed yet through parent site. Middle P5 doesn't exist yet. Follow up in another month
AYCA-4JW63S | 25-29 Tonkin Street, Cronulla | MDU Externals | FTTP - Type 2 | 2CRO-21 | Ertan Cicek | 2019-10-25 | Oct-19 | Marshell | Developer Delay | [18 empty] | 06/07 - L/P/C not ready, site sheds in the way, no pits located, possibly under site sheds - 17/07- Civils 18/07, still no comms room or pathway follow up 23/07 24/07- Waiting for cable tray, follow up required 03/08 - Cable tray unable to be installed due to a temporary hydro pipe in the way. Estimated months until this is taken down. Ertan has been advised 20/02 - revised PON Patching SOW requested to nbn 22/02 - revised PON Patching SOW received 27/02 - possible long delay or job cancelled due to developer lost its funding
AYCA-YGLEJ | 81 Constitution Avenue, Campbell | MDU Externals | FTTP - Type 2 | 9CVI-03 | Ertan Cicek | 2019-11-29 | Nov-19 | Marshell | Pre-Construction | [18 empty] | 01/11 - LAAN requested 09/11 - awaiting for TCP 16/11 - TCP sent to nbn on the 13th of Nov. 23/11 - awaiting for LAAN 30/11 - no change 07/12 - no change 14/12 - no change 21/12 - no change 11/01 - no change 18/01 - no change 23/01 - no further update will be given until LAAN is submitted .
AYCA-481ES7 | 65 George St, Bathurst | MDU Internals | Internal MDU | 2BTH-09 | Nabeel Jaimon | 2020-01-31 | Jan-20 | Marshell | Developer Delay | [5 empty] | N/A | [12 empty] | 06/07 - Forecast start date 27/08 13/07 - No change 20/07 - Possible delay up to 2 years - advised by developer 27/07 - no change 03/08 - No change 10/08 - no change 17/08 - EFSCD just updated to 2020. 24/08 - no change 31/08 - no change 06/09: no change 14/09 - no change 21/09 - no change 28/09 - no change 12/10 - no change 19/10 - no change 25/10 - no change 01/11 - no change 09/11 - no change 16/11 - no change 23/11 - no change 30/11 - no further update will be given until mid 2019 .
AYCA-3W384B | 433-437 Pacific Highway, Asquith | MDU Externals | FTTP - Type 2 | 2HOR-62 | Ertan Cicek | 2020-02-07 | Feb-20 | Marshell | Site Visit | [5 empty] | 18/02 - Requested, haven't received | [12 empty] | 06/07 - Not ready, old houses with temp fence around. Inspected 13/06 26/07: No change 03/08 - no change 18/02 - Requested site contact details, LAANs, dependency status 12/03 - Still early stages, not priority
AYCA-4LZWVS | 266-268 Pennant Hills Rd, Thornleigh | MDU Externals | FTTP - Type 2 | 2PNN-63 | Ertan Cicek | 2020-02-28 | Feb-20 | Marshell | Pre-Construction | [5 empty] | 2019-01-09 | [12 empty] | 16/02 - Contact, LAAN, requested on 20/12/2018 and received. No PON yet 30/03 - EFSCD long way out
AYCA-4VG4KY | 23-25 Chelmsford Place Leeton Library, Leeton | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2LTO-20 | David Yeomans | N/A | N/A | Marshell | Completed | [8 empty] | 2018-06-04 |  | 2018-06-08 |  |  |  |  | 2018-06-14 | Jun-18 |  | 0 | 2018-06-18 |  |  |  |  | 2018-06-19 | Jun-18
AYCA-52JYBU | 7 Buggy Crescent, McKellar | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 9SCU-20 | David Yeomans | N/A | N/A | Marshell | Completed | [5 empty] | 2018-06-25 |  |  | 2018-06-25 | 2018-06-25 | 2018-06-29 |  |  |  |  | 2018-07-02 | Jul-18 |  | 0 | 2018-07-03 |  |  |  |  | 2018-07-23 | Jul-18
AYCA-4C4E63 | 11 Liverpool Street, Cowra | SDU | FTTP - Type 3 (MT-LFN) | 2CWR-01 | David Yeomans | N/A | N/A | Marshell | Completed | [5 empty] | Y |  |  | x | 2018-05-16 | 2018-05-17 |  |  |  |  | 2018-05-17 | May-18 |  | 0 | 2018-06-04 |  |  |  |  | 2018-06-04 | Jun-18
AYCA-4PX9WA | 23 Browne Street, Yass | SDU | FTTP - Type 3 (MT-LFN) | 2YAS-01 | David Yeomans | N/A | N/A | Marshell | Completed | [5 empty] | Y |  |  | 2018-05-28 | 2018-05-29 | 2018-05-30 |  |  |  |  | 2018-05-31 | May-18 |  | 0 | 2018-06-05 |  |  |  |  | 2018-06-05 | Jun-18
AYCA-4WVTLQ | 48 Southlakes Parade, Dubbo | MDU Externals | FTTP - Type 2 | 2DBB-01 | Mark Leal | N/A | N/A | Marshell | Completed | [8 empty] | x | 2018-05-17 | 2018-05-17 |  |  |  |  | 2018-05-17 | May-18 |  | 0 | 2018-06-07 |  |  |  |  | 2018-06-07 | Jun-18
AYCA-5K3OHQ | 93 Ivo Whitton Circuit, Kambah | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 9KBA-23 | Mark Leal | N/A | N/A | Marshell | Completed | [5 empty] | 2018-10-30 |  |  | 2018-11-02 |  | 2018-11-09 |  |  |  |  | 2018-11-02 | Nov-18 |  | 25/10 - LAAN start on the 30th of October 01/11 - no change 06/11 - PC submitted on the 5th of November | 2018-11-05 |  |  |  |  | 2018-11-05 | Nov-18
AYCA-5NNV14 | 30 Barwan Street - Graincorp, Narrabri | Business Segment | FTTP - Type 3 (MT-LFN) | 2NBR-20 | David Yeomans | N/A | N/A | Marshell | Completed | [5 empty] | 2018-11-12 |  | 2018-10-15 | 2018-11-12 | 2018-11-12 | 2018-11-20 |  |  |  |  | 2018-11-20 | Nov-18 |  | 19/10 - design submitted on Monday 25/10 - follow up email for design feedback sent out on the 23rd of October. Final design submitted today 01/11 - planned to start as per the LAAN, 121/11 09/11 - no change 16/11 - civil is completed. Haul and splice commencing next week 23/11 - field wok completed on the 20th. PC Pack next week 27/11 - PC submitted on the 26th of Nov | 2018-11-27 |  |  |  |  | 2018-11-26 | Nov-18
AYCA-5FK9G7 | 113-115 Baker St, Temora | NSB | FTTP - Type 3 (MT-LFN) | 2TEM-20 | Mark Leal | N/A | N/A | Marshell | Completed | [5 empty] | 2018-10-22 |  |  |  | 2018-11-14 | 2018-12-07 |  |  |  |  | 2018-12-07 | Dec-18 |  | 28/08 - Require survey LAAN before survey can commence 05/09 - Survey to commence today 06/09 - Survey completed. ADA 2TEM-20-02 has not been completed yet 14/09 - awaiting for nbn design approval 21/09 - no change 28/09 - design submitted 24/09 12/10 - design approved 02/10. Awaiting for the parent site to be completed 19/10 - no change 25/10 - Awaiting advise from nbn whether the ADA has been PC'ed 01/11 - ADA has been PC'ed 09/11 - scheduled in for this month 16/11 - no change 23/11 - still on track for this month 30/11 - aim for field completion end of next week 07/12 - field completed this week. PC submission mid next week 14/12 - still awaiting for celemetrix report to be fixed 21/12 - PC submitted this week | 2018-12-12 |  |  |  |  | 2018-12-20 | Dec-18
AYCA-5S2CD6 | Murrumbidgee Irrigation: 40 Dunn Avenue, Leeton | Business Segment | FTTP - Type 3 (MT-LFN) | 2LTO-21 | David Yeomans | N/A | N/A | Marshell | Completed | [5 empty] | 2018-12-27 | 2018-11-30 | 2018-11-30 | 2019-01-21 | 2019-01-16 | 2019-02-01 |  |  |  |  | 2019-02-01 | Feb-19 |  | 09/11 - survey is scheduled next week 16/11 - survey is completed. Design is due next week 23/11 - design is due today 26/11 - design is submitted today 30/11 - Version 2.0 of design is due to be submitted today 07/12 - awaiting for nbn design response 14/12 - design is approved. aim to start construction Jan 2019 21/12 - no change 11/01 - design approved this week 18/01 - external haul commencing this week. 23/01 - external haul completed. Splicing to commenc next week . | 2019-02-06 |  |  |  |  | 2019-02-04 | Feb-19
AYCA-5H49UT | 132 Piper Street, Bathurst | SDU | FTTP - Type 3 (MT-LFN) | 2BTH-20 | Mark Leal | N/A | N/A | Marshell | Completed | [5 empty] | 2019-01-07 |  |  | 2019-01-08 | 2019-01-08 | 2019-01-18 |  |  |  |  | 2018-01-24 | Jan-18 |  | 21/12 - CSPO received this week. 11/01 - external haul is completed 18/01 - work order is 90% completed. Few defects. Rectification next week. PC date still holds 23/01 - PC this week. Slightly delayed due to defects . | 2019-01-23 |  |  |  |  | 2019-01-24 | Jan-19
AYCA-5MCPUX | 151 Drake-Brockman Drive, Higgins | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 9SCU-23 | Mark Leal | N/A | N/A | Marshell | Completed | [5 empty] | 2019-02-21 |  |  |  |  | 2019-03-01 |  |  |  |  | 2019-02-28 | Feb-19 |  | 23/11 - extensive build is required. New LAAN required 30/11 - Queries asked to whether we can use transACT network, otherwise approx. 230m of new build is required 07/12 - TransACT network to be used. Awaiting for new LAAN 14/12 - no change 21/12 - awaiting for new LAAN 11/01 - no change 18/01 - Lead-in was completed by developer/owner. Gator joint approval by Zlate. awaiting for LAAN 23/01 - awaiting LAAN. Lead-in construction by the developer is due to be completed within the next 2 weeks 19/02 - LAAN applied by DT 22/02 - external haul and civil completed. Aim to complete this site by end of next week 01/03 - field completed. aim for PC next week | 2019-03-06 |  |  |  |  | 2019-03-04 | Mar-19
AYCA-5XOE8H | 4 Elwin Drive, Orange | Business Segment | FTTP - Type 3 (MT-LFN) | 2ORG-06 | David Yeomans | N/A | N/A | Marshell | Completed | [5 empty] | 2019-03-08 | 2019-02-08 | 2019-02-08 | 2019-03-18 | 2019-03-11 | 2019-03-21 |  |  |  |  | 2019-03-18 | Mar-19 |  | 22/02 - design approved on the 21st of Feb. LAAN is commecing on the 8th of March. Spoke to Pritesh that we are going to start construction on the week of the 18th. | 2019-03-27 |  |  |  |  | 2019-03-22 | Mar-19
AYCA-63B4XW | 65A PARTHENIA ST, Dolans Bay | Business Segment | FTTP - Type 3 (MT-LFN) | 2MIR-27 | David Yeomans | N/A | N/A | Marshell | Completed | [5 empty] | 2019-04-01 | 2019-03-15 | 2019-03-15 | 2019-04-01 |  | 2019-04-12 |  |  |  |  | 2019-04-05 | Apr-19 |  | 15/03 - design is to be submitted today. CLAAN sent today 22/03 - design is conditionally approved 29/03 - construction to commence next week 05/04 - Vis test 03/04 positive | 2019-04-10 |  |  |  |  | 2019-04-10 | Apr-19
AYCA-5V3DPZ | 5,11,1,6,9,21,24,25,26 Winser Cres, Kambah | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 9KBA-23 | Mark Leal | N/A | N/A | Marshell | Completed | [5 empty] | 2019-04-11 |  |  |  |  | 2019-05-10 |  |  |  |  | 2019-05-10 | May-19 |  | 19/03 - aim to perform full scope next week 26/03 - email sent to Mark L asking for CLAAN and direction 29/03 - CLAAN obtained. Start as soon as the CLAAN window is open 05/04 - no change 26/04 - awaiting the report from arborist to proceed with the civil work 02/05 - aim to complete end of this week 10/05 - battery back up to be installed for all 9 premises | 2019-05-17 |  |  |  |  | 2019-05-17 | May-19
AYCA-5V8X5D | 1 Arcadia Street, Warilla | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2SHH-03 | Mark Leal | N/A | N/A | Marshell | Completed | [5 empty] | 2019-04-09 |  |  |  |  | 2019-05-10 |  |  |  |  | 2019-05-10 | May-19 |  | 26/03 - CLAAN requested by Datateks 05/04 - start as soon as the CLAAN open 26/04 - awaiting for the customer to provide internal pathway 02/05 - aim to complete end of next week. Internal pathway completed as advised by the customer 10/05 - field completed this week | 2019-05-17 |  |  |  |  | 2019-05-17 | May-19
AYCA-5KEC98 | 41 Third Ave North, Narromine | MDU Externals | FTTN | 2NMN-20 | Ertan Cicek | N/A | N/A | Marshell | Completed | [5 empty] | 2019-01-30 |  |  | 2019-01-21 | 2019-01-23 | 2019-01-25 |  |  |  |  | 2019-01-23 | Jan-19 |  | 18/01 - CSPO received this week. Awaiting Ertan' confirmation as to how we are going to complete this site | 2019-01-30 |  |  |  |  | 2019-01-23 | Jan-19
AYCA-5AZA4J | BLOCK 26 SECTION 124, Holt | MDU Externals | FTTP - Type 3 (MT-LFN) | 9SCU-08 | Ertan Cicek | N/A | N/A | Marshell | Completed | [5 empty] | 2019-03-06 | [9 empty] | 2019-03-07 | Mar-19 |  | 23/11 - EFSCD still in feb 2019 30/11 - no change 07/12 - no change 14/12 - no change 21/12 - no change 11/01 - no change 18/01 - no change 23/01 - no change 22/02 - advised by nbn that parent site is due for PC today. Lead-in is being fixed by the developer 01/03 - aim for field completion next week | 2019-03-13 |  |  |  |  | 2019-03-08 | Mar-19
AYCA-5ZJJVL | 32 Ivo Whitton CCT, Kambah | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 9KBA-23 | Mark Leal |  |  | Marshell | Completed | [10 empty] | 2019-05-17 |  |  |  |  | 2019-05-20 | May-19 |  | 26/04 - to be done the same time with Kambah group work order 02/05 - possible pushed out to the next 3 weeks 18/05 - field complete will be on Monday, 20/05 | 2019-05-24 |  |  |  |  | 2019-05-22 | May-19
AYCA-61XX6C | Hayters Drive/Tea Tree Court, Suffolk Park | NSB | 0 | 2BYB-20 | Mark Leal |  |  | Marshell | Design | [18 empty] | 01/05 - survey to be scheduled in next week
AYCA-62FYYN | 132 Osborne Road, Burradoo | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2MSV-01 | Mark Leal |  |  | Marshell | Design | [18 empty] | 0
AYCA-527MGD | 108 Lawrence Hargrave Dr, Austinmer | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2COR-02 | Mark Leal |  |  | Marshell | Design | [18 empty] | 0
AYCA-6384TG | 24 Tasman Court, Caves Beach | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2NDS-20 | Mark Leal |  |  | Marshell | Design | [18 empty] | 0
AYCA-5HBFXB | 132 Kite Street, Orange | MDU Externals | FTTN | 2ORG-02 | Mark Leal |  |  | Marshell | Design | [18 empty] | 0
AYCA-62FMLI | 19 Engineering Drive, NORTH BOAMBEE VALLEY | MDU Externals and Internal design only | FTTP - Type 2 | 2CFS-06 | 0 |  |  | Marshell | Design | [6 empty] | 2019-05-28 | 2019-05-28 | [10 empty] | 29/05 - design was submitted 28/05
AYCA-5IS7AL | 274 River Street, Ballina | MDU Externals | FTTP - Type 3 (MT-LFN) | 2BLN-22 | Ertan Cicek |  |  | Marshell | Pre-Construction | [5 empty] | 2019-06-11 | 2019-05-27 | 2019-05-27 | [10 empty] | 0
AYCA-5KAUOH | Lionel Rose, Holt | MDU Externals | FTTP - Type 3 (MT-LFN) | 9SCU-08 | Mark Leal |  |  | Marshell | Pre-Construction | [5 empty] | 2019-06-05 | [12 empty] | 0
AYCA-627R64 | 15 Johnson Street, Forbes | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2FRB-20 | Mark Leal |  |  | Marshell | Design | [18 empty] | 0
AYCA-627OQK | 64 William Street, Condobolin | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2CON-20 | Mark Leal |  |  | Marshell | Design | [18 empty] | 0
AYCA-61KJXQ | 22 Bundaroo St, Bowral | SDU - Tech choice | FTTP - Type 3 (MT-LFN) | 2MSV-04 | Mark Leal |  |  | Marshell | Design | [18 empty] | 0
AYCA-64LL1W | 6-8 Hotham Road, Kirrawee | MDU Externals | 0 | 2CMO-24 | Ertan Cicek |  |  | Marshell | Design | [18 empty] | 0
AYCA-628LT8 | 20 Shepherd St, Liverpool | MDU Externals | 0 | 2LIV-02 | Ertan Cicek |  |  | Marshell | Design | [6 empty] | 2019-05-31 | [11 empty] | 0
AYCA-5SSUZP | Cnr Bettong Avenue & Kaigas Street, Throsby | MDU Externals | 0 | 9CRC-06 | Ertan Cicek |  |  | Marshell | Design | [18 empty] | 0
AYCA-58GJIP | 3 Fairmile Close, Charmhaven | MDU Externals | 0 | 2GRK-02 | Ertan Cicek |  |  | Marshell | Design | [18 empty] | 0
AYCA-5J56F6 | 70-90 Station Street, Mullumbimby | MDU Externals | 0 | 2MUL-01 | Ertan Cicek |  |  | Marshell | Design | [10 empty] | 2019-06-04 | [7 empty] | 0
AYCA-61I1YF | 6 Judy Jakins Drive, Dubbo | MDU Externals | 0 | 2DBB-02 | Ertan Cicek |  |  | Marshell | Design | [18 empty] | 0
AYCA-5PXS5T | 4 Gregory Hills Drive, Gledswood Hills | SDU | FTTP - Type 3 (MT-LFN) | 2NRN-10 | Mark Leal |  |  | Marshell | Pre-Construction | [5 empty] | 2019-06-10 | [12 empty] | 0
AYCA-61I1YF | 6 Judy Jakins Drive, Dubbo | MDU Internals | 0 | 2DBB-02 | 0 |  |  | Marshell | Pre-Construction | [18 empty] | 0
AYCA-5GMMK0 | 17 Bellevue Street, South Nowra | MDU Internals | 0 | 2NWR-03 | 0 |  |  | Marshell | Pre-Construction | [18 empty] | 0
AYCA-5WZRDN | 14 Day Street, Wagga Wagga | MDU Externals | 0 | 2NWR-03 | 0 |  |  | Marshell | Pre-Construction | [18 empty] | 0
AYCA-69DP2M | 150 Tarent Point Road, Taren Point | NSB | 0 | 2MIR-24 | Mark Leal |  |  | Marshell | Design | [18 empty] | 0
LOC000180413714 | 60 Meroo Road, BOMADERRY | Held Order | 0 | 2NWR-06 | Jason Morley |  |  | Marshell | Pre-construction | [18 empty] | 0
AYCA-62BY2V | 1 Hoxton Park Road, Liverpool | MDU Externals | 0 | 2LIV-03 | Ertan Cicek |  |  | Marshell | Design | [18 empty] | 0
Note on D347: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Change tech

## Sheet2
RequestID | Application Name
AYCA-1XN8L5 | 9 Affleck Circuit, 9 Affleck Circuit, NSW 2155
AYCA-21PVTM | 5 Second Avenue
AYCA-24QAXK | 10 Martin Avenue, Arncliffe
AYCA-26KP9Q | Caddies Boulevarde and White Hart Drive
AYCA-2HEWWI | 337-339 Beamish Street, Campsie, NSW 2194
AYCA-2I98H3 | 113-117A Wigram St23-29 Hassall St
AYCA-2LCFXK | Skyview - 1 - 248-252 Liverpool Road, Enfield
AYCA-2M3M8J | 72-84 Empire Circuit, Penrith, NSW 2750
AYCA-2Q0B3G | 148-150 Great Western Hwy, Westmead, NSW, 2145
AYCA-2RG791 | 15-19 Toongabbie Rd , Toongabbie, NSW, 2146 - Mixed used
AYCA-2T05DV | 752 George St South Windsor NSW 2756
AYCA-2V9V2D | 2 Cowan Road & 540A-542 Pacific Highway, Mount Colah, 2079
AYCA-2XJBL7 | 3 Olympic Blvd Sydney Olympic Park
AYCA-30GQWB | 16-20 Withers Rd, Kellyville, NSW- 2155
AYCA-31DCKF | 18-20 Neild Avenue, Darlinghurst
AYCA-33L9HP | Restwell & Leonard St
AYCA-34MTV2 | 133 Parramatta Rd, Homebush, NSW, 2140
AYCA-35DF0W | 1A & 1B President Road
AYCA-35V4R1 | 208-214 Parramatta Rd, Homebush, NSW 2140
AYCA-397TA7 | 6-8 Painters Lane, Terrigal
AYCA-39AB50 | JAAN – 1 12-14 Bouvardia St
AYCA-3AVVT5 | 70 seventeenth Avenue, Austral, NSW 2179
AYCA-3CIGB0 | 1-3 Balmoral St, Waitara, NSW 2077
AYCA-3D0J11 | 15-21 Willis St, Wolli Creek
AYCA-3E5O97 | Hancy - 85-89 Samantha Riley Drive
AYCA-3G1TZ6 | 9-17 Eastern Rd, Turramurra, NSW 2074
AYCA-3JJIX9 | 13-21 University Rd and 1-5 Pinnacle St, Miranda, NSW, 2228
AYCA-3NFID7 | Tench Ave Jamisontown – 1
AYCA-3O1ZGP | 4-6 Elger St, Glebe, NSW 2037
AYCA-3O2CEB | 5 Elger St, Glebe, NSW- 2037
AYCA-3S7B4B | University of Technology Sydney
AYCA-413Z64 | 2B Darcy Road, Westmead
AYCA-41DSOU | 38 Hezlett Road, Kellyville, NSW- 2155
AYCA-41DY76 | 38 Hezlett Road Kellyville NSW
AYCA-42HX6R | 34-42 Spring St, Bondi Junction, NSW2022
AYCA-42N8QF | 38 Macklin Street
AYCA-43APKG | 6-14 Cosgrove Road, Strathfield, NSW 2136
AYCA-44H3AU | 13 Marshall Avenue St Leonards NSW 2065
AYCA-44MH0G | 133-137 Bowden Street
AYCA-45LS90 | 8 Withers Rd, Kellyville, NSW- 2155
AYCA-45U68U | 5 CULLEN AV, JORDAN SPRINGS, NSW, 2747
AYCA-468RZY | 23 Railway Parade
AYCA-468RZY | 23 Railway Parade- Internals
AYCA-476RM9 | 87-91 Campbell Street Liverpool
AYCA-47OO3O | 188 Moore Street
AYCA-47STWW | 130 Elizabeth St, Sydney, NSW 2000
AYCA-48280D | 906 Bourke Street - THE RESERVE
AYCA-48HHL8 | 22 University Rd & 660-664 Kingsway, Miranda
AYCA-48OYT0 | 240 New South Head Road Edgecliff NSW 2027
AYCA-48S696 | 3-7 Wallace Street
AYCA-49OZC4 | 257 Oxford St – 1
AYCA-4BA1DQ | 3 Rowe Drive Potts Hill, NSW 2143
AYCA-4BBYMK | 184 & 186 Old Pitt Town Rd Box Hill, NSW 2765
AYCA-4BC75L | Fairwater Boulevarde, Blacktown
AYCA-4C0Z5Y | Hamptons - Rose Bay - 1
AYCA-4CG9U4 | Dunning Avenue, Roseberry
AYCA-4DBFGM | 87 Parramatta Rd, Camperdown, NSW 2050
AYCA-4DQ6PX | 645 Cobbitty Road - 3
AYCA-4DQ9I8 | 645 Cobbitty Road - 2
AYCA-4EITU0 | The Pinnacle - 100 Castlereagh Street
AYCA-4EZRCH | 1-3 Higherdale Avenue, Miranda
AYCA-4F75OS | 66-68 Cambridge St, Blacktown, Blacktown 2148
AYCA-4JM0L9 | CINQUE - 50-52 East St
AYCA-4KBL5R | 14-18 Primrose Ave & 27-29 Roseberry Ave Rosberry NSW 2018
AYCA-4KKMW0 | 55 Foxall Road, Kellyville, NSW- 2155
AYCA-4KNB05 | 20 Myrtle St, Teralba, NSW- 2284
AYCA-4KZ476 | 38-40 Doonmore St - Penrith 1
AYCA-4L1IJG | 19 Gregory St South West Rocks, NSW 2431
AYCA-4LISRC | 62 Jamboree Avenue, Leppington, NSW 2179
AYCA-4LM7HH | 590-602 New Canterbury Rd
AYCA-4LT337 | 457-463 Victoria Street, Wetherill Park
AYCA-4LVG38 | 9-11 Edgeworth Place, Cartwright, NSW 2168
AYCA-4M02LB | 401-405 Illawarra Road
AYCA-4MFJ6I | 65 Victoria Street Coffs Harbour, NSW, 2450
AYCA-4ND19Q | Chapel Street Rockdale - 1
AYCA-4NNOGX | 240-250 Great Western Hwy Kingswood NSW 2747
AYCA-4NOC4P | 40 Cawarra Road, Caringbah, NSW, 2229
AYCA-4O03IQ | 17 Ryan Street
AYCA-4O03IQ | 17 Ryan Street
AYCA-4OQ160 | 3 Ocean Ridge Terrace, Port Macquarie NSW 2444
AYCA-4P3YPZ | 107 Chapel Road South, Bankstown,NSW 2200
AYCA-4PIIN5 | 101 Church Street (dependent - require 4 Junction St QUBE), Ryde
AYCA-4PPBEB | 8 Sherbrooke Rd, West Ryde, NSW
AYCA-4PQO3D | 12/6 Maida Road, Epping
AYCA-4PRYRR | 161 - 163 Great Western Hwy, Mays Hill, NSW 2145
AYCA-4Q27NU | 50 Raby Rd, Gledswood Hills, NSW- 2557
AYCA-4QHVO8 | 13-15 Pacific Hwy, Gateshead
AYCA-4QID92 | 153-165 Brougham St, Woolloomooloo
AYCA-4QNRBL | 822 Windsor Road Rouse Hill, NSW 2155
AYCA-4R1C1M | William Street, Riverstone
AYCA-4R1E3Q | 144-148 High Street & 35-37 Barber Avenue
AYCA-4RB8MD | 2 Clarke St
AYCA-4RJS2D | 5 Edge St, Boolaroo, NSW- 2284
AYCA-4RS6QG | 31 William Street Alexandria, NSW 2015
AYCA-4SBJVB | 9-11 SWINSON ROAD BLACKTOWN, NSW 2148
AYCA-4SM3QD | Melrose St and Belmore Road (Lorn 6 lots)
AYCA-4SRFAN | ALDI Store Development, Balgowlah
AYCA-4SRFAN | ALDI Store Development, Balgowlah - INTERNAL
AYCA-4T7JU2 | 13 Dudley Avenue, Caringbah South
AYCA-4T8B52 | 3 Edwards Road, Box Hill, NSW- 2765
AYCA-4UE5JN | 46-48 Beaumont St
AYCA-4ULUDH | 5-7 Higherdale Ave., Miranda
AYCA-4UMUPA | 21 Fairway Drive, Kellyville
AYCA-4VFYJV | 27-37 Percy St, Bankstown
AYCA-4VH4MG | 36 Barber Ave, Penrith, NSW- 2750
AYCA-4VJFPP | 19-21 Eve Street
AYCA-4VSW7K | 10-12 Vista St, Penrith, NSW- 2750
AYCA-4W3F0S | 51-53 Foxall Road, Kellyville
AYCA-4W57Z3 | 11-17 Cross St Bankstown, NSW 2200
AYCA-4W844H | 18A Grey Gum Rd, Denman, NSW 2328
AYCA-4WLRNG | 51-53 Foxall road,Kellyville NSW 2155
AYCA-4WQIL0 | 13-15 Vista St, Penrith, NSW 2750
AYCA-4X6TWU | 43-47 Harrow Road - Omar Mosque - EXTERNAL
AYCA-4X6TWU | 43-47 Harrow Road - Omar Mosque - INTERNAL
AYCA-4XC850 | 50-54 Rodley Ave, Penrith, NSW 2750
AYCA-4XR9F8 | 320 Annangrove Rd, Rouse Hill, NSW- 2155
AYCA-4YHOA0 | 8-12 Robilliard St, Mays Hill, NSW 2145
AYCA-4YJULB | 479 Henry Lawson Drive - INTERNAL
AYCA-4Z4FSB | Mainfreight Logistics - 36B Kookaburra Rd N
AYCA-4Z6R8L | 148-160 King St, Sydney, NSW- 2000
AYCA-4Z992M | 2A Napier St and 17 Blue Hills Ave Goonellabah
AYCA-50FP2M | d
AYCA-51V8JL | 11 Thomas Mitchell Drive Muswellbrook NSW 2333
AYCA-52OEM0 | 33 Darley Street East, Mona Vale
AYCA-52UVXU | The Christian, Strathfield South
AYCA-52VCLT | Annandale Place - 1 -
AYCA-52ZO0L | 32 Norval Street - EXTERNAL
AYCA-52ZO0L | 32 Norval Street - INTERNAL
AYCA-54N6L7 | 104-108 Bridge Road, Westmead, NSW 2145
AYCA-54OULE | 71 Hill Rd, Lurnea
AYCA-54WJL3 | Andrews Road , Cranebrook, NSW, 2749
AYCA-5576QH | Ghersi Avenue, Wamberal
AYCA-55AQIZ | 3 Mungo Scott Place, Summer Hill, NSW 2130
AYCA-55AZ5J | 2 Smith st, Summer Hill, NSW 2130
AYCA-55JR8W | 228 King Street, Newtown, NSW- 2042
AYCA-55KUFO | 31 Bay Road Taren Point NSW 2229
AYCA-55RMFH | 1521 The Horsley Dr, Abbotsbury, NSW- 2176
AYCA-55XM3V | 10-12 Roger St, Brookvale, NSW,2100
AYCA-55ZVL2 | 45 Foxall Road, Kellyville
AYCA-562Y8R | 900 Wilton Rd, Appin NSW
AYCA-56B97M | 1 Tangerine St, Fairfield East
AYCA-56I886 | Cecil Ash - 47 Cecil St, Ashfield
AYCA-56PJ6I | 645 Pacific Hwy, Kanwal, NSW- 2259
AYCA-56YY5F | 120-122 Hume Highway, Canley Vale NSW
AYCA-56Z0PS | 37-49 O'Connor Street Chippendale
AYCA-577BDS | 36 Huntingwood Drive Huntingwood - INTERNAL
AYCA-57JCRY | 27a, 31, 33 & 35 Louis Street,Granville, NSW 2142
AYCA-57KT5A | 153 Jamison Rd, Penrith
AYCA-57Y4AJ | 2140 Camden Valley Way
AYCA-583XDD | 117-119 Jamison Rd South Penrith NSW 2750
AYCA-58BKNK | 4 Junction St, Ryde - QUBE
AYCA-59CA2X | 13 Stafford St, Kingswood, NSW- 2747
AYCA-5A2Y34 | 100 George Street, East Maitland
AYCA-5AVN4W | 23-25 Forest Grove, Epping
AYCA-5AXHNZ | 4 Murray Rose Ave, Sydney Olympic Park, NSW, 2127
AYCA-5BOGUB | 11B Lachlan St, Waterloo, NSW 2017- Externals
AYCA-5BOGUB | 11B Lachlan St Waterloo NSW 2017 - Internals
AYCA-5BXBTE | 41 Langer Ave, Caringbah
AYCA-5CMO2F | 6 Parish Dr, Beresfield, NSW- 2322
AYCA-5CQHIP | 24 Barber Ave, Penrith, NSW 2750
AYCA-5CYZU8 | 12 Highgate Circuit, Kellyville, NSW 2155
AYCA-5D2DU0 | Lot 65 Shorebreak Crescent Lake Cathie, NSW 2445
AYCA-5D4EG4 | 8 Totness Court, Castle Hill NSW 2154
AYCA-5DL8UH | Boland Drive, Moree
AYCA-5DPOWN | 13 Technology Drive, Appin - EXTERNAL
AYCA-5DPOWN | 13 Technology Drive, Appin - INTERNAL
AYCA-5DVB9M | 4 Magdalene Terrace, Wolli Creek, NSW 2205
AYCA-5E4D09 | 2-6 Dolerite Way Pemulwuy NSW 2145
AYCA-5EJRTN | 31-31A Perry St, Campsie
AYCA-5ETO6E | 4 Jack Smyth Drive, Hillvue
AYCA-5F0TZX | 6 Bangalley Way, Avalon Beach, NSW- 2107
AYCA-5FCHOB | 23 Grahams Hill Road, Narellan
AYCA-5FCMYJ | 117 Rookwood Road, Yagoona
AYCA-5FE5LS | 50 Hoxton Park Road, Liverpool, NSW- 2170
AYCA-5FJLCJ | 476 Macleay Valley Way, South Kempsey, NSW, 2440
AYCA-5G1AHP | 2-14 Amelia Street, Waterloo -
AYCA-5GPSWE | 100A- 100B Northcote Street, Canterbury
AYCA-5GWBTB | 4 Davies Place, Picton
AYCA-5HY3IQ | 1 Stratheden Street, Kyogle
AYCA-5IOF6P | 120 Hume Highway, Chullora
AYCA-5IWI3A | 26 Queen Street, Stockton
AYCA-5JO5XA | 5-9 White Avenue, Bankstown
AYCA-5JYO3A | 1B Maddox Street, Alexandria NSW 2015
AYCA-5K2YBV | 65 Victoria Street Coffs Harbour, NSW 2450, Victoria Terrace
AYCA-5KDIAQ | 67 Newleaf Parade, Bonnyrigg NSW 2177
AYCA-5KPEKH | Olive Hill Drvie Cobbitty NSW 2570
AYCA-5L49UP | 4 Water Street, Wentworthville NSW 2145
AYCA-5LZJ26 | 72 Canterbury Road, Bankstown , NSW2200
AYCA-5M4R4N | 76 Irwin Street, Werrington NSW 2747
AYCA-5M84RG | 72 Boultwood Street, Coffs Harbour, NSW 2450
AYCA-5MG99P | 593 Old Illawarra Road, Menai NSW 2234
AYCA-5MG99P | 593 Old Illawarra Road Menai NSW 2234
AYCA-5MGOY8 | 589 Old Illawarra Road, Menai NSW 2234
AYCA-5MGOY8 | 589 Old Illawarra Road Menai NSW 2234
AYCA-5MHAO7 | Site 18, Dawn Fraser Avenue Sydney Olympic Park, NSW 2127
AYCA-5ML96W | 24 Blackwood Avenue Casula NSW 2170
AYCA-5ML96W | 24 Blackwood Avenue Casula NSW 2170
AYCA-5MNUDQ | 221 Queen Street Beaconsfield NSW 2015
AYCA-5MWJQ4 | 222 Wallace St Macksville
AYCA-5N0IF2 | 30 Park Ave Coffs Harbour NSW 2450
AYCA-5NB7OP | 83 Redhead Road, Redhead, NSW, 2290
AYCA-5NM0LP | 118 Burwood Road, Croydon Park NSW 2133
AYCA-5NXLZB | 158 Terrigal Drive, Terrigal , NSW 2260
AYCA-5PBMZD | 14 SALISBURY ST URALLA NSW 2358
AYCA-5PIMJX | 36A Park Road, Naremburn, NSW 2065
AYCA-5QX4TH | 164 Cathedral Street, Woolloomooloo, NSW 2011
AYCA-5SX5PK | 51-55 Burraneer Bay Road, Burraneer, NSW 2230
AYCA-5T1531 | 293 Princes Highway, Saint Peters, NSW 2044
AYCA-5WOZHL | 18 Rawson Road, South Wentworthville, NSW 2145
AYCA-EV5EP | Smiths Lane Wongawilli NSW 2530
AYCA-5K1HTP | 18 Gibbons Street, Auburn NSW 2144
AYCA-60KQLM | 44A Foveaux Street, Surry Hills NSW
AYCA-5E4D09 | 2-6 Dolerite Way, Pemulwuy NSW 2145
AYCA-5T1531 | 293 Princes Highway, Saint Peters, NSW 2044
AYCA-Y8UNL | Belmore Street Burwood, NSW 2134
AYCA-5L4YBN | 13a Locosi Street, Schofields
AYCA-3O8ECI | 170-178 Bondi Road, Bondi
AYCA-36XIQO | 9 Fairway Drive, Kellyville
AYCA-5QVLJR | 60 Veron Street, Wentwothville
AYCA-5218CU | 1- Springbrook Boulevarde
AYCA-3T5IJK | 58 George Street, Box Hill
AYCA-5TDQG3 | 20-22 Craig Street, Punchbowl

## EFSCD Data
Request ID | Name | Application Name | Active Status | Application Status | No. of Premises | Technology Deployed | State | Suburb | Address | Post Code | Finance Project Number | Build Type(s) | Estimated First Service Connection Date
AYCA-4PPBEB | 2RYD-63 | Opal Fernleigh - 1 | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | West Ryde | 8 Sherbrooke Rd | 2114 | 178592 | B + E | 2020-03-04
AYCA-3W384B | 2HOR-62 | 433-437 Pacific Highway, Asquith - 1 | Active | Supply Order Raised | 38 | FTTP – Type 2 | NSW | Asquith | 433-437 Pacific Hwy | 2077 | 153443 | B + E | 2020-02-07
AYCA-4Z6R8L | 2DAL-28 | GALILEO PHILLIP STREET JV - 1 | Active | Supply Order Raised | 120 | FTTP – Type 2 | NSW | Sydney | 148-160 King Street | 2000 | 183239 | B + E | 2020-01-31
AYCA-5CQHIP | 2PTH-02 | 24 Barber Ave, Penrith - 1 | Active | Supply Order Raised | 17 | FTTP – Type 2 | NSW | Penrith | 24 Barber Ave | 2750 | 183570 | B + E | 2019-11-19
AYCA-Y8UNL | 2BUR-03 | Burwood Grand - 1 | Active | Supply Order Raised | 535 | FTTP – Type 2 | NSW | Burwood | Belmore Street | 2134 | 189068 | B + E | 2019-09-14
AYCA-54WJL3 | 2PTH-09 | 111 Andrews Road - 1 | Active | Supply Order Raised | 19 | FTTP – Type 3 (MT-LFN) | NSW | Cranebrook | 111 Andrews Rd | 2749 | 180973 | B + E | 2019-09-06
AYCA-4WGB20 | 2STL-60 | 64-66 Chandos St - 1 | Active | Supply Order Raised | 35 | FTTP – Type 2 | NSW | St Leonards | 64-66 Chandos St | 2065 | 186258 | B + E | 2019-07-31
AYCA-54OULE | 2MIL-62 | HILL ROAD LURNEA - 1 | Active | Supply Order Raised | 27 | FTTP – Type 2 | NSW | Lurnea | 71 Hill Rd | 2170 | 186260 | B + E | 2019-07-31
AYCA-4ND19Q | 2ROC-22 | Chapel Street Rockdale - 1 | Active | Supply Order Raised | 128 | FTTP – Type 2 | NSW | Rockdale | 15-21A Bay St | 2216 | 173014 | B + E | 2019-07-20
AYCA-3O1ZGP | 2GBE-62 | Cowper Apartments - 1 | Active | Supply Order Raised | 148 | FTTP – Type 2 | NSW | Glebe | 4-6 Elger St | 2037 | 165968 | B + E | 2019-07-19
AYCA-55RMFH | 2WET-23 | Novella Function Centre - 1 | Active | Supply Order Raised | 5 | FTTP – Type 3 (MT-LFN) | NSW | Abbotsbury | 1521 The Horsley Dr | 2176 | 181730 | B + E | 2019-06-30
AYCA-26KP9Q | 2ROU-02 | Site-36 cnr site Rouse Hill Town Centre | Active | Supply Order Raised | 58 | FTTP – Type 2 | NSW | Rouse Hill | Caddies Boulevard & White Hart Drive | 2155 | 154363 | B + E | 2019-06-14
AYCA-4IIZWC | 2STL-60 | Edge 28 - 1 | Active | Supply Order Raised | 53 | FTTP – Type 2 | NSW | St Leonards | 28 Albany St | 2065 | 176827 | B + E | 2019-06-07
AYCA-1XN8L5 | 2KEL-07 | 2B Hector Court Kellyville - 1 | Active | Supply Order Raised | 59 | FTTP – Type 2 | NSW | Kellyville | 9 Affleck Circuit | 2155 | 175901 | B + E | 2019-06-03
AYCA-56Z0PS | 2HMK-02 | 37 - 49 O'Connor street, Chippendale NSW | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Chippendale | 37-49 O'Connor St | 2008 | 180746 | B + E | 2019-06-03
AYCA-30GQWB | 2ROU-02 | Kellyville Apartments Withers Rd - 1 | Active | Supply Order Raised | 80 | FTTP – Type 2 | NSW | Kellyville | 16-20 Withers Rd | 2155 | 162079 | B + E | 2019-06-01
AYCA-4PEEEK | 2RYD-63 | Ryedale - 1 | Active | Supply Order Raised | 45 | FTTP – Type 2 | NSW | West Ryde | 17-21 Ryedale Rd | 2114 | 174486 | B + E | 2019-05-31
AYCA-4WQIL0 | 2PTH-05 | City Vista Apartments - 1 | Active | Supply Order Raised | 28 | FTTP – Type 2 | NSW | Penrith | 13-15 Vista St | 2750 | 181149 | B + E | 2019-05-31
AYCA-4VSW7K | 2PTH-05 | Vista Apartments - 1 | Active | Supply Order Raised | 82 | FTTP – Type 2 | NSW | Penrith | 10-12 Vista St | 2750 | 181268 | B + E | 2019-05-25
AYCA-3CIGB0 | 2WRO-63 | 1/3 Balmoral Street Residential Developm | Active | Supply Order Raised | 44 | FTTP – Type 2 | NSW | Waitara | 1-3 Balmoral St | 2077 | 159280 | B + E | 2019-05-24
AYCA-5M5US3 | 2BTH-02 | Wark Parade - 2 SP2 | Active | Supply Order Raised | 3 |  | NSW | Windradyne | 1 Wark Parade | 2795 | 189701 | E | 2019-05-24
AYCA-4X1Z9M | 2MIR-26 | Mooki St - 1 | Active | Supply Order Raised | 6 | FTTP – Type 3 (MT-LFN) | NSW | Miranda | 58/60 Karimbla Rd | 2228 | 173160 | B + E | 2019-05-15
AYCA-24QAXK | 2ROC-03 | 10 Martin Ave Arncliffe - 1 & 2 | Active | Supply Order Raised | 159 | FTTP – Type 2 | NSW | Arncliffe | 10 Martin Avenue | 2205 | 131592 | B + E | 2019-05-10
AYCA-48S696 | 2BLK-03 | C.J.T. Pty Ltd - 1 | Active | Supply Order Raised | 34 | FTTP – Type 2 | NSW | Blacktown | 3-7 Wallace St | 2148 | 156711 | B + E | 2019-05-04
AYCA-4BA1DQ | 2SEF-01 | Hillside - 1 | Active | Supply Order Raised | 24 | FTTP – Type 2 | NSW | Potts Hill | 3 Rowe Drive | 2143 | 158801 | B + E | 2019-05-04
AYCA-5KIP6Y | 2WLG-07 | 45 Rosemont Street, West Wollongong NSW | Active | Supply Order Raised | 4 | FTTP – Type 2 | NSW | West Wollongong | 45 Rosemont Street | 2500 | 187104 | B + E | 2019-05-03
AYCA-5SX5PK | 2CRO-23 | 51-55 Burraneer Bay Road, Burraneer - 1 | Active | Supply Order Raised | 14 | FTTP – Type 3 (MT-LFN) | NSW | Burraneer | 51-55 Burraneer Bay Road | 2230 | 192514 | B + E | 2019-05-01
AYCA-2L9FVY | 2HOR-02 | Hornsby - 1 | Active | Supply Order Raised | 111 | FTTP – Type 2 | NSW | Hornsby | 117-119 Pacific Hwy | 2077 | 175977 | B + E | 2019-04-30
AYCA-3S7B4B | 2HMK-02 | BUILDING 2 (CB02) - 1 | Active | Supply Order Raised | 12 | FTTP – Type 2 | NSW | Ultimo | University of Technology Sydney Building 1 15 Broadway, | 2007 | 183941 | B + E | 2019-04-30
AYCA-4LT337 | 2WET-23 | 457-463 Victoria street - 1 | Active | Supply Order Raised | 32 | FTTP – Type 3 (MT-LFN) | NSW | Wetherill Park | 457-463 Victoria Street | 2164 | 174364 | B + E | 2019-04-30
AYCA-4QDZCA | 2STL-61 | The Hume - 1 | Active | Supply Order Raised | 39 | FTTP – Type 2 | NSW | Crows Nest | 31-33 Albany St | 2065 | 174992 | B + E | 2019-04-30
AYCA-3O2CEB | 2GBE-62 | Cowper Street Apartments - 1 | Active | Supply Order Raised | 98 | FTTP – Type 2 | NSW | Glebe | 5 Elger St | 2037 | 165101 | B + E | 2019-04-26
AYCA-58PGFK | 2MSV-03 | 4 NEW FREESTANDING VILLAS - 25 Ascot Rd | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Bowral | 25 Ascot Rd | 2576 | 184634 | B + E | 2019-04-26
AYCA-5OO3VM | 2WLG-01 | 2 Victoria Street, Wollongong - 2 | Active | Supply Order Raised | 5 | FTTP – Type 2 | NSW | Wollongong | 2 Victoria Street | 2500 | 190382 | B + E | 2019-04-16
AYCA-57JCRY | 2GRA-63 | Maria's - 1 | Active | Supply Order Raised | 22 | FTTP – Type 2 | NSW | Granville | 27a, 31, 33 & 35 Louis Street | 2142 | 192892 | B + E | 2019-04-15
AYCA-4H9191 | 2COR-03 | 208-210 Princes Highway - 1 | Active | Supply Order Raised | 7 | FTTP – Type 2 | NSW | Bulli | 208-210 Princes Highway | 2516 | 162471 | B + E | 2019-04-12
AYCA-21PVTM | 2BLK-03 | One Seven - 1 | Active | Supply Order Raised | 146 | FTTP – Type 2 | NSW | Blacktown | 5 Second Avenue | 2148 | 162095 | B + E | 2019-04-06
AYCA-4H8EZO | 2HUH-22 | 117 VICTORIA ROAD - 1 | Active | Supply Order Raised | 29 | FTTP – Type 2 | NSW | Gladesville | 117-123 Victoria Rd | 2111 | 178782 | B + E | 2019-04-05
AYCA-4OCM1V | 2UND-60 | 260-264 Wardell Rd, Marrickville - 1 | Active | Supply Order Raised | 26 | FTTP – Type 2 | NSW | Marrickville | 260-264 Wardell Rd | 2204 | 169909 | B + E | 2019-04-05
AYCA-5HNMQ4 | 2CRO-26 | 2 - 4 Marlo Road, Cronulla - 1 | Active | Supply Order Raised | 10 | FTTP – Type 3 (MT-LFN) | NSW | Cronulla | 2 - 4 Marlo Road | 2230 | 186195 | B + E | 2019-04-05
AYCA-5M5JQ0 | 2HUH-21 | 23A Mars Road, Lane Cove West - 1 | Active | Supply Order Raised | 24 | FTTP – Type 2 | NSW | Lane Cove West | 23A Mars Road | 2066 | 189817 | B + E | 2019-04-05
AYCA-5NXLZB | 2TGL-02 | 158 Terrigal Drive, Terrigal - 1 | Active | Supply Order Raised | 67 | FTTP – Type 2 | NSW | Terrigal | 158 Terrigal Drive | 2260 | 190322 | B + E | 2019-04-05
AYCA-2QFUTJ | 2NRL-20 | Camden Day Hospital - 1 | Active | Supply Order Raised | 5 | FTTN | NSW | Elderslie | 37 Hilder St | 2570 | 156078 | B + E | 2019-04-01
AYCA-328OYF | 2CBT-05 | Aspire Apartments - 1 | Active | Supply Order Raised | 73 | FTTP – Type 2 | NSW | Campbelltown | 37-41 Chamberlain St | 2560 | 165436 | B + E | 2019-04-01
AYCA-4JW63S | 2CRO-21 | Dingle Apartment - 1 | Active | Supply Order Raised | 34 | FTTP – Type 2 | NSW | Cronulla | 25-29 Tonkin St | 2230 | 167015 | B + E | 2019-04-01
AYCA-4LZWVS | 2PNN-63 | Zantia - 1 | Active | Supply Order Raised | 65 | FTTP – Type 2 | NSW | Thornleigh | 266-268 Pennant Hills Rd | 2120 | 177796 | B + E | 2019-04-01
AYCA-3E5O97 | 2ROU-03 | Hancy - 1 | Active | Supply Order Raised | 47 | FTTP – Type 2 | NSW | Kellyville | 85-89 Samantha Riley Dr | 2155 | 162040 | B + E | 2019-03-31
AYCA-2V9V2D | 2HOR-63 | Cowan Road Residential Development - 1 | Active | Supply Order Raised | 50 | FTTP – Type 2 | NSW | Mount Colah | 2 Cowan Road & 540A-542 Pacific Highway | 2079 | 157215 | B + E | 2019-03-29
AYCA-4DW3WX | 2HOR-62 | 18-22 Lords Avenue, Asquith - 1 | Active | Supply Order Raised | 98 | FTTP – Type 2 | NSW | Asquith | 18-22 Lords Ave + 421-425 Pacific Hwy | 2077 | 160203 | B + E | 2019-03-29
AYCA-4UF84M | 2LIV-04 | Spectra Residence - 1 | Active | Supply Order Raised | 41 | FTTP – Type 2 | NSW | Liverpool | 52 Copeland Street | 2170 | 172867 | B + E | 2019-03-29
AYCA-5M84RG | 2CFS-02 | 72 Boultwood Street, Coffs Harbour - 1 | Active | Supply Order Raised | 7 | FTTP – Type 2 | NSW | Coffs Harbour | 72 Boultwood Street | 2450 | 189188 | B + E | 2019-03-29
AYCA-55JR8W | 2NEW-21 | 228 King Street, Newtown - 1 | Active | Supply Order Raised | 9 | FTTP – Type 3 (MT-LFN) | NSW | Newtown | 228 King St | 2042 | 185177 | B + E | 2019-03-25
AYCA-42HX6R | 2BON-61 | Bondi Central - 1 | Active | Supply Order Raised | 126 | FTTP – Type 2 | NSW | Bondi Junction | 34-42 Spring St | 2022 | 166951 | B + E | 2019-03-23
AYCA-47OO3O | 2LIV-03 | 188-190 Moore St Liverpool - 1 | Active | Supply Order Raised | 25 | FTTP – Type 2 | NSW | Liverpool | 188-190 Moore St | 2170 | 158978 | B + E | 2019-03-23
AYCA-578FAA | 2NSY-02 | 229 MILLER STREET, NORTH SYDNEY NSW 2060 | Active | Supply Order Raised | 109 | FTTP – Type 2 | NSW | North Sydney | 229 Miller Street | 2060 | 184960 | B + E | 2019-03-23
AYCA-2I98H3 | 2PAR-61 | Hassall View Pty Ltd - 1 | Active | Supply Order Raised | 153 | FTTP – Type 2 | NSW | Harris Park | 113-117A Wigram St 23-29 Hassall St | 2150 | 162098 | B + E | 2019-03-22
AYCA-4PRYRR | 2PAR-63 | 161-163 Great Western Hwy, Mays Hill - 1 | Active | Supply Order Raised | 22 | FTTP – Type 2 | NSW | Mays Hill | 161-163 Great Western Hwy | 2145 | 186986 | B + E | 2019-03-22
AYCA-5I8I8D | 2PNN-63 | 27-31 Thornleigh Street, Thornleigh - 1 | Active | Supply Order Raised | 32 | FTTP – Type 2 | NSW | Thornleigh | 27-31 Thornleigh Street | 2120 | 186277 | B + E | 2019-03-22
AYCA-5N4NUW | 2HBD-23 | 36 Wyndora Avenue, Freshwater NSW 2096, | Active | Supply Order Raised | 15 | FTTP – Type 2 | NSW | Freshwater | 36 Wyndora Avenue | 2096 | 189737 | B + E | 2019-03-22
AYCA-4YHOA0 | 2PAR-63 | 8 Robilliard St - 1 | Active | Supply Order Raised | 39 | FTTP – Type 2 | NSW | Mays Hill | 8-12 Robilliard St | 2145 | 183393 | B + E | 2019-03-16
AYCA-4C0Z5Y | 2ROS-66 | Hamptons - Rose Bay - 1 | Active | Supply Order Raised | 30 | FTTP – Type 3 (MT-LFN) | NSW | Rose Bay | 554-564 Old South Head Rd | 2029 | 161934 | B + E | 2019-03-15
AYCA-5UQX4I | 2HUH-20 | 29 Moorefield Avenue, Hunters Hill NSW 2 | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Hunters Hill | 29 Moorefield Avenue | 2110 | 193551 | B + E | 2019-03-11
AYCA-42N8QF | 2PEN-67 | Macklin 38 - 1 | Active | Supply Order Raised | 16 | FTTP – Type 2 | NSW | Pendle Hill | 38-40 Macklin Street | 2145 | 161792 | B + E | 2019-03-08
AYCA-4L1IJG | 2SWR-20 | 19 Gregory Street - 1 | Active | Supply Order Raised | 12 | FTTP – Type 2 | NSW | South West Rocks | 19 Gregory St | 2431 | 166953 | A + E | 2019-03-08
AYCA-54N6L7 | 2PAR-60 | Westmead - 1 | Active | Supply Order Raised | 30 | FTTP – Type 2 | NSW | Westmead | 104-108 Bridge Rd | 2145 | 192206 | B + E | 2019-03-08
AYCA-5FILA6 | 2BOW-20 | 12 Marsden Street, Boorowa - 0 | Active | Supply Order Raised | 2 | FTTN | NSW | Boorowa | 12 Marsden Street | 2586 | 185210 | B + E | 2019-03-08
AYCA-40TCKL | 2NSY-02 | The Miller, North Sydney - 1 | Active | Supply Order Raised | 180 | FTTP – Type 2 | NSW | North Sydney | 221 Miller St | 2060 | 159347 | B + E | 2019-03-04
AYCA-3GG3CO | 2MIR-31 | Dianella St - 1 | Active | Supply Order Raised | 64 | FTTP – Type 2 | NSW | Caringbah | 1-13 Dianella St | 2229 | 190218 | B + E | 2019-03-02
AYCA-4ULUDH | 2MIR-26 | 5-7 Higherdale Ave., Miranda - 1 | Active | Supply Order Raised | 38 | FTTP – Type 2 | NSW | Miranda | 5-7 Higherdale Ave | 2228 | 191983 | B + E | 2019-03-02
AYCA-43APKG | 2HOM-20 | A & G Formworkers ( Australia) Pty Ltd - | Active | Supply Order Raised | 1 | FTTP – Type 3 (MT-LFN) | NSW | Strathfield South | 6-14 Cosgrove Road | 2136 | 164826 | B + E | 2019-03-01
AYCA-5JIMDQ | 2DBB-02 | 166 Brisbane Street, Dubbo - 1 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Dubbo | 166 Brisbane Street | 2830 | 192244 | B + E | 2019-03-01
AYCA-1SQ3K5 | 2PAR-01 | 189 Macquarie Street - SP1 | Active | Supply Order Raised | 21 | FTTP – Type 2 | NSW | Parramatta | 189 Macquarie Street | 2150 | 156064 | B + E | 2019-02-28
AYCA-3JJIX9 | 2MIR-28 | Pinnacle - 1 | Active | Supply Order Raised | 137 | FTTP – Type 2 | NSW | Miranda | 13-21 Univerity Rd & 1-5 Pinnacle St | 2228 | 154312 | B + E | 2019-02-28
AYCA-48OYT0 | 2EDG-65 | 240 New South Head Road, Edgecliff NSW - | Active | Supply Order Raised | 22 | FTTP – Type 2 | NSW | Edgecliff | 240 New South Head Rd | 2027 | 161415 | B + E | 2019-02-28
AYCA-4DBFGM | 2NEW-20 | 87 Parramatta Road, Camperdown - 1 | Active | Supply Order Raised | 19 | FTTP – Type 2 | NSW | Camperdown | 87 Parramatta Rd | 2050 | 164021 | B + E | 2019-02-28
AYCA-4NNOGX | 2PTH-02 | 240-250 Great Western Highway - 1 | Active | Supply Order Raised | 122 | FTTP – Type 2 | NSW | Kingswood | 240-250 Great Western Hwy | 2747 | 165991 | B + E | 2019-02-28
AYCA-4UE5JN | 2LID-03 | Auburn 46-48 Beaumont St - 1 | Active | Supply Order Raised | 8 | FTTP – Type 2 | NSW | Auburn | 46-48 Beaumont Street | 2144 | 172204 | B + E | 2019-02-28
AYCA-4XR9F8 | 2ROU-02 | North West Business Centre - 1 | Active | Supply Order Raised | 23 | FTTP – Type 3 (MT-LFN) | NSW | Rouse Hill | 320 Annangrove Rd | 2155 | 181574 | B + E | 2019-02-28
AYCA-55XM3V | 2HBD-20 | Venus Apartments - 1 | Active | Supply Order Raised | 20 | FTTP – Type 2 | NSW | Brookvale | 10-12 Roger St | 2100 | 184254 | B + E | 2019-02-28
AYCA-5BOGUQ | 2PYM-61 | 6 Womerah St, Turramurra - 1 | Active | Supply Order Raised | 18 | FTTP – Type 2 | NSW | Turramurra | 2-6 Womerah St | 2074 | 184657 | B + E | 2019-02-28
AYCA-5DHKDD | 2CRO-22 | 36 Rawson Parade, Caringbah South NSW 22 | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Caringbah South | 36 Rawson Parade | 2229 | 184668 | B + E | 2019-02-28
AYCA-5LC14Q | 2NSY-21 | 100 Mount Street, North Sydney - 1 | Active | Supply Order Raised | 39 | FTTP – Type 2 | NSW | North Sydney | 100 Mount Street | 2060 | 190430 | B + E | 2019-02-28
AYCA-2LCFXK | 2BUR-65 | Skyview - 1 | Active | Supply Order Raised | 21 | FTTP – Type 2 | NSW | Enfield | 248-252 Liverpool Rd | 2136 | 189317 | B + E | 2019-02-22
AYCA-41FBT3 | 2NSY-02 | North - 1 | Active | Supply Order Raised | 67 | FTTP – Type 2 | NSW | North Sydney | 231 Miller St | 2060 | 164899 | B + E | 2019-02-22
AYCA-56PJ6I | 2GRK-01 | Tuggerah Lakes Hospital - 1 | Active | Supply Order Raised | 8 | FTTP – Type 3 (MT-LFN) | NSW | Kanwal | 645 Pacific Hwy | 2259 | 181075 | B + E | 2019-02-22
AYCA-5BOGUB | 2RED-01 | 11B Lachlan St, Waterloo - 1 | Active | Supply Order Raised | 67 | FTTP – Type 2 | NSW | Waterloo | 11B Lachlan St | 2017 | 190109 | B + E | 2019-02-22
AYCA-5CMO2F | 2TAR-01 | 6 Parish Dr, Beresfield - 1 | Active | Supply Order Raised | 10 | FTTP – Type 2 | NSW | Beresfield | 6 Parish Dr | 2322 | 184658 | B + E | 2019-02-22
AYCA-5F1MOI | 2MSV-03 | Martha Street, Bowral - 1 | Active | Supply Order Raised | 24 | FTTP – Type 3 (MT-LFN) | NSW | Bowral | 1 Martha Street | 2576 | 187273 | B + E | 2019-02-22
AYCA-5K2YBV | 2CFS-03 | Victoria Terrace - 1 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Coffs Harbour | 65 Victoria Street | 2450 | 189909 | B + E | 2019-02-22
AYCA-3D0J11 | 2ROC-02 | Aspect - 1 | Active | Supply Order Raised | 90 | FTTP – Type 2 | NSW | Wolli Creek | 15-21 Willis St | 2205 | 153465 | B + E | 2019-02-18
AYCA-52VCLT | 2NEW-20 | Annandale Place - 1 | Active | Supply Order Raised | 36 | FTTP – Type 2 | NSW | Annandale | 33-53 Nelson St | 2038 | 183400 | B + E | 2019-02-16
AYCA-55AQIZ | 2ASH-63 | Summer Hill Flour Mill - 3 Bld 3AB &3CD | Active | Supply Order Raised | 143 | FTTP – Type 2 | NSW | Summer Hill | 3 Mungo Scott Place | 2130 | 183404 | B + E | 2019-02-16
AYCA-4L3R6E | 2MIR-26 | VENTURA AVE - 1 | Active | Supply Order Raised | 9 | FTTP – Type 3 (MT-LFN) | NSW | Miranda | 4-6 Ventura Ave | 2228 | 166399 | B + E | 2019-02-15
AYCA-4P3YPZ | 2BAN-67 | Chapel Road Studios - 1 | Active | Supply Order Raised | 5 | FTTP – Type 2 | NSW | Bankstown | 107 Chapel Road South | 2200 | 186254 | B + E | 2019-02-15
AYCA-4X6TWU | 2LID-08 | Omar Mosque - final stages | Active | Supply Order Raised | 2 | FTTP – Type 2 | NSW | Auburn | 43-47 Harrow Rd | 2144 | 177336 | B + E | 2019-02-15
AYCA-5A2Y34 | 2MAI-03 | 100 George St, East Maitland NSW 2323, A | Active | Supply Order Raised | 1 | FTTP – Type 2 | NSW | East Maitland | 100 George Street | 2323 | 181918 | B + E | 2019-02-15
AYCA-397TA7 | 2TGL-02 | Aria Terrigal - Building 1 - 1 | Active | Supply Order Raised | 18 | FTTP – Type 2 | NSW | Terrigal | 6-8 Painters Lane | 2260 | 160792 | B + E | 2019-02-08
AYCA-5M7EQR | 2NWR-01 | 40 Basil Street, South Nowra - 1 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | South Nowra | 40 Basil Street | 2541 | 189340 | B + E | 2019-02-08
AYCA-57DG41 | 2BTH-01 | Opal Bathurst Aged Care Facility - 1 | Active | Supply Order Raised | 4 | FTTP – Type 2 | NSW | Bathurst | 93 Stanley St | 2795 | 180126 | B + E | 2019-02-07
AYCA-5RHH4X | 2PNN-68 | 68 Beecroft Road, Beecroft NSW 2119, Aus | Active | Supply Order Raised | 7 | FTTP – Type 3 (MT-LFN) | NSW | Beecroft | 68 Beecroft Road | 2119 | 192083 | B + E | 2019-02-05
AYCA-468RZY | 2LID-04 | 23 RAILWAY PARADE - 1 | Active | Supply Order Raised | 5 | FTTP – Type 2 | NSW | Lidcombe | 23 Railway Parade | 2141 | 156882 | B + E | 2019-02-04
AYCA-49DBF5 | 2CRO-21 | Pavilion Cronulla - 1 | Active | Supply Order Raised | 36 | FTTP – Type 2 | NSW | Cronulla | 33-39 Croydon St | 2230 | 161039 | B + E | 2019-02-04
AYCA-4VH4MG | 2PTH-02 | 36-38 Barber Ave, Penrith - 1 | Active | Supply Order Raised | 44 | FTTP – Type 2 | NSW | Penrith | 36 Barber Ave | 2750 | 180016 | B + E | 2019-02-04
AYCA-52OEM0 | 2MON-25 | 33 Darley Street - 1 | Active | Supply Order Raised | 5 | FTTP – Type 3 (MT-LFN) | NSW | Mona Vale | 33 Darley Street East | 2103 | 183201 | B + E | 2019-02-04
AYCA-3CFI3W | 2EPP-05 | 120 Herring Road - 1 | Active | Supply Order Raised | 200 | FTTP – Type 2 | NSW | Marsfield | 120 Herring Rd | 2122 | 147752 | B + E | 2019-02-02
AYCA-58BKNK | 2RYD-66 | QUBE - 1 | Active | Supply Order Raised | 42 | FTTP – Type 2 | NSW | Ryde | 2-6 Junction St | 2112 | 181672 | B + E | 2019-02-02
AYCA-5KDIAQ | 2ERP-60 | 67 Newleaf Parade, Bonnyrigg NSW 2177, A | Active | Supply Order Raised | 18 | FTTP – Type 3 (MT-LFN) | NSW | Bonnyrigg | 67 Newleaf Parade | 2177 | 189695 | B + E | 2019-02-02
AYCA-47STWW | 2CYS-11 | One30 Hyde Park - 1 | Active | Supply Order Raised | 150 | FTTP – Type 2 | NSW | Sydney | 130 Elizabeth St | 2000 | 161414 | B + E | 2019-02-01
AYCA-5G4WE4 | 2MON-20 | 1473 Pittwater Road, North Narrabeen - 4 | Active | Supply Order Raised | 13 | FTTP – Type 3 (MT-LFN) | NSW | North Narrabeen | 1473 Pittwater Road | 2101 | 187141 | B + E | 2019-02-01
AYCA-31DCKF | 2EAS-64 | Advanx Encore - 1 | Active | Supply Order Raised | 40 | FTTP – Type 2 | NSW | Darlinghurst | 18-20 Neild Ave | 2010 | 175959 | B + E | 2019-01-31
AYCA-35V4R1 | 2HOM-03 | 208-214 Parramatta Road Homebush - 1 | Active | Supply Order Raised | 155 | FTTP – Type 2 | NSW | Homebush | 208-214 Parramatta Rd | 2140 | 166378 | B + E | 2019-01-31
AYCA-3NFID7 | 2PTH-04 | Tench Ave Jamisontown - 1 | Active | Supply Order Raised | 13 | FTTP – Type 2 | NSW | Jamisontown | 78-88 Tench Ave | 2750 | 161033 | B + E | 2019-01-31
AYCA-4EZRCH | 2MIR-26 | 1-3 Higherdale Ave, Miranda - 1 | Active | Supply Order Raised | 68 | FTTP – Type 2 | NSW | Miranda | 1-3 Higherdale Ave | 2228 | 164024 | B + E | 2019-01-31
AYCA-5CXXCR | 2BTM-21 | 30 Golf Links Dr, Batemans Bay - 1 | Active | Supply Order Raised | 16 | FTTP – Type 2 | NSW | Batemans Bay | 30 Golf Links Drive | 2536 | 183798 | B + E | 2019-01-31
AYCA-5RXMK0 | 9QBN-08 | 96 Bayldon Road, Queanbeyan West - 1 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Queanbeyan West | 96 Bayldon Road | 2620 | 192282 | B + E | 2019-01-31
AYCA-56B97M | 2SEF-61 | 1 Tangerine Street Fairfield East | Active | Supply Order Raised | 18 | FTTP – Type 2 | NSW | Fairfield East | 1 Tangerine Street | 2165 | 183538 | B + E | 2019-01-30
AYCA-4UMUPA | 2KEL-07 | Department of Education - 1 | Active | Supply Order Raised | 3 | FTTP – Type 2 | NSW | Kellyville | 21 Fairway Dr | 2155 | 174997 | B + E | 2019-01-29
AYCA-49OZC4 | 2EAS-65 | 257 Oxford St - 1 | Active | Supply Order Raised | 19 | FTTP – Type 2 | NSW | Paddington | 257 Oxford Street | 2021 | 158732 | B + E | 2019-01-28
AYCA-5M4R4N | 2SHA-64 | 76 Irwin Street, Werrington NSW 2747, Au | Active | Supply Order Raised | 12 | FTTP – Type 3 (MT-LFN) | NSW | Werrington | 74-76 Irwin Street | 2747 | 188995 | B + E | 2019-01-28
AYCA-5MG99P | 2MEN-62 | 593 Old Illawarra Road, Menai NSW 2234, | Active | Supply Order Raised | 5 | FTTP – Type 3 (MT-LFN) | NSW | Menai | 593 Old Illawarra Road | 2234 | 189818 | B + E | 2019-01-28
AYCA-5MGOY8 | 2MEN-62 | 589 Old Illawarra Road, Menai NSW 2234, | Active | Supply Order Raised | 3 | FTTP – Type 3 (MT-LFN) | NSW | Menai | 591 Old Illawarra Road | 2234 | 189819 | B + E | 2019-01-28
AYCA-4YZGFK | 2PEN-66 | boronia st - 1 | Active | Supply Order Raised | 15 | FTTP – Type 3 (MT-LFN) | NSW | South Wentworthville | 51 Boronia St | 2145 | 177339 | B + E | 2019-01-25
AYCA-5NM0LP | 2BUR-65 | 118 Burwood Road, Croydon Park NSW 2133, | Active | Supply Order Raised | 12 | FTTP – Type 3 (MT-LFN) | NSW | Croydon Park | 118 Burwood Road | 2133 | 189216 | B + E | 2019-01-25
AYCA-4SRFAN | 2BAL-62 | ALDI Store Development - Balgowlah - 1 | Active | Supply Order Raised | 2 | FTTP – Type 3 (MT-LFN) | NSW | Balgowlah | 22/26 Roseberry St | 2093 | 175478 | B + E | 2019-01-22
AYCA-2RG791 | 2PEN-61 | Mixed Development - 1 | Active | Supply Order Raised | 59 | FTTP – Type 2 | NSW | Toongabbie | 15-19 Toongabbie Rd | 2146 | 187086 | B + E | 2019-01-19
AYCA-2XJBL7 | 2SIL-02 | Site 9 - 1 | Active | Supply Order Raised | 9 | FTTP – Type 2 | NSW | Sydney Olympic Park | 3 Olympic Blvd | 2127 | 160138 | B + E | 2019-01-18
AYCA-4EITU0 | 2LIV-02 | The Pinnacle - 100 Castlereagh Street - | Active | Supply Order Raised | 141 | FTTP – Type 2 | NSW | Liverpool | 10 Norfolk St | 2170 | 160664 | B + E | 2019-01-14
AYCA-57Y170 | 2BRY-01 | Morrow Building - 1 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Berry | 17 Hitchcocks Ln | 2535 | 181585 | B + E | 2019-01-14
AYCA-5MHAO7 | 2SIL-02 | NSWRL Centre of Excellence - 1 | Active | Supply Order Raised | 6 | FTTP – Type 3 (MT-LFN) | NSW | Sydney Olympic Park | Site 18, Dawn Fraser Avenue | 2127 | 190591 | B + E | 2019-01-14
AYCA-4LVG38 | 2MIL-20 | 9-11 Edgeworth Place, Cartwright - 1 | Active | Supply Order Raised | 31 | FTTP – Type 2 | NSW | Cartwright | 9-11 Edgeworth Pl | 2168 | 191504 | B + E | 2019-01-12
AYCA-4Q27NU | 2BRG-03 | Emerald Hills Retail Development - 2 | Active | Supply Order Raised | 20 | FTTP – Type 2 | NSW | Gledswood Hills | 50 Raby Rd | 2557 | 174487 | B + E | 2019-01-11
AYCA-54A0VP | 2PYM-62 | Charles Court - 1 | Active | Supply Order Raised | 17 | FTTP – Type 2 | NSW | Warrawee | 7 Cherry St | 2074 | 191031 | B + E | 2019-01-10
AYCA-4VJFPP | 2NEW-22 | 19-21 Eve St, Erskineville - 1 | Active | Supply Order Raised | 21 | FTTP – Type 2 | NSW | Erskineville | 19-21 Eve St | 2043 | 177334 | B + E | 2019-01-09
AYCA-45U68U | 2PTH-12 | VC7 - 1 | Active | Supply Order Raised | 40 | FTTP – Type 2 | NSW | Jordan Springs | 5 Cullen Avenue | 2747 | 181693 | B + E | 2019-01-07
AYCA-4PQO3D | 2EPP-62 | LUCILLE - 1 | Active | Supply Order Raised | 62 | FTTP – Type 2 | NSW | Epping | 12/6 Maida Rd | 2121 | 181696 | B + E | 2019-01-07
AYCA-4R1E3Q | 2PTH-02 | Home On High - 1 | Active | Supply Order Raised | 102 | FTTP – Type 2 | NSW | Penrith | 144-148 High Street & 35-37 Barber Avenue | 2750 | 176345 | B + E | 2018-12-21
AYCA-5DVB9M | 2ROC-02 | 4 Magdalene Terrace, Wolli Creek - 1 | Active | Supply Order Raised | 124 | FTTP – Type 2 | NSW | Wolli Creek | 4 Magdalene Terrace | 2205 | 186354 | B + E | 2018-12-21
AYCA-5FE5LS | 2LIV-03 | 46-50 Hoxton Park Road, Liverpool - 1 | Active | Supply Order Raised | 34 | FTTP – Type 2 | NSW | Liverpool | 46-50 Hoxton Park Road | 2170 | 185923 | B + E | 2018-12-20
AYCA-4CG9U4 | 2KNS-04 | 29-31 Dunning Avenue Rosebery - 1 | Active | Supply Order Raised | 32 | FTTP – Type 2 | NSW | Rosebery | 29-31 Dunning Ave | 2018 | 181955 | B + E | 2018-12-13
AYCA-5SK61D | 2NWR-03 | 38 Cumberland Avenue, South Nowra NSW 25 | Active | Supply Order Raised | 1 | FTTP – Type 2 | NSW | South Nowra | 39 Cumberland Avenue | 2541 | 192782 | B + E | 2018-12-05
AYCA-413Z64 | 2PAR-64 | THE DARCY - 1 | Active | Supply Order Raised | 37 | FTTP – Type 2 | NSW | Westmead | 2B Darcy Rd | 2145 | 155179 | B + E | 2018-11-30
AYCA-4NOC4P | 2MIR-22 | 40 Cawarra Road - 1 | Active | Supply Order Raised | 16 | FTTP – Type 2 | NSW | Caringbah | 40 Cawarra Road | 2229 | 181351 | B + E | 2018-11-30
AYCA-5PIMJX | 2STL-66 | 36A Park Road, Naremburn - 1 | Active | Supply Order Raised | 8 | FTTP – Type 3 (MT-LFN) | NSW | Naremburn | 36A Park Road | 2065 | 190629 | B + E | 2018-10-22
AYCA-5L49UP | 2PEN-64 | 4 Water Street, Wentworthville NSW 2145, | Active | Supply Order Raised | 11 | FTTP – Type 3 (MT-LFN) | NSW | Wentworthville | 4 Water Street | 2145 | 188325 | B + E | 2018-09-10
AYCA-5N0IF2 | 2CFS-03 | Non Standard Builds - 30 Park Ave Coffs | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Coffs Harbour | 30 Park Ave | 2450 | 188862 | B + E | 2018-08-22
AYCA-5MNUDQ | 2KNS-03 | Non Standard Builds - 221 Queen St Beaco | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Beaconsfield | 221 Queen Street | 2015 | 187150 | B + E | 2018-08-18
AYCA-5BXBTE | 2MIR-27 | 41 Langer Ave, Caringbah South NSW 2229, | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Caringbah South | 41 LANGER AVENUE | 2229 | 183789 | B + E | 2018-06-04
AYCA-5F1RYP | 2EDG-66 | 114 New South Head Road, Edgecliff - 1 | Active | Supply Order Raised | 7 | HFC | NSW | Edgecliff | 114 New South Head Road | 2027 | 183814 | B + E | 2018-06-01
AYCA-5FA5OM | 2MIR-24 | 4-6 Crammond Boulevard, Caringbah - 1 | Active | Supply Order Raised | 6 | FTTP – Type 3 (MT-LFN) | NSW | Caringbah | 4-6 Crammond Boulevard | 2229 | 184811 | B + E | 2018-06-01
AYCA-476RM9 | 2LIV-04 | Non Standard Builds - 87-91 Campbell St, | Active | Dev Transferred to Build | 76 |  | NSW | Liverpool | 87-91 Campbell St | 2170 | 159520 | B + E | 2017-02-15
AYCA-5JRURV | 9BLC-20 | 37 Belconnen Way, Weetangera - 1 | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | ACT | Weetangera | 37 Belconnen Way | 2614 | 188989 | B + E | 2019-01-21
AYCA-481ES7 | 2BTH-09 | Sitecar - 915 | Active | Supply Order Raised | 3 | FTTP – Type 3 (MT-LFN) | NSW | Bathurst | 65 George St | 2795 | 163663 | B + E | 2020-01-31
AYCA-41DSMK | 2ROU-03 | 49 Halloway - 3 | Active | Supply Order Raised | 1 | FTTP – Type 2 | NSW | Kellyville | 38 Hezlett Road | 2155 | 156718 | D | 2019-10-18
AYCA-41DY76 | 2ROU-03 | 49 Halloway - 2 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Kellyville | 38 Hezlett Road | 2155 | 156720 | D | 2019-10-18
AYCA-41DSOU | 2ROU-03 | 49 Halloway - 4 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Kellyville | 38 Hezlett Road | 2155 | 156719 | D | 2019-09-02
AYCA-4RJS2D | 2CHL-05 | High Point on Edge - 1 | Active | Supply Order Raised | 7 | FTTP – Type 3 (MT-LFN) | NSW | Boolaroo | 5 Edge St | 2284 | 168810 | B + D | 2019-08-16
AYCA-2T05DV | 2RCH-04 | ISAAC DEVELOPMENTS BLIGH PARK - 1 | Active | Supply Order Raised | 4 | FTTP – Type 2 | NSW | South Windsor | 752 George St | 2756 | 163188 | B + D | 2019-07-25
AYCA-EV5EP | 2DAP-01 | Vista Park - 6 | Active | Supply Order Raised | 12 | FTTP – Type 2 | NSW | Wongawilli | Smiths Lane | 2530 | 175796 | D | 2019-05-31
AYCA-5KIP6Y | 2WLG-07 | 45 Rosemont Street, West Wollongong NSW | Active | Supply Order Raised | 4 | FTTP – Type 2 | NSW | West Wollongong | 45 Rosemont Street | 2500 | 187104 | B + E | 2019-05-03
AYCA-58PGFK | 2MSV-03 | 4 NEW FREESTANDING VILLAS - 25 Ascot Rd | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Bowral | 25 Ascot Rd | 2576 | 184634 | B + E | 2019-04-26
AYCA-4H9191 | 2COR-03 | 208-210 Princes Highway - 1 | Active | Supply Order Raised | 7 | FTTP – Type 2 | NSW | Bulli | 208-210 Princes Highway | 2516 | 162471 | B + E | 2019-04-12
AYCA-5KPEKH | 2NRN-06 | Olive Hill Drive, Cobbitty - 6 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Cobbitty | Olive Hill Drive | 2570 | 191391 | B + D | 2019-03-29
AYCA-5JIMDQ | 2DBB-02 | 166 Brisbane Street, Dubbo - 1 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Dubbo | 166 Brisbane Street | 2830 | 192244 | B + E | 2019-03-01
AYCA-LYHJJ | 2MTT-02 | Renwick - DA06B | Active | Supply Order Raised | 8 | FTTP – Type 2 | NSW | Mittagong | 10 Cardigan St | 2575 | 183911 | D | 2019-03-01
AYCA-4W183C | 2WLG-02 | The Quad - 1 | Active | Supply Order Raised | 4 | FTTP – Type 2 | NSW | Wollongong | 71 Auburn St | 2500 | 178048 | B + E | 2019-02-28
AYCA-4W844H | 2DNM-20 | Grey Gum Road, Denman - 1 | Active | Supply Order Raised | 4 | FTTN | NSW | Denman | 18A Grey Gum Rd | 2328 | 177335 | B + D | 2019-02-28
AYCA-5BOGUB | 2RED-01 | 11B Lachlan St, Waterloo - 1 | Active | Supply Order Raised | 67 | FTTP – Type 2 | NSW | Waterloo | 11B Lachlan St | 2017 | 190109 | B + E | 2019-02-22
AYCA-4X6TWU | 2LID-08 | Omar Mosque - final stages | Active | Supply Order Raised | 2 | FTTP – Type 2 | NSW | Auburn | 43-47 Harrow Rd | 2144 | 177336 | B + E | 2019-02-15
AYCA-4MFJ6I | 2CFS-03 | Victoria Terrace - 1 | Active | Supply Order Raised | 2 | FTTP – Type 2 | NSW | Coffs Harbour | 65 Victoria Street | 2450 | 166142 | B + D | 2019-02-13
AYCA-5D2DU0 | 2LCT-01 | Seawide Estate - 4 | Active | Supply Order Raised | 10 | FTTP – Type 2 | NSW | Lake Cathie | Lot 65 Shorebreak Crescent | 2445 | 183799 | D | 2019-02-08
AYCA-57DG41 | 2BTH-01 | Opal Bathurst Aged Care Facility - 1 | Active | Supply Order Raised | 4 | FTTP – Type 2 | NSW | Bathurst | 93 Stanley St | 2795 | 180126 | B + E | 2019-02-07
AYCA-468RZY | 2LID-04 | 23 RAILWAY PARADE - 1 | Active | Supply Order Raised | 5 | FTTP – Type 2 | NSW | Lidcombe | 23 Railway Parade | 2141 | 156882 | B + E | 2019-02-04
AYCA-583XDD | 2PTH-02 | Rise Projects PTY LTD - 1 | Active | Supply Order Raised | 12 | FTTP – Type 2 | NSW | South Penrith | 117-119 Jamison Rd | 2750 | 180129 | B + D | 2019-02-01
AYCA-577BDS | 2BLK-07 | 36 Huntingwood Drive - 1 | Active | Supply Order Raised | 3 | FTTP – Type 2 | NSW | Huntingwood | 36 Huntingwood Drive | 2148 | 180681 | B + E | 2019-01-31
AYCA-48QOI8 | 2NRN-05 | ELDERSLIE - 1 | Active | Supply Order Raised | 7 | FTTN | NSW | Elderslie | 155F Lodges Road | 2570 | 161511 | B + D | 2019-01-28
AYCA-5MG99P | 2MEN-62 | 593 Old Illawarra Road, Menai NSW 2234, | Active | Supply Order Raised | 5 | FTTP – Type 3 (MT-LFN) | NSW | Menai | 593 Old Illawarra Road | 2234 | 189818 | B + E | 2019-01-28
AYCA-5MGOY8 | 2MEN-62 | 589 Old Illawarra Road, Menai NSW 2234, | Active | Supply Order Raised | 3 | FTTP – Type 3 (MT-LFN) | NSW | Menai | 591 Old Illawarra Road | 2234 | 189819 | B + E | 2019-01-28
AYCA-4DQ6PX | 2NRN-06 | 645 Cobbitty Road - 3 | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Cobbitty | Cobbitty Rd | 2570 | 162516 | D | 2019-01-25
AYCA-4DQ9I8 | 2NRN-06 | 645 Cobbitty Road - 2 | Active | Supply Order Raised | 6 | FTTP – Type 3 (MT-LFN) | NSW | Cobbitty | Cobbitty Rd | 2570 | 162517 | D | 2019-01-25
AYCA-4YJULB | 2REV-20 | Flower Power - 1 | Active | Supply Order Raised | 9 | FTTP – Type 3 (MT-LFN) | NSW | Milperra | 479 Henry Lawson Drive | 2214 | 177523 | A + E | 2019-01-25
AYCA-4SRFAN | 2BAL-62 | ALDI Store Development - Balgowlah - 1 | Active | Supply Order Raised | 2 | FTTP – Type 3 (MT-LFN) | NSW | Balgowlah | 22/26 Roseberry St | 2093 | 175478 | B + E | 2019-01-22
AYCA-4BBYMK | 2ROU-01 | Old Pitt Town Road - 1 Community | Active | Supply Order Raised | 7 | FTTP – Type 3 (MT-LFN) | NSW | Box Hill | 184 & 186 Old Pitt Town Rd | 2765 | 162606 | D | 2019-01-16
AYCA-5ALAXU | 2ORG-02 | Shiralee - 1A | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Orange | 104 Lysterfield Rd | 2800 | 181921 | D | 2019-01-10
AYCA-4HTS7R | 2RIV-03 | 875 Marsden Park - 1 | Active | Supply Order Raised | 4 | FTTP – Type 2 | NSW | Marsden Park | 875 Richmond Rd | 2765 | 163669 | B + D | 2018-12-14
AYCA-5SK61D | 2NWR-03 | 38 Cumberland Avenue, South Nowra NSW 25 | Active | Supply Order Raised | 1 | FTTP – Type 2 | NSW | South Nowra | 39 Cumberland Avenue | 2541 | 192782 | B + E | 2018-12-05
AYCA-3AVVT5 | 2BRG-01 | 70-100 Seventeenth Ave, Austral - 2 | Active | Supply Order Raised | 9 | FTTP – Type 3 (MT-LFN) | NSW | Austral | 70 Seventeenth Avenue | 2179 | 149109 | D | 2018-11-16
AYCA-5MWJQ4 | 2MAC-22 | Fairway Gardens - 1A | Active | Supply Order Raised | 2 | FTTP – Type 3 (MT-LFN) | NSW | Macksville | 222 Wallace St | 2447 | 188997 | D | 2018-10-31
AYCA-5QTMEE | 2KEL-07 | Non Standard Builds - 68-82 Fairway Driv | Active | Supply Order Raised | 8 | FTTP – Type 2 | NSW | Kellyville | 68-82 Fairway Drive | 2155 | 190574 | B + D | 2018-10-03
AYCA-5PYJJF | 2KCL-02 | Non Standard Builds - Sailfish Way Kings | Active | Supply Order Raised | 28 | FTTP – Type 2 | NSW | Kingscliff | Sailfish Way & Seaside Drive |  | 190383 | B + D | 2018-09-24
AYCA-5PBMZD | 2URL-20 | Non Standard Builds - 14 SALISBURY ST | Active | Supply Order Raised | 4 | FTTN | NSW | URALLA | 14 SALISBURY ST | 2358 | 189825 | B + D | 2018-09-18
AYCA-4YZZ1I | 2ABN-03 | Boulevarde - 1 | Active | Supply Order Raised | 4 | FTTN | NSW | Oak Flats | 149 The Boulevarde | 2529 | 175688 | B + D | 2018-09-17
AYCA-5KAX1D | 2MDG-01 | Non Standard Builds - 20 Burrundulla Av, | Active | Supply Order Raised | 11 | FTTN | NSW | Mudgee | 20 Burrundulla Ave | 2850 | 185812 | B + D | 2018-07-23
AYCA-5FA5OM | 2MIR-24 | 4-6 Crammond Boulevard, Caringbah - 1 | Active | Supply Order Raised | 6 | FTTP – Type 3 (MT-LFN) | NSW | Caringbah | 4-6 Crammond Boulevard | 2229 | 184811 | B + E | 2018-06-01
AYCA-5DL8UH | 2MRE-02 | Non Standard Builds - Boland Drive Moree | Active | Supply Order Raised | 6 | FTTP – Type 3 (MT-LFN) | NSW | Moree | Boland Drive | 2400 | 183224 | B + C | 2018-05-10
AYCA-54DAGS | 2PTH-07 | 29 Park Avenue Kingswood - 29 Park Avenu | Active | Supply Order Raised | 10 | FTTP – Type 2 | NSW | Kingswood | 29 Park Ave | 2747 | 185853 | B + D | 2018-03-01
AYCA-476RM9 | 2LIV-04 | Non Standard Builds - 87-91 Campbell St, | Active | Dev Transferred to Build | 76 |  | NSW | Liverpool | 87-91 Campbell St | 2170 | 159520 | B + E | 2017-02-15
AYCA-5FK9G7 | 2TEM-20 | Non Standard Builds - 113 Baker St Temor | Active | Supply Order Raised | 7 | FTTP – Type 3 (MT-LFN) | NSW | Temora | 113-115 Baker Street | 2666 | 187094 | B + D

## Count
Count of Project Status | Column Labels
Row Labels | Apr-18 | Aug-18 | Jul-18 | Jun-18 | Mar-18 | May-18 | (blank) | Sep-18 | Oct-18 | Nov-18 | Grand Total
Completed | 13 | 29 | 32 | 33 | 2 | 32 | 20 | 29 | 10 | 13 | 213
Developer Delay | [6 empty] | 59 |  |  |  | 59
Heritage Delay | [6 empty] | 2 |  |  |  | 2
In Construction | [6 empty] | 19 |  |  |  | 19
In Design | [6 empty] | 4 |  |  |  | 4
NBN Delay | [6 empty] | 8 |  |  |  | 8
NBN External Delay | [6 empty] | 1 |  |  |  | 1
NBN Internal Delay | [6 empty] | 2 |  |  |  | 2
Parent Site Delay | [6 empty] | 3 |  |  |  | 3
Pre-construction | [6 empty] | 19 |  |  |  | 19
Site Visit | [6 empty] | 36 |  |  |  | 36
Site Visit | [6 empty] | 1 |  |  |  | 1
Survey and Design | [6 empty] | 1 |  |  |  | 1
Site Viit | [6 empty] | 1 |  |  |  | 1
(blank)
Complete | [6 empty] | 1 |  |  |  | 1
Ste Visit | [6 empty] | 1 |  |  |  | 1
Site Vist | [6 empty] | 1 |  |  |  | 1
Council Delay | [6 empty] | 1 |  |  |  | 1
Grand Total | 13 | 29 | 32 | 33 | 2 | 32 | 180 | 29 | 10 | 13 | 373

## Sheet1 (hidden)
Request ID | Name | Application Name | Active Status | Application Status | No. of Premises | Technology Deployed | State | Suburb | Address | Post Code | Finance Project Number | Build Type(s) | Estimated First Service Connection Date | Pathway Design Status | Trans / Dist NDD Status | Trans / Dist Contract Type | Trans / Dist Order Status | Trans / Dist WR/WI Issued Date | CLAAN Status | NBN Co Project Manager (Trans / Dist) | Supplier (Trans / Dist)
AYCA-476RM9 | 2LIV-04 | Non Standard Builds - 87-91 Campbell St, | Active | Dev Transferred to Build | 76 |  | NSW | Liverpool | 87-91 Campbell St | 2170 | 159520 | B + E | 2017-02-15 |  | Reservation Response Received | MWA - RFQ | WI Issued | 2017-09-21 12:00 |  | Andrew Mahasay | Datateks
AYCA-4QG9AV | 2KIA-02 | Non Standard Builds - 33 Shoalhaven St K | Active | Dev Transferred to Build | 12 | FTTP – Type 2 | NSW | Kiama | 33 Shoalhaven St | 2533 | 174993 | B + E | 2017-09-08 |  | Reservation Response Received | MWA - RFQ | WI Issued | 2018-02-23 12:00 |  | Andrew Mahasay | Datateks
AYCA-4TBHNX | 2SHH-05 | Non Standard Builds - 125 Lake Entrance | Active | Dev Transferred to Build | 18 | FTTN | NSW | Barrack Heights | 125 Lake Entrance Road, | 2528 | 169541 | B + E | 2017-10-04 |  | Completed (No Telstra Duct) | MWA - RFQ | WI Issued | 2018-02-15 12:00 |  | Mark Leal | Datateks
AYCA-4EIN5M | 2KCL-02 | 171 Casuarina Way Pty Ltd - 1 | Active | Supply Order Raised | 17 | FTTP – Type 2 | NSW | Casuarina | Lot 171 Casuarina Way | 2487 | 159992 | B + E | 2018-03-23 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2017-10-19 12:00 |  | Ertan Cicek | Datateks
AYCA-52381N | 2SUX-01 | David Kirkwood - 1 | Active | Supply Order Raised | 4 | FTTN | NSW | Sussex Inlet | 284 River Rd | 2540 | 180917 | B + E | 2018-05-01 | Design Accepted | Completed (No Telstra Duct) | MWA - RFQ | WI Issued | 2018-06-12 12:00 |  | Ertan Cicek | Datateks
AYCA-57CH4J | 2CRO-01 | KURNELL 1 - 4 | Active | Supply Order Raised | 5 | FTTP – Type 3 (MT-LFN) | NSW | Kurnell | 8/268A Captain Cook Dr | 2231 | 181281 | B + E | 2018-05-01 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-28 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4MNF1P | 2NRN-10 | Gregory Hill Health Hub - 0 | Active | Supply Order Raised | 29 | FTTP – Type 3 (MT-LFN) | NSW | Gregory Hills | Gregory Hills Dr | 2557 | 178033 | B + E | 2018-05-19 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-24 12:00 |  | Nabeel Jaimon | Datateks
AYCA-5DBDK2 | 2ABN-03 | 8 Werrang St, Albion Park Rail NSW 2527, | Active | Developer Contract Signed | 4 | FTTN | NSW | Albion Park Rail | 8 Werrang Street | 2527 | 183801 | B + E | 2018-06-01 | Design Accepted | Completed (No Telstra Duct) | MWA - RFQ | Recommendation Endorsed |  | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-5DPOWN | 2APN-01 | 13 Technology Dr, Appin NSW 2560, Austra | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Appin | 13 Technology Drive | 2560 | 183808 | B + E | 2018-06-01 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-20 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-5F1RYP | 2EDG-66 | 114 New South Head Road, Edgecliff - 1 | Active | Supply Order Raised | 8 | FTTP – Type 3 (MT-LFN) | NSW | Edgecliff | 114 New South Head Road | 2027 | 183814 | B + E | 2018-06-01 |  | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-22 12:00 | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-55KUFO | 2MIR-22 | Bay Road Taren Point - 1 | Active | Supply Order Raised | 13 | FTTP – Type 3 (MT-LFN) | NSW | Taren Point | 31 Bay Rd | 2229 | 181966 | B + E | 2018-06-13 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-30 12:00 |  | Ertan Cicek | Datateks
AYCA-52UC2N | 2LIV-12 | Westrac - 3 | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Casula | Beech Rd | 2170 | 182667 | B + E | 2018-06-29 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-07 12:00 |  | Ertan Cicek | Datateks
AYCA-4KXY8F | 2BTH-02 | Wark Parade - 1 | Active | Supply Order Raised | 2 | FTTP – Type 3 (MT-LFN) | NSW | Windradyne | 1 Wark Parade | 2795 | 163912 | B + E | 2018-07-12 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-02-20 12:00 |  | Ertan Cicek | Datateks
AYCA-3MEHNA | 9BLC-04 | Block 1 Section 22 Lawson - 1 | Active | Supply Order Raised | 46 | FTTP – Type 2 | ACT | Lawson | Nevertire St | 2617 | 181656 | B + E | 2018-07-14 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-06-28 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-52950S | 2BUR-65 | United Apartments - 1 | Active | Supply Order Raised | 25 | FTTP – Type 2 | NSW | Burwood | 147-153 Liverpool Rd | 2134 | 177000 | B + E | 2018-07-16 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-16 12:00 |  | Nabeel Jaimon | Datateks
AYCA-5BX3DW | 2NEW-23 | 7-9 Hutchinson St, St Peters - 1 | Active | Supply Order Raised | 8 | FTTP – Type 3 (MT-LFN) | NSW | St Peters | 7-9 Hutchinson St | 2044 | 183627 | B + E | 2018-07-16 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-29 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4T7JU2 | 2MIR-25 | 13 dudley ave - 1 | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Caringbah South | 13 Dudley Avenue | 2229 | 177476 | B + E | 2018-07-18 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-24 12:00 |  | Ertan Cicek | Datateks
AYCA-53E534 | 2LIV-12 | Glenfield Gains - 1 | Active | Supply Order Raised | 11 | FTTP – Type 2 | NSW | Glenfield | 25 Glenfield Rd | 2167 | 178433 | B + E | 2018-07-18 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-03-22 12:00 |  |  | Datateks
AYCA-2Y5DX4 | 2EPP-65 | Bridgeland Investment - 1 | Active | Supply Order Raised | 41 | FTTP – Type 2 | NSW | Epping | 3 & 16 Hazlewood Pl | 2121 | 156068 | B + E | 2018-07-20 | Design Accepted | Reservation Response Received | MWA - RFQ | WI Issued | 2017-04-08 12:00 |  | Ertan Cicek | Datateks
AYCA-442ZEA | 2PAR-63 | Pinnacle - 1 | Active | Supply Order Raised | 76 | FTTP – Type 2 | NSW | Westmead | 2 Good Street | 2145 | 158313 | B + E | 2018-07-20 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-02-22 12:00 |  | Ertan Cicek | Datateks
AYCA-48280D | 2RED-03 | THE RESERVE - 1 | Active | Supply Order Raised | 352 | FTTP – Type 2 | NSW | Zetland | 906 Bourke St | 2017 | 160331 | B + E | 2018-07-20 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-03-13 12:00 |  | Lindy Chan | Datateks
AYCA-4R1HNT | 2MIL-62 | 6-8 Facey Cres, Lurnea - 1 | Active | Supply Order Raised | 8 | FTTP – Type 3 (MT-LFN) | NSW | Lurnea | 6-8 Facey Cres | 2170 | 176925 | B + E | 2018-07-20 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-02 12:00 |  | Nabeel Jaimon | Datateks
AYCA-34MTV2 | 2BUR-07 | HB - 1 | Active | Supply Order Raised | 35 | FTTP – Type 2 | NSW | Homebush | 133 Parramatta Rd | 2140 | 160851 | B + E | 2018-07-27 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-06-13 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4JM0L9 | 2DRU-60 | CINQUE FIVE DOCK - 1 | Active | Supply Order Raised | 22 | FTTP – Type 2 | NSW | Five Dock | 50-52 East St | 2046 | 171495 | B + E | 2018-07-27 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-19 12:00 |  | Lindy Chan | Datateks
AYCA-1SQ3K5 | 2PAR-01 | 189 Macquarie Street - SP1 | Active | Supply Order Raised | 21 | FTTP – Type 2 | NSW | Parramatta | 189 Macquarie Street | 2150 | 156064 | B + E | 2018-07-31 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2017-05-08 12:00 |  | Lindy Chan | Datateks
AYCA-4RGB2W | 2EAS-62 | OMNIA - 1 | Active | Supply Order Raised | 149 | FTTP – Type 2 | NSW | Potts Point | 111-139 Darlinghurst Rd | 2011 | 178373 | B + E | 2018-07-31 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-04 12:00 |  | Ertan Cicek | Datateks
AYCA-4V7F3M | 2LAK-22 | LAKEMBA - 1 | Active | Supply Order Raised | 5 | FTTP – Type 3 (MT-LFN) | NSW | Lakemba | 23 Willeroo Street | 2195 | 183955 | B + E | 2018-08-03 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-07-04 12:00 | CLAAN Sent to DP |  | Datateks
AYCA-48V6NM | 2PTH-05 | Quest Hotel - 1 | Active | Supply Order Raised | 7 | FTTP – Type 2 | NSW | Penrith | Lord Sheffield Circuit | 2750 | 182659 | B + E | 2018-08-04 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-05-30 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4EOA07 | 2MIR-24 | 298 - 300 Taren Point Road - 1 | Active | Supply Order Raised | 42 | FTTP – Type 2 | NSW | Caringbah | 298-300 Taren Point Rd | 2229 | 178956 | B + E | 2018-08-06 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-03-16 12:00 |  | Ertan Cicek | Datateks
AYCA-3TP6RP | 2SIL-04 | Majors Bay Mortlake Residential - 2 | Active | Supply Order Raised | 227 | FTTP – Type 2 | NSW | Mortlake | 8 Hilly St | 2137 | 156063 | B + E | 2018-08-10 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-01-10 12:00 |  | Ertan Cicek | Datateks
AYCA-2YGB4Y | 2BLK-01 | Opal Aged Care Facility - Blacktown - 1 | Active | Supply Order Raised | 5 | FTTP – Type 2 | NSW | Blacktown | 37-43 Kildare Rd | 2148 | 137108 | B + E | 2018-08-13 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-02-27 12:00 |  | Nabeel Jaimon | Datateks
AYCA-58QIXQ | 2LIV-02 | 35 Scott St Liverpool - 1 | Active | Supply Order Raised | 15 | FTTP – Type 2 | NSW | Liverpool | 29 Scott St | 2170 | 180130 | B + E | 2018-08-13 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-24 12:00 |  |  | Datateks
AYCA-5ALZB0 | 2BLK-07 | 1 Huntingwood Drive - 2 | Active | Supply Order Raised | 1 | FTTP – Type 2 | NSW | Huntingwood | 6 Woods Cl | 2148 | 181922 | B + E | 2018-08-15 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-12 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-2Q0B3G | 2PAR-63 | ST GEORGE COMMUNITY HOUSING - 1 | Active | Supply Order Raised | 76 | FTTP – Type 2 | NSW | Westmead | 148-150 Great Western Hwy | 2145 | 156081 | B + E | 2018-08-17 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-17 12:00 |  | Ertan Cicek | Datateks
AYCA-4VFYJV | 2BAN-64 | Percy Towers - 1 | Active | Supply Order Raised | 70 | FTTP – Type 2 | NSW | Bankstown | 27-37 Percy St | 2200 | 171508 | B + E | 2018-08-17 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-08 18:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-52ZO0L | 2LID-04 | Norval St Boarding House - 1 | Active | Supply Order Raised | 10 | FTTP – Type 2 | NSW | Auburn | 32 Norval St | 2144 | 177658 | B + E | 2018-08-17 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued |  |  | Ertan Cicek | Datateks
AYCA-59DV6W | 2CRR-72 | 41 Nelson St, Fairfield | Active | Supply Order Raised | 29 | FTTP – Type 2 | NSW | Fairfield | 41 Nelson St | 2165 | 183318 | B + E | 2018-08-18 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-06-06 12:00 |  | Ertan Cicek | Datateks
AYCA-5CSK69 | 2LIV-03 | 94 Flowerdale Rd, Liverpool NSW 2170, Au | Active | Supply Order Raised | 7 | FTTP – Type 2 | NSW | Liverpool | 94 Flowerdale Rd, | 2170 | 183855 | B + E | 2018-08-20 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-15 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-3TBATE | 2PAR-61 | Skyrise - 1 | Active | Supply Order Raised | 233 | FTTP – Type 2 | NSW | Parramatta | 11 Hassall St | 2150 | 171863 | B + E | 2018-08-24 | Design Accepted | Reservation Response Received | MWA - RFQ | WI Issued | 2018-03-09 12:00 |  | Andrew Partalis | Datateks
AYCA-4QID92 | 2EAS-63 | IDA Potts Point - 1 | Active | Supply Order Raised | 34 | FTTP – Type 2 | NSW | Woolloomooloo | 153-165 Brougham St | 2011 | 170149 | B + E | 2018-08-27 | Design Accepted | Reservation Response Received | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-5AZ97T | 2BTH-02 | Wark Parade - 2 | Active | Supply Order Raised | 9 | FTTP – Type 3 (MT-LFN) | NSW | Windradyne | 1 Wark Parade | 2795 | 181260 | B + E | 2018-08-30 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-15 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4SOX62 | 2LIV-03 | R & S Investments NSW - 1 | Active | Supply Order Raised | 10 | FTTP – Type 2 | NSW | Liverpool | 186 Moore St | 2170 | 170944 | B + E | 2018-08-31 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-16 12:00 |  | Ertan Cicek | Datateks
AYCA-57KT5A | 2PTH-02 | Octavia - 1 | Active | Supply Order Raised | 8 | FTTP – Type 2 | NSW | Penrith | 153 Jamison Rd | 2750 | 183775 | B + E | 2018-08-31 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-18 12:00 | CLAAN Sent to DP |  | Datateks
AYCA-5AVN4W | 2EPP-62 | 23-25 Forest Grove, Epping - 1 | Active | Supply Order Raised | 60 | FTTP – Type 2 | NSW | Epping | 23-25 Forest Grove | 2121 | 181924 | B + E | 2018-08-31 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-18 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-3CFI3W | 2EPP-05 | 120 Herring Road - 1 | Active | Supply Order Raised | 200 | FTTP – Type 2 | NSW | Marsfield | 120 Herring Rd | 2122 | 147752 | B + E | 2018-09-03 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-03 12:00 |  | Ertan Cicek | Datateks
AYCA-3V5BM6 | 2DRU-61 | 197-199 Lyons Rd Drummoyne - 1 | Active | Supply Order Raised | 19 | FTTP – Type 2 | NSW | Drummoyne | 197-199 Lyons Rd | 2047 | 162500 | B + E | 2018-09-03 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-24 12:00 |  | Lindy Chan | Datateks
AYCA-57CAFW | 2CRO-01 | KURNELL 2 - Nearing Completion | Active | Supply Order Raised | 3 | FTTP – Type 3 (MT-LFN) | NSW | Kurnell | 262A Captain Cook Dr | 2231 | 181026 | B + E | 2018-09-03 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-26 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-56B97M | 2SEF-61 | 1 Tangerine Street Fairfield East | Active | Supply Order Raised | 18 | FTTP – Type 2 | NSW | Fairfield East | 1 Tangerine Street | 2165 | 183538 | B + E | 2018-09-10 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-12 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-55JW1J | 2BOT-01 | Maison - 1 | Active | Supply Order Raised | 67 | FTTP – Type 2 | NSW | Maroubra | 180-188 Maroubra Rd | 2035 | 181728 | A + E | 2018-09-11 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-22 12:00 |  | Ertan Cicek | Datateks
AYCA-39AB50 | 2HOR-62 | JAAN - 1 | Active | Supply Order Raised | 37 | FTTP – Type 2 | NSW | Asquith | 12-14 Bouvardia St | 2077 | 158697 | B + E | 2018-09-17 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2017-06-22 12:00 |  | Ertan Cicek | Datateks
AYCA-5576QH | 2TGL-02 | 3 GHERSI - 1st Stage - Frame | Active | Supply Order Raised | 6 | FTTP – Type 3 (MT-LFN) | NSW | Wamberal | 3 Ghersi Ave | 2260 | 180922 | B + E | 2018-09-17 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-14 12:00 |  | Ertan Cicek | Datateks
AYCA-56I886 | 2ASH-64 | Cecil Ash - 1 | Active | Supply Order Raised | 37 | FTTP – Type 2 | NSW | Ashfield | 47 Cecil St | 2131 | 180847 | B + E | 2018-09-21 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-13 12:00 | CLAAN Sent to DP |  | Datateks
AYCA-2QFUTJ | 2NRL-20 | Camden Day Hospital - 1 | Active | Supply Order Raised | 5 | FTTN | NSW | Elderslie | 37 Hilder St | 2570 | 156078 | B + E | 2018-09-24 | Design Accepted | Completed (No Telstra Duct) | MWA - RFQ | WI Issued | 2017-10-18 12:00 |  | Ertan Cicek | Datateks
AYCA-3NFID7 | 2PTH-04 | Tench Ave Jamisontown - 1 | Active | Supply Order Raised | 13 | FTTP – Type 2 | NSW | Jamisontown | 78-88 Tench Ave | 2750 | 161033 | B + E | 2018-09-24 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2017-12-19 12:00 |  | Ertan Cicek | Datateks
AYCA-4YZGFK | 2PEN-66 | boronia st - 1 | Active | Supply Order Raised | 15 | FTTP – Type 3 (MT-LFN) | NSW | South Wentworthville | 51 Boronia St | 2145 | 177339 | B + E | 2018-09-24 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-03-02 12:00 |  | Ertan Cicek | Datateks
AYCA-44MH0G | 2RYD-63 | Genesis Shepherds Bay - 1 | Active | Supply Order Raised | 61 | FTTP – Type 2 | NSW | Meadowbank | 133-137 Bowden St | 2114 | 155933 | B + E | 2018-09-27 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-18 12:00 |  | Ertan Cicek | Datateks
AYCA-1L7010 | 2LID-08 | Mixed Use Development - Tower A and B | Active | Supply Order Raised | 217 | FTTP – Type 2 | NSW | Auburn | 18 Harrow Road & 93 Auburn Road | 2144 | 161994 | B + E | 2018-09-28 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2017-12-12 12:00 |  | Ertan Cicek | Datateks
AYCA-21PVTM | 2BLK-03 | One Seven - 1 | Active | Supply Order Raised | 146 | FTTP – Type 2 | NSW | Blacktown | 5 Second Avenue | 2148 | 162095 | B + E | 2018-09-28 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-02-20 12:00 |  | Ertan Cicek | Datateks
AYCA-44H3AU | 2STL-65 | EMBASSY TOWERS, STAGE 2 - 1 | Active | Supply Order Raised | 276 | FTTP – Type 2 | NSW | St Leonards | 13 Marshall Ave | 2065 | 157762 | B + E | 2018-09-28 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-21 12:00 |  |  | Datateks
AYCA-4JW63S | 2CRO-21 | Dingle Apartment - 1 | Active | Supply Order Raised | 34 | FTTP – Type 2 | NSW | Cronulla | 25-29 Tonkin St | 2230 | 167015 | B + E | 2018-09-28 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-29 12:00 |  | Ertan Cicek | Datateks
AYCA-4PQO3D | 2EPP-62 | LUCILLE - 1 | Active | Supply Order Raised | 62 | FTTP – Type 2 | NSW | Epping | 12/6 Maida Rd | 2121 | 181696 | B + E | 2018-09-28 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-23 12:00 |  | Ertan Cicek | Datateks
AYCA-56PP6W | 2BAN-67 | KOI Bankstown - 1 | Active | Supply Order Raised | 23 | FTTP – Type 3 (MT-LFN) | NSW | Bankstown | 55-57 Chelmsford Ave | 2200 | 184128 | B + E | 2018-09-28 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-29 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-58BKNK | 2RYD-66 | QUBE - 1 | Active | Supply Order Raised | 42 | FTTP – Type 2 | NSW | Ryde | 2-6 Junction St | 2112 | 181672 | B + E | 2018-09-29 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-06 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-2XJBL7 | 2SIL-02 | Site 9 - 1 | Active | Supply Order Raised | 12 | FTTP – Type 2 | NSW | Sydney Olympic Park | 3 Olympic Blvd | 2127 | 160138 | B + E | 2018-09-30 | Awaiting Corrective Action | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-29 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-397TA7 | 2TGL-02 | Aria Terrigal - Building 1 - 1 | Active | Supply Order Raised | 18 | FTTP – Type 2 | NSW | Terrigal | 6-8 Painters Lane | 2260 | 160792 | B + E | 2018-10-01 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-26 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4KZ476 | 2PTH-02 | Penrith 1 - 1 | Active | Supply Order Raised | 71 | FTTP – Type 2 | NSW | Penrith | 38-40 Doonmore St | 2750 | 171616 | B + E | 2018-10-01 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-23 12:00 |  | Ertan Cicek | Datateks
AYCA-4O03IQ | 2COR-09 | 17 RYAN STREET, BALGOWNIE - 1 | Active | Supply Order Raised | 7 | FTTP – Type 3 (MT-LFN) | NSW | Balgownie | 17 Ryan Street | 2519 | 167597 | B + E | 2018-10-01 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-02-27 12:00 |  | Nabeel Jaimon | Datateks
AYCA-54WJL3 | 2PTH-09 | 111 Andrews Road - 1 | Active | Supply Order Raised | 14 | FTTP – Type 3 (MT-LFN) | NSW | Cranebrook | 111 Andrews Rd | 2749 | 180973 | B + E | 2018-10-01 | Awaiting Corrective Action | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-19 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-56Z0PS | 2HMK-02 | 37 - 49 O'Connor street, Chippendale NSW | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Chippendale | 37-49 O'Connor St | 2008 | 180746 | B + E | 2018-10-01 | Awaiting Corrective Action | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-15 12:00 |  | Ertan Cicek | Datateks
AYCA-4CG9U4 | 2KNS-04 | 29-31 Dunning Avenue Rosebery - 1 | Active | Supply Order Raised | 32 | FTTP – Type 2 | NSW | Rosebery | 29-31 Dunning Ave | 2018 | 181955 | B + E | 2018-10-05 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-11 10:15 |  | Ertan Cicek | Datateks
AYCA-5AXHNZ | 2SIL-02 | 4 Murray Rose Ave, Sydney Olympic Park - | Active | Supply Order Raised | 27 | FTTP – Type 3 (MT-LFN) | NSW | Sydney Olympic Park | 4 Murray Rose Avenue | 2127 | 183022 | B + E | 2018-10-12 | Awaiting Corrective Action | Reservation Response Received | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-57S6JD | 2REV-20 | 50 Violet St Revesby - 1 | Active | Supply Order Raised | 5 | FTTP – Type 3 (MT-LFN) | NSW | Revesby | 50/42 Violet St | 2212 | 180854 | B + E | 2018-10-15 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-08 16:15 |  |  | Datateks
AYCA-413Z64 | 2PAR-64 | THE DARCY - 1 | Active | Supply Order Raised | 36 | FTTP – Type 2 | NSW | Westmead | 2B Darcy Rd | 2145 | 155179 | B + E | 2018-10-19 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-24 12:00 |  | Ertan Cicek | Datateks
AYCA-45Q6J5 | 2EPP-62 | Luxcon Epping - 1 | Active | Supply Order Raised | 63 | FTTP – Type 2 | NSW | Epping | 35 Oxford St | 2121 | 170455 | B + E | 2018-10-19 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-21 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4KBL5R | 2KNS-03 | Primrose Terraces - 1 | Active | Supply Order Raised | 44 | FTTP – Type 2 | NSW | Rosebery | 14-18 Primrose Ave & 27-29 Rosebery Ave | 2018 | 171209 | B + E | 2018-10-19 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-05-30 12:00 |  | Lindy Chan | Datateks
AYCA-4PIIN5 | 2RYD-66 | RYDEVIEW - 1 | Active | Supply Order Raised | 36 | FTTP – Type 2 | NSW | Ryde | 101 Church St | 2112 | 172853 | B + E | 2018-10-19 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-05-11 12:00 |  | Ertan Cicek | Datateks
AYCA-328OYF | 2CBT-05 | Aspire Apartments - 1 | Active | Supply Order Raised | 73 | FTTP – Type 2 | NSW | Campbelltown | 37-41 Chamberlain St | 2560 | 165436 | B + E | 2018-10-24 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-07-05 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-468RZY | 2LID-04 | 23 RAILWAY PARADE - 1 | Active | Supply Order Raised | 5 | FTTP – Type 2 | NSW | Lidcombe | 23 Railway Parade | 2141 | 156882 | B + E | 2018-10-29 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued |  |  | Ertan Cicek | Datateks
AYCA-4RB8MD | 2LID-03 | 2 Clarke St Berala - 1 | Active | Supply Order Raised | 5 | FTTP – Type 2 | NSW | Berala | 2 Clarke St | 2141 | 168809 | B + E | 2018-10-29 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-24 12:00 |  | Nabeel Jaimon | Datateks
AYCA-5A2Y34 | 2MAI-03 | 100 George St, East Maitland NSW 2323, A | Active | Supply Order Raised | 2 | FTTP – Type 2 | NSW | East Maitland | 100 George Street | 2323 | 181918 | B + E | 2018-10-29 | Awaiting Corrective Action | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-06-06 12:00 |  | Ertan Cicek | Datateks
AYCA-48HHL8 | 2MIR-28 | Palisade - 1 | Active | Supply Order Raised | 204 | FTTP – Type 2 | NSW | Miranda | 2-22 University Rd & 660-664 Kingsway | 2228 | 183378 | B + E | 2018-10-31 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-07-04 12:00 | CLAAN Sent to DP |  | Datateks
AYCA-57Y170 | 2BRY-01 | Morrow Building - 1 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Berry | 17 Hitchcocks Ln | 2535 | 181585 | B + E | 2018-10-31 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-4UMUPA | 2KEL-07 | Department of Education - 1 | Active | Supply Order Raised | 3 | FTTP – Type 2 | NSW | Kellyville | 21 Fairway Dr | 2155 | 174997 | B + E | 2018-11-01 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-07-06 11:15 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-3O2CEB | 2GBE-62 | Cowper Street Apartments - 1 | Active | Developer Contract Signed | 98 | FTTP – Type 2 | NSW | Glebe | 5 Elger St | 2037 | 165101 | B + E | 2018-11-02 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-4EZRCH | 2MIR-26 | 1-3 Higherdale Ave, Miranda - 1 | Active | Supply Order Raised | 68 | FTTP – Type 2 | NSW | Miranda | 1-3 Higherdale Ave | 2228 | 164024 | B + E | 2018-11-05 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-12 12:00 | CLAAN Sent to DP |  | Datateks
AYCA-4Z4FSB | 2MIL-20 | Mainfreight Logistics - 1 | Active | Supply Order Raised | 2 | FTTN | NSW | Prestons | 36B Kookaburra Rd N | 2170 | 176930 | B + E | 2018-11-05 | Design Accepted | Reservation Response Received | MWA - RFQ | WI Issued | 2018-04-19 12:00 |  | Ertan Cicek | Datateks
AYCA-31DCKF | 2EAS-64 | Advanx Encore - 1 | Active | Supply Order Raised | 40 | FTTP – Type 2 | NSW | Darlinghurst | 18-20 Neild Ave | 2010 | 175959 | B + E | 2018-11-09 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-01 12:00 |  | Lindy Chan | Datateks
AYCA-523PM8 | 9MNK-01 | crn beaconsfield & leonora stbob - 1 | Active | Supply Order Raised | 14 | FTTP – Type 3 (MT-LFN) | ACT | Fyshwick | 8 Beaconsfield St | 2609 | 177812 | B + E | 2018-11-12 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-07 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-21R8AP | 2WLG-07 | 12-14 New Dapto Rd Wollongong - 1 | Active | Supply Order Raised | 38 | FTTP – Type 2 | NSW | Wollongong | 12-14 New Dapto Road | 2500 | 175987 | B + E | 2018-11-17 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-07-05 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4QHVO8 | 2CHL-07 | Gateshead Stage 2 Industrial Units - 1 | Active | Supply Order Raised | 16 | FTTP – Type 3 (MT-LFN) | NSW | Gateshead | 13-15 Pacific Hwy | 2290 | 179863 | B + E | 2018-11-21 | Design Accepted | Reservation Response Received | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-4X1Z9M | 2MIR-26 | Mooki St - 1 | Active | Supply Order Raised | 6 | FTTP – Type 3 (MT-LFN) | NSW | Miranda | 58/60 Karimbla Rd | 2228 | 173160 | B + E | 2018-11-22 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-07-05 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-2V9V2D | 2HOR-63 | Cowan Road Residential Development - 1 | Active | Supply Order Raised | 50 | FTTP – Type 2 | NSW | Mount Colah | 2 Cowan Road & 540A-542 Pacific Highway | 2079 | 157215 | B + E | 2018-11-23 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-07-05 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-57DG41 | 2BTH-01 | Opal Bathurst Aged Care Facility - 1 | Active | Supply Order Raised | 4 | FTTP – Type 2 | NSW | Bathurst | 93 Stanley St | 2795 | 180126 | B + E | 2018-11-23 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-42N8QF | 2PEN-67 | Macklin 38 - 1 | Active | Supply Order Raised | 17 | FTTP – Type 2 | NSW | Pendle Hill | 38-40 Macklin Street | 2145 | 161792 | B + E | 2018-11-26 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-02-23 12:00 |  | Ertan Cicek | Datateks
AYCA-55RMFH | 2WET-23 | Novella Function Centre - 1 | Active | Developer Contract Signed | 5 | FTTP – Type 3 (MT-LFN) | NSW | Abbotsbury | 1521 The Horsley Dr | 2176 | 181730 | B + E | 2018-11-29 | Design Accepted | Reservation Response Received | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE |  | Datateks
AYCA-30GQWB | 2ROU-02 | Kellyville Apartments Withers Rd - 1 | Active | Developer Contract Signed | 80 | FTTP – Type 2 | NSW | Kellyville | 16-20 Withers Rd | 2155 | 162079 | B + E | 2018-11-30 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-3D0J11 | 2ROC-02 | Aspect - 1 | Active | Supply Order Raised | 90 | FTTP – Type 2 | NSW | Wolli Creek | 15-21 Willis St | 2205 | 153465 | B + E | 2018-11-30 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-08 21:30 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-3E5O97 | 2ROU-03 | Hancy - 1 | Active | Supply Order Raised | 47 | FTTP – Type 2 | NSW | Kellyville | 85-89 Samantha Riley Dr | 2155 | 162040 | B + E | 2018-11-30 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-01-05 12:00 |  | Ertan Cicek | Datateks
AYCA-4L3R6E | 2MIR-26 | VENTURA AVE - 1 | Active | Supply Order Raised | 9 | FTTP – Type 3 (MT-LFN) | NSW | Miranda | 4-6 Ventura Ave | 2228 | 166399 | B + E | 2018-11-30 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-07 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4LT337 | 2WET-23 | 457-463 Victoria street - 1 | Active | Developer Contract Signed | 32 | FTTP – Type 3 (MT-LFN) | NSW | Wetherill Park | 457-463 Victoria Street | 2164 | 174364 | B + E | 2018-11-30 | Design Accepted | Reservation Response Received | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-4X6TWU | 2LID-08 | Omar Mosque - final stages | Active | Supply Order Raised | 2 | FTTP – Type 2 | NSW | Auburn | 43-47 Harrow Rd | 2144 | 177336 | B + E | 2018-11-30 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-03-01 12:00 |  | Nabeel Jaimon | Datateks
AYCA-49DBF5 | 2CRO-21 | Pavilion Cronulla - 1 | Active | Developer Contract Signed | 36 | FTTP – Type 2 | NSW | Cronulla | 33-39 Croydon St | 2230 | 161039 | B + E | 2018-12-01 | Design Accepted | Reservation Response Received | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-4XR9F8 | 2ROU-02 | North West Business Centre - 1 | Active | Developer Contract Signed | 23 | FTTP – Type 3 (MT-LFN) | NSW | Rouse Hill | 320 Annangrove Rd | 2155 | 181574 | B + E | 2018-12-01 | Design Accepted | Reservation Response Received | MWA - SOPR | DCE Generated |  | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-56PJ6I | 2GRK-01 | Tuggerah Lakes Hospital - 1 | Active | Supply Order Raised | 8 | FTTP – Type 3 (MT-LFN) | NSW | Kanwal | 645 Pacific Hwy | 2259 | 181075 | B + E | 2018-12-01 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-07-12 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4Z6R8L | 2DAL-28 | GALILEO PHILLIP STREET JV - 1 | Active | Developer Contract Signed | 108 | FTTP – Type 2 | NSW | Sydney | 148-160 King Street | 2000 | 183239 | B + E | 2018-12-03 | Awaiting Corrective Action | Reservation Response Received | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-3S7B4B | 2HMK-02 | BUILDING 2 (CB02) - 1 | Active | Developer Contract Signed | 12 | FTTP – Type 2 | NSW | Ultimo | University of Technology Sydney Building 1 15 Broadway, | 2007 | 183941 | B + E | 2018-12-06 | Design Accepted | Reservation Response Received | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-4M02LB | 2UND-62 | 401-405 Illawarra Road, Marrickville - 1 | Active | Supply Order Raised | 25 | FTTP – Type 2 | NSW | Marrickville | 401-405 Illawarra Rd | 2204 | 176259 | B + E | 2018-12-07 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-03-22 12:00 |  | Lindy Chan | Datateks
AYCA-4VH4MG | 2PTH-02 | 36-38 Barber Ave, Penrith - 1 | Active | Developer Contract Signed | 44 | FTTP – Type 2 | NSW | Penrith | 36 Barber Ave | 2750 | 180016 | B + E | 2018-12-15 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | DCE Generated |  | CLAAN Sent to DP |  | Datateks
AYCA-48OYT0 | 2EDG-65 | 240 New South Head Road, Edgecliff NSW - | Active | Supply Order Raised | 22 | FTTP – Type 2 | NSW | Edgecliff | 240 New South Head Rd | 2027 | 161415 | B + E | 2018-12-17 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-30 12:00 |  |  | Datateks
AYCA-4LM7HH | 2UND-61 | Wattle Hill - 1 | Active | Supply Order Raised | 47 | FTTP – Type 2 | NSW | Hurlstone Park | 590-602 New Canterbury Rd | 2193 | 165375 | B + E | 2018-12-18 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-03-29 12:00 |  | Ertan Cicek | Datateks
AYCA-4QDZCA | 2STL-61 | The Hume - 1 | Active | Supply Order Raised | 39 | FTTP – Type 2 | NSW | Crows Nest | 31-33 Albany St | 2065 | 174992 | B + E | 2018-12-18 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-07-13 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4VSW7K | 2PTH-05 | Vista Apartments - 1 | Active | Developer Contract Signed | 82 | FTTP – Type 2 | NSW | Penrith | 10-12 Vista St | 2750 | 181268 | B + E | 2018-12-20 | Design Accepted | Reservation Response Received | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-4OCM1V | 2UND-60 | 260-264 Wardell Rd, Marrickville - 1 | Active | Developer Contract Signed | 26 | FTTP – Type 2 | NSW | Marrickville | 260-264 Wardell Rd | 2204 | 169909 | B + E | 2018-12-21 | Design Accepted | Reservation Response Received | MWA - SOPR | DCE Generated |  | CLAAN Sent to LASE | Ertan Cicek | Datateks
AYCA-52OEM0 | 2MON-25 | 33 Darley Street - 1 | Active | Supply Order Raised | 5 | FTTP – Type 3 (MT-LFN) | NSW | Mona Vale | 33 Darley Street East | 2103 | 183201 | B + E | 2018-12-21 |  | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-14 12:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-4VJFPP | 2NEW-22 | 19-21 Eve St, Erskineville - 1 | Active | Supply Order Raised | 21 | FTTP – Type 2 | NSW | Erskineville | 19-21 Eve St | 2043 | 177334 | B + E | 2019-01-09 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-03-07 12:00 |  | Lindy Chan | Datateks
AYCA-33L9HP | 2BAN-64 | Restwell Street, Bankstown - 1 | Active | Supply Order Raised | 161 | FTTP – Type 2 | NSW | Bankstown | Restwell & Leonard St | 2200 | 179182 | B + E | 2019-01-11 |  | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-30 12:00 |  |  | Datateks
AYCA-4SRFAN | 2BAL-62 | ALDI Store Development - Balgowlah - 1 | Active | Supply Order Raised | 2 | FTTP – Type 3 (MT-LFN) | NSW | Balgowlah | 22/26 Roseberry St | 2093 | 175478 | B + E | 2019-01-22 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-14 12:00 |  | Lindy Chan | Datateks
AYCA-4UE5JN | 2LID-03 | Auburn 46-48 Beaumont St - 1 | Active | Supply Order Raised | 8 | FTTP – Type 2 | NSW | Auburn | 46-48 Beaumont Street | 2144 | 172204 | B + E | 2019-01-31 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-05-21 12:00 |  |  | Datateks
AYCA-48S696 | 2BLK-03 | C.J.T. Pty Ltd - 1 | Active | Supply Order Raised | 34 | FTTP – Type 2 | NSW | Blacktown | 3-7 Wallace St | 2148 | 156711 | B + E | 2019-02-22 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-03 12:00 | CLAAN Sent to DP | Nabeel Jaimon | Datateks
AYCA-24QAXK | 2ROC-03 | 10 Martin Ave Arncliffe - 1 & 2 | Active | Supply Order Raised | 159 | FTTP – Type 2 | NSW | Arncliffe | 10 Martin Avenue | 2205 | 131592 | B + E | 2019-03-01 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-05-23 12:00 |  | Michael Tram | Datateks
AYCA-35DF0W | 2KEL-07 | 1, 1A & 1B President Rd, Kellyville - 1 | Active | Supply Order Raised | 16 | FTTP – Type 2 | NSW | Kellyville | 1, 1A & 1B President Rd | 2155 | 173632 | B + E | 2019-03-29 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-03-08 12:00 |  | Lindy Chan | Datateks
AYCA-4H8EZO | 2HUH-22 | 117 VICTORIA ROAD - 1 | Active | Supply Order Raised | 29 | FTTP – Type 2 | NSW | Gladesville | 117-123 Victoria Rd | 2111 | 178782 | B + E | 2019-04-05 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-04 12:00 |  | Ertan Cicek | Datateks
AYCA-47OO3O | 2LIV-03 | 188-190 Moore St Liverpool - 1 | Active | Supply Order Raised | 25 | FTTP – Type 2 | NSW | Liverpool | 188-190 Moore St | 2170 | 158978 | B + E | 2019-04-29 | Design Accepted | Completed (No Telstra Duct) | MWA - SOPR | WI Issued | 2018-02-22 12:00 |  | Ertan Cicek | Datateks
AYCA-4NNOGX | 2PTH-02 | 240-250 Great Western Highway - 1 | Active | Supply Order Raised | 123 | FTTP – Type 2 | NSW | Kingswood | 240-250 Great Western Hwy | 2747 | 165991 | B + E | 2019-05-30 | Awaiting Corrective Action | Reservation Response Received | MWA - SOPR | WI Issued | 2018-04-23 12:00 |  | Ertan Cicek | Datateks
AYCA-4IIZWC | 2STL-60 | Edge 28 - 1 | Active | Supply Order Raised | 53 | FTTP – Type 2 | NSW | St Leonards | 28 Albany St | 2065 | 176827 | B + E | 2019-06-07 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-06-08 16:00 | CLAAN Sent to DP | Ertan Cicek | Datateks
AYCA-26KP9Q | 2ROU-02 | Site-36 cnr site Rouse Hill Town Centre | Active | Supply Order Raised | 58 | FTTP – Type 2 | NSW | Rouse Hill | Caddies Boulevard & White Hart Drive | 2155 | 154363 | B + E | 2019-06-14 |  | Reservation Response Received | MWA - SOPR | WI Issued | 2018-03-15 12:00 |  | Ertan Cicek | Datateks
AYCA-3W384B | 2HOR-62 | 433-437 Pacific Highway, Asquith - 1 | Active | Supply Order Raised | 38 | FTTP – Type 2 | NSW | Asquith | 433-437 Pacific Hwy | 2077 | 153443 | B + E | 2020-02-07 | Design Accepted | Reservation Response Received | MWA - SOPR | WI Issued | 2018-03-29 12:00 |  | Ertan Cicek | Datateks
AYCA-476RM9 | 2LIV-04 | Non Standard Builds - 87-91 Campbell St, | Active | Dev Transferred to Build | 76 |  | NSW | Liverpool | 87-91 Campbell St | 2170 | 159520 | B + E | 2017-02-15 | Not Applicable | MWA - RFQ | WI Issued | 2017-09-21 12:00 |  | Andrew Mahasay | Datateks
AYCA-50FP2M | 2ROU-03 | Non Standard Builds - Oxlade Street Kell | Active | Supply Order Raised | 24 | FTTP – Type 2 | NSW | Kellyville | Oxlade Street | 2155 | 174594 | B + D | 2017-12-18 | Completed | MWA - SOPR | WI Issued | 2018-05-02 12:00 |  | Sogand Mohtat | Datateks
AYCA-54SUCD | 2PKE-06 | Non Standard Builds - Warehouse Pl | Active | Supply Order Raised | 11 | FTTP – Type 3 (MT-LFN) | NSW | Berkeley | Warehouse Pl | 2506 | 177518 | B + D | 2018-02-08 | Completed | MWA - SOPR | WI Issued | 2018-05-02 12:00 |  | Mark Leal | Datateks
AYCA-547JTQ | 2DBB-04 | Rawson St Dubbo - 1 | Active | Supply Order Raised | 3 | FTTP – Type 2 | NSW | Dubbo | 1d Rawson St | 2830 | 178176 | B + D | 2018-05-31 | Completed | MWA - SOPR | WI Issued | 2018-05-31 12:00 |  | Andrew Mahasay | Datateks
AYCA-5DPOWN | 2APN-01 | 13 Technology Dr, Appin NSW 2560, Austra | Active | Supply Order Raised | 4 | FTTP – Type 3 (MT-LFN) | NSW | Appin | 13 Technology Drive | 2560 | 183808 | B + E | 2018-06-01 | Area Plan Ready | MWA - SOPR | WI Issued | 2018-07-16 12:00 | CLAAN Sent to DP | Richard Huffadine | Datateks
AYCA-4VAQ8P | 9SCU-07 | 1/65 Macgregor - 1 | Active | Supply Order Raised | 3 | FTTN | ACT | MacGregor | 11 Prevost Pl | 2615 | 176675 | B + D | 2018-07-04 | Completed | MWA - RFQ | WI Issued | 2018-05-08 12:00 |  | Andrew Mahasay | Datateks
AYCA-53E534 | 2LIV-12 | Glenfield Gains - 1 | Active | Supply Order Raised | 11 | FTTP – Type 2 | NSW | Glenfield | 25 Glenfield Rd | 2167 | 178433 | B + E | 2018-07-18 | Not Applicable | MWA - SOPR | WI Issued | 2018-03-20 12:00 |  | Nabeel Jaimon | Datateks
AYCA-541Y7O | 2WAU-20 | Beechwood - 4A | Active | Supply Order Raised | 3 | FTTP – Type 3 (MT-LFN) | NSW | Beechwood | 728-730 | 2446 | 176960 | D | 2018-07-30 | Completed | MWA - SOPR | WI Issued | 2018-04-30 12:00 |  | Andrew Mahasay | Datateks
AYCA-4SV0JO | 2ING-65 | Ingleburn Industrial Estate, Stage 2 - 1 | Active | Supply Order Raised | 2 | FTTP – Type 3 (MT-LFN) | NSW | Ingleburn | 41-47 Stennett Rd | 2565 | 178376 | B + E | 2018-07-31 | Not Applicable | MWA - SOPR | WI Issued | 2018-03-15 12:00 |  | Richard Huffadine | Datateks
AYCA-54QSHT | 2MIL-20 | LOT A KURRAJONG ROAD PRESTONS 2170 - 1 | Active | Supply Order Raised | 1 | FTTP – Type 3 (MT-LFN) | NSW | Prestons | 42A Kurrajong Rd | 2170 | 177662 | B + E | 2018-08-02 | Not Applicable | MWA - SOPR | WI Issued | 2018-04-11 12:00 |  | Nabeel Jaimon | Datateks
AYCA-4LYVIU | 2BTH-01 | Arndilly - 2 | Active | Supply Order Raised | 2 | FTTN | NSW | Bathurst | 136 Peel Street | 2795 | 164108 | B + D | 2018-08-03 | Completed | MWA - RFQ | WI Issued | 2017-10-24 12:00 |  | Andrew Mahasay | Datateks
AYCA-5ALZB0 | 2BLK-07 | 1 Huntingwood Drive - 2 | Active | Supply Order Raised | 1 | FTTP – Type 2 | NSW | Huntingwood | 6 Woods Cl | 2148 | 181922 | B + E | 2018-08-15 | Not Applicable | MWA - SOPR | WI Issued | 2018-07-10 12:00 | CLAAN Sent to DP | Nabeel Jaimon | Datateks
AYCA-52ZO0L | 2LID-04 | Norval St Boarding House - 1 | Active | Supply Order Raised | 10 | FTTP – Type 2 | NSW | Auburn | 32 Norval St | 2144 | 177658 | B + E | 2018-08-17 | Not Applicable | MWA - SOPR | WI Issued | 2018-03-15 12:00 |  | Richard Huffadine | Datateks
AYCA-4HTS7R | 2RIV-03 | 875 Marsden Park - 1 | Active | Supply Order Raised | 4 | FTTP – Type 2 | NSW | Marsden Park | 875 Richmond Rd | 2765 | 163669 | B + D | 2018-08-31 | Completed | MWA - SOPR | WI Issued | 2018-01-10 12:00 |  | Andrew Mahasay | Datateks
AYCA-LYHJJ | 2MTT-02 | Renwick - DA06B | Active | Supply Order Raised | 8 | FTTP – Type 2 | NSW | Mittagong | 10 Cardigan St | 2575 | 183911 | D | 2018-08-31 | Completed | MWA - SOPR | WI Issued | 2018-06-15 12:00 | CLAAN Sent to DP | Andrew Mahasay | Datateks
AYCA-4BBYMK | 2ROU-01 | Old Pitt Town Road - 1 Community | Active | Supply Order Raised | 7 | FTTP – Type 3 (MT-LFN) | NSW | Box Hill | 184 & 186 Old Pitt Town Rd | 2765 | 162606 | D | 2018-09-03 | Completed | MWA - SOPR | WI Issued | 2018-05-30 12:00 | CLAAN Sent to DP | Andrew Mahasay | Datateks
AYCA-3V2064 | 2WAG-01 | Cooramin Street, Boorooma - 10 | Active | Supply Order Raised | 7 | FTTP – Type 2 | NSW | Boorooma | 29 Gibson St | 2650 | 153854 | B + D | 2018-09-07 | Completed | MWA - SOPR | WI Issued | 2018-04-30 12:00 |  | Andrew Mahasay | Datateks
AYCA-4YZZ1I | 2ABN-03 | Boulevarde - 1 | Active | Supply Order Raised | 4 | FTTN | NSW | Oak Flats | 149 The Boulevarde | 2529 | 175688 | B + D | 2018-09-17 | Completed | MWA - RFQ | WI Issued | 2018-05-25 12:00 | CLAAN Sent to Council | Andrew Mahasay | Datateks
AYCA-4O03IQ | 2COR-09 | 17 RYAN STREET, BALGOWNIE - 1 | Active | Supply Order Raised | 7 | FTTP – Type 3 (MT-LFN) | NSW | Balgownie | 17 Ryan Street | 2519 | 167597 | B + E | 2018-10-01 | Area Plan Ready | MWA - SOPR | WI Issued | 2018-03-15 12:00 |  | Nabeel Jaimon | Datateks
AYCA-2T05DV | 2RCH-04 | ISAAC DEVELOPMENTS BLIGH PARK - 1 | Active | Supply Order Raised | 4 | FTTP – Type 2 | NSW | South Windsor | 752 George St | 2756 | 163188 | B + D | 2018-10-12 | Completed | MWA - SOPR | WI Issued | 2018-06-21 12:00 | CLAAN Sent to Council | Andrew Mahasay | Datateks
AYCA-481ES7 | 2BTH-09 | Sitecar - 915 | Active | Supply Order Raised | 3 | FTTP – Type 3 (MT-LFN) | NSW | Bathurst | 65 George St | 2795 | 163663 | B + E | 2018-10-18 | Area Plan Ready | MWA - SOPR | WI Issued | 2018-06-15 12:00 |  | Nabeel Jaimon | Datateks
AYCA-4IEHVB | 2CAH-21 | Bottlebrush Place - 1 | Active | Supply Order Raised | 6 | FTTN | NSW | Lakewood | Bottlebrush Place | 2443 | 163493 | B + D | 2018-10-19 | Completed | MWA - RFQ | WI Issued | 2018-05-29 12:00 |  | Andrew Mahasay | Datateks
AYCA-3BBGCI | 2RIV-04 | Sand & Soil Yard - 1 | Active | Supply Order Raised | 2 | FTTP – Type 2 | NSW | Box Hill | 737 Windsor Rd | 2765 | 163205 | B + D | 2018-10-26 | Completed | MWA - SOPR | WI Issued | 2018-05-08 12:00 |  | Andrew Mahasay | Datateks
AYCA-468RZY | 2LID-04 | 23 RAILWAY PARADE - 1 | Active | Supply Order Raised | 5 | FTTP – Type 2 | NSW | Lidcombe | 23 Railway Parade | 2141 | 156882 | B + E | 2018-10-29 | Not Applicable | MWA - SOPR | WI Issued | 2018-02-01 12:00 |  | Nabeel Jaimon | Datateks
AYCA-4YJULB | 2REV-20 | Flower Power - 1 | Active | Supply Order Raised | 9 | FTTP – Type 3 (MT-LFN) | NSW | Milperra | 479 Henry Lawson Drive | 2214 | 177523 | A + E | 2018-10-29 | Not Applicable | MWA - SOPR | WI Issued | 2018-05-07 12:00 |  | Nabeel Jaimon | Datateks
AYCA-4LHC6F | 2DBB-01 | Magnolia Estate - 5 | Active | Supply Order Raised | 10 | FTTP – Type 2 | NSW | Dubbo | 30 Ritz Pl | 2830 | 165370 | D | 2018-11-01 | Completed | MWA - SOPR | WI Issued | 2018-05-30 12:00 | CLAAN Sent to DP | Andrew Mahasay | Datateks
AYCA-4R1C1M | 2RIV-07 | Crown, Edmund, William Street - 9 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Riverstone | William St | 2765 | 169377 | D | 2018-11-01 | Completed | MWA - SOPR | WI Issued | 2018-05-31 12:00 | CLAAN Sent to DP | Andrew Mahasay | Datateks
AYCA-4W183C | 2WLG-02 | The Quad - 1 | Active | Supply Order Raised | 4 | FTTP – Type 2 | NSW | Wollongong | 71 Auburn St | 2500 | 178048 | B + E | 2018-11-05 | Not Applicable | MWA - SOPR | WI Issued | 2018-05-22 12:00 |  | Nabeel Jaimon | Datateks
AYCA-52S52D | 2BTH-01 | Rankens Bridge Farm - 4 | Active | Supply Order Raised | 6 | FTTP – Type 2 | NSW | Eglinton | 18 Hobson Cl | 2795 | 176513 | D | 2018-11-19 | Completed | MWA - SOPR | WI Issued | 2018-06-01 12:00 | CLAAN Sent to DP | Mark Leal | Datateks
AYCA-4X6TWU | 2LID-08 | Omar Mosque - final stages | Active | Supply Order Raised | 2 | FTTP – Type 2 | NSW | Auburn | 43-47 Harrow Rd | 2144 | 177336 | B + E | 2018-11-30 | Not Applicable | MWA - SOPR | WI Issued | 2018-03-06 12:00 |  | Nabeel Jaimon | Datateks
AYCA-577BDS | 2BLK-07 | 36 Huntingwood Drive - 1 | Active | Supply Order Raised | 3 | FTTP – Type 2 | NSW | Huntingwood | 36 Huntingwood Drive | 2148 | 180681 | B + E | 2018-12-03 | Not Applicable | MWA - SOPR | WI Issued | 2018-06-04 12:00 | CLAAN Sent to DP | Richard Huffadine | Datateks
AYCA-4OJUJI | 2GLB-04 | 20 Cathcart Street - 1 | Active | Supply Order Raised | 3 | FTTN | NSW | Goulburn | 20 Cathcart St | 2580 | 166621 | B + D | 2018-12-10 | Completed | MWA - RFQ | WI Issued | 2018-05-18 12:00 |  | Andrew Mahasay | Datateks
AYCA-4SRFAN | 2BAL-62 | ALDI Store Development - Balgowlah - 1 | Active | Supply Order Raised | 2 | FTTP – Type 3 (MT-LFN) | NSW | Balgowlah | 22/26 Roseberry St | 2093 | 175478 | B + E | 2019-01-22 | Not Applicable | MWA - SOPR | WI Issued | 2018-03-14 12:00 |  | Lindy Chan | Datateks
AYCA-53Y8BE | 2WEL-01 | Nolan-Montefiore - 1 | Active | Supply Order Raised | 4 | FTTN | NSW | Montefiores | 17 Nicholii St | 2820 | 178065 | B + D | 2019-01-31 | Completed | MWA - RFQ | WI Issued | 2018-05-14 12:00 |  | Andrew Mahasay | Datateks