## Sheet1
Item No. | Date | Datateks Issue Comments | Phil Blake Reply to issue | Date | Action Completed or required
1 | 2019-02-18 | Login Details for Marshell Antonio | Completed | 2019-02-19 | Completed
2 | 2019-02-18 | Login for Marshell and Damien Owncloud | Completed | 2019-02-19 | Completed
3 | 2019-03-20 | No Dashboard Info | This is where we can collect any items that you need highlighted for whatever reason, and statistics |  | Needs further work from Phil
4 | 2019-03-20 | Basics: Project name, need the full name of the project, including the MW AYCA number example, MW21638- AYCA-3NFID7 | Not all items have both an AYCA and a MW number Projects/Can you extract the full name of the project and add it into the Project name? Looks like it was my mistake the earlier email, should be like the following,MW21638- AYCA-3NFID7-2PTH-04 - Tench Ave Jamisontown | 2019-03-29 | Needs further work from Phil
4a | 2019-03-30 | Projects/Can you extract the full name of the project and add it into the Project name? Looks like it was my mistake the earlier email, should be like the following, MW21638- AYCA-3NFID7-2PTH-04 - Tench Ave Jamisontown 1 |  |  | New item open
5 | 2019-03-20 | Basics: Don’t need the Minor works number area, just duplicating the above | For now I’ve created an “Identifiers” tab that holds the “duplicate” numbers - this is in case we need to sort or display these numbers anywhere like in a template. You can ignore then for now and moving forward I will most likely hide the information and have it automatically update from the project title, rather than have the title be based on these numbers. | 2019-03-29 | Completed
6 | 2019-03-20 | Basics: Don’t need the AYCA number area, another duplication of above. | For now I’ve created an “Identifiers” tab that holds the “duplicate” numbers - this is in case we need to sort or display these numbers anywhere like in a template. You can ignore then for now and moving forward I will most likely hide the information and have it automatically update from the project title, rather than have the title be based on these numbers. | 2019-03-29 | Completed
7 | 2019-03-20 | Location: Need the address added from the financial sheet | I’ve done my best here. Not every item has both the “AYCA” and “MW” number, or a SAM or an address, and not all are in the same order, however, where possible all the information from that column has been imported. There are some rows like… MW21699-AYCA-3E5O97-2ROU-03-Hancy - 1 MW417R000536-2BGI-20-STELLAR NPDL_MWR (A417)-Boggabri …where I’ve imported the extra details (like “Hancy-1” and "STELLAR NPDL_MWR (A417)-Boggabri” into the address field. | 2019-03-29 | need to revisit the issue.
8 | 2019-03-20 | Locations: Need the location / area added from the financial sheet |  | 2019-03-29 | need to revisit the issue.
9 | 2019-03-20 | Locations: Need the SAM info extracted from the project title in the financial sheet |  | 2019-03-29 | need to revisit the issue.
9a | 2019-03-30 | SAM info as per below highlighted in red. Each project will have this as a SAM id.. |  |  | New item open
10 | 2019-03-20 | Locations: Dial before you dig, so if it required what happens then. Is there an area to save the dials? |  | 2019-03-29 | need to revisit the issue.
11 | 2019-03-20 | Financials: Need to add in the A401 RFQ rate card.. see attached only one rate card for the client. I will get the Sub contractor rate card for the A401 to you shortly. | I’ve started on this as it’s a part of the variation logic. I’ll finish the Subcontractor Jobs / PO’s and publish it all together | 2019-03-29 | need to revisit the issue.
12 | 2019-03-20 | Financials: PO creation for the sub-contractor using the various Subby rate cards? |  | 2019-03-29 | need to revisit the issue.
13 | 2019-03-20 | Financials: Need to be able to see the and download my financial spreadsheet | Will do. I’ve added fields for all the dates and will add them to the UI over the next week. | 2019-03-29 | need to revisit the issue. Can't see a an export function. Has this function been completed
14 | 2019-03-20 | Financials: Can you add in the all of the fields form the financial spreadsheet to the database? | Will do. I’ve added fields for all the dates and will add them to the UI over the next week. | 2019-03-29 | need to revisit the issue. Can't see a an export function. Has this function been completed
15 | 2019-03-20 | Financials: New financial spreadsheet attached, please update the database | Completed | 2019-03-29 | Completed
16 | 2019-03-20 | Contacts: Please add in the PE name from the attached financial sheet | Completed | 2019-03-29 | Completed
17 | 2019-03-20 | Templates: Unable to create a doc from the templates | I’ll start on templates on Monday. I have already written the templating code so I’m hoping it just a matter of making sure the right fields end up in the right place. I have created buttons for the templates that will generate and download the template when pressed. |  | need to revisit the issue.
18 | 2019-03-20 | Templates: What is the mechanism that allows us to create the templates? | I’ll start on templates on Monday. I have already written the templating code so I’m hoping it just a matter of making sure the right fields end up in the right place. I have created buttons for the templates that will generate and download the template when pressed. |  | need to revisit the issue.
19 | 2019-03-20 | New Items required: Need an area to add in comments from the project engineers, see attached fortnightly forecast MDU SUD. If you can import that data to associated projects that will be great. Also add the columns for the spreadsheet into the basics | I’m working on this today. I’ll add a “Comments” tab to the UI of Projects. |  | need to revisit the issue.
19a | 2019-03-30 | Is it possible to get a new tab in the projects tab for this data to be captured?? |  |  | New item open
20 | 2019-03-20 | New Items required: Combine Basic and Location into one form and rename it Project Info | I combined the four tabs from your subsequent email. Just realised I hadn’t renamed the tab - I’ve updated the name in development and it will be updated with the next publication. |  | Completed
21 | 2019-03-20 | Materials: Need to have an area where we can add in the number count for each line item. | Allow to create any number of “Warehouses” that each contain a list of Material Transactions - Materials In and Materials Out. This should allow a record of what materials (and quantities) were present in any warehouse at any point in time. Does this sound like it’s on the right track? yes Do you want to track who has what at any time? No Just in the warehouse at the moment If so, each subbie will also have a “warehouse” of materials that have been supplied to them? No just stock on hand |  | Answers in purple
21a | 2019-03-30 | still need this so we can populate the items with a count of the item |  |  | New item open
22 | 2019-03-20 | Materials: Need to be able to export a spreadsheet with the stock levels |  |  | Still Waiting on export function and ability to add count numbers to the item. As of the 24/4/19
22a | 2019-03-30 | Still can’t see a export button to export items in stock to a excel spreadsheet Still no export function |  |  | New item open
23 | 2019-03-20 | Materials: Marshells need an ACT are to add his materials Same as the above item 21 |  |  | Answers in purple
23a | 2019-03-30 | Does this sound like it’s on the right track? Yes and will confirm once online Do you want to track who has what at any time? yes If so, each subbie will also have a “warehouse” of materials that have been supplied to them? Yes lets try it and see how it goes. |  |  | Reply sent on the 30/3/19
24 | 2019-03-20 | File Storage: File storage do we have a dropbox feature with the database? | Yes. OwnCloud works just like DropBox It can be accessed at: https://ecm.datateks.com.au/ It does not allow email addresses as user names so you login as “damienmarov” with the current password “Damien” It’s been setup so you and Marshell can add and manage users and any content. The easiest way to use it is to install the OwnCloud client on your laptop. You can download the windows version from: https://owncloud.org/download/#owncloud-desktop-client-windows Then it works pretty much like DropBox. Everyone has a folder on their computer that syncs to the server. |  | Action Marsh and DM to investigate owncloud and structure
25 | 2019-03-20 | File Storage: If so how do we get access to it? We would like to cease using dropbox. |  |  | Still Open
26 | 2019-03-20 | File Storage: We would like to start adding folders for the staff to use and update | same as above |  | Action Marsh and DM to investigate owncloud and structure
27 | 2019-03-20 | File Storage: We would like to start to share the folders with the sub-contractors | same as above |  | Action Marsh and DM to investigate owncloud and structure
28 | 2019-03-30 | Projects/Identifier, this tab needs to be deleted, same info in the basic Tab | I have hidden the tab. |  | Completed
29 | 2019-03-30 | Projects/CSPO tab is also not required, same info in the basic Tab. The PE’s or PA can enter details of the CSPO manually | To confirm, when you login you will never need to see them so don’t need them taking space on your interface? This will only appear on the PE’s / PA interface |  | Completed
30 | 2019-03-30 | Projects/ Basic tab can I get the full list of Locations added in please see attached Spreadsheet column B | Done. |  | Completed
31 | 2019-03-30 | Projects/Basic tab can the contact details be populated with column a of the attached spreadsheet | Done. |  | Completed
32 | 2019-03-30 | Projects/New tab Financials using columns R, S, T, U, V, X, and Y from the attached spreadsheet.. | Done. |  | Completed
33 | 2019-03-30 | Projects/ Need a new tab for the Datateks invoice details see below | Done. |  | Completed
34 | 2019-03-30 | Projects/ Search function comes up with an error see below
35 | 2019-03-30 | With the attached spreadsheet you will notice a new Contract Minor Work Maximo. Please include these in the update as I will provide further info on the contract shortly.. Contracts/ need to add in a new contract “Minor Works Maximo” This contract has started over 4 weeks ago. Didn’t want to flood you with new stuff until we get the database right. Seeing that we have over 30 new projects that fall in the queue it may be time to add it in. See attached financials to date. Please upload the latest data.. | I’ve imported the new contracts and projects.
36 | 2019-03-30 | Can we rename the Basic Tab as Project Details? | Done. |  | Completed
37 | 2019-03-30 | Can we rename the Template Tab as Submission Documents? | Done. |  | Completed
38 | 2019-04-24 | When Deleting projects from Projects Tab receive the following error
39 | 2019-04-24 | Project Tab, Submission docs, still can't create the template docs, completion Certificates, Variation Template, Payment Claims, Sub Contractor statements & Sub Contractor declaration As of the 8/5/19 still not working, also tried again on the 17/5/19 and still not working |  |  | New Item, 17/05/19
40 | 2019-04-24 | projects Tab Submission docs, Generate Subcontractor Statement, incorrect spelling on stateement
41 | 2019-05-08 | Need to tidy up the Cotracts page. Only 3 Contracts available column A now has the contracts. See embedded updated financial Spreadsheet. Same as Item 35 |  |  | New Item
42 | 2019-05-08 | Owncloud login details, Can you craete Login details for Marshell and myself please. Unable to access the site since the update of the software. Also the app for the mobiles is a purchase, is that correct? |  |  | New Item
43 | 2019-05-17 | Contractors Tab, Insurances. Please additional two insert boxes, three types of insurances that we need to cover off. Public Liability Workers Comp Public Indemnity Insurance |  |  | New Item, 17/05/19
44 | 2019-05-17 | Contractors Minor works agreement tab, Can't exit out of page, can't go back to contractors front page, can't get back to the dashboard very clunky. When it goes back to the dashboard and then click on contarctors ot takes you back to the edit minor works agreement date |  |  | New Item, 17/05/19
45 | 2019-05-17 | Rate Cards. Need to separate the clients and sub contractor rate cards. Tab for Clients and a tab for Sub Contractors |  |  | New Item, 17/05/19
46 | 2019-05-17 | Contracts: Only 3 contracts exist with NBN, Minor Works, A401 RFQ & A417 as per the current financial spreadsheet. |  |  | New Item, 17/05/19
47 | 2019-05-17 | dates in all areas need to be changed from US to Aust date format |  |  | New Item, 17/05/19
48 | 2019-05-17 | Please add in new Minor Works rate card. |  |  | New Item, 17/05/19
49 | 2019-05-17 | Current Financial spreadsheet need all of the columns in the of the spreadsheet in the project tab. See updated spreadsheet as of the 17/5/19 disregard the spreadsheet sent on the 16/5/19. See attached item 46 new spreadsheet |  |  | New Item, 17/05/19
50 | 2019-05-17 | ProjectSpreadsheet 16 May 2019 Extraction from database is missing the invoice dates for completed and invoice projects |  |  | New Item, 17/05/19
51 | 2019-05-17 | ProjectSpreadsheet 16 May 2019 Extraction from database, Column Z missing NBN PO/PM names |  |  | New Item, 17/05/19